## STRATUS PACKAGES -ALL PROJECTS
Package Name | Tracking Status | Qty Planned | Qty Complete | %Complete | Hours Estimated | Actual Hours | Division | COST CODE | FAB # | JOB# (HIDDEN) | FOREMAN CONTACT | LOCATION | CATEGORY | PRE-FAB ITEM | QUANTITY PER BUILD | STATUS (HIDDEN) | PROJECT NAME (HIDDEN) | DETAILER | DETAIL DUE BY | DETAIL COMPLETE | DETAIL APPROVAL | MATERIAL RECEIVED | MATERIAL RECEIVED HELPER (HIDDEN) | EQUIPMENT RECEIVED | EQUIPMENT RECEIVED HELPER (HIDDEN) | APPROVAL TO BEGIN FAB | ESTIMATED MAN HOURS PER BUILD (HIDDEN) | WORK DAYS (HIDDEN) | WORK DAYS | CREW | PRE-FAB BUILD START | PRE-FAB BUILD END | PROJECTED COMPLETE DATE | PROJECTED LATER THAN DUE HELPER (HIDDEN) | DUE ON SITE | DUE ONSITE-PROJECT SCHEDULE DUE ONSITE (HIDDEN) | PROJECT SCHEDULE DUE ON SITE DATE (REFERENCE) | SHIPPED TO SITE | CREW MEMBERS (HIDDEN) | PRE-FAB COMPLETE | MATERIAL TRANSFER | STATION (HIDDEN) | PROJECT MANAGER (HIDDEN) | FAB HELPER (HIDDEN) | BUILD YEAR (HIDDEN) | MATERIAL LOCATION (HIDDEN) | PRE-FAB ACTUAL BUILD TIME (PER UNIT) (HIDDEN) | PRE-FAB ACTUAL BUILD TIME (TOTAL) | PRE-FAB ESTIMATED BUILD TIME (PER UNIT) (HIDDEN) | PRE-FAB ESTIMATED BUILD TIME (TOTAL) | CONEST ESTIMATED HOURS (PER UNIT) (HIDDEN) | CONEST ESTIMATED BUILD TIME (TOTAL) (HIDDEN) | CONEST VS ACTUAL LOWEST - HELPER (HIDDEN) | CONEST LESS THAN ACTUAL - HELPER (HIDDEN) | ESTIMATED VS ACTUAL LOWEST - HELPER (HIDDEN) | ESTIMATED LOWER - HELPER (HIDDEN) | BUILD YEAR HELPER (HIDDEN) | FAB#-JOB# | ACTIVITY DESCRIPTION (HIDDEN) | PROJECT SCHEDULE ROW # (HIDDEN) | ITEM LINK TO IN PROJECT SCHEDULE | ACTIVITY ID | COST CODE HELPER (HIDDEN) | STAR (HIDDEN) | Activity ID PREFAB Helper (HIDDEN) | Activity ID Project Schedule Sheet | % Complete | QA/QC COMPLETE | BIM/CAD COORDINATOR | COORDINATION COMPLETE DUE DATE | COORDINATION COMPLETED | TODAY (HIDDEN) | DAYS FROM TODAY TO PREFAB START (HIDDEN) | STATION CONFIRMED | Last Sync From STRATUS (UTC) | STRATUS.STRATUS_INJECTED_REFERENCE_TYPE_ID | STRATUS_PackageId | STRATUS.Model | STRATUS.#Parts | STRATUS.Hours Estimated | STRATUS.#Assemblies | STRATUS.Project Number | STRATUS.Required | STRATUS.Project Name | STRATUS.Actual Hours | STRATUS.STRATUS_INJECTED_TRACKING_STATUS | STRATUS.%Complete | STRATUS.Division | STRATUS.Package Name | STRATUS.STRATUS_INJECTED_FABRICATION_PARTS_EXIST | STRATUS.Description | STRATUS.#Total Parts | STRATUS.Package Number | STRATUS.#Tasks
[9 empty] | 1406 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1406 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1406-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1406 |  |  | PF.1406 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00518-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00518-LEVEL 28-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00518-320001TUR | 0
[9 empty] | 1407 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1407 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1407-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1407 |  |  | PF.1407 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00519-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00519-LEVEL 29-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00519-320001TUR | 0
[9 empty] | 1408 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1408 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1408-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1408 |  |  | PF.1408 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00520-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/13/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00520-LEVEL 30-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00520-320001TUR | 0
[9 empty] | 1409 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1409 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1409-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1409 |  |  | PF.1409 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00521-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00521-LEVEL 31-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00521-320001TUR | 0
[9 empty] | 1410 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1410 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1410-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1410 |  |  | PF.1410 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00522-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00522-LEVEL 32-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00522-320001TUR | 0
[9 empty] | 1411 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1411 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1411-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1411 |  |  | PF.1411 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00523-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00523-LEVEL 33-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00523-320001TUR | 0
[9 empty] | 1412 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1412 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1412-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1412 |  |  | PF.1412 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00524-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00524-LEVEL 34-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00524-320001TUR | 0
[9 empty] | 1413 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1413 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1413-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1413 |  |  | PF.1413 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00525-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00525-LEVEL 35-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00525-320001TUR | 0
[9 empty] | 1414 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1414 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1414-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1414 |  |  | PF.1414 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00526-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00526-LEVEL 36-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00526-320001TUR | 0
[9 empty] | 1415 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1415 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1415-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1415 |  |  | PF.1415 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00527-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00527-LEVEL 37-CND-CONDUIT RISER SLEEVES | False | CONDUIT RISER SLEEVES | 0 | FAB-00527-320001TUR | 0
[9 empty] | 1416 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1416 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1416-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1416 |  |  | PF.1416 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00528-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00528-LEVEL 38-CND-CONDUIT RISER SLEEVES | False | CONDUIT RISER SLEEVES | 0 | FAB-00528-320001TUR | 0
[9 empty] | 1417 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1417 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1417-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1417 |  |  | PF.1417 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00529-320001TUR | MXD_RESI_JAP_ELEC | 0 | 30.00 | 0 | 320001TUR | 8/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00529-MULTI LEVEL-TMP-SPIDER BOXES | False | SPIDER BOXES | 0 | FAB-00529-320001TUR | 0
[9 empty] | 1418 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1418 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1418-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1418 |  |  | PF.1418 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00530-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.80 | 0 | 320001TUR | 10/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00530-LEVEL 2-LGT-S50-THREADED ROD CEILING MOUNT-VAULT | False | S50-THREADED ROD CEILING MOUNT-VAULT | 0 | FAB-00530-320001TUR | 0
[9 empty] | 1419 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1419 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1419-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1419 |  |  | PF.1419 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00531-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.50 | 0 | 320001TUR | 9/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00531-LEVEL 2-LGT-S50-WALL MOUNT VAULT+L2.5 | False | S50-WALL MOUNT VAULT L2.5 | 0 | FAB-00531-320001TUR | 0
[9 empty] | 1420 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1420 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1420-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1420 |  |  | PF.1420 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00532-320001TUR | MXD_RESI_JAP_ELEC | 0 | 5.28 | 0 | 320001TUR | 9/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00532-MULTI LEVEL-IW-EUH HEATER PREWIRE | False | EUH HEATER PREWIRE | 0 | FAB-00532-320001TUR | 0
[9 empty] | 1421 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1421 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1421-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1421 |  |  | PF.1421 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00533-320001TUR | MXD_RESI_JAP_ELEC | 0 | 48.00 | 0 | 320001TUR | 10/20/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00533-LEVEL 1-IW-UNIT HEATERS-INSTALL MOUNTING HARDWARE | False | UNIT HEATERS INSTALL MOUNTING HARDWARE | 0 | FAB-00533-320001TUR | 0
[9 empty] | 1422 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1422 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1422-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1422 |  |  | PF.1422 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00534-320001TUR | MXD_RESI_JAP_ELEC | 0 | 43.61 | 0 | 320001TUR | 12/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00534-LEVEL 13-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00534-320001TUR | 0
[9 empty] | 1423 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1423 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1423-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1423 |  |  | PF.1423 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00535-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00535-LEVEL 22-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00535-320001TUR | 0
[9 empty] | 1424 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1424 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1424-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1424 |  |  | PF.1424 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00536-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00536-LEVEL 23-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00536-320001TUR | 0
[9 empty] | 1425 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1425 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1425-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1425 |  |  | PF.1425 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00537-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00537-LEVEL 24-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00537-320001TUR | 0
[9 empty] | 1426 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1426 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1426-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1426 |  |  | PF.1426 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00538-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00538-LEVEL 25-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00538-320001TUR | 0
[9 empty] | 1427 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1427 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1427-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1427 |  |  | PF.1427 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00539-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00539-LEVEL 26-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00539-320001TUR | 0
[9 empty] | 1428 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1428 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1428-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1428 |  |  | PF.1428 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00540-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 4/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00540-LEVEL 27-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00540-320001TUR | 0
[9 empty] | 1429 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1429 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1429-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1429 |  |  | PF.1429 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00541-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 5/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00541-LEVEL 31-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00541-320001TUR | 0
[9 empty] | 1430 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1430 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1430-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1430 |  |  | PF.1430 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00542-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 4/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00542-LEVEL 28-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00542-320001TUR | 0
[9 empty] | 1431 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1431 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1431-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1431 |  |  | PF.1431 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00543-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 5/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00543-LEVEL 32-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00543-320001TUR | 0
[9 empty] | 1432 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1432 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1432-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1432 |  |  | PF.1432 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00544-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 4/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00544-LEVEL 29-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00544-320001TUR | 0
[9 empty] | 1433 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1433 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1433-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1433 |  |  | PF.1433 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00545-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 5/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00545-LEVEL 33-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00545-320001TUR | 0
[9 empty] | 1434 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1434 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1434-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1434 |  |  | PF.1434 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00546-320001TUR | MXD_RESI_JAP_ELEC | 0 | 34.85 | 0 | 320001TUR | 5/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00546-LEVEL 34-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00546-320001TUR | 0
[9 empty] | 1435 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1435 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1435-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1435 |  |  | PF.1435 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00547-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 4/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00547-LEVEL 30-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00547-320001TUR | 0
[9 empty] | 1436 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1436 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1436-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1436 |  |  | PF.1436 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00548-320001TUR | MXD_RESI_JAP_ELEC | 0 | 34.85 | 0 | 320001TUR | 6/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00548-LEVEL 35-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00548-320001TUR | 0
[9 empty] | 1437 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1437 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1437-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1437 |  |  | PF.1437 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00549-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 6/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00549-LEVEL 36-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00549-320001TUR | 0
[9 empty] | 1438 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1438 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1438-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1438 |  |  | PF.1438 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00550-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00550-LEVEL 3-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00550-320001TUR | 0
[9 empty] | 1439 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1439 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1439-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1439 |  |  | PF.1439 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00551-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00551-LEVEL 4-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00551-320001TUR | 0
[9 empty] | 1440 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1440 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1440-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1440 |  |  | PF.1440 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00552-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00552-LEVEL 5-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00552-320001TUR | 0
[9 empty] | 1441 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1441 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1441-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1441 |  |  | PF.1441 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00553-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00553-LEVEL 6-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00553-320001TUR | 0
[9 empty] | 1442 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1442 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1442-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1442 |  |  | PF.1442 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00554-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00554-LEVEL 7-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00554-320001TUR | 0
[9 empty] | 1443 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1443 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1443-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1443 |  |  | PF.1443 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00555-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00555-LEVEL 8-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00555-320001TUR | 0
[9 empty] | 1444 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1444 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1444-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1444 |  |  | PF.1444 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00556-320001TUR | MXD_RESI_JAP_ELEC | 0 | 44.33 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00556-LEVEL 9-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00556-320001TUR | 0
[9 empty] | 1445 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1445 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1445-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1445 |  |  | PF.1445 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00557-320001TUR | MXD_RESI_JAP_ELEC | 0 | 44.33 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00557-LEVEL 10-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00557-320001TUR | 0
[9 empty] | 1446 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1446 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1446-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1446 |  |  | PF.1446 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00558-320001TUR | MXD_RESI_JAP_ELEC | 0 | 44.33 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00558-LEVEL 11-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00558-320001TUR | 0
[9 empty] | 1447 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1447 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1447-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1447 |  |  | PF.1447 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00559-320001TUR | MXD_RESI_JAP_ELEC | 0 | 44.33 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00559-LEVEL 12-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00559-320001TUR | 0
[9 empty] | 1448 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1448 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1448-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1448 |  |  | PF.1448 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00560-320001TUR | MXD_RESI_JAP_ELEC | 0 | 43.61 | 0 | 320001TUR | 1/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00560-LEVEL 14-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00560-320001TUR | 0
[9 empty] | 1449 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1449 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1449-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1449 |  |  | PF.1449 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00561-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00561-LEVEL 15-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00561-320001TUR | 0
[9 empty] | 1450 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1450 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1450-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1450 |  |  | PF.1450 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00562-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00562-LEVEL 16-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00562-320001TUR | 0
[9 empty] | 1451 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1451 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1451-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1451 |  |  | PF.1451 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00563-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00563-LEVEL 17-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00563-320001TUR | 0
[9 empty] | 1452 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1452 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1452-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1452 |  |  | PF.1452 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00564-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 2/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00564-LEVEL 18-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00564-320001TUR | 0
[9 empty] | 1453 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1453 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1453-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1453 |  |  | PF.1453 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00565-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 2/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00565-LEVEL 19-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00565-320001TUR | 0
[9 empty] | 1454 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1454 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1454-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1454 |  |  | PF.1454 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00566-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00566-LEVEL 20-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00566-320001TUR | 0
[9 empty] | 1455 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1455 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1455-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1455 |  |  | PF.1455 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00567-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 2/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00567-LEVEL 21-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00567-320001TUR | 0
[9 empty] | 1456 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1456 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1456-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1456 |  |  | PF.1456 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00568-320001TUR | MXD_RESI_JAP_ELEC | 0 | 5.32 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00568-LEVEL 1-LGT-LOADING DOCK S50 FIXTURE STRUT ASSEMBLIES | False | LOADING DOCK S50 FIXTURE STRUT ASSEMBLIES | 0 | FAB-00568-320001TUR | 0
[9 empty] | 1457 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1457 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1457-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1457 |  |  | PF.1457 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00569-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.37 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00569-LEVEL 3-IW-MOCK UP UNIT-S-2 INWALL | False | LEVEL 3-MOCK UP UNIT S-2 INWALL | 0 | FAB-00569-320001TUR | 0
[9 empty] | 1458 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1458 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1458-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1458 |  |  | PF.1458 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00570-320001TUR | MXD_RESI_JAP_ELEC | 0 | 5.65 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00570-LEVEL 3-IW-MOCK UP UNIT-A-1 INWALL | False | LEVEL 3-MOCK UP UNIT A-1 INWALL | 0 | FAB-00570-320001TUR | 0
[9 empty] | 1459 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1459 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1459-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1459 |  |  | PF.1459 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00571-320001TUR | MXD_RESI_JAP_ELEC | 0 | 60.00 | 0 | 320001TUR | 9/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00571-LEVEL 3-TMP-CORE HOLE-PLYWOOD PLUG | False | CORE HOLE PLYWOOD PLUG | 0 | FAB-00571-320001TUR | 0
[9 empty] | 1460 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1460 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1460-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1460 |  |  | PF.1460 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00572-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.80 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00572-LEVEL 3-TMP-L3-UNITS TEMP LIGHTING-STRINGERS | False | L3-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00572-320001TUR | 0
[9 empty] | 1461 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1461 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1461-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1461 |  |  | PF.1461 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00573-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.80 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00573-LEVEL 4-TMP-L4-UNITS TEMP LIGHTING-STRINGERS | False | L4-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00573-320001TUR | 0
[9 empty] | 1462 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1462 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1462-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1462 |  |  | PF.1462 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00574-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.80 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00574-LEVEL 5-TMP-L5-UNITS TEMP LIGHTING-STRINGERS | False | L5-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00574-320001TUR | 0
[9 empty] | 1463 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1463 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1463-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1463 |  |  | PF.1463 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00575-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.20 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00575-LEVEL 7-TMP-L7-UNITS TEMP LIGHTING-STRINGERS | False | L7-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00575-320001TUR | 0
[9 empty] | 1464 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1464 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1464-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1464 |  |  | PF.1464 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00576-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.20 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00576-LEVEL 8-TMP-L8-UNITS TEMP LIGHTING-STRINGERS | False | L8-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00576-320001TUR | 0
[9 empty] | 1465 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1465 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1465-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1465 |  |  | PF.1465 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00577-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.20 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00577-LEVEL 9-TMP-L9-UNITS TEMP LIGHTING-STRINGERS | False | L9-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00577-320001TUR | 0
[9 empty] | 1466 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1466 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1466-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1466 |  |  | PF.1466 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00578-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00578-LEVEL 10-TMP-L10-UNITS TEMP LIGHTING-STRINGERS | False | L10-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00578-320001TUR | 0
[9 empty] | 1467 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1467 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1467-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1467 |  |  | PF.1467 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00579-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00579-LEVEL 11-TMP-L11-UNITS TEMP LIGHTING-STRINGERS | False | L11-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00579-320001TUR | 0
[9 empty] | 1468 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1468 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1468-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1468 |  |  | PF.1468 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00580-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00580-LEVEL 12-TMP-L12-UNITS TEMP LIGHTING-STRINGERS | False | L12-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00580-320001TUR | 0
[9 empty] | 1469 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1469 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1469-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1469 |  |  | PF.1469 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00581-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 12/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00581-LEVEL 13-TMP-L13-UNITS TEMP LIGHTING-STRINGERS | False | L13-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00581-320001TUR | 0
[9 empty] | 1470 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1470 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1470-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1470 |  |  | PF.1470 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00582-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 1/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00582-LEVEL 14-TMP-L14-UNITS TEMP LIGHTHING-STRINGERS | False | L14-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00582-320001TUR | 0
[9 empty] | 1471 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1471 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1471-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1471 |  |  | PF.1471 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00583-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00583-LEVEL 15-TMP-L15-UNITS TEMP LIGHTHING-STRINGERS | False | L15-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00583-320001TUR | 0
[9 empty] | 1472 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1472 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1472-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1472 |  |  | PF.1472 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00584-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00584-LEVEL 16-TMP-L16-UNITS TEMP LIGHTHING-STRINGERS | False | L16-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00584-320001TUR | 0
[9 empty] | 1473 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1473 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1473-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1473 |  |  | PF.1473 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00585-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00585-LEVEL 17-TMP-L17-UNITS TEMP LIGHTHING-STRINGERS | False | L17-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00585-320001TUR | 0
[9 empty] | 1474 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1474 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1474-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1474 |  |  | PF.1474 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00586-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 2/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00586-LEVEL 18-TMP-L18-UNITS TEMP LIGHTHING-STRINGERS | False | L18-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00586-320001TUR | 0
[9 empty] | 1475 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1475 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1475-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1475 |  |  | PF.1475 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00587-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 2/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00587-LEVEL 19-TMP-L19-UNITS TEMP LIGHTHING-STRINGERS | False | L19-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00587-320001TUR | 0
[9 empty] | 1476 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1476 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1476-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1476 |  |  | PF.1476 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00588-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00588-LEVEL 20-TMP-L20-UNITS TEMP LIGHTHING-STRINGERS | False | L20-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00588-320001TUR | 0
[9 empty] | 1477 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1477 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1477-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1477 |  |  | PF.1477 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00589-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 2/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00589-LEVEL 21-TMP-L21-UNITS TEMP LIGHTHING-STRINGERS | False | L21-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00589-320001TUR | 0
[9 empty] | 1478 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1478 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1478-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1478 |  |  | PF.1478 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00590-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00590-LEVEL 22-TMP-L22-UNITS TEMP LIGHTHING-STRINGERS | False | L22-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00590-320001TUR | 0
[9 empty] | 1479 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1479 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1479-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1479 |  |  | PF.1479 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00591-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00591-LEVEL 23-TMP-L23-UNITS TEMP LIGHTHING-STRINGERS | False | L23-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00591-320001TUR | 0
[9 empty] | 1480 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1480 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1480-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1480 |  |  | PF.1480 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00592-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00592-LEVEL 24-TMP-L24-UNITS TEMP LIGHTHING-STRINGERS | False | L24-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00592-320001TUR | 0
[9 empty] | 1481 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1481 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1481-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1481 |  |  | PF.1481 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00593-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00593-LEVEL 25-TMP-L25-UNITS TEMP LIGHTHING-STRINGERS | False | L25-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00593-320001TUR | 0
[9 empty] | 1482 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1482 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1482-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1482 |  |  | PF.1482 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00594-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00594-LEVEL 26-TMP-L26-UNITS TEMP LIGHTHING-STRINGERS | False | L26-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00594-320001TUR | 0
[9 empty] | 1483 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1483 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1483-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1483 |  |  | PF.1483 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00595-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 4/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00595-LEVEL 27-TMP-L27-UNITS TEMP LIGHTHING-STRINGERS | False | L27-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00595-320001TUR | 0
[9 empty] | 1484 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1484 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1484-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1484 |  |  | PF.1484 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00596-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 4/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00596-LEVEL 28-TMP-L28-UNITS TEMP LIGHTHING-STRINGERS | False | L28-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00596-320001TUR | 0
[9 empty] | 1485 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1485 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1485-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1485 |  |  | PF.1485 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00597-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 4/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00597-LEVEL 29-TMP-L29-UNITS TEMP LIGHTHING-STRINGERS | False | L29-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00597-320001TUR | 0
[9 empty] | 1486 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1486 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1486-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1486 |  |  | PF.1486 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00598-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 4/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00598-LEVEL 30-TMP-L30-UNITS TEMP LIGHTHING-STRINGERS | False | L30-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00598-320001TUR | 0
[9 empty] | 1487 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1487 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1487-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1487 |  |  | PF.1487 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00599-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 5/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00599-LEVEL 31-TMP-L31-UNITS TEMP LIGHTHING-STRINGERS | False | L31-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00599-320001TUR | 0
[9 empty] | 1488 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1488 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1488-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1488 |  |  | PF.1488 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00600-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 5/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00600-LEVEL 32-TMP-L32-UNITS TEMP LIGHTHING-STRINGERS | False | L32-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00600-320001TUR | 0
[9 empty] | 1489 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1489 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1489-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1489 |  |  | PF.1489 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00601-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 5/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00601-LEVEL 33-TMP-L33-UNITS TEMP LIGHTHING-STRINGERS | False | L33-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00601-320001TUR | 0
[9 empty] | 1490 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1490 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1490-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1490 |  |  | PF.1490 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00602-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 5/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00602-LEVEL 34-TMP-L34-UNITS TEMP LIGHTHING-STRINGERS | False | L34-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00602-320001TUR | 0
[9 empty] | 1491 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1491 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1491-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1491 |  |  | PF.1491 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00603-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.20 | 0 | 320001TUR | 6/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00603-LEVEL 35-TMP-L35-UNITS TEMP LIGHTHING-STRINGERS | False | L35-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00603-320001TUR | 0
[9 empty] | 1492 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1492 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1492-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1492 |  |  | PF.1492 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00604-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.20 | 0 | 320001TUR | 6/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00604-LEVEL 36-TMP-L36-UNITS TEMP LIGHTHING-STRINGERS | False | L36-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00604-320001TUR | 0
[9 empty] | 1493 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1493 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1493-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1493 |  |  | PF.1493 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00605-320001TUR | MXD_RESI_JAP_ELEC | 0 | 17.55 | 0 | 320001TUR | 10/13/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00605-LEVEL 11-LGT-BOH DEVICES-L11-L36 | False | BOH DEVICES L11-L36 | 0 | FAB-00605-320001TUR | 0
[9 empty] | 1494 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1494 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1494-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1494 |  |  | PF.1494 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00150 | SMC PILOT PROJECT_R23 | 8 | 0.25 | 0 | 00001SMC |  | PILOT TEST(R23) |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % | VDC | -LEVEL 1-SUP-01 | False |  | 8 | FAB-00150 | 0
[9 empty] | 1495 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1495 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1495-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1495 |  |  | PF.1495 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00146 | SMC PILOT PROJECT_R23 | 33 | 0.00 | 1 | 00001SMC | 9/24/2025 | PILOT TEST(R23) |  | Packages (FAB) Confirmed | 50.0 % | VDC | 01-LEVEL 1-DE- XFMER01 | False |  | 41 | FAB-00146 | 0
[9 empty] | 1496 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1496 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1496-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1496 |  |  | PF.1496 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00147 | SMC PILOT PROJECT_R23 | 8 | 0.00 | 0 | 00001SMC | 9/24/2025 | PILOT TEST(R23) |  | Packages (FAB) Confirmed | 50.0 % | VDC | 02-LEVEL 1-DE-ENCLOSURES01 | False |  | 8 | FAB-00147 | 0
[9 empty] | 1497 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1497 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1497-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1497 |  |  | PF.1497 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00148 | SMC PILOT PROJECT_R23 | 13 | 0.00 | 0 | 00001SMC | 9/24/2025 | PILOT TEST(R23) |  | Design Stage | 10.0 % | VDC | 03-LEVEL 1-PB-01 | False |  | 13 | FAB-00148 | 0
[9 empty] | 1498 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1498 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1498-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1498 |  |  | PF.1498 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00149 | SMC PILOT PROJECT_R23 | 22 | 0.75 | 0 | 00001SMC | 9/24/2025 | PILOT TEST(R23) |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % | VDC | 04-LEVEL 1-SUP-01 | False |  | 22 | FAB-00149 | 0
[9 empty] | 1499 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1499 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1499-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1499 |  |  | PF.1499 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00153_00001SMC | SMC PILOT PROJECT_R23 | 0 | 0.00 | 0 | 00001SMC |  | PILOT TEST(R23) |  | New Item | 35.0 % |  | FAB-00001--CND | False |  | 0 | FAB-00153_00001SMC | 0
[9 empty] | 1006 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1006 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1006-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1006 |  |  | PF.1006 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00118-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00118-LEVEL 14-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 14-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00118-320001TUR | 0
[9 empty] | 1007 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1007 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1007-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1007 |  |  | PF.1007 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00119-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00119-LEVEL 15-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 15-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00119-320001TUR | 0
[9 empty] | 1008 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1008 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1008-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1008 |  |  | PF.1008 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00120-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00120-LEVEL 16-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 16-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00120-320001TUR | 0
[9 empty] | 1009 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1009 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1009-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1009 |  |  | PF.1009 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00121-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00121-LEVEL 17-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 17-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00121-320001TUR | 0
[9 empty] | 1010 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1010 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1010-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1010 |  |  | PF.1010 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00122-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00122-LEVEL 18-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 18-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00122-320001TUR | 0
[9 empty] | 1011 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1011 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1011-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1011 |  |  | PF.1011 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00123-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/4/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00123-LEVEL 19-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 19-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00123-320001TUR | 0
[9 empty] | 1012 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1012 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1012-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1012 |  |  | PF.1012 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00124-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00124-LEVEL 20-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 20-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00124-320001TUR | 0
[9 empty] | 1013 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1013 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1013-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1013 |  |  | PF.1013 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00125-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00125-LEVEL 21-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 21-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00125-320001TUR | 0
[9 empty] | 1014 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1014 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1014-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1014 |  |  | PF.1014 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00126-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00126-LEVEL 22-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 22-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00126-320001TUR | 0
[9 empty] | 1015 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1015 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1015-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1015 |  |  | PF.1015 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00127-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00127-LEVEL 23-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 23-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00127-320001TUR | 0
[9 empty] | 1016 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1016 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1016-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1016 |  |  | PF.1016 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00128-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00128-LEVEL 24-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 24-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00128-320001TUR | 0
[9 empty] | 1017 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1017 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1017-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1017 |  |  | PF.1017 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00129-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00129-LEVEL 25-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 25-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00129-320001TUR | 0
[9 empty] | 1018 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1018 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1018-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1018 |  |  | PF.1018 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00130-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00130-LEVEL 26-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 26-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00130-320001TUR | 0
[9 empty] | 1019 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1019 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1019-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1019 |  |  | PF.1019 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00131-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00131-LEVEL 27-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 27-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00131-320001TUR | 0
[9 empty] | 1020 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1020 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1020-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1020 |  |  | PF.1020 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00132-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/8/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00132-LEVEL 28-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 28-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00132-320001TUR | 0
[9 empty] | 1021 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1021 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1021-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1021 |  |  | PF.1021 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00133-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00133-LEVEL 29-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 29-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00133-320001TUR | 0
[9 empty] | 1022 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1022 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1022-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1022 |  |  | PF.1022 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00134-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00134-LEVEL 30-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 30-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00134-320001TUR | 0
[9 empty] | 1023 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1023 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1023-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1023 |  |  | PF.1023 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00135-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00135-LEVEL 31-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 31-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00135-320001TUR | 0
[9 empty] | 1024 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1024 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1024-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1024 |  |  | PF.1024 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00136-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00136-LEVEL 32-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 32-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00136-320001TUR | 0
[9 empty] | 1025 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1025 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1025-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1025 |  |  | PF.1025 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00137-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00137-LEVEL 33-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 33-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00137-320001TUR | 0
[9 empty] | 1026 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1026 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1026-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1026 |  |  | PF.1026 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00138-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00138-LEVEL 34-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 34-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00138-320001TUR | 0
[9 empty] | 1027 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1027 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1027-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1027 |  |  | PF.1027 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00139-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00139-LEVEL 35-CND-TIER 3 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 35-TIER 3 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00139-320001TUR | 0
[9 empty] | 1028 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1028 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1028-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1028 |  |  | PF.1028 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00140-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 6/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00140-LEVEL 36-CND-TIER 3 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 36-TIER 3 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00140-320001TUR | 0
[9 empty] | 1029 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1029 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1029-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1029 |  |  | PF.1029 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00141-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 6/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00141-LEVEL 37-CND-AMENITY-MEP PH PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 37-AMENITY-MEP PH PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00141-320001TUR | 0
[9 empty] | 1030 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1030 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1030-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1030 |  |  | PF.1030 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00142-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00142-LEVEL 38-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 38 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00142-320001TUR | 0
[9 empty] | 1031 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1031 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1031-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1031 |  |  | PF.1031 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00143-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00143-LEVEL B1-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL B1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00143-320001TUR | 0
[9 empty] | 1032 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1032 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1032-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1032 |  |  | PF.1032 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00144-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00144-LEVEL 1-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00144-320001TUR | 0
[9 empty] | 1033 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1033 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1033-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1033 |  |  | PF.1033 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00145-320001TUR | MXD_RESI_JAP_ELEC | 0 | 15.60 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00145-LEVEL 2-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00145-320001TUR | 0
[9 empty] | 1034 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1034 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1034-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1034 |  |  | PF.1034 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00146-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 3/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00146-LEVEL 3-LGT-PODIUM LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 3-PODIUM LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00146-320001TUR | 0
[9 empty] | 1035 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1035 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1035-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1035 |  |  | PF.1035 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00147-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 3/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00147-LEVEL 4-LGT-PODIUM LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 4-PODIUM LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00147-320001TUR | 0
[9 empty] | 1036 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1036 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1036-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1036 |  |  | PF.1036 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00148-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 3/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00148-LEVEL 5-LGT-PODIUM LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 5-PODIUM LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00148-320001TUR | 0
[9 empty] | 1037 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1037 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1037-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1037 |  |  | PF.1037 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00149-320001TUR | MXD_RESI_JAP_ELEC | 0 | 15.60 | 0 | 320001TUR | 4/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00149-LEVEL 6-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 6 LEVEL 6 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00149-320001TUR | 0
[9 empty] | 1038 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1038 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1038-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1038 |  |  | PF.1038 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00150-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00150-LEVEL 7-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 7-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00150-320001TUR | 0
[9 empty] | 1039 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1039 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1039-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1039 |  |  | PF.1039 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00151-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/8/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00151-LEVEL 8-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 8-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00151-320001TUR | 0
[9 empty] | 1040 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1040 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1040-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1040 |  |  | PF.1040 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00152-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00152-LEVEL 9-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 9-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00152-320001TUR | 0
[9 empty] | 1041 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1041 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1041-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1041 |  |  | PF.1041 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00153-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00153-LEVEL 10-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 10-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00153-320001TUR | 0
[9 empty] | 1042 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1042 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1042-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1042 |  |  | PF.1042 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00154-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00154-LEVEL 11-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 11-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00154-320001TUR | 0
[9 empty] | 1043 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1043 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1043-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1043 |  |  | PF.1043 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00155-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 5/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00155-LEVEL 12-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 12-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00155-320001TUR | 0
[9 empty] | 1044 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1044 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1044-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1044 |  |  | PF.1044 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00156-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 5/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00156-LEVEL 13-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 13-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00156-320001TUR | 0
[9 empty] | 1045 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1045 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1045-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1045 |  |  | PF.1045 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00157-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 5/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00157-LEVEL 14-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 14-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00157-320001TUR | 0
[9 empty] | 1046 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1046 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1046-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1046 |  |  | PF.1046 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00158-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 5/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00158-LEVEL 15-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 15-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00158-320001TUR | 0
[9 empty] | 1047 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1047 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1047-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1047 |  |  | PF.1047 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00159-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00159-LEVEL 16-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 16-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00159-320001TUR | 0
[9 empty] | 1048 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1048 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1048-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1048 |  |  | PF.1048 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00160-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00160-LEVEL 17-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 17-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00160-320001TUR | 0
[9 empty] | 1049 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1049 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1049-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1049 |  |  | PF.1049 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00161-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00161-LEVEL 18-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 18-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00161-320001TUR | 0
[9 empty] | 1050 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1050 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1050-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1050 |  |  | PF.1050 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00162-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/24/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00162-LEVEL 19-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 19-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00162-320001TUR | 0
[9 empty] | 1051 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1051 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1051-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1051 |  |  | PF.1051 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00163-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00163-LEVEL 20-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 20-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00163-320001TUR | 0
[9 empty] | 1052 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1052 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1052-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1052 |  |  | PF.1052 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00164-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/8/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00164-LEVEL 21-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 21-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00164-320001TUR | 0
[9 empty] | 1053 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1053 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1053-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1053 |  |  | PF.1053 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00165-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00165-LEVEL 22-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 22-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00165-320001TUR | 0
[9 empty] | 1054 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1054 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1054-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1054 |  |  | PF.1054 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00166-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00166-LEVEL 23-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 23-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00166-320001TUR | 0
[9 empty] | 1055 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1055 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1055-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1055 |  |  | PF.1055 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00167-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00167-LEVEL 24-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 24-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00167-320001TUR | 0
[9 empty] | 1056 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1056 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1056-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1056 |  |  | PF.1056 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00168-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 8/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00168-LEVEL 25-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 25-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00168-320001TUR | 0
[9 empty] | 1057 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1057 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1057-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1057 |  |  | PF.1057 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00169-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 8/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00169-LEVEL 26-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 26-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00169-320001TUR | 0
[9 empty] | 1058 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1058 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1058-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1058 |  |  | PF.1058 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00170-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 8/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00170-LEVEL 27-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 27-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00170-320001TUR | 0
[9 empty] | 1059 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1059 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1059-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1059 |  |  | PF.1059 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00171-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 8/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00171-LEVEL 28-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 28-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00171-320001TUR | 0
[9 empty] | 1060 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1060 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1060-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1060 |  |  | PF.1060 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00172-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00172-LEVEL 29-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 29-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00172-320001TUR | 0
[9 empty] | 1061 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1061 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1061-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1061 |  |  | PF.1061 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00173-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00173-LEVEL 30-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 30-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00173-320001TUR | 0
[9 empty] | 1062 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1062 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1062-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1062 |  |  | PF.1062 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00174-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00174-LEVEL 31-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 31-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00174-320001TUR | 0
[9 empty] | 1063 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1063 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1063-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1063 |  |  | PF.1063 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00175-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00175-LEVEL 32-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 32-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00175-320001TUR | 0
[9 empty] | 1064 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1064 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1064-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1064 |  |  | PF.1064 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00176-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00176-LEVEL 33-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 33-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00176-320001TUR | 0
[9 empty] | 1065 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1065 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1065-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1065 |  |  | PF.1065 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00177-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 10/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00177-LEVEL 34-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 34-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00177-320001TUR | 0
[9 empty] | 1066 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1066 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1066-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1066 |  |  | PF.1066 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00178-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 10/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00178-LEVEL 35-LGT-TIER 3 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 35-TIER 3 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00178-320001TUR | 0
[9 empty] | 1067 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1067 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1067-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1067 |  |  | PF.1067 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00179-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 10/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00179-LEVEL 36-LGT-TIER 3 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 36-TIER 3 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00179-320001TUR | 0
[9 empty] | 1068 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1068 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1068-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1068 |  |  | PF.1068 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00180-320001TUR | MXD_RESI_JAP_ELEC | 0 | 15.60 | 0 | 320001TUR | 10/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00180-LEVEL 37-LGT-AMENITY-MEP PH LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 37-AMENITY-MEP PH LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00180-320001TUR | 0
[9 empty] | 1069 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1069 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1069-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1069 |  |  | PF.1069 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00181-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00181-LEVEL 38-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 38 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00181-320001TUR | 0
[9 empty] | 1070 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1070 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1070-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1070 |  |  | PF.1070 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00182-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00182-LEVEL 39-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 39 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00182-320001TUR | 0
[9 empty] | 1071 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1071 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1071-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1071 |  |  | PF.1071 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00183-320001TUR | MXD_RESI_JAP_ELEC | 0 | 16.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00183-LEVEL B1-LGT-LIGHTING CONTROL PANEL ASSEMBLY WIRED | False | LIGHTING CONTROL PANEL ASSEMBLY WIRED | 0 | FAB-00183-320001TUR | 0
[9 empty] | 1072 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1072 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1072-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1072 |  |  | PF.1072 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00184-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.12 | 0 | 320001TUR | 9/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00184-LEVEL B1-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL B1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00184-320001TUR | 0
[9 empty] | 1073 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1073 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1073-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1073 |  |  | PF.1073 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00185-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.77 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00185-LEVEL 1-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00185-320001TUR | 0
[9 empty] | 1074 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1074 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1074-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1074 |  |  | PF.1074 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00186-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.24 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00186-LEVEL 2-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00186-320001TUR | 0
[9 empty] | 1075 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1075 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1075-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1075 |  |  | PF.1075 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00187-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00187-LEVEL 3-IW-PODIUM JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 3-PODIUM JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00187-320001TUR | 0
[9 empty] | 1076 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1076 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1076-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1076 |  |  | PF.1076 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00188-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00188-LEVEL 4-IW-PODIUM JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 4-PODIUM JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00188-320001TUR | 0
[9 empty] | 1077 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1077 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1077-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1077 |  |  | PF.1077 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00189-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00189-LEVEL 5-IW-PODIUM JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 5-PODIUM JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00189-320001TUR | 0
[9 empty] | 1078 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1078 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1078-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1078 |  |  | PF.1078 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00190-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.24 | 0 | 320001TUR | 9/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00190-LEVEL 6-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 6 LEVEL 6 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00190-320001TUR | 0
[9 empty] | 1079 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1079 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1079-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1079 |  |  | PF.1079 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00191-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00191-LEVEL 7-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 7-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00191-320001TUR | 0
[9 empty] | 1080 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1080 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1080-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1080 |  |  | PF.1080 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00192-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00192-LEVEL 8-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 8-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00192-320001TUR | 0
[9 empty] | 1081 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1081 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1081-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1081 |  |  | PF.1081 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00193-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00193-LEVEL 9-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 9-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00193-320001TUR | 0
[9 empty] | 1082 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1082 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1082-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1082 |  |  | PF.1082 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00194-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00194-LEVEL 10-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 10-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00194-320001TUR | 0
[9 empty] | 1083 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1083 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1083-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1083 |  |  | PF.1083 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00195-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00195-LEVEL 11-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 11-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00195-320001TUR | 0
[9 empty] | 1084 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1084 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1084-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1084 |  |  | PF.1084 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00196-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00196-LEVEL 12-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 12-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00196-320001TUR | 0
[9 empty] | 1085 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1085 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1085-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1085 |  |  | PF.1085 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00197-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00197-LEVEL 13-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 13-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00197-320001TUR | 0
[9 empty] | 1086 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1086 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1086-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1086 |  |  | PF.1086 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00198-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 1/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00198-LEVEL 14-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 14-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00198-320001TUR | 0
[9 empty] | 1087 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1087 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1087-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1087 |  |  | PF.1087 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00199-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 1/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00199-LEVEL 15-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 15-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00199-320001TUR | 0
[9 empty] | 1088 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1088 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1088-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1088 |  |  | PF.1088 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00200-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 1/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00200-LEVEL 16-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 16-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00200-320001TUR | 0
[9 empty] | 1089 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1089 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1089-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1089 |  |  | PF.1089 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00201-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 2/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00201-LEVEL 17-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 17-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00201-320001TUR | 0
[9 empty] | 1090 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1090 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1090-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1090 |  |  | PF.1090 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00202-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 2/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00202-LEVEL 18-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 18-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00202-320001TUR | 0
[9 empty] | 1091 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1091 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1091-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1091 |  |  | PF.1091 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00203-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 2/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00203-LEVEL 19-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 19-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00203-320001TUR | 0
[9 empty] | 1092 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1092 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1092-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1092 |  |  | PF.1092 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00204-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 2/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00204-LEVEL 20-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 20-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00204-320001TUR | 0
[9 empty] | 1093 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1093 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1093-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1093 |  |  | PF.1093 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00205-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 3/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00205-LEVEL 21-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 21-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00205-320001TUR | 0
[9 empty] | 1094 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1094 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1094-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1094 |  |  | PF.1094 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00206-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00206-LEVEL 22-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 22-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00206-320001TUR | 0
[9 empty] | 1095 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1095 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1095-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1095 |  |  | PF.1095 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00207-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 3/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00207-LEVEL 23-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 23-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00207-320001TUR | 0
[9 empty] | 1096 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1096 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1096-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1096 |  |  | PF.1096 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00208-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 3/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00208-LEVEL 24-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 24-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00208-320001TUR | 0
[9 empty] | 1097 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1097 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1097-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1097 |  |  | PF.1097 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00209-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 4/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00209-LEVEL 25-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 25-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00209-320001TUR | 0
[9 empty] | 1098 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1098 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1098-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1098 |  |  | PF.1098 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00210-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 4/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00210-LEVEL 26-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 26-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00210-320001TUR | 0
[9 empty] | 1099 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1099 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1099-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1099 |  |  | PF.1099 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00211-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 4/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00211-LEVEL 27-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 27-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00211-320001TUR | 0
[9 empty] | 1100 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1100 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1100-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1100 |  |  | PF.1100 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00212-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 4/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00212-LEVEL 28-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 28-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00212-320001TUR | 0
[9 empty] | 1101 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1101 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1101-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1101 |  |  | PF.1101 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00213-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 5/4/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00213-LEVEL 29-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 29-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00213-320001TUR | 0
[9 empty] | 1102 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1102 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1102-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1102 |  |  | PF.1102 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00214-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 5/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00214-LEVEL 30-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 30-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00214-320001TUR | 0
[9 empty] | 1103 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1103 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1103-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1103 |  |  | PF.1103 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00215-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 5/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00215-LEVEL 31-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 31-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00215-320001TUR | 0
[9 empty] | 1104 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1104 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1104-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1104 |  |  | PF.1104 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00216-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 5/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00216-LEVEL 32-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 32-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00216-320001TUR | 0
[9 empty] | 1105 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1105 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1105-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1105 |  |  | PF.1105 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00217-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 6/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00217-LEVEL 33-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 33-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00217-320001TUR | 0
[9 empty] | 1106 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1106 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1106-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1106 |  |  | PF.1106 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00218-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 6/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00218-LEVEL 34-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 34-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00218-320001TUR | 0
[9 empty] | 1107 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1107 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1107-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1107 |  |  | PF.1107 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00219-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 6/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00219-LEVEL 35-IW-TIER 3 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 35-TIER 3 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00219-320001TUR | 0
[9 empty] | 1108 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1108 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1108-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1108 |  |  | PF.1108 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00220-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 6/24/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00220-LEVEL 36-IW-TIER 3 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 36-TIER 3 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00220-320001TUR | 0
[9 empty] | 1109 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1109 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1109-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1109 |  |  | PF.1109 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00221-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.95 | 0 | 320001TUR | 7/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00221-LEVEL 37-IW-AMENITY-MEP PH JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 37-AMENITY-MEP PH JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00221-320001TUR | 0
[9 empty] | 1110 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1110 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1110-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1110 |  |  | PF.1110 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00222-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.24 | 0 | 320001TUR | 7/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00222-LEVEL 38-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 38 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00222-320001TUR | 0
[9 empty] | 1111 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1111 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1111-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1111 |  |  | PF.1111 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00223-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00223-LEVEL B1-SUP-HANGER STRUT-POWER | False | LEVEL B1 HANGER STRUT POWER | 0 | FAB-00223-320001TUR | 0
[9 empty] | 1112 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1112 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1112-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1112 |  |  | PF.1112 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00224-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00224-LEVEL 1-SUP-HANGER STRUT-POWER | False | LEVEL 1 HANGER STRUT POWER | 0 | FAB-00224-320001TUR | 0
[9 empty] | 1113 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1113 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1113-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1113 |  |  | PF.1113 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00225-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00225-LEVEL 2-SUP-HANGER STRUT-POWER | False | LEVEL 2 HANGER STRUT POWER | 0 | FAB-00225-320001TUR | 0
[9 empty] | 1114 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1114 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1114-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1114 |  |  | PF.1114 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00226-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00226-LEVEL 6-SUP-HANGER STRUT-POWER-WEST SIDE | False | LEVEL 6 HANGER STRUT POWER-WEST SIDE | 0 | FAB-00226-320001TUR | 0
[9 empty] | 1115 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1115 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1115-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1115 |  |  | PF.1115 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00227-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/9/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00227-LEVEL 36-SUP-TIER 3 HANGER STRUT-POWER | False | LEVEL 36-TIER 3 HANGER STRUT POWER | 0 | FAB-00227-320001TUR | 0
[9 empty] | 1116 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1116 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1116-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1116 |  |  | PF.1116 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00228-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00228-LEVEL 37-SUP-AMENITY-MEP PH HANGER STRUT-POWER | False | LEVEL 37-AMENITY-MEP PH HANGER STRUT POWER | 0 | FAB-00228-320001TUR | 0
[9 empty] | 1117 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1117 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1117-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1117 |  |  | PF.1117 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00229-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00229-LEVEL 38-SUP-HANGER STRUT-POWER | False | LEVEL 38 HANGER STRUT POWER | 0 | FAB-00229-320001TUR | 0
[9 empty] | 1118 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1118 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1118-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1118 |  |  | PF.1118 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00230-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00230-LEVEL B1-CND-PIPE BENDS-LARGE POWER | False | LEVEL B1 PIPE BENDS LARGE POWER | 0 | FAB-00230-320001TUR | 0
[9 empty] | 1119 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1119 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1119-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1119 |  |  | PF.1119 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00231-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00231-LEVEL 1-CND-PIPE BENDS-LARGE POWER | False | LEVEL 1 PIPE BENDS LARGE POWER | 0 | FAB-00231-320001TUR | 0
[9 empty] | 1120 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1120 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1120-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1120 |  |  | PF.1120 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00232-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00232-LEVEL 2-CND-PIPE BENDS-LARGE POWER | False | LEVEL 2 PIPE BENDS LARGE POWER | 0 | FAB-00232-320001TUR | 0
[9 empty] | 1121 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1121 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1121-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1121 |  |  | PF.1121 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00233-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00233-LEVEL 6-CND-PIPE BENDS-LARGE POWER | False | LEVEL 6 LEVEL 6 PIPE BENDS LARGE POWER | 0 | FAB-00233-320001TUR | 0
[9 empty] | 1122 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1122 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1122-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1122 |  |  | PF.1122 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00234-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00234-LEVEL 36-CND-TIER 3 PIPE BENDS-LARGE POWER | False | LEVEL 36-TIER 3 PIPE BENDS LARGE POWER | 0 | FAB-00234-320001TUR | 0
[9 empty] | 1123 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1123 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1123-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1123 |  |  | PF.1123 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00235-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00235-LEVEL 37-CND-AMENITY-MEP PH PIPE BENDS-LARGE POWER | False | LEVEL 37-AMENITY-MEP PH PIPE BENDS LARGE POWER | 0 | FAB-00235-320001TUR | 0
[9 empty] | 1124 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1124 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1124-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1124 |  |  | PF.1124 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00236-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00236-LEVEL 38-CND-PIPE BENDS-LARGE POWER | False | LEVEL 38 PIPE BENDS LARGE POWER | 0 | FAB-00236-320001TUR | 0
[9 empty] | 1125 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1125 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1125-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1125 |  |  | PF.1125 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00237-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00237-LEVEL B1-CND-MODULAR EMT-5 LARGE | False | LEVEL B1 MODULAR EMT 5 LARGE | 0 | FAB-00237-320001TUR | 0
[9 empty] | 1126 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1126 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1126-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1126 |  |  | PF.1126 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00238-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00238-LEVEL 1-CND-MODULAR EMT-5 LARGE | False | LEVEL 1 MODULAR EMT 5 LARGE | 0 | FAB-00238-320001TUR | 0
[9 empty] | 1127 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1127 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1127-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1127 |  |  | PF.1127 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00239-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00239-LEVEL 35-CND-TIER 3-MODULAR EMT-5 LARGE | False | LEVEL 35-TIER 3-MODULAR EMT 5 LARGE | 0 | FAB-00239-320001TUR | 0
[9 empty] | 1128 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1128 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1128-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1128 |  |  | PF.1128 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00240-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00240-LEVEL 36-CND-TIER 3-MODULAR EMT-5 LARGE | False | LEVEL 36-TIER 3-MODULAR EMT 5 LARGE | 0 | FAB-00240-320001TUR | 0
[9 empty] | 1129 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1129 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1129-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1129 |  |  | PF.1129 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00241-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00241-LEVEL 37-CND-AMENITY-MEP PH-MODULAR EMT-5 LARGE | False | LEVEL 37-AMENITY-MEP PH-MODULAR EMT 5 LARGE | 0 | FAB-00241-320001TUR | 0
[9 empty] | 1130 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1130 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1130-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1130 |  |  | PF.1130 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00242-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00242-LEVEL 38-CND-MODULAR EMT-5 LARGE | False | LEVEL 38 MODULAR EMT 5 LARGE | 0 | FAB-00242-320001TUR | 0
[9 empty] | 1131 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1131 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1131-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1131 |  |  | PF.1131 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00243-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00243-LEVEL 39-CND-MODULAR EMT-5 LARGE | False | LEVEL 39 MODULAR EMT 5 LARGE | 0 | FAB-00243-320001TUR | 0
[9 empty] | 1132 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1132 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1132-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1132 |  |  | PF.1132 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00244-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00244-LEVEL B1-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL B1 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00244-320001TUR | 0
[9 empty] | 1133 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1133 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1133-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1133 |  |  | PF.1133 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00245-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00245-LEVEL 1-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 1 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00245-320001TUR | 0
[9 empty] | 1134 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1134 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1134-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1134 |  |  | PF.1134 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00246-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00246-LEVEL 2-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 2 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00246-320001TUR | 0
[9 empty] | 1135 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1135 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1135-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1135 |  |  | PF.1135 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00247-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00247-LEVEL 3-CND-PODIUM-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 3-PODIUM-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00247-320001TUR | 0
[9 empty] | 1136 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1136 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1136-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1136 |  |  | PF.1136 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00248-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00248-LEVEL 4-CND-PODIUM-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 4-PODIUM-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00248-320001TUR | 0
[9 empty] | 1137 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1137 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1137-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1137 |  |  | PF.1137 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00249-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00249-LEVEL 5-CND-PODIUM-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 5-PODIUM-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00249-320001TUR | 0
[9 empty] | 1138 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1138 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1138-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1138 |  |  | PF.1138 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00250-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00250-LEVEL 6-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 6 LEVEL 6-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00250-320001TUR | 0
[9 empty] | 1139 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1139 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1139-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1139 |  |  | PF.1139 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00251-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00251-LEVEL 7-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 7-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00251-320001TUR | 0
[9 empty] | 1140 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1140 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1140-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1140 |  |  | PF.1140 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00252-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00252-LEVEL 8-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 8-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00252-320001TUR | 0
[9 empty] | 1141 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1141 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1141-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1141 |  |  | PF.1141 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00253-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00253-LEVEL 9-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 9-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00253-320001TUR | 0
[9 empty] | 1142 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1142 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1142-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1142 |  |  | PF.1142 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00254-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00254-LEVEL 10-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 10-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00254-320001TUR | 0
[9 empty] | 1143 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1143 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1143-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1143 |  |  | PF.1143 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00255-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00255-LEVEL 11-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 11-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00255-320001TUR | 0
[9 empty] | 1144 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1144 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1144-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1144 |  |  | PF.1144 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00256-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00256-LEVEL 12-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 12-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00256-320001TUR | 0
[9 empty] | 1145 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1145 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1145-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1145 |  |  | PF.1145 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00257-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00257-LEVEL 13-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 13-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00257-320001TUR | 0
[9 empty] | 1146 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1146 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1146-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1146 |  |  | PF.1146 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00258-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00258-LEVEL 14-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 14-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00258-320001TUR | 0
[9 empty] | 1147 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1147 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1147-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1147 |  |  | PF.1147 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00259-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00259-LEVEL 15-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 15-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00259-320001TUR | 0
[9 empty] | 1148 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1148 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1148-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1148 |  |  | PF.1148 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00260-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00260-LEVEL 16-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 16-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00260-320001TUR | 0
[9 empty] | 1149 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1149 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1149-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1149 |  |  | PF.1149 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00261-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00261-LEVEL 17-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 17-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00261-320001TUR | 0
[9 empty] | 1150 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1150 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1150-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1150 |  |  | PF.1150 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00262-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00262-LEVEL 18-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 18-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00262-320001TUR | 0
[9 empty] | 1151 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1151 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1151-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1151 |  |  | PF.1151 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00263-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00263-LEVEL 19-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 19-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00263-320001TUR | 0
[9 empty] | 1152 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1152 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1152-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1152 |  |  | PF.1152 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00264-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00264-LEVEL 20-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 20-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00264-320001TUR | 0
[9 empty] | 1153 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1153 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1153-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1153 |  |  | PF.1153 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00265-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00265-LEVEL 21-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 21-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00265-320001TUR | 0
[9 empty] | 1154 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1154 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1154-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1154 |  |  | PF.1154 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00266-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00266-LEVEL 22-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 22-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00266-320001TUR | 0
[9 empty] | 1155 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1155 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1155-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1155 |  |  | PF.1155 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00267-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00267-LEVEL 23-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 23-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00267-320001TUR | 0
[9 empty] | 1156 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1156 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1156-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1156 |  |  | PF.1156 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00268-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00268-LEVEL 24-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 24-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00268-320001TUR | 0
[9 empty] | 1157 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1157 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1157-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1157 |  |  | PF.1157 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00269-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00269-LEVEL 25-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 25-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00269-320001TUR | 0
[9 empty] | 1158 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1158 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1158-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1158 |  |  | PF.1158 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00270-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00270-LEVEL 26-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 26-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00270-320001TUR | 0
[9 empty] | 1159 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1159 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1159-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1159 |  |  | PF.1159 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00271-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00271-LEVEL 27-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 27-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00271-320001TUR | 0
[9 empty] | 1160 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1160 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1160-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1160 |  |  | PF.1160 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00272-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00272-LEVEL 28-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 28-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00272-320001TUR | 0
[9 empty] | 1161 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1161 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1161-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1161 |  |  | PF.1161 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00273-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00273-LEVEL 29-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 29-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00273-320001TUR | 0
[9 empty] | 1162 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1162 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1162-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1162 |  |  | PF.1162 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00274-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00274-LEVEL 30-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 30-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00274-320001TUR | 0
[9 empty] | 1163 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1163 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1163-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1163 |  |  | PF.1163 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00275-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00275-LEVEL 31-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 31-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00275-320001TUR | 0
[9 empty] | 1164 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1164 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1164-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1164 |  |  | PF.1164 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00276-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00276-LEVEL 32-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 32-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00276-320001TUR | 0
[9 empty] | 1165 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1165 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1165-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1165 |  |  | PF.1165 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00277-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00277-LEVEL 33-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 33-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00277-320001TUR | 0
[9 empty] | 1166 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1166 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1166-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1166 |  |  | PF.1166 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00278-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00278-LEVEL 34-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 34-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00278-320001TUR | 0
[9 empty] | 1167 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1167 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1167-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1167 |  |  | PF.1167 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00279-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00279-LEVEL 35-CND-TIER 3-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 35-TIER 3-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00279-320001TUR | 0
[9 empty] | 1168 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1168 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1168-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1168 |  |  | PF.1168 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00280-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00280-LEVEL 36-CND-TIER 3-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 36-TIER 3-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00280-320001TUR | 0
[9 empty] | 1169 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1169 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1169-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1169 |  |  | PF.1169 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00281-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00281-LEVEL 37-CND-AMENITY-MEP PH-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 37-AMENITY-MEP PH-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00281-320001TUR | 0
[9 empty] | 1170 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1170 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1170-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1170 |  |  | PF.1170 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00282-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00282-LEVEL 38-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 38 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00282-320001TUR | 0
[9 empty] | 1171 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1171 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1171-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1171 |  |  | PF.1171 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00283-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00283-LEVEL 39-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 39 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00283-320001TUR | 0
[9 empty] | 1172 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1172 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1172-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1172 |  |  | PF.1172 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00284-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.50 | 0 | 320001TUR | 7/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00284-LEVEL 1-DE-PANEL ASSEMBLY-STRUT BUILD DH1-EDH1-EL1-LH1-MH1-PL1-SDP1-SP1-LRH1 | False | LEVEL 1 PANEL ASSEMBLY STRUT BUILD DH1 EDH1 EL1 LH1 MH1 PL1 SDP1 SP1 LRH1 | 0 | FAB-00284-320001TUR | 0
[9 empty] | 1173 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1173 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1173-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1173 |  |  | PF.1173 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00285-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.50 | 0 | 320001TUR | 10/20/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00285-LEVEL 2-DE-PANEL ASSEMBLY-STRUT BUILD LH2-MH2-PL2-SP2 | False | LEVEL 2 PANEL ASSEMBLY STRUT BUILD LH2 MH2 PL2 SP2 | 0 | FAB-00285-320001TUR | 0
[9 empty] | 1174 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1174 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1174-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1174 |  |  | PF.1174 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00286-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00286-LEVEL 4-DE-PODIUM-PL4 PANEL ASSEMBLY | False | LEVEL 4-PODIUM-PL4 PANEL ASSEMBLY | 0 | FAB-00286-320001TUR | 0
[9 empty] | 1175 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1175 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1175-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1175 |  |  | PF.1175 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00287-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.50 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00287-LEVEL 5-DE-PODIUM-HPH5-EPH5-EPL5 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 5-PODIUM-HPH5EPH5EPL5 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00287-320001TUR | 0
[9 empty] | 1176 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1176 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1176-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1176 |  |  | PF.1176 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00288-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.00 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00288-LEVEL 6-DE-PANEL ASSEMBLY-STRUT BUILD DH6-LH6-PLM6-PL6 | False | LEVEL 6 LEVEL 6-PANEL ASSEMBLY STRUT BUILD DH6 LH6 PLM6 PL6 | 0 | FAB-00288-320001TUR | 0
[9 empty] | 1177 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1177 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1177-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1177 |  |  | PF.1177 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00289-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00289-LEVEL 6-DE-PODIUM-PL6 PANEL ASSEMBLY | False | LEVEL 6-PODIUM-PL6 PANEL ASSEMBLY | 0 | FAB-00289-320001TUR | 0
[9 empty] | 1178 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1178 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1178-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1178 |  |  | PF.1178 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00290-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 11/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00290-LEVEL 10-DE-EPH10-EPL10 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 10-EPH10EPL10 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00290-320001TUR | 0
[9 empty] | 1179 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1179 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1179-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1179 |  |  | PF.1179 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00291-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00291-LEVEL 11-DE-TIER 1-PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 11-TIER 1-PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00291-320001TUR | 0
[9 empty] | 1180 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1180 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1180-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1180 |  |  | PF.1180 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00292-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00292-LEVEL 14-DE-TIER 1-PL14-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 14-TIER 1-PL14 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00292-320001TUR | 0
[9 empty] | 1181 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1181 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1181-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1181 |  |  | PF.1181 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00293-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 12/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00293-LEVEL 15-DE-TIER 2-EPH15-EPL15 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 15-TIER 2-EPH15EPL15 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00293-320001TUR | 0
[9 empty] | 1182 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1182 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1182-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1182 |  |  | PF.1182 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00294-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00294-LEVEL 17-DE-TIER 2-HPH17 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 17-TIER 2-HPH17 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00294-320001TUR | 0
[9 empty] | 1183 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1183 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1183-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1183 |  |  | PF.1183 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00295-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00295-LEVEL 20-DE-TIER 2-EPH20-EPL20 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 20-TIER 2-EPH20EPL20 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00295-320001TUR | 0
[9 empty] | 1184 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1184 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1184-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1184 |  |  | PF.1184 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00296-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00296-LEVEL 22-DE-TIER 2-PL22 | False | LEVEL 22-TIER 2-PL22 | 0 | FAB-00296-320001TUR | 0
[9 empty] | 1185 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1185 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1185-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1185 |  |  | PF.1185 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00297-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00297-LEVEL 24-DE-TIER 2-PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 24-TIER 2-PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00297-320001TUR | 0
[9 empty] | 1186 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1186 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1186-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1186 |  |  | PF.1186 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00298-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 3/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00298-LEVEL 25-DE-TIER 2-PANEL PL25 | False | LEVEL 25-TIER 2-PANEL PL25 | 0 | FAB-00298-320001TUR | 0
[9 empty] | 1187 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1187 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1187-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1187 |  |  | PF.1187 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00299-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 4/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00299-LEVEL 28-DE-TIER 2-PANEL PL28 | False | LEVEL 28-TIER 2-PANEL PL28 | 0 | FAB-00299-320001TUR | 0
[9 empty] | 1188 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1188 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1188-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1188 |  |  | PF.1188 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00300-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.50 | 0 | 320001TUR | 4/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00300-LEVEL 29-DE-TIER 2-PANEL HPH29-EPH29-EPL29 | False | LEVEL 29-TIER 2-PANEL HPH29EPH29EPL29 | 0 | FAB-00300-320001TUR | 0
[9 empty] | 1189 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1189 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1189-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1189 |  |  | PF.1189 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00301-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 4/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00301-LEVEL 31-DE-TIER 2-PANEL PL31 | False | LEVEL 31-TIER 2-PANEL PL31 | 0 | FAB-00301-320001TUR | 0
[9 empty] | 1190 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1190 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1190-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1190 |  |  | PF.1190 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00302-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 5/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00302-LEVEL 34-DE-TIER 2-PANEL PL34 | False | LEVEL 34-TIER 2-PANEL PL34 | 0 | FAB-00302-320001TUR | 0
[9 empty] | 1191 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1191 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1191-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1191 |  |  | PF.1191 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00303-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.50 | 0 | 320001TUR | 2/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00303-LEVEL 37-DE-AMENITY-MEP PH-PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 37-AMENITY-MEP PH-PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00303-320001TUR | 0
[9 empty] | 1192 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1192 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1192-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1192 |  |  | PF.1192 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00304-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00304-LEVEL 3-DE-PODIUM-HPH3 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 3-PODIUM-HPH3 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00304-320001TUR | 0
[9 empty] | 1193 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1193 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1193-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1193 |  |  | PF.1193 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00305-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00305-LEVEL 4-DE-PODIUM-PANEL EPH4-EPL4 | False | LEVEL 4-PODIUM-PANEL EPH4EPL4 | 0 | FAB-00305-320001TUR | 0
[9 empty] | 1194 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1194 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1194-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1194 |  |  | PF.1194 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00306-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 8/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00306-LEVEL 5-DE-PODIUM-METER STACK | False | LEVEL 5-PODIUM-METER STACK | 0 | FAB-00306-320001TUR | 0
[9 empty] | 1195 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1195 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1195-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1195 |  |  | PF.1195 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00307-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 8/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00307-LEVEL 6-DE-METER STACK | False | LEVEL 6 LEVEL 6-METER STACK | 0 | FAB-00307-320001TUR | 0
[9 empty] | 1196 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1196 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1196-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1196 |  |  | PF.1196 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00308-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 9/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00308-LEVEL 7-DE-TIER 1-METER STACK | False | LEVEL 7-TIER 1-METER STACK | 0 | FAB-00308-320001TUR | 0
[9 empty] | 1197 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1197 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1197-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1197 |  |  | PF.1197 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00309-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00309-LEVEL 8-DE-PL8-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 8-PL8 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00309-320001TUR | 0
[9 empty] | 1198 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1198 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1198-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1198 |  |  | PF.1198 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00310-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 11/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00310-LEVEL 9-DE-HPH9 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 9-HPH9 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00310-320001TUR | 0
[9 empty] | 1199 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1199 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1199-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1199 |  |  | PF.1199 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00311-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00311-LEVEL 10-DE-TIER 1-METER STACK | False | LEVEL 10-TIER 1-METER STACK | 0 | FAB-00311-320001TUR | 0
[9 empty] | 1200 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1200 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1200-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1200 |  |  | PF.1200 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00312-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 11/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00312-LEVEL 11-DE-PL11-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 11-PL11 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00312-320001TUR | 0
[9 empty] | 1201 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1201 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1201-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1201 |  |  | PF.1201 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00313-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00313-LEVEL 12-DE-TIER 1-METER STACK | False | LEVEL 12-TIER 1-METER STACK | 0 | FAB-00313-320001TUR | 0
[9 empty] | 1202 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1202 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1202-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1202 |  |  | PF.1202 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00314-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00314-LEVEL 13-DE-TIER 1-HPH13 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 13-TIER 1-HPH13 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00314-320001TUR | 0
[9 empty] | 1203 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1203 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1203-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1203 |  |  | PF.1203 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00315-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 10/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00315-LEVEL 14-DE-TIER 1-METER STACK | False | LEVEL 14-TIER 1-METER STACK | 0 | FAB-00315-320001TUR | 0
[9 empty] | 1204 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1204 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1204-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1204 |  |  | PF.1204 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00316-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00316-LEVEL 15-DE-TIER 2-METER STACK | False | LEVEL 15-TIER 2-METER STACK | 0 | FAB-00316-320001TUR | 0
[9 empty] | 1205 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1205 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1205-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1205 |  |  | PF.1205 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00317-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00317-LEVEL 16-DE-TIER 2-METER STACK | False | LEVEL 16-TIER 2-METER STACK | 0 | FAB-00317-320001TUR | 0
[9 empty] | 1206 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1206 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1206-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1206 |  |  | PF.1206 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00318-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00318-LEVEL 17-DE-TIER 2-PL17-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 17-TIER 2-PL17 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00318-320001TUR | 0
[9 empty] | 1207 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1207 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1207-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1207 |  |  | PF.1207 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00319-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00319-LEVEL 18-DE-TIER 2-METER STACK | False | LEVEL 18-TIER 2-METER STACK | 0 | FAB-00319-320001TUR | 0
[9 empty] | 1208 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1208 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1208-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1208 |  |  | PF.1208 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00320-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00320-LEVEL 19-DE-TIER 2-METER STACK | False | LEVEL 19-TIER 2-METER STACK | 0 | FAB-00320-320001TUR | 0
[9 empty] | 1209 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1209 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1209-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1209 |  |  | PF.1209 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00321-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00321-LEVEL 20-DE-TIER 2-PL20-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 20-TIER 2-PL20 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00321-320001TUR | 0
[9 empty] | 1210 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1210 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1210-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1210 |  |  | PF.1210 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00322-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00322-LEVEL 21-DE-TIER 2-METER STACK | False | LEVEL 21-TIER 2-METER STACK | 0 | FAB-00322-320001TUR | 0
[9 empty] | 1211 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1211 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1211-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1211 |  |  | PF.1211 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00323-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00323-LEVEL 22-DE-TIER 2-METER STACK | False | LEVEL 22-TIER 2-METER STACK | 0 | FAB-00323-320001TUR | 0
[9 empty] | 1212 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1212 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1212-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1212 |  |  | PF.1212 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00324-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00324-LEVEL 23-DE-TIER 2-METER STACK | False | LEVEL 23-TIER 2-METER STACK | 0 | FAB-00324-320001TUR | 0
[9 empty] | 1213 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1213 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1213-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1213 |  |  | PF.1213 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00325-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00325-LEVEL 24-DE-TIER 2-METER STACK | False | LEVEL 24-TIER 2-METER STACK | 0 | FAB-00325-320001TUR | 0
[9 empty] | 1214 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1214 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1214-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1214 |  |  | PF.1214 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00326-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00326-LEVEL 25-DE-TIER 2-METER STACK | False | LEVEL 25-TIER 2-METER STACK | 0 | FAB-00326-320001TUR | 0
[9 empty] | 1215 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1215 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1215-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1215 |  |  | PF.1215 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00327-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00327-LEVEL 26-DE-TIER 2-METER STACK | False | LEVEL 26-TIER 2-METER STACK | 0 | FAB-00327-320001TUR | 0
[9 empty] | 1216 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1216 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1216-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1216 |  |  | PF.1216 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00328-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00328-LEVEL 27-DE-TIER 2-METER STACK | False | LEVEL 27-TIER 2-METER STACK | 0 | FAB-00328-320001TUR | 0
[9 empty] | 1217 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1217 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1217-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1217 |  |  | PF.1217 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00329-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00329-LEVEL 28-DE-TIER 2-METER STACK | False | LEVEL 28-TIER 2-METER STACK | 0 | FAB-00329-320001TUR | 0
[9 empty] | 1218 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1218 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1218-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1218 |  |  | PF.1218 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00330-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00330-LEVEL 29-DE-TIER 2-METER STACK | False | LEVEL 29-TIER 2-METER STACK | 0 | FAB-00330-320001TUR | 0
[9 empty] | 1219 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1219 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1219-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1219 |  |  | PF.1219 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00331-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00331-LEVEL 30-DE-TIER 2-METER STACK | False | LEVEL 30-TIER 2-METER STACK | 0 | FAB-00331-320001TUR | 0
[9 empty] | 1220 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1220 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1220-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1220 |  |  | PF.1220 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00332-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00332-LEVEL 31-DE-TIER 2-METER STACK | False | LEVEL 31-TIER 2-METER STACK | 0 | FAB-00332-320001TUR | 0
[9 empty] | 1221 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1221 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1221-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1221 |  |  | PF.1221 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00333-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00333-LEVEL 32-DE-TIER 2-METER STACK | False | LEVEL 32-TIER 2-METER STACK | 0 | FAB-00333-320001TUR | 0
[9 empty] | 1222 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1222 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1222-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1222 |  |  | PF.1222 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00334-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00334-LEVEL 33-DE-TIER 2-METER STACK | False | LEVEL 33-TIER 2-METER STACK | 0 | FAB-00334-320001TUR | 0
[9 empty] | 1223 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1223 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1223-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1223 |  |  | PF.1223 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00335-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00335-LEVEL 34-DE-TIER 2-METER STACK | False | LEVEL 34-TIER 2-METER STACK | 0 | FAB-00335-320001TUR | 0
[9 empty] | 1224 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1224 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1224-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1224 |  |  | PF.1224 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00336-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 4/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00336-LEVEL 35-DE-TIER 3-METER STACK | False | LEVEL 35-TIER 3-METER STACK | 0 | FAB-00336-320001TUR | 0
[9 empty] | 1225 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1225 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1225-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1225 |  |  | PF.1225 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00337-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 4/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00337-LEVEL 36-DE-TIER 3-METER STACK | False | LEVEL 36-TIER 3-METER STACK | 0 | FAB-00337-320001TUR | 0
[9 empty] | 1226 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1226 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1226-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1226 |  |  | PF.1226 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00338-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.33 | 0 | 320001TUR | 8/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00338-LEVEL 1-DE-TRANSFORMER T4 | False | LEVEL 1 TRANSFORMER T4 | 0 | FAB-00338-320001TUR | 0
[9 empty] | 1227 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1227 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1227-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1227 |  |  | PF.1227 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00339-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.33 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00339-LEVEL 6-DE-TRANSFORMER T5 & T4 | False | LEVEL 6-TRANSFORMER T5 & T4 | 0 | FAB-00339-320001TUR | 0
[9 empty] | 1228 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1228 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1228-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1228 |  |  | PF.1228 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00340-320001TUR | MXD_RESI_JAP_ELEC | 0 | 80.00 | 0 | 320001TUR | 2/4/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00340-LEVEL 37-DE-AMENITY-MEP PH-MODULAR ELECT ASSEMBLY-SMALL-PLACEHOLDER | False | LEVEL 37-AMENITY-MEP PH-MODULAR ELECT ASSEMBLY SMALL PLACEHOLDER | 0 | FAB-00340-320001TUR | 0
[9 empty] | 1229 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1229 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1229-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1229 |  |  | PF.1229 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00341-320001TUR | MXD_RESI_JAP_ELEC | 0 | 80.00 | 0 | 320001TUR | 2/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00341-LEVEL 37-DE-AMENITY-MEP PH-MODULAR ELECT ASSEMBLY-SMALL-PLACEHOLDER | False | LEVEL 37-AMENITY-MEP PH-MODULAR ELECT ASSEMBLY SMALL PLACEHOLDER | 0 | FAB-00341-320001TUR | 0
[9 empty] | 1230 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1230 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1230-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1230 |  |  | PF.1230 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00342-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.60 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00342-LEVEL 1-IW-CHIEF BOXES-AV-1 RECEPTACLE | False | LEVEL 1 CHIEF BOXES AV 1 RECEPTACLE | 0 | FAB-00342-320001TUR | 0
[9 empty] | 1231 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1231 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1231-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1231 |  |  | PF.1231 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00343-320001TUR | MXD_RESI_JAP_ELEC | 0 | 13.00 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00343-LEVEL 2-IW-CHIEF BOXES-AV-2 RECEPTACLES | False | LEVEL 2 CHIEF BOXES AV 2 RECEPTACLES | 0 | FAB-00343-320001TUR | 0
[9 empty] | 1232 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1232 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1232-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1232 |  |  | PF.1232 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00344-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.90 | 0 | 320001TUR | 10/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00344-LEVEL 6-IW-CHIEF BOXES-AV-1 RECEPTACLE | False | LEVEL 6 LEVEL 6-CHIEF BOXES AV 1 RECEPTACLE | 0 | FAB-00344-320001TUR | 0
[9 empty] | 1233 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1233 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1233-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1233 |  |  | PF.1233 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00345-320001TUR | MXD_RESI_JAP_ELEC | 0 | 26.00 | 0 | 320001TUR | 6/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00345-LEVEL 37-IW-AMENITY-MEP PH-CHIEF BOXES-AV-2 RECEPTACLES | False | LEVEL 37-AMENITY-MEP PH-CHIEF BOXES AV 2 RECEPTACLES | 0 | FAB-00345-320001TUR | 0
[9 empty] | 1234 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1234 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1234-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1234 |  |  | PF.1234 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00346-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00346-LEVEL 1-TMP-TEMPS-LARGE | False | LEVEL 1 TEMPS LARGE | 0 | FAB-00346-320001TUR | 0
[9 empty] | 1235 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1235 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1235-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1235 |  |  | PF.1235 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00347-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00347-LEVEL 7-TMP-TIER 1-TEMPS-LARGE | False | LEVEL 7-TIER 1-TEMPS LARGE | 0 | FAB-00347-320001TUR | 0
[9 empty] | 1236 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1236 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1236-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1236 |  |  | PF.1236 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00348-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 8/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00348-LEVEL 18-TMP-TIER 2-45KVA PDU | False | LEVEL 18-TIER 2-45KVA PDU | 0 | FAB-00348-320001TUR | 0
[9 empty] | 1237 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1237 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1237-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1237 |  |  | PF.1237 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00349-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00349-LEVEL 24-TMP-TIER 2-45KVA PDU # 082 | False | LEVEL 24-TIER 2-45KVA PDU # 082 | 0 | FAB-00349-320001TUR | 0
[9 empty] | 1238 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1238 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1238-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1238 |  |  | PF.1238 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00350-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 9/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00350-LEVEL 30-TMP-TIER 2-75KVA PDU#068 | False | LEVEL 30-TIER 2-75KVA PDU#068 | 0 | FAB-00350-320001TUR | 0
[9 empty] | 1239 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1239 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1239-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1239 |  |  | PF.1239 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00351-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 12/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00351-LEVEL 37-TMP-TIER 2-75KVA PDU | False | LEVEL 37-TIER 2-75KVA PDU | 0 | FAB-00351-320001TUR | 0
[9 empty] | 1240 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1240 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1240-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1240 |  |  | PF.1240 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00352-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00352-LEVEL 38-TMP-75KVA PDU | False | LEVEL 38-75KVA PDU | 0 | FAB-00352-320001TUR | 0
[9 empty] | 1241 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1241 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1241-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1241 |  |  | PF.1241 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00353-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00353-LEVEL B1-TMP-TEMPS-SMALL | False | LEVEL B1 TEMPS SMALL | 0 | FAB-00353-320001TUR | 0
[9 empty] | 1242 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1242 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1242-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1242 |  |  | PF.1242 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00354-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00354-LEVEL 1-TMP-TEMPS-SMALL | False | LEVEL 1 TEMPS SMALL | 0 | FAB-00354-320001TUR | 0
[9 empty] | 1243 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1243 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1243-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1243 |  |  | PF.1243 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00355-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00355-LEVEL 2-TMP-TEMPS-SMALL | False | LEVEL 2 TEMPS SMALL | 0 | FAB-00355-320001TUR | 0
[9 empty] | 1244 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1244 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1244-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1244 |  |  | PF.1244 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00356-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00356-LEVEL 3-TMP-PODIUM-TEMPS-SMALL | False | LEVEL 3-PODIUM-TEMPS SMALL | 0 | FAB-00356-320001TUR | 0
[9 empty] | 1245 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1245 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1245-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1245 |  |  | PF.1245 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00357-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00357-LEVEL 4-TMP-PODIUM-TEMPS-SMALL | False | LEVEL 4-PODIUM-TEMPS SMALL | 0 | FAB-00357-320001TUR | 0
[9 empty] | 1246 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1246 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1246-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1246 |  |  | PF.1246 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00358-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00358-LEVEL 5-TMP-PODIUM-TEMPS-SMALL | False | LEVEL 5-PODIUM-TEMPS SMALL | 0 | FAB-00358-320001TUR | 0
[9 empty] | 1247 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1247 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1247-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1247 |  |  | PF.1247 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00359-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00359-LEVEL 6-TMP-TEMPS-SMALL | False | LEVEL 6 LEVEL 6-TEMPS SMALL | 0 | FAB-00359-320001TUR | 0
[9 empty] | 1248 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1248 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1248-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1248 |  |  | PF.1248 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00360-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00360-LEVEL 7-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 7-TIER 1-TEMPS SMALL | 0 | FAB-00360-320001TUR | 0
[9 empty] | 1249 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1249 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1249-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1249 |  |  | PF.1249 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00361-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00361-LEVEL 8-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 8-TIER 1-TEMPS SMALL | 0 | FAB-00361-320001TUR | 0
[9 empty] | 1250 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1250 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1250-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1250 |  |  | PF.1250 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00362-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00362-LEVEL 9-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 9-TIER 1-TEMPS SMALL | 0 | FAB-00362-320001TUR | 0
[9 empty] | 1251 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1251 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1251-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1251 |  |  | PF.1251 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00363-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00363-LEVEL 10-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 10-TIER 1-TEMPS SMALL | 0 | FAB-00363-320001TUR | 0
[9 empty] | 1252 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1252 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1252-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1252 |  |  | PF.1252 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00364-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00364-LEVEL 11-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 11-TIER 1-TEMPS SMALL | 0 | FAB-00364-320001TUR | 0
[9 empty] | 1253 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1253 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1253-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1253 |  |  | PF.1253 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00365-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00365-LEVEL 12-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 12-TIER 1-TEMPS SMALL | 0 | FAB-00365-320001TUR | 0
[9 empty] | 1254 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1254 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1254-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1254 |  |  | PF.1254 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00366-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00366-LEVEL 13-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 13-TIER 1-TEMPS SMALL | 0 | FAB-00366-320001TUR | 0
[9 empty] | 1255 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1255 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1255-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1255 |  |  | PF.1255 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00367-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00367-LEVEL 14-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 14-TIER 1-TEMPS SMALL | 0 | FAB-00367-320001TUR | 0
[9 empty] | 1256 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1256 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1256-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1256 |  |  | PF.1256 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00368-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00368-LEVEL 15-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 15-TIER 2-TEMPS SMALL | 0 | FAB-00368-320001TUR | 0
[9 empty] | 1257 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1257 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1257-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1257 |  |  | PF.1257 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00369-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00369-LEVEL 16-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 16-TIER 2-TEMPS SMALL | 0 | FAB-00369-320001TUR | 0
[9 empty] | 1258 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1258 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1258-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1258 |  |  | PF.1258 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00370-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00370-LEVEL 17-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 17-TIER 2-TEMPS SMALL | 0 | FAB-00370-320001TUR | 0
[9 empty] | 1259 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1259 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1259-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1259 |  |  | PF.1259 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00371-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00371-LEVEL 18-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 18-TIER 2-TEMPS SMALL | 0 | FAB-00371-320001TUR | 0
[9 empty] | 1260 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1260 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1260-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1260 |  |  | PF.1260 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00372-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00372-LEVEL 19-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 19-TIER 2-TEMPS SMALL | 0 | FAB-00372-320001TUR | 0
[9 empty] | 1261 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1261 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1261-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1261 |  |  | PF.1261 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00373-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00373-LEVEL 20-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 20-TIER 2-TEMPS SMALL | 0 | FAB-00373-320001TUR | 0
[9 empty] | 1262 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1262 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1262-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1262 |  |  | PF.1262 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00374-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00374-LEVEL 21-TMP-TIER 2-SPIDER BOXES | False | LEVEL 21-TIER 2-SPIDER BOXES | 0 | FAB-00374-320001TUR | 0
[9 empty] | 1263 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1263 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1263-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1263 |  |  | PF.1263 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00375-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00375-LEVEL 22-TMP-TIER 2-SPIDER BOXES | False | LEVEL 22-TIER 2-SPIDER BOXES | 0 | FAB-00375-320001TUR | 0
[9 empty] | 1264 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1264 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1264-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1264 |  |  | PF.1264 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00376-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00376-LEVEL 23-TMP-TIER 2-SPIDER BOXES | False | LEVEL 23-TIER 2-SPIDER BOXES | 0 | FAB-00376-320001TUR | 0
[9 empty] | 1265 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1265 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1265-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1265 |  |  | PF.1265 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00377-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00377-LEVEL 24-TMP-TIER 2-SPIDER BOXES | False | LEVEL 24-TIER 2-SPIDER BOXES | 0 | FAB-00377-320001TUR | 0
[9 empty] | 1266 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1266 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1266-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1266 |  |  | PF.1266 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00378-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00378-LEVEL 25-TMP-TIER 2-SPIDER BOXES | False | LEVEL 25-TIER 2-SPIDER BOXES | 0 | FAB-00378-320001TUR | 0
[9 empty] | 1267 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1267 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1267-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1267 |  |  | PF.1267 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00379-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00379-LEVEL 26-TMP-TIER 2-SPIDER BOXES | False | LEVEL 26-TIER 2-SPIDER BOXES | 0 | FAB-00379-320001TUR | 0
[9 empty] | 1268 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1268 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1268-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1268 |  |  | PF.1268 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00380-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00380-LEVEL 27-TMP-TIER 2-SPIDER BOXES | False | LEVEL 27-TIER 2-SPIDER BOXES | 0 | FAB-00380-320001TUR | 0
[9 empty] | 1269 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1269 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1269-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1269 |  |  | PF.1269 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00381-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00381-LEVEL 28-TMP-TIER 2-SPIDER BOXES | False | LEVEL 28-TIER 2-SPIDER BOXES | 0 | FAB-00381-320001TUR | 0
[9 empty] | 1270 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1270 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1270-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1270 |  |  | PF.1270 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00382-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00382-LEVEL 29-TMP-TIER 2-SPIDER BOXES | False | LEVEL 29-TIER 2-SPIDER BOXES | 0 | FAB-00382-320001TUR | 0
[9 empty] | 1271 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1271 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1271-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1271 |  |  | PF.1271 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00383-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00383-LEVEL 30-TMP-TIER 2-SPIDER BOXES | False | LEVEL 30-TIER 2-SPIDER BOXES | 0 | FAB-00383-320001TUR | 0
[9 empty] | 1272 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1272 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1272-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1272 |  |  | PF.1272 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00384-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 11/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00384-LEVEL 31-TMP-TIER 2-SPIDER BOXES | False | LEVEL 31-TIER 2-SPIDER BOXES | 0 | FAB-00384-320001TUR | 0
[9 empty] | 1273 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1273 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1273-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1273 |  |  | PF.1273 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00385-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00385-LEVEL 32-TMP-TIER 2-SPIDER BOXES | False | LEVEL 32-TIER 2-SPIDER BOXES | 0 | FAB-00385-320001TUR | 0
[9 empty] | 1274 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1274 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1274-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1274 |  |  | PF.1274 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00386-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00386-LEVEL 33-TMP-TIER 2-SPIDER BOXES | False | LEVEL 33-TIER 2-SPIDER BOXES | 0 | FAB-00386-320001TUR | 0
[9 empty] | 1275 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1275 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1275-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1275 |  |  | PF.1275 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00387-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00387-LEVEL 34-TMP-TIER 2-SPIDER BOXES | False | LEVEL 34-TIER 2-SPIDER BOXES | 0 | FAB-00387-320001TUR | 0
[9 empty] | 1276 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1276 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1276-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1276 |  |  | PF.1276 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00388-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00388-LEVEL 35-TMP-TIER 3-SPIDER BOXES | False | LEVEL 35-TIER 3-SPIDER BOXES | 0 | FAB-00388-320001TUR | 0
[9 empty] | 1277 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1277 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1277-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1277 |  |  | PF.1277 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00389-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00389-LEVEL 36-TMP-TIER 3-SPIDER BOXES | False | LEVEL 36-TIER 3-SPIDER BOXES | 0 | FAB-00389-320001TUR | 0
[9 empty] | 1278 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1278 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1278-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1278 |  |  | PF.1278 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00390-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 12/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00390-LEVEL 37-TMP-AMENITY-MEP PH-SPIDER BOXES | False | LEVEL 37-AMENITY-MEP PH-SPIDER BOXES | 0 | FAB-00390-320001TUR | 0
[9 empty] | 1279 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1279 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1279-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1279 |  |  | PF.1279 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00391-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00391-LEVEL 38-TMP-SPIDER BOXES | False | LEVEL 38-SPIDER BOXES | 0 | FAB-00391-320001TUR | 0
[9 empty] | 1280 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1280 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1280-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1280 |  |  | PF.1280 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00392-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 2/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00392-LEVEL 39-TMP-SPIDER BOXES | False | LEVEL 39-SPIDER BOXES | 0 | FAB-00392-320001TUR | 0
[9 empty] | 1281 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1281 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1281-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1281 |  |  | PF.1281 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00393-320001TUR | MXD_RESI_JAP_ELEC | 0 | 75.00 | 0 | 320001TUR | 5/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00393-LEVEL 39-DE-ROOFTOP DISCONNECTS | False | ROOFTOP DISCONNECTS | 0 | FAB-00393-320001TUR | 0
[9 empty] | 1282 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1282 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1282-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1282 |  |  | PF.1282 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00394-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00394-LEVEL 1-CND-5in and 4in RIGID NIPPLES | False | 5in and 4in RIGID NIPPLES | 0 | FAB-00394-320001TUR | 0
[9 empty] | 1283 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1283 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1283-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1283 |  |  | PF.1283 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00395-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 6/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00395-LEVEL 13-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00395-320001TUR | 0
[9 empty] | 1284 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1284 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1284-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1284 |  |  | PF.1284 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00396-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 6/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00396-LEVEL 14-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00396-320001TUR | 0
[9 empty] | 1285 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1285 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1285-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1285 |  |  | PF.1285 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00397-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00397-LEVEL 15-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00397-320001TUR | 0
[9 empty] | 1286 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1286 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1286-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1286 |  |  | PF.1286 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00398-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00398-LEVEL 16-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00398-320001TUR | 0
[9 empty] | 1287 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1287 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1287-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1287 |  |  | PF.1287 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00399-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00399-LEVEL 17-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00399-320001TUR | 0
[9 empty] | 1288 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1288 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1288-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1288 |  |  | PF.1288 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00400-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00400-LEVEL 18-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00400-320001TUR | 0
[9 empty] | 1289 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1289 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1289-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1289 |  |  | PF.1289 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00401-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00401-LEVEL 19-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00401-320001TUR | 0
[9 empty] | 1290 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1290 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1290-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1290 |  |  | PF.1290 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00402-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00402-LEVEL 20-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00402-320001TUR | 0
[9 empty] | 1291 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1291 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1291-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1291 |  |  | PF.1291 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00403-320001TUR | MXD_RESI_JAP_ELEC | 0 | 31.00 | 0 | 320001TUR | 7/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00403-MULTI LEVEL-TMP-temp power quad outlets | False | temp power quad outlets | 0 | FAB-00403-320001TUR | 0
[9 empty] | 1292 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1292 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1292-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1292 |  |  | PF.1292 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00404-320001TUR | MXD_RESI_JAP_ELEC | 0 | 31.00 | 0 | 320001TUR | 8/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00404-MULTI LEVEL-TMP-temp power quad outlets | False | temp power quad outlets | 0 | FAB-00404-320001TUR | 0
[9 empty] | 1293 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1293 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1293-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1293 |  |  | PF.1293 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00405-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00405-LEVEL 21-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00405-320001TUR | 0
[9 empty] | 1294 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1294 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1294-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1294 |  |  | PF.1294 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00406-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00406-LEVEL 22-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00406-320001TUR | 0
[9 empty] | 1295 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1295 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1295-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1295 |  |  | PF.1295 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00407-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00407-LEVEL 23-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00407-320001TUR | 0
[9 empty] | 1296 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1296 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1296-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1296 |  |  | PF.1296 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00408-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00408-LEVEL 24-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00408-320001TUR | 0
[9 empty] | 1297 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1297 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1297-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1297 |  |  | PF.1297 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00409-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00409-LEVEL 25-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00409-320001TUR | 0
[9 empty] | 1298 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1298 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1298-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1298 |  |  | PF.1298 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00410-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00410-LEVEL 26-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00410-320001TUR | 0
[9 empty] | 1299 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1299 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1299-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1299 |  |  | PF.1299 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00411-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00411-LEVEL 27-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00411-320001TUR | 0
[9 empty] | 1300 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1300 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1300-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1300 |  |  | PF.1300 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00412-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00412-LEVEL 28-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00412-320001TUR | 0
[9 empty] | 1301 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1301 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1301-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1301 |  |  | PF.1301 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00413-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00413-LEVEL 29-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00413-320001TUR | 0
[9 empty] | 1302 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1302 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1302-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1302 |  |  | PF.1302 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00414-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00414-LEVEL 30-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00414-320001TUR | 0
[9 empty] | 1303 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1303 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1303-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1303 |  |  | PF.1303 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00415-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00415-LEVEL 31-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00415-320001TUR | 0
[9 empty] | 1304 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1304 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1304-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1304 |  |  | PF.1304 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00416-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00416-LEVEL 32-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00416-320001TUR | 0
[9 empty] | 1305 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1305 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1305-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1305 |  |  | PF.1305 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00417-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00417-LEVEL 33-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00417-320001TUR | 0
[9 empty] | 1306 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1306 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1306-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1306 |  |  | PF.1306 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00418-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00418-LEVEL 34-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00418-320001TUR | 0
[9 empty] | 1307 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1307 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1307-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1307 |  |  | PF.1307 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00419-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00419-LEVEL 35-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00419-320001TUR | 0
[9 empty] | 1308 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1308 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1308-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1308 |  |  | PF.1308 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00420-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00420-LEVEL 36-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00420-320001TUR | 0
[9 empty] | 1309 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1309 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1309-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1309 |  |  | PF.1309 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00421-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00421-LEVEL 37-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00421-320001TUR | 0
[9 empty] | 1310 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1310 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1310-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1310 |  |  | PF.1310 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00422-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00422-LEVEL 38-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00422-320001TUR | 0
[9 empty] | 1311 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1311 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1311-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1311 |  |  | PF.1311 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00423-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00423-LEVEL 39-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00423-320001TUR | 0
[9 empty] | 1312 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1312 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1312-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1312 |  |  | PF.1312 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00424-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00424-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00424-320001TUR | 0
[9 empty] | 1313 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1313 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1313-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1313 |  |  | PF.1313 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00425-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00425-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00425-320001TUR | 0
[9 empty] | 1314 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1314 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1314-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1314 |  |  | PF.1314 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00426-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00426-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00426-320001TUR | 0
[9 empty] | 1315 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1315 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1315-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1315 |  |  | PF.1315 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00427-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00427-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00427-320001TUR | 0
[9 empty] | 1316 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1316 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1316-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1316 |  |  | PF.1316 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00428-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00428-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00428-320001TUR | 0
[9 empty] | 1317 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1317 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1317-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1317 |  |  | PF.1317 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00429-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00429-LEVEL 21-DE-PANEL HPH21 | False | PANEL HPH21 | 0 | FAB-00429-320001TUR | 0
[9 empty] | 1318 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1318 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1318-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1318 |  |  | PF.1318 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00430-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 2/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00430-LEVEL 24-DE-PANEL EPH24-EPL24 | False | PANEL EPH24EPL24 | 0 | FAB-00430-320001TUR | 0
[9 empty] | 1319 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1319 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1319-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1319 |  |  | PF.1319 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00431-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00431-LEVEL 25-DE-PANEL HPH25 | False | PANEL HPH25 | 0 | FAB-00431-320001TUR | 0
[9 empty] | 1320 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1320 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1320-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1320 |  |  | PF.1320 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00432-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 5/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00432-LEVEL 33-DE-PANEL HPH33 | False | PANEL HPH33 | 0 | FAB-00432-320001TUR | 0
[9 empty] | 1321 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1321 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1321-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1321 |  |  | PF.1321 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00433-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 5/8/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00433-LEVEL 34-DE-PANELS EPH34-EPL34 | False | PANELS EPH34EPL34 | 0 | FAB-00433-320001TUR | 0
[9 empty] | 1322 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1322 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1322-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1322 |  |  | PF.1322 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00434-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00434-LEVEL 18-CND-6in PVC X 8in LONG CONTROL POINTS | False | 6in PVC X 8in LONG CONTROL POINTS | 0 | FAB-00434-320001TUR | 0
[9 empty] | 1323 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1323 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1323-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1323 |  |  | PF.1323 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00435-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00435-LEVEL 19-CND-6in PVC X 8in LONG CONTROL POINTS | False | 6in PVC X 8in LONG CONTROL POINTS | 0 | FAB-00435-320001TUR | 0
[9 empty] | 1324 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1324 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1324-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1324 |  |  | PF.1324 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00436-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00436-LEVEL 20-CND-6in PVC X 8in LONG CONTROL POINTS | False | 6in PVC X 8in LONG CONTROL POINTS | 0 | FAB-00436-320001TUR | 0
[9 empty] | 1325 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1325 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1325-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1325 |  |  | PF.1325 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00437-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00437-LEVEL 21-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00437-320001TUR | 0
[9 empty] | 1326 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1326 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1326-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1326 |  |  | PF.1326 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00438-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00438-LEVEL 22-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00438-320001TUR | 0
[9 empty] | 1327 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1327 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1327-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1327 |  |  | PF.1327 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00439-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00439-LEVEL 23-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00439-320001TUR | 0
[9 empty] | 1328 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1328 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1328-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1328 |  |  | PF.1328 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00440-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00440-LEVEL 24-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00440-320001TUR | 0
[9 empty] | 1329 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1329 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1329-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1329 |  |  | PF.1329 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00441-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00441-LEVEL 25-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00441-320001TUR | 0
[9 empty] | 1330 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1330 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1330-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1330 |  |  | PF.1330 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00442-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00442-LEVEL 26-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00442-320001TUR | 0
[9 empty] | 1331 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1331 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1331-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1331 |  |  | PF.1331 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00443-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00443-LEVEL 27-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00443-320001TUR | 0
[9 empty] | 1332 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1332 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1332-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1332 |  |  | PF.1332 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00444-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00444-LEVEL 28-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00444-320001TUR | 0
[9 empty] | 1333 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1333 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1333-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1333 |  |  | PF.1333 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00445-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00445-LEVEL 29-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00445-320001TUR | 0
[9 empty] | 1334 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1334 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1334-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1334 |  |  | PF.1334 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00446-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00446-LEVEL 30-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00446-320001TUR | 0
[9 empty] | 1335 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1335 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1335-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1335 |  |  | PF.1335 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00447-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00447-LEVEL 31-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00447-320001TUR | 0
[9 empty] | 1336 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1336 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1336-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1336 |  |  | PF.1336 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00448-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00448-LEVEL 32-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00448-320001TUR | 0
[9 empty] | 1337 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1337 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1337-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1337 |  |  | PF.1337 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00449-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00449-LEVEL 33-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00449-320001TUR | 0
[9 empty] | 1338 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1338 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1338-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1338 |  |  | PF.1338 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00450-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00450-LEVEL 34-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00450-320001TUR | 0
[9 empty] | 1339 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1339 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1339-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1339 |  |  | PF.1339 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00451-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00451-LEVEL 35-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00451-320001TUR | 0
[9 empty] | 1340 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1340 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1340-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1340 |  |  | PF.1340 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00452-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00452-LEVEL 36-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00452-320001TUR | 0
[9 empty] | 1341 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1341 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1341-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1341 |  |  | PF.1341 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00453-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00453-LEVEL 37-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00453-320001TUR | 0
[9 empty] | 1342 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1342 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1342-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1342 |  |  | PF.1342 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00454-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00454-LEVEL 38-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00454-320001TUR | 0
[9 empty] | 1343 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1343 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1343-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1343 |  |  | PF.1343 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00455-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00455-LEVEL 39-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00455-320001TUR | 0
[9 empty] | 1344 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1344 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1344-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1344 |  |  | PF.1344 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00456-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.27 | 0 | 320001TUR | 8/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00456-LEVEL 1-IW-shallow box-beam mockup | False | shallow box beam mockup | 0 | FAB-00456-320001TUR | 0
[9 empty] | 1345 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1345 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1345-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1345 |  |  | PF.1345 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00457-320001TUR | MXD_RESI_JAP_ELEC | 0 | 40.00 | 0 | 320001TUR | 8/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00457-MULTI LEVEL-TMP-SPIDER BOXES -15FT-FEMAILE WHIPS | False | SPIDER BOXES -15FT-FEMAILE WHIPS | 0 | FAB-00457-320001TUR | 0
[9 empty] | 1346 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1346 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1346-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1346 |  |  | PF.1346 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00458-320001TUR | MXD_RESI_JAP_ELEC | 0 | 16.00 | 0 | 320001TUR | 8/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00458-SITE-TMP-TEMP PANELS | False | TEMP PANELS | 0 | FAB-00458-320001TUR | 0
[9 empty] | 1347 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1347 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1347-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1347 |  |  | PF.1347 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00459-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00459-LEVEL 3-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00459-320001TUR | 0
[9 empty] | 1348 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1348 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1348-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1348 |  |  | PF.1348 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00460-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00460-LEVEL 4-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00460-320001TUR | 0
[9 empty] | 1349 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1349 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1349-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1349 |  |  | PF.1349 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00461-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00461-LEVEL 5-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00461-320001TUR | 0
[9 empty] | 1350 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1350 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1350-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1350 |  |  | PF.1350 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00462-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00462-LEVEL 6-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00462-320001TUR | 0
[9 empty] | 1351 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1351 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1351-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1351 |  |  | PF.1351 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00463-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00463-LEVEL 7-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00463-320001TUR | 0
[9 empty] | 1352 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1352 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1352-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1352 |  |  | PF.1352 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00464-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00464-LEVEL 8-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00464-320001TUR | 0
[9 empty] | 1353 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1353 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1353-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1353 |  |  | PF.1353 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00465-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00465-LEVEL 9-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00465-320001TUR | 0
[9 empty] | 1354 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1354 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1354-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1354 |  |  | PF.1354 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00466-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00466-LEVEL 10-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00466-320001TUR | 0
[9 empty] | 1355 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1355 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1355-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1355 |  |  | PF.1355 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00467-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00467-LEVEL 11-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00467-320001TUR | 0
[9 empty] | 1356 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1356 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1356-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1356 |  |  | PF.1356 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00468-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00468-LEVEL 12-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00468-320001TUR | 0
[9 empty] | 1357 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1357 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1357-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1357 |  |  | PF.1357 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00469-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00469-LEVEL 13-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00469-320001TUR | 0
[9 empty] | 1358 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1358 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1358-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1358 |  |  | PF.1358 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00470-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00470-LEVEL 14-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00470-320001TUR | 0
[9 empty] | 1359 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1359 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1359-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1359 |  |  | PF.1359 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00471-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00471-LEVEL 15-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00471-320001TUR | 0
[9 empty] | 1360 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1360 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1360-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1360 |  |  | PF.1360 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00472-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00472-LEVEL 16-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00472-320001TUR | 0
[9 empty] | 1361 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1361 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1361-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1361 |  |  | PF.1361 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00473-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00473-LEVEL 17-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00473-320001TUR | 0
[9 empty] | 1362 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1362 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1362-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1362 |  |  | PF.1362 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00474-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00474-LEVEL 18-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00474-320001TUR | 0
[9 empty] | 1363 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1363 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1363-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1363 |  |  | PF.1363 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00475-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00475-LEVEL 19-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00475-320001TUR | 0
[9 empty] | 1364 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1364 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1364-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1364 |  |  | PF.1364 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00476-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00476-LEVEL 20-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00476-320001TUR | 0
[9 empty] | 1365 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1365 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1365-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1365 |  |  | PF.1365 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00477-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00477-LEVEL 21-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00477-320001TUR | 0
[9 empty] | 1366 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1366 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1366-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1366 |  |  | PF.1366 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00478-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00478-LEVEL 22-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00478-320001TUR | 0
[9 empty] | 1367 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1367 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1367-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1367 |  |  | PF.1367 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00479-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00479-LEVEL 23-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00479-320001TUR | 0
[9 empty] | 1368 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1368 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1368-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1368 |  |  | PF.1368 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00480-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00480-LEVEL 24-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00480-320001TUR | 0
[9 empty] | 1369 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1369 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1369-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1369 |  |  | PF.1369 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00481-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00481-LEVEL 25-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00481-320001TUR | 0
[9 empty] | 1370 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1370 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1370-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1370 |  |  | PF.1370 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00482-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00482-LEVEL 26-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00482-320001TUR | 0
[9 empty] | 1371 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1371 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1371-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1371 |  |  | PF.1371 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00483-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00483-LEVEL 27-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00483-320001TUR | 0
[9 empty] | 1372 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1372 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1372-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1372 |  |  | PF.1372 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00484-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00484-LEVEL 28-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00484-320001TUR | 0
[9 empty] | 1373 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1373 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1373-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1373 |  |  | PF.1373 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00485-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00485-LEVEL 29-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00485-320001TUR | 0
[9 empty] | 1374 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1374 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1374-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1374 |  |  | PF.1374 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00486-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00486-LEVEL 30-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00486-320001TUR | 0
[9 empty] | 1375 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1375 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1375-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1375 |  |  | PF.1375 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00487-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00487-LEVEL 31-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00487-320001TUR | 0
[9 empty] | 1376 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1376 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1376-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1376 |  |  | PF.1376 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00488-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00488-LEVEL 32-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00488-320001TUR | 0
[9 empty] | 1377 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1377 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1377-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1377 |  |  | PF.1377 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00489-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00489-LEVEL 33-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00489-320001TUR | 0
[9 empty] | 1378 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1378 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1378-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1378 |  |  | PF.1378 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00490-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00490-LEVEL 34-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00490-320001TUR | 0
[9 empty] | 1379 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1379 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1379-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1379 |  |  | PF.1379 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00491-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00491-LEVEL 35-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00491-320001TUR | 0
[9 empty] | 1380 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1380 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1380-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1380 |  |  | PF.1380 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00492-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00492-LEVEL 36-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00492-320001TUR | 0
[9 empty] | 1381 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1381 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1381-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1381 |  |  | PF.1381 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00493-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00493-LEVEL 3-CND-CONDUIT RISER SLEEVES | False | CONDUIT RISER SLEEVES | 0 | FAB-00493-320001TUR | 0
[9 empty] | 1382 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1382 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1382-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1382 |  |  | PF.1382 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00494-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00494-LEVEL 4-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00494-320001TUR | 0
[9 empty] | 1383 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1383 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1383-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1383 |  |  | PF.1383 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00495-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00495-LEVEL 5-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00495-320001TUR | 0
[9 empty] | 1384 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1384 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1384-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1384 |  |  | PF.1384 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00496-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00496-LEVEL 6-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00496-320001TUR | 0
[9 empty] | 1385 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1385 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1385-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1385 |  |  | PF.1385 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00497-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00497-LEVEL 7-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00497-320001TUR | 0
[9 empty] | 1386 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1386 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1386-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1386 |  |  | PF.1386 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00498-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00498-LEVEL 8-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00498-320001TUR | 0
[9 empty] | 1387 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1387 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1387-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1387 |  |  | PF.1387 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00499-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00499-LEVEL 9-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00499-320001TUR | 0
[9 empty] | 1388 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1388 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1388-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1388 |  |  | PF.1388 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00500-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00500-LEVEL 10-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00500-320001TUR | 0
[9 empty] | 1389 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1389 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1389-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1389 |  |  | PF.1389 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00501-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00501-LEVEL 11-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00501-320001TUR | 0
[9 empty] | 1390 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1390 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1390-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1390 |  |  | PF.1390 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00502-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00502-LEVEL 12-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00502-320001TUR | 0
[9 empty] | 1391 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1391 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1391-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1391 |  |  | PF.1391 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00503-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00503-LEVEL 13-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00503-320001TUR | 0
[9 empty] | 1392 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1392 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1392-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1392 |  |  | PF.1392 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00504-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00504-LEVEL 14-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00504-320001TUR | 0
[9 empty] | 1393 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1393 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1393-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1393 |  |  | PF.1393 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00505-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00505-LEVEL 15-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00505-320001TUR | 0
[9 empty] | 1394 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1394 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1394-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1394 |  |  | PF.1394 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00506-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00506-LEVEL 16-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00506-320001TUR | 0
[9 empty] | 1395 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1395 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1395-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1395 |  |  | PF.1395 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00507-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00507-LEVEL 17-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00507-320001TUR | 0
[9 empty] | 1396 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1396 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1396-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1396 |  |  | PF.1396 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00508-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00508-LEVEL 18-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00508-320001TUR | 0
[9 empty] | 1397 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1397 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1397-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1397 |  |  | PF.1397 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00509-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00509-LEVEL 19-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00509-320001TUR | 0
[9 empty] | 1398 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1398 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1398-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1398 |  |  | PF.1398 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00510-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00510-LEVEL 20-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00510-320001TUR | 0
[9 empty] | 1399 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1399 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1399-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1399 |  |  | PF.1399 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00511-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00511-LEVEL 21-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00511-320001TUR | 0
[9 empty] | 1400 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1400 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1400-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1400 |  |  | PF.1400 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00512-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00512-LEVEL 22-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00512-320001TUR | 0
[9 empty] | 1401 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1401 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1401-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1401 |  |  | PF.1401 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00513-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00513-LEVEL 23-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00513-320001TUR | 0
[9 empty] | 1402 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1402 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1402-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1402 |  |  | PF.1402 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00514-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00514-LEVEL 24-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00514-320001TUR | 0
[9 empty] | 1403 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1403 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1403-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1403 |  |  | PF.1403 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00515-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00515-LEVEL 25-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00515-320001TUR | 0
[9 empty] | 1404 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1404 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1404-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1404 |  |  | PF.1404 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00516-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00516-LEVEL 26-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00516-320001TUR | 0
[9 empty] | 1405 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1405 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1405-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1405 |  |  | PF.1405 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00517-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00517-LEVEL 27-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00517-320001TUR | 0
[9 empty] | 606 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 606 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 606-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.606 |  |  | PF.606 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00146 | SIMMONS_ELEC | 0 | 1.00 | 1 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100.0 % |  | CND---01 | False |  | 42 | 200019SKA-00146 | 0
[9 empty] | 607 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 607 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 607-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.607 |  |  | PF.607 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00011 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-04 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 15 | 0 | 200019SKA-00011 | 0
[9 empty] | 608 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 608 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 608-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.608 |  |  | PF.608 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00015 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-05 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00015 | 0
[9 empty] | 609 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 609 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 609-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.609 |  |  | PF.609 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00024 | SIMMONS_ELEC | 0 | 12.00 | 29 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-06 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 19 | 5698 | 200019SKA-00024 | 0
[9 empty] | 610 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 610 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 610-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.610 |  |  | PF.610 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00028 | SIMMONS_ELEC | 0 | 1.00 | 4 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-07 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 18 | 467 | 200019SKA-00028 | 0
[9 empty] | 611 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 611 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 611-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.611 |  |  | PF.611 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00032 | SIMMONS_ELEC | 0 | 1.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-08 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 11 | 355 | 200019SKA-00032 | 0
[9 empty] | 612 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 612 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 612-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.612 |  |  | PF.612 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00036 | SIMMONS_ELEC | 0 | 2.00 | 15 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-09 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 08 | 1120 | 200019SKA-00036 | 0
[9 empty] | 613 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 613 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 613-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.613 |  |  | PF.613 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00037 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-10 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00037 | 0
[9 empty] | 614 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 614 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 614-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.614 |  |  | PF.614 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00041 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-11 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 08 | 0 | 200019SKA-00041 | 0
[9 empty] | 615 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 615 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 615-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.615 |  |  | PF.615 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00046 | SIMMONS_ELEC | 0 | 4.00 | 16 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-12 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 17 | 3387 | 200019SKA-00046 | 0
[9 empty] | 616 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 616 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 616-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.616 |  |  | PF.616 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00050 | SIMMONS_ELEC | 0 | 1.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-13 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 13 | 359 | 200019SKA-00050 | 0
[9 empty] | 617 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 617 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 617-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.617 |  |  | PF.617 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00054 | SIMMONS_ELEC | 0 | 1.00 | 7 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-14 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 09 | 377 | 200019SKA-00054 | 0
[9 empty] | 618 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 618 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 618-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.618 |  |  | PF.618 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00066 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-15 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\ROOF LEVEL | 0 | 200019SKA-00066 | 0
[9 empty] | 619 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 619 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 619-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.619 |  |  | PF.619 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00069 | SIMMONS_ELEC | 0 | 1.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-16 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 730 | 200019SKA-00069 | 0
[9 empty] | 620 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 620 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 620-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.620 |  |  | PF.620 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00073 | SIMMONS_ELEC | 0 | 1.00 | 10 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-17 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 457 | 200019SKA-00073 | 0
[9 empty] | 621 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 621 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 621-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.621 |  |  | PF.621 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00076 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-18 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00076 | 0
[9 empty] | 622 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 622 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 622-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.622 |  |  | PF.622 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00080 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-19 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00080 | 0
[9 empty] | 623 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 623 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 623-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.623 |  |  | PF.623 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00082 | SIMMONS_ELEC | 0 | 1.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100.0 % |  | CND--ABOVE PODIUM-20 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 324 | 200019SKA-00082 | 0
[9 empty] | 624 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 624 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 624-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.624 |  |  | PF.624 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00084 | SIMMONS_ELEC | 0 | 2.00 | 22 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-21 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 1229 | 200019SKA-00084 | 0
[9 empty] | 625 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 625 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 625-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.625 |  |  | PF.625 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00086 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-22 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00086 | 0
[9 empty] | 626 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 626 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 626-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.626 |  |  | PF.626 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00088 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-23 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00088 | 0
[9 empty] | 627 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 627 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 627-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.627 |  |  | PF.627 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00090 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-24 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00090 | 0
[9 empty] | 628 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 628 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 628-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.628 |  |  | PF.628 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00093 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-25 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00093 | 0
[9 empty] | 629 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 629 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 629-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.629 |  |  | PF.629 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00094 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-26 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00094 | 0
[9 empty] | 630 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 630 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 630-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.630 |  |  | PF.630 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00095 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-27 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00095 | 0
[9 empty] | 631 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 631 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 631-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.631 |  |  | PF.631 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00098 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-28 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00098 | 0
[9 empty] | 632 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 632 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 632-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.632 |  |  | PF.632 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00099 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-29 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00099 | 0
[9 empty] | 633 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 633 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 633-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.633 |  |  | PF.633 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00100 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--ABOVE PODIUM-30 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00100 | 0
[9 empty] | 634 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 634 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 634-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.634 |  |  | PF.634 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00106 | SIMMONS_ELEC | 0 | 1.00 | 2 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100.0 % |  | CND--ABOVE PODIUM-31 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 14 | 558 | 200019SKA-00106 | 0
[9 empty] | 635 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 635 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 635-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.635 |  |  | PF.635 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00107 | SIMMONS_ELEC | 0 | 1.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND--GRID - ORTHO-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL B01 | 342 | 200019SKA-00107 | 0
[9 empty] | 636 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 636 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 636-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.636 |  |  | PF.636 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00010 | SIMMONS_ELEC | 0 | 14.00 | 76 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 01 | 11220 | 200019SKA-00010 | 0
[9 empty] | 637 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 637 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 637-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.637 |  |  | PF.637 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00019 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-02 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 01 | 0 | 200019SKA-00019 | 0
[9 empty] | 638 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 638 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 638-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.638 |  |  | PF.638 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00059 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-04 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00059 | 0
[9 empty] | 639 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 639 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 639-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.639 |  |  | PF.639 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00063 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-05 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00063 | 0
[9 empty] | 640 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 640 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 640-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.640 |  |  | PF.640 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00092 | SIMMONS_ELEC | 0 | 6.00 | 48 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-06 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 5223 | 200019SKA-00092 | 0
[9 empty] | 641 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 641 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 641-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.641 |  |  | PF.641 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00096 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-07 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00096 | 0
[9 empty] | 642 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 642 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 642-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.642 |  |  | PF.642 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00097 | SIMMONS_ELEC | 0 | 6.00 | 38 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-08 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 3868 | 200019SKA-00097 | 0
[9 empty] | 643 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 643 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 643-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.643 |  |  | PF.643 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00101 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-09 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00101 | 0
[9 empty] | 644 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 644 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 644-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.644 |  |  | PF.644 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00102 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-10 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00102 | 0
[9 empty] | 645 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 645 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 645-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.645 |  |  | PF.645 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00103 | SIMMONS_ELEC | 0 | 3.00 | 21 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100.0 % |  | CND-LEVEL 01-ABOVE PODIUM-11 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 02 | 1835 | 200019SKA-00103 | 0
[9 empty] | 646 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 646 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 646-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.646 |  |  | PF.646 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00104 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-12 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00104 | 0
[9 empty] | 647 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 647 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 647-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.647 |  |  | PF.647 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00105 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | CND-LEVEL 01-ABOVE PODIUM-13 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 02 | 0 | 200019SKA-00105 | 0
[9 empty] | 648 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 648 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 648-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.648 |  |  | PF.648 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00148-25 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10.0 % |  | DE----001 | False |  | 0 | 200019SKA-00148-25 | 0
[9 empty] | 649 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 649 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 649-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.649 |  |  | PF.649 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00147 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | DE---01 | False | Fa | 0 | 200019SKA-00147 | 0
[9 empty] | 650 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 650 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 650-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.650 |  |  | PF.650 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00149-25 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10.0 % |  | DE-LEVEL 02--ABOVE PODIUM-001 | False |  | 0 | 200019SKA-00149-25 | 0
[9 empty] | 651 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 651 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 651-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.651 |  |  | PF.651 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00145 | SIMMONS_ELEC | 0 | 0.00 | 1 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10.0 % |  | DE-LEVEL 02-ABOVE PODIUM-01 | False |  | 76 | 200019SKA-00145 | 0
[9 empty] | 652 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 652 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 652-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.652 |  |  | PF.652 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00005 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 15 | 0 | 200019SKA-00005 | 0
[9 empty] | 653 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 653 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 653-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.653 |  |  | PF.653 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00009 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-02 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00009 | 0
[9 empty] | 654 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 654 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 654-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.654 |  |  | PF.654 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00018 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-04 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00018 | 0
[9 empty] | 655 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 655 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 655-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.655 |  |  | PF.655 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00031 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-05 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 18 | 0 | 200019SKA-00031 | 0
[9 empty] | 656 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 656 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 656-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.656 |  |  | PF.656 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00035 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-06 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00035 | 0
[9 empty] | 657 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 657 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 657-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.657 |  |  | PF.657 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00040 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-07 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00040 | 0
[9 empty] | 658 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 658 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 658-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.658 |  |  | PF.658 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00045 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-08 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 08 | 0 | 200019SKA-00045 | 0
[9 empty] | 659 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 659 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 659-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.659 |  |  | PF.659 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00049 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-09 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 17 | 0 | 200019SKA-00049 | 0
[9 empty] | 660 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 660 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 660-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.660 |  |  | PF.660 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00053 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-10 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 13 | 0 | 200019SKA-00053 | 0
[9 empty] | 661 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 661 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 661-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.661 |  |  | PF.661 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00057 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-11 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 09 | 0 | 200019SKA-00057 | 0
[9 empty] | 662 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 662 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 662-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.662 |  |  | PF.662 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00065 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-12 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00065 | 0
[9 empty] | 663 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 663 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 663-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.663 |  |  | PF.663 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00072 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-13 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00072 | 0
[9 empty] | 664 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 664 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 664-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.664 |  |  | PF.664 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00075 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-14 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00075 | 0
[9 empty] | 665 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 665 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 665-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.665 |  |  | PF.665 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00079 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-15 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00079 | 0
[9 empty] | 666 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 666 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 666-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.666 |  |  | PF.666 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00081 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-16 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00081 | 0
[9 empty] | 667 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 667 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 667-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.667 |  |  | PF.667 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00083 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-17 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00083 | 0
[9 empty] | 668 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 668 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 668-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.668 |  |  | PF.668 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00085 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-18 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00085 | 0
[9 empty] | 669 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 669 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 669-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.669 |  |  | PF.669 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00087 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-19 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00087 | 0
[9 empty] | 670 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 670 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 670-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.670 |  |  | PF.670 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00089 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-20 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00089 | 0
[9 empty] | 671 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 671 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 671-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.671 |  |  | PF.671 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00091 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-21 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00091 | 0
[9 empty] | 672 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 672 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 672-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.672 |  |  | PF.672 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00116 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-22 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00116 | 0
[9 empty] | 673 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 673 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 673-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.673 |  |  | PF.673 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00117 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-23 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00117 | 0
[9 empty] | 674 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 674 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 674-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.674 |  |  | PF.674 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00118 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-24 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00118 | 0
[9 empty] | 675 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 675 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 675-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.675 |  |  | PF.675 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00119 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-25 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00119 | 0
[9 empty] | 676 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 676 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 676-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.676 |  |  | PF.676 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00121 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-26 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00121 | 0
[9 empty] | 677 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 677 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 677-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.677 |  |  | PF.677 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00123 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT--1-ABOVE PODIUM-27 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 14 | 0 | 200019SKA-00123 | 0
[9 empty] | 678 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 678 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 678-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.678 |  |  | PF.678 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00023 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT-LEVEL 01-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 01 | 0 | 200019SKA-00023 | 0
[9 empty] | 679 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 679 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 679-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.679 |  |  | PF.679 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00122 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT-LEVEL 01-GRID - ORTHO-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 02 | 0 | 200019SKA-00122 | 0
[9 empty] | 680 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 680 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 680-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.680 |  |  | PF.680 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00120 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT-LEVEL 03-GRID - ORTHO-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00120 | 0
[9 empty] | 681 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 681 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 681-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.681 |  |  | PF.681 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00027 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT-LEVEL 18-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 19 | 0 | 200019SKA-00027 | 0
[9 empty] | 682 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 682 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 682-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.682 |  |  | PF.682 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00124 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT-LEVEL B01-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL B01 | 0 | 200019SKA-00124 | 0
[9 empty] | 683 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 683 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 683-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.683 |  |  | PF.683 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00068 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | LGT-ROOF LEVEL-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\ROOF LEVEL | 0 | 200019SKA-00068 | 0
[9 empty] | 684 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 684 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 684-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.684 |  |  | PF.684 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00004 | SIMMONS_ELEC | 0 | 0.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 15 | 359 | 200019SKA-00004 | 0
[9 empty] | 685 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 685 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 685-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.685 |  |  | PF.685 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00017 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-04 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00017 | 0
[9 empty] | 686 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 686 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 686-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.686 |  |  | PF.686 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00026 | SIMMONS_ELEC | 0 | 0.00 | 30 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-05 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 19 | 6206 | 200019SKA-00026 | 0
[9 empty] | 687 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 687 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 687-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.687 |  |  | PF.687 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00030 | SIMMONS_ELEC | 0 | 0.00 | 4 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-06 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 18 | 467 | 200019SKA-00030 | 0
[9 empty] | 688 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 688 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 688-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.688 |  |  | PF.688 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00034 | SIMMONS_ELEC | 0 | 0.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-07 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 11 | 355 | 200019SKA-00034 | 0
[9 empty] | 689 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 689 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 689-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.689 |  |  | PF.689 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00039 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-08 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00039 | 0
[9 empty] | 690 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 690 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 690-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.690 |  |  | PF.690 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00043 | SIMMONS_ELEC | 0 | 0.00 | 15 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-09 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 08 | 1120 | 200019SKA-00043 | 0
[9 empty] | 691 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 691 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 691-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.691 |  |  | PF.691 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00044 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-10 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 08 | 0 | 200019SKA-00044 | 0
[9 empty] | 692 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 692 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 692-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.692 |  |  | PF.692 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00048 | SIMMONS_ELEC | 0 | 0.00 | 16 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-11 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 17 | 3387 | 200019SKA-00048 | 0
[9 empty] | 693 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 693 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 693-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.693 |  |  | PF.693 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00052 | SIMMONS_ELEC | 0 | 0.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-12 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 13 | 359 | 200019SKA-00052 | 0
[9 empty] | 694 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 694 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 694-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.694 |  |  | PF.694 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00056 | SIMMONS_ELEC | 0 | 0.00 | 7 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-13 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 09 | 377 | 200019SKA-00056 | 0
[9 empty] | 695 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 695 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 695-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.695 |  |  | PF.695 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00067 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-14 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\ROOF LEVEL | 0 | 200019SKA-00067 | 0
[9 empty] | 696 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 696 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 696-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.696 |  |  | PF.696 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00071 | SIMMONS_ELEC | 0 | 0.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-15 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 730 | 200019SKA-00071 | 0
[9 empty] | 697 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 697 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 697-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.697 |  |  | PF.697 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00074 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-16 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00074 | 0
[9 empty] | 698 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 698 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 698-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.698 |  |  | PF.698 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00078 | SIMMONS_ELEC | 0 | 0.00 | 10 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-17 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 457 | 200019SKA-00078 | 0
[9 empty] | 699 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 699 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 699-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.699 |  |  | PF.699 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00125 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-18 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00125 | 0
[9 empty] | 700 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 700 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 700-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.700 |  |  | PF.700 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00126 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-19 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00126 | 0
[9 empty] | 701 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 701 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 701-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.701 |  |  | PF.701 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00127 | SIMMONS_ELEC | 0 | 0.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100.0 % |  | PB--ABOVE PODIUM-20 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 324 | 200019SKA-00127 | 0
[9 empty] | 702 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 702 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 702-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.702 |  |  | PF.702 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00128 | SIMMONS_ELEC | 0 | 0.00 | 22 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-21 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 1229 | 200019SKA-00128 | 0
[9 empty] | 703 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 703 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 703-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.703 |  |  | PF.703 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00129 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-22 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00129 | 0
[9 empty] | 704 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 704 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 704-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.704 |  |  | PF.704 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00130 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-23 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00130 | 0
[9 empty] | 705 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 705 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 705-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.705 |  |  | PF.705 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00131 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-24 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00131 | 0
[9 empty] | 706 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 706 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 706-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.706 |  |  | PF.706 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00132 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-25 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00132 | 0
[9 empty] | 707 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 707 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 707-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.707 |  |  | PF.707 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00136 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--ABOVE PODIUM-26 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00136 | 0
[9 empty] | 708 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 708 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 708-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.708 |  |  | PF.708 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00143 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100.0 % |  | PB--ABOVE PODIUM-27 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 14 | 0 | 200019SKA-00143 | 0
[9 empty] | 709 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 709 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 709-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.709 |  |  | PF.709 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00144 | SIMMONS_ELEC | 0 | 0.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB--GRID - ORTHO-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL B01 | 342 | 200019SKA-00144 | 0
[9 empty] | 710 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 710 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 710-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.710 |  |  | PF.710 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00021 | SIMMONS_ELEC | 0 | 0.00 | 76 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 01 | 11220 | 200019SKA-00021 | 0
[9 empty] | 711 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 711 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 711-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.711 |  |  | PF.711 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00022 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-02 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 01 | 0 | 200019SKA-00022 | 0
[9 empty] | 712 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 712 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 712-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.712 |  |  | PF.712 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00061 | SIMMONS_ELEC | 0 | 0.00 | 52 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-03 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 05 | 6680 | 200019SKA-00061 | 0
[9 empty] | 713 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 713 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 713-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.713 |  |  | PF.713 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00064 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-04 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00064 | 0
[9 empty] | 714 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 714 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 714-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.714 |  |  | PF.714 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00133 | SIMMONS_ELEC | 0 | 0.00 | 48 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-05 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 5223 | 200019SKA-00133 | 0
[9 empty] | 715 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 715 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 715-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.715 |  |  | PF.715 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00134 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-06 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00134 | 0
[9 empty] | 716 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 716 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 716-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.716 |  |  | PF.716 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00135 | SIMMONS_ELEC | 0 | 0.00 | 38 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-07 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 3868 | 200019SKA-00135 | 0
[9 empty] | 717 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 717 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 717-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.717 |  |  | PF.717 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00137 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-08 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00137 | 0
[9 empty] | 718 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 718 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 718-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.718 |  |  | PF.718 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00138 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-09 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00138 | 0
[9 empty] | 719 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 719 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 719-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.719 |  |  | PF.719 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00139 | SIMMONS_ELEC | 0 | 0.00 | 22 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10.0 % |  | PB-LEVEL 01-ABOVE PODIUM-10 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 02 | 1911 | 200019SKA-00139 | 0
[9 empty] | 720 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 720 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 720-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.720 |  |  | PF.720 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00140 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-11 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00140 | 0
[9 empty] | 721 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 721 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 721-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.721 |  |  | PF.721 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00141 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-12 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00141 | 0
[9 empty] | 722 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 722 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 722-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.722 |  |  | PF.722 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00142 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | PB-LEVEL 01-ABOVE PODIUM-13 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 02 | 0 | 200019SKA-00142 | 0
[9 empty] | 723 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 723 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 723-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.723 |  |  | PF.723 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00115 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 01-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL B01 | 0 | 200019SKA-00115 | 0
[9 empty] | 724 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 724 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 724-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.724 |  |  | PF.724 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00020 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 01-GRID - ORTHO-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 01 | 0 | 200019SKA-00020 | 0
[9 empty] | 725 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 725 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 725-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.725 |  |  | PF.725 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00060 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 02-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00060 | 0
[9 empty] | 726 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 726 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 726-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.726 |  |  | PF.726 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00062 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 02-ABOVE PODIUM-02 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00062 | 0
[9 empty] | 727 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 727 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 727-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.727 |  |  | PF.727 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00112 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 02-ABOVE PODIUM-03 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00112 | 0
[9 empty] | 728 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 728 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 728-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.728 |  |  | PF.728 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00113 | SIMMONS_ELEC | 0 | 0.00 | 1 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10.0 % |  | RACK PACKAGE-LEVEL 02-ABOVE PODIUM-04 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 02 | 76 | 200019SKA-00113 | 0
[9 empty] | 729 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 729 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 729-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.729 |  |  | PF.729 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00111 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 03-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00111 | 0
[9 empty] | 730 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 730 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 730-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.730 |  |  | PF.730 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00007 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-02 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00007 | 0
[9 empty] | 731 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 731 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 731-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.731 |  |  | PF.731 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00012 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-03 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 15 | 0 | 200019SKA-00012 | 0
[9 empty] | 732 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 732 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 732-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.732 |  |  | PF.732 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00016 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-04 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00016 | 0
[9 empty] | 733 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 733 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 733-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.733 |  |  | PF.733 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00029 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-05 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 18 | 0 | 200019SKA-00029 | 0
[9 empty] | 734 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 734 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 734-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.734 |  |  | PF.734 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00033 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-06 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00033 | 0
[9 empty] | 735 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 735 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 735-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.735 |  |  | PF.735 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00038 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-07 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00038 | 0
[9 empty] | 736 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 736 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 736-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.736 |  |  | PF.736 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00042 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-08 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 08 | 0 | 200019SKA-00042 | 0
[9 empty] | 737 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 737 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 737-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.737 |  |  | PF.737 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00047 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-09 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 17 | 0 | 200019SKA-00047 | 0
[9 empty] | 738 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 738 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 738-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.738 |  |  | PF.738 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00051 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-10 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 13 | 0 | 200019SKA-00051 | 0
[9 empty] | 739 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 739 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 739-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.739 |  |  | PF.739 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00070 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-11 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00070 | 0
[9 empty] | 740 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 740 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 740-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.740 |  |  | PF.740 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00077 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-12 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00077 | 0
[9 empty] | 741 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 741 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 741-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.741 |  |  | PF.741 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00108 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-13 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00108 | 0
[9 empty] | 742 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 742 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 742-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.742 |  |  | PF.742 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00109 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-14 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00109 | 0
[9 empty] | 743 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 743 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 743-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.743 |  |  | PF.743 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00110 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-15 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00110 | 0
[9 empty] | 744 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 744 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 744-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.744 |  |  | PF.744 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00114 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-16 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 14 | 0 | 200019SKA-00114 | 0
[9 empty] | 745 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 745 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 745-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.745 |  |  | PF.745 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00055 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 09-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 09 | 0 | 200019SKA-00055 | 0
[9 empty] | 746 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 746 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 746-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.746 |  |  | PF.746 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 200019SKA-00025 | SIMMONS_ELEC | 0 | 0.00 | 1 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50.0 % |  | RACK PACKAGE-LEVEL 19-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 19 | 3 | 200019SKA-00025 | 0
[9 empty] | 747 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 747 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 747-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.747 |  |  | PF.747 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00152 | MXD_RESI_JAP_ELEC | 8 | 0.00 | 19 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Design Stage | 10.0 % |  | -LEVEL 11-40-DE-01 | False |  | 136 | FAB-00152 | 0
[9 empty] | 748 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 748 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 748-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.748 |  |  | PF.748 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00151 | MXD_RESI_JAP_ELEC | 1710 | 0.00 | 2 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Packages (FAB) Confirmed | 50.0 % |  | 002-LEVEL B1-10-DE-01 | False |  | 1716 | FAB-00151 | 0
[9 empty] | 749 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 749 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 749-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.749 |  |  | PF.749 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 320001TUR-FAB-00003-25 | MXD_RESI_JAP_ELEC | 761 | 0.00 | 0 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00025-IW-Level 3-36-Units | False |  | 761 | 320001TUR-FAB-00003-25 | 0
[9 empty] | 750 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 750 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 750-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.750 |  |  | PF.750 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 320001TUR-FAB-00004-25 | MXD_RESI_JAP_ELEC | 33 | 0.00 | 3 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Design Stage | 10.0 % |  | FAB-00026-CND-LEVEL 37-LEVEL 15 | False | Riser | 48 | 320001TUR-FAB-00004-25 | 0
[9 empty] | 751 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 751 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 751-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.751 |  |  | PF.751 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-145 | PRINCIPIO - ELEC - SMC - 2023 | 1024 | 9.75 | 0 | 180035PGG | 9/18/2025 | P&G Gillette |  | Design Stage | 10.0 % | VDC | -NORTH MEZZ CABLE TRAY HANGERS-SUP-01 | False |  | 1024 | FAB-145 | 0
[9 empty] | 752 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 752 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 752-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.752 |  |  | PF.752 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00001-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 8/30/2024 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00001-CND-RIGID NIPPLES | False |  | 0 | 180035PGG-FAB-00001-25 | 0
[9 empty] | 753 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 753 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 753-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.753 |  |  | PF.753 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00002-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 9/16/2024 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00002-SUP-1 5-8- strut cut - 1--6- | False |  | 0 | 180035PGG-FAB-00002-25 | 0
[9 empty] | 754 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 754 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 754-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.754 |  |  | PF.754 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00003-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 10/3/2024 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00003-CND-4- grc nipples | False |  | 0 | 180035PGG-FAB-00003-25 | 0
[9 empty] | 755 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 755 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 755-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.755 |  |  | PF.755 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00004-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 10/18/2024 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00004-CND-1-4-grc- 4-5- grc nipples | False |  | 0 | 180035PGG-FAB-00004-25 | 0
[9 empty] | 756 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 756 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 756-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.756 |  |  | PF.756 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00005-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 2.00 | 0 | 180035PGG | 11/20/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00005-IW-FA IN WALL DEVICES | False |  | 0 | 180035PGG-FAB-00005-25 | 0
[9 empty] | 757 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 757 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 757-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.757 |  |  | PF.757 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00006-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 11/3/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00006-IW-FA IN WALL DEVICES | False |  | 0 | 180035PGG-FAB-00006-25 | 0
[9 empty] | 758 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 758 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 758-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.758 |  |  | PF.758 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00008-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 11/7/2025 | P&G Gillette |  | Issued for Fabrication | 100.0 % |  | FAB-00008-IW-ELECTRICAL ROUGH-TEL COM DEVICE | False |  | 0 | 180035PGG-FAB-00008-25 | 0
[9 empty] | 759 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 759 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 759-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.759 |  |  | PF.759 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00009-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 2.00 | 0 | 180035PGG | 11/20/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00009-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00009-25 | 0
[9 empty] | 760 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 760 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 760-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.760 |  |  | PF.760 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00010-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 12/28/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00010-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00010-25 | 0
[9 empty] | 761 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 761 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 761-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.761 |  |  | PF.761 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00011-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/3/2025 | P&G Gillette |  | Issued for Fabrication | 100.0 % |  | FAB-00011-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00011-25 | 0
[9 empty] | 762 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 762 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 762-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.762 |  |  | PF.762 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00013-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 8/4/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00013-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00013-25 | 0
[9 empty] | 763 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 763 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 763-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.763 |  |  | PF.763 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00014-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 8/4/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00014-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00014-25 | 0
[9 empty] | 764 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 764 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 764-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.764 |  |  | PF.764 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00015-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 11/18/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00015-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00015-25 | 0
[9 empty] | 765 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 765 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 765-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.765 |  |  | PF.765 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00016-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 12/25/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00016-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00016-25 | 0
[9 empty] | 766 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 766 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 766-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.766 |  |  | PF.766 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00017-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 10/7/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00017-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00017-25 | 0
[9 empty] | 767 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 767 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 767-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.767 |  |  | PF.767 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00018-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 10/29/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00018-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00018-25 | 0
[9 empty] | 768 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 768 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 768-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.768 |  |  | PF.768 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00019-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 11/20/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00019-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00019-25 | 0
[9 empty] | 769 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 769 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 769-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.769 |  |  | PF.769 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00020-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 11/18/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00020-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00020-25 | 0
[9 empty] | 770 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 770 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 770-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.770 |  |  | PF.770 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00021-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/31/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00021-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00021-25 | 0
[9 empty] | 771 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 771 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 771-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.771 |  |  | PF.771 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00022-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.20 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00022-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00022-25 | 0
[9 empty] | 772 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 772 |  |  | #DIVIDE BY ZERO | 2 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 772-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.772 |  |  | PF.772 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00023-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 36.44 | 0 | 180035PGG | 9/1/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00023-IW-MAIN LEVEL IN WALL ROUGH PLAN SECTION B | False |  | 0 | 180035PGG-FAB-00023-25 | 0
[9 empty] | 773 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 773 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 773-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.773 |  |  | PF.773 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00024-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 2/6/2026 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00024-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00024-25 | 0
[9 empty] | 774 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 774 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 774-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.774 |  |  | PF.774 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00025-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 11/17/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00025-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00025-25 | 0
[9 empty] | 775 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 775 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 775-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.775 |  |  | PF.775 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00026-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00026-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00026-25 | 0
[9 empty] | 776 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 776 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 776-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.776 |  |  | PF.776 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00027-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 1/9/2026 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00027-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00027-25 | 0
[9 empty] | 777 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 777 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 777-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.777 |  |  | PF.777 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00028-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.20 | 0 | 180035PGG | 2/2/2026 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00028-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00028-25 | 0
[9 empty] | 778 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 778 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 778-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.778 |  |  | PF.778 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00030-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.20 | 0 | 180035PGG | 1/14/2026 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00030-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00030-25 | 0
[9 empty] | 779 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 779 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 779-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.779 |  |  | PF.779 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00031-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 9/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00031-CND-INSTALL OH ELECT PIPING | False |  | 0 | 180035PGG-FAB-00031-25 | 0
[9 empty] | 780 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 780 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 780-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.780 |  |  | PF.780 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00032-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 27.33 | 0 | 180035PGG | 11/14/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00032-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00032-25 | 0
[9 empty] | 781 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 781 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 781-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.781 |  |  | PF.781 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00033-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 12/8/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00033-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00033-25 | 0
[9 empty] | 782 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 782 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 782-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.782 |  |  | PF.782 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00034-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 10/3/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00034-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00034-25 | 0
[9 empty] | 783 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 783 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 783-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.783 |  |  | PF.783 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00035-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 27.33 | 0 | 180035PGG | 10/27/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00035-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00035-25 | 0
[9 empty] | 784 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 784 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 784-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.784 |  |  | PF.784 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00036-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 11/18/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00036-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00036-25 | 0
[9 empty] | 785 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 785 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 785-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.785 |  |  | PF.785 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00037-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 8/4/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00037-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00037-25 | 0
[9 empty] | 786 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 786 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 786-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.786 |  |  | PF.786 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00038-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 8/4/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00038-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00038-25 | 0
[9 empty] | 787 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 787 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 787-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.787 |  |  | PF.787 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00039-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 60.00 | 0 | 180035PGG | 11/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00039-DE-VFD ASSEMBLIES | False |  | 0 | 180035PGG-FAB-00039-25 | 0
[9 empty] | 788 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 788 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 788-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.788 |  |  | PF.788 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00040-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 9/11/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00040-SUP-STAIR 1- STAIR 3 | False |  | 0 | 180035PGG-FAB-00040-25 | 0
[9 empty] | 789 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 789 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 789-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.789 |  |  | PF.789 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00041-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 60.00 | 0 | 180035PGG | 6/26/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00041-DE-ROOF DISCONNECTS | False |  | 0 | 180035PGG-FAB-00041-25 | 0
[9 empty] | 790 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 790 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 790-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.790 |  |  | PF.790 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00042-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 31 | 180035PGG | 8/1/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00042-CND-SPOOL - A - SECTION 6 | False |  | 2564 | 180035PGG-FAB-00042-25 | 0
[9 empty] | 791 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 791 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 791-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.791 |  |  | PF.791 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00043-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 6 | 180035PGG | 8/1/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00043-CND-SPOOL - B - SECTION 6 | False |  | 277 | 180035PGG-FAB-00043-25 | 0
[9 empty] | 792 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 792 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 792-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.792 |  |  | PF.792 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00044-25 | PRINCIPIO - ELEC - SMC - 2023 | 1 | 1.00 | 23 | 180035PGG | 7/7/2025 | P&G Gillette |  | Received on Jobsite | 15.7 % |  | FAB-00044-CND-SPOOL - C - SECTION 1 | False |  | 1238 | 180035PGG-FAB-00044-25 | 51
[9 empty] | 793 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 793 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 793-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.793 |  |  | PF.793 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00045-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 7 | 180035PGG | 7/25/2025 | P&G Gillette |  | Issued for Fabrication | 14.5 % | Shop Labor-Station 9 | FAB-00045-CND-SPOOL - F - SECTION 1 | False |  | 417 | 180035PGG-FAB-00045-25 | 55
[9 empty] | 794 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 794 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 794-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.794 |  |  | PF.794 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00046-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 8 | 180035PGG | 6/30/2025 | P&G Gillette |  | Issued for Fabrication | 17.9 % | Shop Labor-Station 9 | FAB-00046-CND-SPOOL - G - SECTION 1 | False |  | 290 | 180035PGG-FAB-00046-25 | 67
[9 empty] | 795 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 795 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 795-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.795 |  |  | PF.795 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00047-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 10 | 180035PGG | 6/30/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00047-CND-SPOOL - H - SECTION 1 | False |  | 456 | 180035PGG-FAB-00047-25 | 0
[9 empty] | 796 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 796 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 796-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.796 |  |  | PF.796 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00048-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 2.00 | 27 | 180035PGG | 7/11/2025 | P&G Gillette |  | Received on Jobsite | 0.0 % |  | FAB-00048-CND-SPOOL - I - SECTION 1 | False |  | 1254 | 180035PGG-FAB-00048-25 | 47
[9 empty] | 797 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 797 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 797-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.797 |  |  | PF.797 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00049-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/1/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00049-CND-SPARE LINE ITEM | False |  | 0 | 180035PGG-FAB-00049-25 | 0
[9 empty] | 798 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 798 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 798-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.798 |  |  | PF.798 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00050-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 8 | 180035PGG | 8/18/2025 | P&G Gillette |  | Issued for Fabrication | 0.0 % | Shop Labor-Station 9 | FAB-00050-CND-SPOOL - H - SECTION 2 | False |  | 360 | 180035PGG-FAB-00050-25 | 11
[9 empty] | 799 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 799 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 799-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.799 |  |  | PF.799 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00051-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 56 | 180035PGG | 7/25/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00051-CND-PIPE BENDS -LARGE- POWER | False |  | 157 | 180035PGG-FAB-00051-25 | 0
[9 empty] | 800 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 800 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 800-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.800 |  |  | PF.800 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00052-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 41.00 | 12 | 180035PGG | 6/24/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00052-SUP-SECTION 1 MEZZ HANGERS -59-65-5 - A-5-A-9- | False |  | 4834 | 180035PGG-FAB-00052-25 | 0
[9 empty] | 801 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 801 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 801-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.801 |  |  | PF.801 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00053-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 22.75 | 7 | 180035PGG | 7/7/2025 | P&G Gillette |  | Issued for Fabrication | 0.0 % |  | FAB-00053-SUP-MAIN LEVEL HANGERS-SECTION 6- | False |  | 2384 | 180035PGG-FAB-00053-25 | 280
[9 empty] | 802 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 802 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 802-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.802 |  |  | PF.802 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00054-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 8 | 180035PGG | 8/18/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00054-CND-SPOOL - I - SECTION 2 | False |  | 412 | 180035PGG-FAB-00054-25 | 0
[9 empty] | 803 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 803 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 803-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.803 |  |  | PF.803 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00055-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.00 | 0 | 180035PGG | 9/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00055-IW-IDF WIREMOLD | False |  | 0 | 180035PGG-FAB-00055-25 | 0
[9 empty] | 804 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 804 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 804-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.804 |  |  | PF.804 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00056-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.00 | 0 | 180035PGG | 9/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00056-IW-IDF WIREMOLD | False |  | 0 | 180035PGG-FAB-00056-25 | 0
[9 empty] | 805 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 805 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 805-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.805 |  |  | PF.805 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00057-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 24.00 | 0 | 180035PGG | 7/31/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00057-DE-75 KVA PDU- | False |  | 0 | 180035PGG-FAB-00057-25 | 0
[9 empty] | 806 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 806 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 806-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.806 |  |  | PF.806 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00059-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 5 | 180035PGG | 8/11/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00059-CND-SPOOL - J - SECTION 5 | False |  | 203 | 180035PGG-FAB-00059-25 | 0
[9 empty] | 807 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 807 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 807-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.807 |  |  | PF.807 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00060-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 10 | 180035PGG | 7/14/2025 | P&G Gillette |  | Received on Jobsite | 0.0 % |  | FAB-00060-CND-SPOOL - D - SECTION 3 | False |  | 389 | 180035PGG-FAB-00060-25 | 1
[9 empty] | 808 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 808 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 808-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.808 |  |  | PF.808 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00061-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 13 | 180035PGG | 7/18/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00061-CND-SPOOL - E - SECTION 3 | False |  | 567 | 180035PGG-FAB-00061-25 | 0
[9 empty] | 809 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 809 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 809-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.809 |  |  | PF.809 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00062-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 6 | 180035PGG | 8/25/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00062-CND-SPOOL - H - SECTION 4 -DELIVERY 1- j | False |  | 231 | 180035PGG-FAB-00062-25 | 0
[9 empty] | 810 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 810 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 810-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.810 |  |  | PF.810 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00063-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 5 | 180035PGG | 8/25/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00063-CND-SPOOL - I - SECTION 4 -DELIVERY 1- | False |  | 204 | 180035PGG-FAB-00063-25 | 0
[9 empty] | 811 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 811 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 811-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.811 |  |  | PF.811 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00064-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.50 | 23 | 180035PGG | 8/18/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00064-CND-SPOOL - C - SECTION 5 | False |  | 1453 | 180035PGG-FAB-00064-25 | 0
[9 empty] | 812 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 812 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 812-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.812 |  |  | PF.812 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00065-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 4 | 180035PGG | 8/11/2025 | P&G Gillette |  | Received on Jobsite | 0.0 % |  | FAB-00065-CND-SPOOL - E - SECTION 5 | False |  | 111 | 180035PGG-FAB-00065-25 | 6
[9 empty] | 813 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 813 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 813-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.813 |  |  | PF.813 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00066-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00066-CND-SPOOL - A - SECTION 6 | False |  | 0 | 180035PGG-FAB-00066-25 | 0
[9 empty] | 814 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 814 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 814-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.814 |  |  | PF.814 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00067-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00067-CND-SPOOL - B - SECTION 6 | False |  | 0 | 180035PGG-FAB-00067-25 | 0
[9 empty] | 815 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 815 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 815-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.815 |  |  | PF.815 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00068-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00068-DE-TEMP PDU 75KVA | False |  | 0 | 180035PGG-FAB-00068-25 | 0
[9 empty] | 816 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 816 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 816-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.816 |  |  | PF.816 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00069-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG | 9/8/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00069-DE-TEMP PDU 75KVA | False |  | 0 | 180035PGG-FAB-00069-25 | 0
[9 empty] | 817 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 817 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 817-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.817 |  |  | PF.817 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00070-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG | 9/8/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00070-DE-TEMP PDU 75KVA | False |  | 0 | 180035PGG-FAB-00070-25 | 0
[9 empty] | 818 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 818 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 818-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.818 |  |  | PF.818 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00071-25 | PRINCIPIO - ELEC - SMC - 2023 | 5 | 9.00 | 0 | 180035PGG | 10/14/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00071-DE-VFD BUILD EF 8-9-14A-14B-15 | False | NOT SHOWN | 5 | 180035PGG-FAB-00071-25 | 0
[9 empty] | 819 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 819 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 819-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.819 |  |  | PF.819 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00072-25 | PRINCIPIO - ELEC - SMC - 2023 | 2 | 4.50 | 0 | 180035PGG | 10/14/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00072-DE-VFD BUILD EF 3A-3B | False | NOT SHOWN | 2 | 180035PGG-FAB-00072-25 | 0
[9 empty] | 820 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 820 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 820-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.820 |  |  | PF.820 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00073-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/14/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % |  | FAB-00073-DE-VFD BUILD EF 5-6-18 | False | NOT SHOWN | 0 | 180035PGG-FAB-00073-25 | 0
[9 empty] | 821 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 821 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 821-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.821 |  |  | PF.821 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00074-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.50 | 0 | 180035PGG | 10/14/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % |  | FAB-00074-DE-VFD BUILD EF 12-17 | False |  | 0 | 180035PGG-FAB-00074-25 | 0
[9 empty] | 822 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 822 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 822-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.822 |  |  | PF.822 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00075-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 3/21/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00075-CND-4- RIGID NIPPLES | False | NOT SHOWN | 0 | 180035PGG-FAB-00075-25 | 0
[9 empty] | 823 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 823 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 823-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.823 |  |  | PF.823 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00076-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 4/9/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00076-CND-POLE BASE PIPE BENDS | False |  | 0 | 180035PGG-FAB-00076-25 | 0
[9 empty] | 824 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 824 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 824-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.824 |  |  | PF.824 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00077_180035PGG | PRINCIPIO - ELEC - SMC - 2023 | 3 | 0.00 | 0 | 180035PGG |  | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00077--DE-VFD-CHP-8 | False | VFD-CHP-8 | 3 | FAB-00077_180035PGG | 0
[9 empty] | 825 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 825 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 825-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.825 |  |  | PF.825 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00077-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 9.00 | 0 | 180035PGG | 11/24/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % |  | FAB-00077-DE-VFD BUILD CHP-7-8 | False |  | 0 | 180035PGG-FAB-00077-25 | 0
[9 empty] | 826 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 826 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 826-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.826 |  |  | PF.826 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00078-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 9.00 | 0 | 180035PGG | 11/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00078-DE-VFD BUILD CHP-1-2-4-5 | False |  | 0 | 180035PGG-FAB-00078-25 | 0
[9 empty] | 827 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 827 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 827-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.827 |  |  | PF.827 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00079-25 | PRINCIPIO - ELEC - SMC - 2023 | 9 | 15.00 | 1 | 180035PGG | 12/10/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00079-DE-BDA PANEL ASSEMBLY - MEZZANINE | False |  | 11 | 180035PGG-FAB-00079-25 | 0
[9 empty] | 828 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 828 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 828-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.828 |  |  | PF.828 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00080-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00080-CND-WIREMOLD ASSEMBLIES - AHU SHUT DOWN | False |  | 0 | 180035PGG-FAB-00080-25 | 0
[9 empty] | 829 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 829 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 829-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.829 |  |  | PF.829 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00081-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 72.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00081-IW-WIREMOLD ASSEMBLIES - RELAYS | False |  | 0 | 180035PGG-FAB-00081-25 | 0
[9 empty] | 830 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 830 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 830-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.830 |  |  | PF.830 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00082-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 12.00 | 0 | 180035PGG | 9/1/2025 | P&G Gillette |  | Hold | 0.0 % |  | FAB-00082-DE-LEVEL 1 PUMP HOUSE ASSEMBLY | False |  | 0 | 180035PGG-FAB-00082-25 | 0
[9 empty] | 831 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 831 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 831-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.831 |  |  | PF.831 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00083-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 30.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % |  | FAB-00083-DE-PANEL ASSEMBLIES - LEVEL 1 MAIN MANUFACTURING | False | NOT SHOWN | 0 | 180035PGG-FAB-00083-25 | 0
[9 empty] | 832 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 832 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 832-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.832 |  |  | PF.832 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00084-25 | PRINCIPIO - ELEC - SMC - 2023 | 27 | 10.00 | 1 | 180035PGG | 12/29/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00084-DE-PANEL ASSEMBLIES - LEVEL MEZZANINE | False |  | 29 | 180035PGG-FAB-00084-25 | 0
[9 empty] | 833 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 833 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 833-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.833 |  |  | PF.833 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00086-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 15.00 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00086-DE-POWER SUPPLY ASSEMBLY - LEVEL MEZZANINE MANUFACTURING | False |  | 0 | 180035PGG-FAB-00086-25 | 0
[9 empty] | 834 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 834 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 834-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.834 |  |  | PF.834 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00087-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 15.00 | 0 | 180035PGG | 5/14/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00087-DE-POWER SUPPLY ASSEMBLY - LEVEL 1 MAIN WAREHOUSE MV SWITCHGEAR ENCLOSURE | False |  | 0 | 180035PGG-FAB-00087-25 | 0
[9 empty] | 835 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 835 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 835-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.835 |  |  | PF.835 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00088-25 | PRINCIPIO - ELEC - SMC - 2023 | 11 | 15.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % |  | FAB-00088-DE-POWER SUPPLY ASSEMBLY - LEVEL 1 MAIN MANUFACTURING | False |  | 11 | 180035PGG-FAB-00088-25 | 0
[9 empty] | 836 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 836 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 836-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.836 |  |  | PF.836 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00089-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Issued for Fabrication | 100.0 % |  | FAB-00089-DE-ELEVATOR RECALL ASSEMBLY - LEVEL 1 | False | NOT SHOWN | 0 | 180035PGG-FAB-00089-25 | 0
[9 empty] | 837 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 837 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 837-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.837 |  |  | PF.837 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00090-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 9.00 | 0 | 180035PGG | 5/27/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00090-DE-SPIDER BOXES | False |  | 0 | 180035PGG-FAB-00090-25 | 0
[9 empty] | 838 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 838 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 838-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.838 |  |  | PF.838 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00091-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00091-DE-Power Supply MAIN WAREHOUSE Janitor Closet PS2 | False |  | 0 | 180035PGG-FAB-00091-25 | 0
[9 empty] | 839 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 839 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 839-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.839 |  |  | PF.839 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00091-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 15.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00091-DE-Power Supply MAIN WAREHOUSE Janitor Closet PS2 | False |  | 0 | 180035PGG-FAB-00091-25 | 0
[9 empty] | 840 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 840 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 840-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.840 |  |  | PF.840 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00092-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 100.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00092-IW-DUCT SMOKE BUILDS | False |  | 0 | 180035PGG-FAB-00092-25 | 0
[9 empty] | 841 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 841 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 841-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.841 |  |  | PF.841 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00093-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 30.00 | 0 | 180035PGG | 5/30/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00093-DE-FIRE ALARM FIRE COMMAND CENTER | False | NOT SHOWN | 0 | 180035PGG-FAB-00093-25 | 0
[9 empty] | 842 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 842 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 842-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.842 |  |  | PF.842 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00094-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 19.83 | 0 | 180035PGG | 7/7/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00094-IW-JB WITH TERM BLOCK | False |  | 0 | 180035PGG-FAB-00094-25 | 0
[9 empty] | 843 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 843 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 843-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.843 |  |  | PF.843 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00095-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.61 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00095-PB-JB WITH TERM BLOCK | False |  | 0 | 180035PGG-FAB-00095-25 | 0
[9 empty] | 844 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 844 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 844-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.844 |  |  | PF.844 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00096-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.83 | 0 | 180035PGG | 6/6/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00096-PB-CUTOUT BOTTOM OF STAINLESS NEXWCOM CAN | False |  | 0 | 180035PGG-FAB-00096-25 | 0
[9 empty] | 845 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 845 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 845-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.845 |  |  | PF.845 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00097-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.50 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00097-LGT-FA SWIVELS | False |  | 0 | 180035PGG-FAB-00097-25 | 0
[9 empty] | 846 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 846 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 846-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.846 |  |  | PF.846 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00098-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 2.70 | 0 | 180035PGG | 6/17/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00098-IW-exterior wall in wall rough | False |  | 0 | 180035PGG-FAB-00098-25 | 0
[9 empty] | 847 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 847 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 847-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.847 |  |  | PF.847 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00099-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 7/28/2025 | P&G Gillette |  | FAB CANCELLED | 0.0 % |  | FAB-00099-DE-STICK BUILT PANELS | False |  | 0 | 180035PGG-FAB-00099-25 | 0
[9 empty] | 848 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 848 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 848-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.848 |  |  | PF.848 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00100-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG | 7/4/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00100-DE-OPEN CLEAN-KO SEAL 1200AMP 120-208V TEMPS GEAR | False |  | 0 | 180035PGG-FAB-00100-25 | 0
[9 empty] | 849 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 849 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 849-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.849 |  |  | PF.849 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00101-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.75 | 2 | 180035PGG | 8/11/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00101-SUP-SLAB ON GRADE SECTION 2 HANGERS | False |  | 570 | 180035PGG-FAB-00101-25 | 0
[9 empty] | 850 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 850 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 850-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.850 |  |  | PF.850 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00102-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 15.00 | 6 | 180035PGG | 8/4/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00102-SUP-MEZZANINE HANGERS SECTION 5 HANGERS | False |  | 1653 | 180035PGG-FAB-00102-25 | 0
[9 empty] | 851 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 851 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 851-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.851 |  |  | PF.851 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00103-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 10.00 | 3 | 180035PGG | 8/11/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 100.0 % |  | FAB-00103-SUP-SLAB ON GRADE SECTION 4 HANGERS | False |  | 1196 | 180035PGG-FAB-00103-25 | 243
[9 empty] | 852 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 852 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 852-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.852 |  |  | PF.852 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00104-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.00 | 1 | 180035PGG | 9/18/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % | Shop Labor-Station 9 | FAB-00104-SUP-SLAB ON GRADE SECTION 8 HANGERS | False |  | 600 | 180035PGG-FAB-00104-25 | 0
[9 empty] | 853 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 853 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 853-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.853 |  |  | PF.853 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00105-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 1 | 180035PGG | 9/18/2025 | P&G Gillette |  | Shipped to Jobsite | 0.0 % | Shop Labor-Station 9 | FAB-00105-SUP-SLAB ON GRADE SECTION 7 HANGERS | False |  | 844 | 180035PGG-FAB-00105-25 | 96
[9 empty] | 854 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 854 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 854-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.854 |  |  | PF.854 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00106-25 | PRINCIPIO - ELEC - SMC - 2023 | 2 | 1.50 | 4 | 180035PGG | 7/28/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00106-DE-SINGLE TUB BUILDS BATCH 1 | False |  | 142 | 180035PGG-FAB-00106-25 | 0
[9 empty] | 855 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 855 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 855-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.855 |  |  | PF.855 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00107-25 | PRINCIPIO - ELEC - SMC - 2023 | 68 | 25.95 | 10 | 180035PGG | 7/28/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00107-DE-DOUBLE TUB BUILDS BATCH 1 | False |  | 418 | 180035PGG-FAB-00107-25 | 0
[9 empty] | 856 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 856 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 856-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.856 |  |  | PF.856 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00108-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 3 | 180035PGG | 8/18/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00108-DE-SINGLE TUB BUILDS BATCH 2 | False |  | 105 | 180035PGG-FAB-00108-25 | 0
[9 empty] | 857 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 857 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 857-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.857 |  |  | PF.857 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00109-25 | PRINCIPIO - ELEC - SMC - 2023 | 1 | 21.62 | 10 | 180035PGG | 8/18/2025 | P&G Gillette |  | Design Stage | 10.0 % |  | FAB-00109-DE-DOUBLE TUB BUILDS BATCH 2 | False |  | 351 | 180035PGG-FAB-00109-25 | 0
[9 empty] | 858 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 858 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 858-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.858 |  |  | PF.858 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00110-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 0 | 180035PGG | 9/11/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % |  | FAB-00110-DE-SINGLE TUB BUILDS BATCH 3 | False |  | 0 | 180035PGG-FAB-00110-25 | 0
[9 empty] | 859 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 859 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 859-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.859 |  |  | PF.859 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00111-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 14.55 | 10 | 180035PGG | 9/11/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % |  | FAB-00111-DE-DOUBLE TUB BUILDS BATCH 3 | False |  | 350 | 180035PGG-FAB-00111-25 | 0
[9 empty] | 860 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 860 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 860-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.860 |  |  | PF.860 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00112-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.60 | 0 | 180035PGG | 8/5/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00112-PB-12 x 12 x 48- HR TROUGHS | False |  | 0 | 180035PGG-FAB-00112-25 | 0
[9 empty] | 861 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 861 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 861-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.861 |  |  | PF.861 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00113-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 23.84 | 0 | 180035PGG | 8/5/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00113-PB-MC SATELLITE JUNCTION BOXES | False |  | 0 | 180035PGG-FAB-00113-25 | 0
[9 empty] | 862 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 862 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 862-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.862 |  |  | PF.862 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00114-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 12.00 | 0 | 180035PGG | 8/11/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00114-DE-TEMP POWER RACKS | False |  | 0 | 180035PGG-FAB-00114-25 | 0
[9 empty] | 863 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 863 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 863-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.863 |  |  | PF.863 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00115-25 | PRINCIPIO - ELEC - SMC - 2023 | 31 | 1.50 | 0 | 180035PGG | 8/8/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00115-DE-BDA MAST | False |  | 31 | 180035PGG-FAB-00115-25 | 0
[9 empty] | 864 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 864 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 864-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.864 |  |  | PF.864 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00116-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 6 | 180035PGG | 7/31/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00116-CND-SPOOL - C - SECTION 6 | False |  | 252 | 180035PGG-FAB-00116-25 | 0
[9 empty] | 865 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 865 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 865-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.865 |  |  | PF.865 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00117-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 13 | 180035PGG | 7/31/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % | Field Labor | FAB-00117-CND-SECTION 6 PIPE BENDS | False |  | 50 | 180035PGG-FAB-00117-25 | 0
[9 empty] | 866 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 866 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 866-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.866 |  |  | PF.866 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00118-25 | PRINCIPIO - ELEC - SMC - 2023 | 10 | 6.00 | 0 | 180035PGG | 10/1/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35.0 % |  | FAB-00118-DE-VFD STICK BUILD HWP 1- HWP 2 | False |  | 10 | 180035PGG-FAB-00118-25 | 0
[9 empty] | 867 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 867 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 867-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.867 |  |  | PF.867 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00119-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/1/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00119-DE-VFD STICK BUILD HWP 4- HWP 5 | False | NOT SHOWN | 0 | 180035PGG-FAB-00119-25 | 0
[9 empty] | 868 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 868 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 868-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.868 |  |  | PF.868 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00120-25 | PRINCIPIO - ELEC - SMC - 2023 | 10 | 6.00 | 0 | 180035PGG | 10/3/2025 | P&G Gillette |  | Issued for Fabrication | 100.0 % |  | FAB-00120-DE-VFD STICK BUILD PHCP -1- PHCP -2 | False | NOT SHOWN | 10 | 180035PGG-FAB-00120-25 | 0
[9 empty] | 869 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 869 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 869-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.869 |  |  | PF.869 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00121-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/3/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00121-DE-VFD STICK BUILD PHCP -3A- PHCP -3B | False |  | 0 | 180035PGG-FAB-00121-25 | 0
[9 empty] | 870 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 870 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 870-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.870 |  |  | PF.870 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00122-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/6/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00122-DE-VFD STICK BUILD PHCP -4A- PHCP -4B | False |  | 0 | 180035PGG-FAB-00122-25 | 0
[9 empty] | 871 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 871 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 871-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.871 |  |  | PF.871 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00123-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/6/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00123-DE-VFD STICK BUILD PHCP -5A- PHCP -5B | False |  | 0 | 180035PGG-FAB-00123-25 | 0
[9 empty] | 872 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 872 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 872-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.872 |  |  | PF.872 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00124-25 | PRINCIPIO - ELEC - SMC - 2023 | 14 | 6.00 | 0 | 180035PGG | 10/7/2025 | P&G Gillette |  | Issued for Fabrication | 100.0 % | VDC | FAB-00124-DE-VFD STICK BUILD PHCP -6A- PHCP -6B | False |  | 14 | 180035PGG-FAB-00124-25 | 0
[9 empty] | 873 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 873 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 873-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.873 |  |  | PF.873 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00125-25 | PRINCIPIO - ELEC - SMC - 2023 | 1 | 1.00 | 7 | 180035PGG | 9/3/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00125-CND-SPOOL - I -SECTION 4 -DELIVERY 2- | False |  | 346 | 180035PGG-FAB-00125-25 | 0
[9 empty] | 874 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 874 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 874-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.874 |  |  | PF.874 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00126-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 14 | 180035PGG | 9/3/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00126-CND-SPOOL - HI -SECTION 4 -DELIVERY 2- | False |  | 734 | 180035PGG-FAB-00126-25 | 0
[9 empty] | 875 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 875 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 875-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.875 |  |  | PF.875 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00127-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 4 | 180035PGG | 8/4/2025 | P&G Gillette |  | Received on Jobsite | 10.0 % |  | FAB-00127-SUP-FA MINI HANGERS -SECTION 5- | False |  | 758 | 180035PGG-FAB-00127-25 | 0
[9 empty] | 876 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 876 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 876-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.876 |  |  | PF.876 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00128-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.28 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00128-IW-IDF IN WALL ROOM 211 | False |  | 0 | 180035PGG-FAB-00128-25 | 0
[9 empty] | 877 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 877 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 877-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.877 |  |  | PF.877 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00129-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.28 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00129-IW-IDF IN WALL ROOM 224 | False |  | 0 | 180035PGG-FAB-00129-25 | 0
[9 empty] | 878 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 878 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 878-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.878 |  |  | PF.878 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00130-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.32 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00130-PB-IDF SECURITY JBS ROOM 224 | False |  | 0 | 180035PGG-FAB-00130-25 | 0
[9 empty] | 879 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 879 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 879-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.879 |  |  | PF.879 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00131-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.66 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00131-PB-IDF SECURITY JBS ROOM 134 | False |  | 0 | 180035PGG-FAB-00131-25 | 0
[9 empty] | 880 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 880 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 880-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.880 |  |  | PF.880 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00132-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.28 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00132-IW-IDF IN WALL ROOM 134 | False |  | 0 | 180035PGG-FAB-00132-25 | 0
[9 empty] | 881 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 881 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 881-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.881 |  |  | PF.881 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00133-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.66 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00133-PB-IDF SECURITY JBS ROOM 221 | False |  | 0 | 180035PGG-FAB-00133-25 | 0
[9 empty] | 882 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 882 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 882-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.882 |  |  | PF.882 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00134-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.00 | 0 | 180035PGG | 9/25/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-00134-IW-IDF WIREMOLD | False |  | 0 | 180035PGG-FAB-00134-25 | 0
[9 empty] | 883 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 883 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 883-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.883 |  |  | PF.883 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00135-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 47.20 | 0 | 180035PGG | 9/25/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00135-LGT-MEZZANINE LIGHTING CONTROL | False |  | 0 | 180035PGG-FAB-00135-25 | 0
[9 empty] | 884 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 884 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 884-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.884 |  |  | PF.884 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00136-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 47.20 | 0 | 180035PGG | 9/25/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00136-LGT-MAIN LEVEL LIGHTING CONTROL | False |  | 0 | 180035PGG-FAB-00136-25 | 0
[9 empty] | 885 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 885 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 885-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.885 |  |  | PF.885 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 180035PGG-FAB-00137-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 16 | 180035PGG | 9/22/2025 | P&G Gillette |  | Shipped to Jobsite | 100.0 % | Shipping & Receiving | FAB-00137-CND-SPOOL - HI -SECTION 8 | False | MODULAR EMT | 792 | 180035PGG-FAB-00137-25 | 130
[9 empty] | 886 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 886 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 886-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.886 |  |  | PF.886 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 6232025SMC-FAB-00141-25 | PRINCIPIO - ELEC - SMC - 2023 | 48 | 0.00 | 2 | 180035PGG |  | P&G Gillette |  | Packages (FAB) Confirmed | 50.0 % |  | FAB-00142-DE-PERIMETER FOOTING-B2 | False |  | 52 | 6232025SMC-FAB-00141-25 | 0
[9 empty] | 887 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 887 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 887-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.887 |  |  | PF.887 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-077.1_180035PGG | PRINCIPIO - ELEC - SMC - 2023 | 3 | 0.00 | 0 | 180035PGG |  | P&G Gillette |  | Shipped to Jobsite | 100.0 % |  | FAB-077.1-MAIN LEVEL-DE-VFD-CHP-7 | False | VFD-CHP-7 | 3 | FAB-077.1_180035PGG | 0
[9 empty] | 888 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 888 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 888-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.888 |  |  | PF.888 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | 150273WAL-00001-25 | MGH GBJ_ELEC_SMC_Stratus | 203 | 0.00 | 0 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Packages (FAB) Confirmed | 50.0 % |  | CND---ROOF LINE (TOP OF INSULATION)-001 | False |  | 203 | 150273WAL-00001-25 | 0
[9 empty] | 889 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 889 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 889-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.889 |  |  | PF.889 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00001-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00001-LEVEL 3-DE-Level 3-Load Centers 125A | False | Level 3-Load Centers 125A | 0 | FAB-00001-320001TUR | 0
[9 empty] | 890 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 890 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 890-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.890 |  |  | PF.890 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00002-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 10/20/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00002-LEVEL 3-DE-Level 3-Load Centers 150A | False | Level 3-Load Centers 150A | 0 | FAB-00002-320001TUR | 0
[9 empty] | 891 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 891 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 891-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.891 |  |  | PF.891 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO | TRUE |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00003-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00003-LEVEL 4-DE-Level 4-Load Centers 125A | False | Level 4-Load Centers 125A | 0 | FAB-00003-320001TUR | 0
[9 empty] | 892 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 892 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 892-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.892 |  |  | PF.892 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00004-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00004-LEVEL 4-DE-Level 4-Load Centers 150A | False | Level 4-Load Centers 150A | 0 | FAB-00004-320001TUR | 0
[9 empty] | 893 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 893 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 893-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.893 |  |  | PF.893 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00005-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00005-LEVEL 5-DE-Level 5-Load Centers 125A | False | Level 5-Load Centers 125A | 0 | FAB-00005-320001TUR | 0
[9 empty] | 894 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 894 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 894-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.894 |  |  | PF.894 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00006-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00006-LEVEL 5-DE-Level 5-Load Centers 150A | False | Level 5-Load Centers 150A | 0 | FAB-00006-320001TUR | 0
[9 empty] | 895 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 895 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 895-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.895 |  |  | PF.895 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00007-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00007-LEVEL 7-DE-Level 7-Load Centers 125A | False | Level 7-Load Centers 125A | 0 | FAB-00007-320001TUR | 0
[9 empty] | 896 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 896 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 896-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.896 |  |  | PF.896 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00008-320001TUR | MXD_RESI_JAP_ELEC | 0 | 31.68 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00008-LEVEL 7-DE-Level 7-Load Centers 150A | False | Level 7-Load Centers 150A | 0 | FAB-00008-320001TUR | 0
[9 empty] | 897 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 897 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 897-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.897 |  |  | PF.897 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00009-320001TUR | MXD_RESI_JAP_ELEC | 0 | 48.37 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00009-LEVEL 8-DE-Level 8-Load Centers 125A | False | Level 8-Load Centers 125A | 0 | FAB-00009-320001TUR | 0
[9 empty] | 898 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 898 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 898-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.898 |  |  | PF.898 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00010-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00010-LEVEL 8-DE-Level 8-Load Centers 150A | False | Level 8-Load Centers 150A | 0 | FAB-00010-320001TUR | 0
[9 empty] | 899 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 899 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 899-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.899 |  |  | PF.899 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00011-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 12/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00011-LEVEL 9-DE-Level 9-Load Centers 125A | False | Level 9-Load Centers 125A | 0 | FAB-00011-320001TUR | 0
[9 empty] | 900 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 900 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 900-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.900 |  |  | PF.900 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00012-320001TUR | MXD_RESI_JAP_ELEC | 0 | 31.68 | 0 | 320001TUR | 1/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00012-LEVEL 9-DE-Level 9-Load Centers 150A | False | Level 9-Load Centers 150A | 0 | FAB-00012-320001TUR | 0
[9 empty] | 901 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 901 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 901-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.901 |  |  | PF.901 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00013-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00013-LEVEL 10-DE-Level 10-Load Centers 125A | False | Level 10-Load Centers 125A | 0 | FAB-00013-320001TUR | 0
[9 empty] | 902 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 902 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 902-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.902 |  |  | PF.902 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00014-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00014-LEVEL 10-DE-Level 10-Load Centers 150A | False | Level 10-Load Centers 150A | 0 | FAB-00014-320001TUR | 0
[9 empty] | 903 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 903 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 903-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.903 |  |  | PF.903 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00015-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00015-LEVEL 11-DE-Level 11-Load Centers 125A | False | Level 11-Load Centers 125A | 0 | FAB-00015-320001TUR | 0
[9 empty] | 904 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 904 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 904-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.904 |  |  | PF.904 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00016-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00016-LEVEL 11-DE-Level 11-Load Centers 150A | False | Level 11-Load Centers 150A | 0 | FAB-00016-320001TUR | 0
[9 empty] | 905 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 905 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 905-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.905 |  |  | PF.905 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00017-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00017-LEVEL 12-DE-Level 12-Load Centers 125A | False | Level 12-Load Centers 125A | 0 | FAB-00017-320001TUR | 0
[9 empty] | 906 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 906 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 906-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.906 |  |  | PF.906 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00018-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00018-LEVEL 12-DE-Level 12-Load Centers 150A | False | Level 12-Load Centers 150A | 0 | FAB-00018-320001TUR | 0
[9 empty] | 907 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 907 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 907-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.907 |  |  | PF.907 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00019-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00019-LEVEL 13-DE-Level 13-Load Centers 125A | False | Level 13-Load Centers 125A | 0 | FAB-00019-320001TUR | 0
[9 empty] | 908 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 908 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 908-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.908 |  |  | PF.908 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00020-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00020-LEVEL 13-DE-Level 13-Load Centers 150A | False | Level 13-Load Centers 150A | 0 | FAB-00020-320001TUR | 0
[9 empty] | 909 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 909 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 909-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.909 |  |  | PF.909 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00021-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 3/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00021-LEVEL 14-DE-Level 14-Load Centers 125A | False | Level 14-Load Centers 125A | 0 | FAB-00021-320001TUR | 0
[9 empty] | 910 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 910 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 910-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.910 |  |  | PF.910 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00022-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00022-LEVEL 14-DE-Level 14-Load Centers 150A | False | Level 14-Load Centers 150A | 0 | FAB-00022-320001TUR | 0
[9 empty] | 911 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 911 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 911-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.911 |  |  | PF.911 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00023-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 3/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00023-LEVEL 15-DE-Level 15-Load Centers 125A | False | Level 15-Load Centers 125A | 0 | FAB-00023-320001TUR | 0
[9 empty] | 912 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 912 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 912-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.912 |  |  | PF.912 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00024-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00024-LEVEL 15-DE-Level 15-Load Centers 150A | False | Level 15-Load Centers 150A | 0 | FAB-00024-320001TUR | 0
[9 empty] | 913 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 913 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 913-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.913 |  |  | PF.913 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00025-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 4/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00025-LEVEL 16-DE-Level 16-Load Centers 125A | False | Level 16-Load Centers 125A | 0 | FAB-00025-320001TUR | 0
[9 empty] | 914 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 914 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 914-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.914 |  |  | PF.914 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00026-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 4/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00026-LEVEL 16-DE-Level 16-Load Centers 150A | False | Level 16-Load Centers 150A | 0 | FAB-00026-320001TUR | 0
[9 empty] | 915 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 915 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 915-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.915 |  |  | PF.915 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00027-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 4/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00027-LEVEL 17-DE-Level 17-Load Centers 125A | False | Level 17-Load Centers 125A | 0 | FAB-00027-320001TUR | 0
[9 empty] | 916 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 916 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 916-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.916 |  |  | PF.916 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00028-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 4/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00028-LEVEL 17-DE-Level 17-Load Centers 150A | False | Level 17-Load Centers 150A | 0 | FAB-00028-320001TUR | 0
[9 empty] | 917 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 917 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 917-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.917 |  |  | PF.917 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00029-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 5/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00029-LEVEL 18-DE-Level 18-Load Centers 125A | False | Level 18-Load Centers 125A | 0 | FAB-00029-320001TUR | 0
[9 empty] | 918 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 918 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 918-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.918 |  |  | PF.918 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00030-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 5/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00030-LEVEL 18-DE-Level 18-Load Centers 150A | False | Level 18-Load Centers 150A | 0 | FAB-00030-320001TUR | 0
[9 empty] | 919 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 919 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 919-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.919 |  |  | PF.919 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00031-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 5/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00031-LEVEL 19-DE-Level 19-Load Centers 125A | False | Level 19-Load Centers 125A | 0 | FAB-00031-320001TUR | 0
[9 empty] | 920 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 920 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 920-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.920 |  |  | PF.920 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00032-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 5/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00032-LEVEL 19-DE-Level 19-Load Centers 150A | False | Level 19-Load Centers 150A | 0 | FAB-00032-320001TUR | 0
[9 empty] | 921 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 921 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 921-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.921 |  |  | PF.921 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00033-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 6/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00033-LEVEL 20-DE-Level 20-Load Centers 125A | False | Level 20-Load Centers 125A | 0 | FAB-00033-320001TUR | 0
[9 empty] | 922 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 922 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 922-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.922 |  |  | PF.922 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00034-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00034-LEVEL 20-DE-Level 20-Load Centers 150A | False | Level 20-Load Centers 150A | 0 | FAB-00034-320001TUR | 0
[9 empty] | 923 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 923 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 923-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.923 |  |  | PF.923 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00035-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00035-LEVEL 21-DE-Level 21-Load Centers 125A | False | Level 21-Load Centers 125A | 0 | FAB-00035-320001TUR | 0
[9 empty] | 924 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 924 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 924-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.924 |  |  | PF.924 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00036-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00036-LEVEL 21-DE-Level 21-Load Centers 150A | False | Level 21-Load Centers 150A | 0 | FAB-00036-320001TUR | 0
[9 empty] | 925 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 925 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 925-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.925 |  |  | PF.925 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00037-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00037-LEVEL 22-DE-Level 22-Load Centers 125A | False | Level 22-Load Centers 125A | 0 | FAB-00037-320001TUR | 0
[9 empty] | 926 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 926 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 926-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.926 |  |  | PF.926 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00038-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00038-LEVEL 22-DE-Level 22-Load Centers 150A | False | Level 22-Load Centers 150A | 0 | FAB-00038-320001TUR | 0
[9 empty] | 927 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 927 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 927-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.927 |  |  | PF.927 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00039-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00039-LEVEL 23-DE-Level 23-Load Centers 125A | False | Level 23-Load Centers 125A | 0 | FAB-00039-320001TUR | 0
[9 empty] | 928 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 928 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 928-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.928 |  |  | PF.928 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00040-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00040-LEVEL 23-DE-Level 23-Load Centers 150A | False | Level 23-Load Centers 150A | 0 | FAB-00040-320001TUR | 0
[9 empty] | 929 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 929 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 929-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.929 |  |  | PF.929 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00041-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00041-LEVEL 24-DE-Level 24-Load Centers 125A | False | Level 24-Load Centers 125A | 0 | FAB-00041-320001TUR | 0
[9 empty] | 930 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 930 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 930-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.930 |  |  | PF.930 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00042-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00042-LEVEL 24-DE-Level 24-Load Centers 150A | False | Level 24-Load Centers 150A | 0 | FAB-00042-320001TUR | 0
[9 empty] | 931 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 931 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 931-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.931 |  |  | PF.931 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00043-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00043-LEVEL 25-DE-Level 25-Load Centers 125A | False | Level 25-Load Centers 125A | 0 | FAB-00043-320001TUR | 0
[9 empty] | 932 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 932 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 932-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.932 |  |  | PF.932 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00044-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00044-LEVEL 25-DE-Level 25-Load Centers 150A | False | Level 25-Load Centers 150A | 0 | FAB-00044-320001TUR | 0
[9 empty] | 933 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 933 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 933-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.933 |  |  | PF.933 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00045-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00045-LEVEL 26-DE-Level 26-Load Centers 125A | False | Level 26-Load Centers 125A | 0 | FAB-00045-320001TUR | 0
[9 empty] | 934 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 934 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 934-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.934 |  |  | PF.934 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00046-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00046-LEVEL 26-DE-Level 26-Load Centers 150A | False | Level 26-Load Centers 150A | 0 | FAB-00046-320001TUR | 0
[9 empty] | 935 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 935 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 935-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.935 |  |  | PF.935 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00047-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00047-LEVEL 27-DE-Level 27-Load Centers 125A | False | Level 27-Load Centers 125A | 0 | FAB-00047-320001TUR | 0
[9 empty] | 936 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 936 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 936-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.936 |  |  | PF.936 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00048-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00048-LEVEL 27-DE-Level 27-Load Centers 150A | False | Level 27-Load Centers 150A | 0 | FAB-00048-320001TUR | 0
[9 empty] | 937 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 937 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 937-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.937 |  |  | PF.937 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00049-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00049-LEVEL 28-DE-Level 28-Load Centers 125A | False | Level 28-Load Centers 125A | 0 | FAB-00049-320001TUR | 0
[9 empty] | 938 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 938 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 938-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.938 |  |  | PF.938 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00050-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00050-LEVEL 28-DE-Level 28-Load Centers 150A | False | Level 28-Load Centers 150A | 0 | FAB-00050-320001TUR | 0
[9 empty] | 939 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 939 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 939-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.939 |  |  | PF.939 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00051-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00051-LEVEL 29-DE-Level 29-Load Centers 125A | False | Level 29-Load Centers 125A | 0 | FAB-00051-320001TUR | 0
[9 empty] | 940 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 940 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 940-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.940 |  |  | PF.940 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00052-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00052-LEVEL 29-DE-Level 29-Load Centers 150A | False | Level 29-Load Centers 150A | 0 | FAB-00052-320001TUR | 0
[9 empty] | 941 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 941 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 941-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.941 |  |  | PF.941 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00053-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00053-LEVEL 30-DE-Level 30-Load Centers 125A | False | Level 30-Load Centers 125A | 0 | FAB-00053-320001TUR | 0
[9 empty] | 942 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 942 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 942-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.942 |  |  | PF.942 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00054-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00054-LEVEL 30-DE-Level 30-Load Centers 150A | False | Level 30-Load Centers 150A | 0 | FAB-00054-320001TUR | 0
[9 empty] | 943 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 943 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 943-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.943 |  |  | PF.943 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00055-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00055-LEVEL 31-DE-Level 31-Load Centers 125A | False | Level 31-Load Centers 125A | 0 | FAB-00055-320001TUR | 0
[9 empty] | 944 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 944 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 944-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.944 |  |  | PF.944 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00056-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00056-LEVEL 31-DE-Level 31-Load Centers 150A | False | Level 31-Load Centers 150A | 0 | FAB-00056-320001TUR | 0
[9 empty] | 945 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 945 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 945-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.945 |  |  | PF.945 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00057-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00057-LEVEL 32-DE-Level 32-Load Centers 125A | False | Level 32-Load Centers 125A | 0 | FAB-00057-320001TUR | 0
[9 empty] | 946 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 946 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 946-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.946 |  |  | PF.946 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00058-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00058-LEVEL 32-DE-Level 32-Load Centers 150A | False | Level 32-Load Centers 150A | 0 | FAB-00058-320001TUR | 0
[9 empty] | 947 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 947 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 947-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.947 |  |  | PF.947 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00059-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00059-LEVEL 33-DE-Level 33-Load Centers 125A | False | Level 33-Load Centers 125A | 0 | FAB-00059-320001TUR | 0
[9 empty] | 948 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 948 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 948-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.948 |  |  | PF.948 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00060-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00060-LEVEL 33-DE-Level 33-Load Centers 150A | False | Level 33-Load Centers 150A | 0 | FAB-00060-320001TUR | 0
[9 empty] | 949 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 949 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 949-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.949 |  |  | PF.949 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00061-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 3/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00061-LEVEL 34-DE-Level 34-Load Centers 125A | False | Level 34-Load Centers 125A | 0 | FAB-00061-320001TUR | 0
[9 empty] | 950 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 950 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 950-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.950 |  |  | PF.950 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00062-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00062-LEVEL 34-DE-Level 34-Load Centers 150A | False | Level 34-Load Centers 150A | 0 | FAB-00062-320001TUR | 0
[9 empty] | 951 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 951 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 951-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.951 |  |  | PF.951 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00063-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.44 | 0 | 320001TUR | 3/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00063-LEVEL 35-DE-Level 35-Load Centers 150A | False | Level 35-Load Centers 150A | 0 | FAB-00063-320001TUR | 0
[9 empty] | 952 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 952 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 952-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.952 |  |  | PF.952 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00064-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.44 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00064-LEVEL 36-DE-Level 36-Load Centers 150A | False | Level 36-Load Centers 150A | 0 | FAB-00064-320001TUR | 0
[9 empty] | 953 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 953 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 953-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.953 |  |  | PF.953 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00065-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.73 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00065-LEVEL B1-IW-LAUNDRY-BATHROOM IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL B1 LAUNDRY-BATHROOM IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00065-320001TUR | 0
[9 empty] | 954 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 954 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 954-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.954 |  |  | PF.954 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00066-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.56 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00066-LEVEL 1-IW-IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00066-320001TUR | 0
[9 empty] | 955 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 955 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 955-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.955 |  |  | PF.955 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00067-320001TUR | MXD_RESI_JAP_ELEC | 0 | 9.11 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00067-LEVEL 2-IW-IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00067-320001TUR | 0
[9 empty] | 956 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 956 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 956-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.956 |  |  | PF.956 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00068-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00068-LEVEL 3-IW-PODIUM IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 3-PODIUM IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00068-320001TUR | 0
[9 empty] | 957 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 957 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 957-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.957 |  |  | PF.957 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00069-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00069-LEVEL 4-IW-PODIUM IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 4-PODIUM IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00069-320001TUR | 0
[9 empty] | 958 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 958 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 958-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.958 |  |  | PF.958 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00070-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00070-LEVEL 5-IW-PODIUM IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 5-PODIUM IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00070-320001TUR | 0
[9 empty] | 959 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 959 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 959-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.959 |  |  | PF.959 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00071-320001TUR | MXD_RESI_JAP_ELEC | 0 | 17.86 | 0 | 320001TUR | 10/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00071-LEVEL 6-IW-IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 6 LEVEL 6 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00071-320001TUR | 0
[9 empty] | 960 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 960 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 960-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.960 |  |  | PF.960 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00072-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00072-LEVEL 7-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 7-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00072-320001TUR | 0
[9 empty] | 961 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 961 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 961-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.961 |  |  | PF.961 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00073-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00073-LEVEL 8-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 8-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00073-320001TUR | 0
[9 empty] | 962 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 962 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 962-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.962 |  |  | PF.962 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00074-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00074-LEVEL 9-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 9-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00074-320001TUR | 0
[9 empty] | 963 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 963 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 963-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.963 |  |  | PF.963 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00075-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00075-LEVEL 10-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 10-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00075-320001TUR | 0
[9 empty] | 964 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 964 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 964-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.964 |  |  | PF.964 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00076-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00076-LEVEL 11-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 11-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00076-320001TUR | 0
[9 empty] | 965 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 965 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 965-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.965 |  |  | PF.965 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00077-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00077-LEVEL 12-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 12-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00077-320001TUR | 0
[9 empty] | 966 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 966 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 966-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.966 |  |  | PF.966 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00078-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00078-LEVEL 13-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 13-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00078-320001TUR | 0
[9 empty] | 967 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 967 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 967-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.967 |  |  | PF.967 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00079-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00079-LEVEL 14-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 14-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00079-320001TUR | 0
[9 empty] | 968 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 968 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 968-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.968 |  |  | PF.968 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00080-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00080-LEVEL 15-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 15-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00080-320001TUR | 0
[9 empty] | 969 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 969 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 969-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.969 |  |  | PF.969 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00081-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00081-LEVEL 16-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 16-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00081-320001TUR | 0
[9 empty] | 970 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 970 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 970-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.970 |  |  | PF.970 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00082-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00082-LEVEL 17-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 17-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00082-320001TUR | 0
[9 empty] | 971 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 971 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 971-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.971 |  |  | PF.971 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00083-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00083-LEVEL 18-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 18-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00083-320001TUR | 0
[9 empty] | 972 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 972 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 972-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.972 |  |  | PF.972 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00084-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00084-LEVEL 19-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 19-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00084-320001TUR | 0
[9 empty] | 973 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 973 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 973-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.973 |  |  | PF.973 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00085-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00085-LEVEL 20-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 20-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00085-320001TUR | 0
[9 empty] | 974 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 974 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 974-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.974 |  |  | PF.974 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00086-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00086-LEVEL 21-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 21-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00086-320001TUR | 0
[9 empty] | 975 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 975 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 975-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.975 |  |  | PF.975 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00087-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00087-LEVEL 22-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 22-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00087-320001TUR | 0
[9 empty] | 976 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 976 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 976-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.976 |  |  | PF.976 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00088-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00088-LEVEL 23-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 23-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00088-320001TUR | 0
[9 empty] | 977 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 977 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 977-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.977 |  |  | PF.977 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00089-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00089-LEVEL 24-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 24-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00089-320001TUR | 0
[9 empty] | 978 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 978 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 978-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.978 |  |  | PF.978 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00090-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00090-LEVEL 25-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 25-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00090-320001TUR | 0
[9 empty] | 979 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 979 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 979-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.979 |  |  | PF.979 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00091-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00091-LEVEL 26-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 26-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00091-320001TUR | 0
[9 empty] | 980 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 980 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 980-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.980 |  |  | PF.980 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00092-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00092-LEVEL 27-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 27-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00092-320001TUR | 0
[9 empty] | 981 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 981 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 981-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.981 |  |  | PF.981 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00093-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00093-LEVEL 28-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 28-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00093-320001TUR | 0
[9 empty] | 982 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 982 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 982-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.982 |  |  | PF.982 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00094-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00094-LEVEL 29-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 29-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00094-320001TUR | 0
[9 empty] | 983 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 983 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 983-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.983 |  |  | PF.983 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00095-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00095-LEVEL 30-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 30-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00095-320001TUR | 0
[9 empty] | 984 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 984 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 984-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.984 |  |  | PF.984 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00096-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00096-LEVEL 31-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 31-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00096-320001TUR | 0
[9 empty] | 985 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 985 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 985-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.985 |  |  | PF.985 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00097-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00097-LEVEL 32-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 32-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00097-320001TUR | 0
[9 empty] | 986 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 986 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 986-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.986 |  |  | PF.986 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00098-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00098-LEVEL 33-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 33-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00098-320001TUR | 0
[9 empty] | 987 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 987 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 987-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.987 |  |  | PF.987 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00099-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 3/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00099-LEVEL 34-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 34-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00099-320001TUR | 0
[9 empty] | 988 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 988 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 988-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.988 |  |  | PF.988 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00100-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 3/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00100-LEVEL 35-IW-TIER 3 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 35-TIER 3 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00100-320001TUR | 0
[9 empty] | 989 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 989 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 989-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.989 |  |  | PF.989 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00101-320001TUR | MXD_RESI_JAP_ELEC | 0 | 18.22 | 0 | 320001TUR | 3/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00101-LEVEL 36-IW-TIER 3 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 36-TIER 3 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00101-320001TUR | 0
[9 empty] | 990 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 990 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 990-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.990 |  |  | PF.990 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00102-320001TUR | MXD_RESI_JAP_ELEC | 0 | 18.22 | 0 | 320001TUR | 3/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00102-LEVEL 37-IW-AMENITY-MEP PH IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 37-AMENITY-MEP PH IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00102-320001TUR | 0
[9 empty] | 991 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 991 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 991-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.991 |  |  | PF.991 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00103-320001TUR | MXD_RESI_JAP_ELEC | 0 | 9.11 | 0 | 320001TUR | 7/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00103-LEVEL 38-IW-IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 38 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00103-320001TUR | 0
[9 empty] | 992 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 992 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 992-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.992 |  |  | PF.992 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00104-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00104-LEVEL B1-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL B1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00104-320001TUR | 0
[9 empty] | 993 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 993 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 993-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.993 |  |  | PF.993 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00105-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00105-LEVEL 1-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00105-320001TUR | 0
[9 empty] | 994 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 994 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 994-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.994 |  |  | PF.994 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00106-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00106-LEVEL 2-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00106-320001TUR | 0
[9 empty] | 995 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 995 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 995-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.995 |  |  | PF.995 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00107-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00107-LEVEL 3-CND-PODIUM PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 3-PODIUM PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00107-320001TUR | 0
[9 empty] | 996 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 996 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 996-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.996 |  |  | PF.996 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00108-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00108-LEVEL 4-CND-PODIUM PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 4-PODIUM PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00108-320001TUR | 0
[9 empty] | 997 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 997 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 997-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.997 |  |  | PF.997 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00109-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00109-LEVEL 5-CND-PODIUM PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 5-PODIUM PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00109-320001TUR | 0
[9 empty] | 998 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 998 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 998-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.998 |  |  | PF.998 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00110-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00110-LEVEL 6-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 6 LEVEL 6 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00110-320001TUR | 0
[9 empty] | 999 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 999 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 999-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.999 |  |  | PF.999 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00111-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00111-LEVEL 7-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 7-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00111-320001TUR | 0
[9 empty] | 1000 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1000 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1000-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1000 |  |  | PF.1000 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00112-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00112-LEVEL 8-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 8-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00112-320001TUR | 0
[9 empty] | 1001 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1001 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1001-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1001 |  |  | PF.1001 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00113-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00113-LEVEL 9-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 9-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00113-320001TUR | 0
[9 empty] | 1002 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1002 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1002-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1002 |  |  | PF.1002 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00114-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00114-LEVEL 10-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 10-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00114-320001TUR | 0
[9 empty] | 1003 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1003 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1003-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1003 |  |  | PF.1003 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00115-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00115-LEVEL 11-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 11-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00115-320001TUR | 0
[9 empty] | 1004 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1004 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1004-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1004 |  |  | PF.1004 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00116-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00116-LEVEL 12-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 12-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00116-320001TUR | 0
[9 empty] | 1005 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 1005 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 1005-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.1005 |  |  | PF.1005 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:14:33 | 4 | FAB-00117-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0.0 % |  | FAB-00117-LEVEL 13-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 13-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00117-320001TUR | 0
[8 empty] | 9000030 | 100 | 320001TUR | Stephen Yee | LEVEL 35 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 35 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-24 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-03-03 | 2026-03-04 | 2026-03-06 |  | 2026-03-10 | DATES MISALIGNED | 2026-06-09 | [5 empty] | Kerri Pandolfi | 100 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 100-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1618 | LEVEL 35 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.100 | 9000030 |  | PF.100 | PF.100 | 0% |  |  | 2026-02-17 |  | 2025-10-05 | 108
[8 empty] | 9000030 | 101 | 320001TUR | Stephen Yee | LEVEL 36 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 36 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 100 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-26 | [7 empty] | 18.22 | 1.1388 | 2 | 2 | 2026-03-05 | 2026-03-08 | 2026-03-10 |  | 2026-03-10 | DATES MISALIGNED | 2026-06-16 | [5 empty] | Kerri Pandolfi | 101 | 26 |  | 0 | 0 | 0.1822 | 18.22 | 1.15 | 115 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 101-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1651 | LEVEL 36 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.101 | 9000030 |  | PF.101 | PF.101 | 0% |  |  | 2026-02-19 |  | 2025-10-05 | 110
[8 empty] | 9000030 | 102 | 320001TUR | Stephen Yee | LEVEL 37 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 37 - AMENITY/MEP PH IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 100 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-23 | [7 empty] | 18.22 | 1.1388 | 2 | 2 | 2026-03-02 | 2026-03-04 | 2026-03-06 |  | 2026-03-06 | DATES MISALIGNED | 2026-06-16 | [5 empty] | Kerri Pandolfi | 102 | 26 |  | 0 | 0 | 0.1822 | 18.22 | 1.15 | 115 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 102-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1624 | LEVEL 36 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.102 | 9000030 |  | PF.102 | PF.102 | 0% |  |  | 2026-02-16 |  | 2025-10-05 | 107
[8 empty] | 9000030 | 103 | 320001TUR | Stephen Yee | LEVEL 38 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 38 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 50 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-06-19 | [7 empty] | 9.11 | 0.56938 | 1 | 2 | 2026-06-26 | 2026-06-29 | 2026-07-01 |  | 2026-07-01 |  | 2026-07-01 | [5 empty] | Kerri Pandolfi | 103 | 26 |  | 0 | 0 | 0.1822 | 9.11 | 1.15 | 57.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 103-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1708 | LEVEL 38 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.103 | 9000030 |  | PF.103 | PF.103 | 0% |  |  | 2026-06-12 |  | 2025-10-05 | 191
[8 empty] | 9000103 | 104 | 320001TUR | Stephen Yee | LEVEL B1 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL B1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 2 | Gray | 121 BROADWAY MXD TOWER | Eddie Velez | 2025-09-19 | 2025-09-19 | JOHN CORSO | TRUE | true | TRUE | True | APPROVED | 0.5 | 0.03125 | 1 | 2 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-14 |  |  |  |  | Image 2025-09-30 10-33-54.jpeg |  | 3 | Kerri Pandolfi | 104 | 25 |  | 0.25 | 0.5 | 0.25 | 0.5 | 1.74 | 3.48 | 0.25 | 1.49 | 0.25 | 0 | 25 | 104-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1977 |  | PF.104 | 9000103 |  | PF.104 | PF.104 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000103 | 105 | 320001TUR | Stephen Yee | LEVEL 1 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 17 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-15 | 2025-08-21 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4.25 | 0.26562 | 1 | 2 | 2025-08-22 | 2025-08-23 | 2025-08-25 |  | 2025-10-14 | DATES MISALIGNED | 2025-08-25 |  |  | Image 2025-09-30 10-34-16.jpeg |  | 3 | Kerri Pandolfi | 105 | 25 |  | 0.14706 | 2.5 | 0.25 | 4.25 | 1.74 | 29.58 | 0.25 | 1.49 | 0.14706 | -0.10294 | 25 | 105-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 113 | INSTALL - LEVEL 1 - TELCOM BNDS | PF.105 | 9000103 |  | PF.105 | PF.105 | 99% | TRUE |  | 2025-08-08 |  | 2025-10-05 | -31 | TRUE
[8 empty] | 9000103 | 106 | 320001TUR | Stephen Yee | LEVEL 2 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 25 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 6.25 | 0.39062 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | DATES MISALIGNED | 2025-09-08 | [5 empty] | Kerri Pandolfi | 106 | 25 |  | 0 | 0 | 0.25 | 6.25 | 1.74 | 43.5 | 0.25 | 1.49 | 0 | -0.25 | 25 | 106-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 152 | LEVEL 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.106 | 9000103 |  | PF.106 | PF.106 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000103 | 107 | 320001TUR | Stephen Yee | LEVEL 3 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 3 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-03 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-10-10 | 2025-10-13 | 2025-10-15 |  | 2025-10-15 |  | 2025-10-24 | TRUE |  | X |  |  | Kerri Pandolfi | 107 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 107-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 333 | INSTALL - LEVEL 3 - TELCOM BNDS | PF.107 | 9000103 |  | PF.107 | DELETED | 100% |  |  | 2025-09-26 |  | 2025-10-05 | 6
[8 empty] | 9000103 | 108 | 320001TUR | Stephen Yee | LEVEL 4 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 4 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-10 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-10-17 | 2025-10-20 | 2025-10-22 |  | 2025-10-24 |  | 2025-10-31 | TRUE |  | X |  |  | Kerri Pandolfi | 108 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 108-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 374 | INSTALL - LEVEL 4 - TELCOM BNDS | PF.108 | 9000103 |  | PF.108 | DELETED | 100% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[8 empty] | 9000103 | 109 | 320001TUR | Stephen Yee | LEVEL 5 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 5 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-10-31 | 2025-11-02 | 2025-11-04 |  | 2025-11-04 |  | 2025-11-07 | TRUE |  | X |  |  | Kerri Pandolfi | 109 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 109-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 403 | INSTALL - LEVEL 5 - TELCOM BNDS | PF.109 | 9000103 |  | PF.109 | DELETED | 100% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[8 empty] | 9000103 | 110 | 320001TUR | Stephen Yee | LEVEL 6 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 6 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 13 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3.25 | 0.20312 | 1 | 2 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-28 | DATES MISALIGNED | 2025-09-16 |  |  |  |  | 2 | Kerri Pandolfi | 110 | 25 |  | 0.076923 | 1 | 0.25 | 3.25 | 1.74 | 22.62 | 0.25 | 1.49 | 0.076923 | -0.17308 | 25 | 110-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 198 | INSTALL - LEVEL 6 - TELCOM BNDS | PF.110 | 9000103 |  | PF.110 | PF.110 | 30.77% |  |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000103 | 111 | 320001TUR | Stephen Yee | LEVEL 7 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 7 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 | DATES MISALIGNED | 2025-11-21 | [5 empty] | Kerri Pandolfi | 111 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 111-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 483 | INSTALL - LEVEL 7 - TELCOM BNDS | PF.111 | 9000103 |  | PF.111 | PF.111 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[8 empty] | 9000103 | 112 | 320001TUR | Stephen Yee | LEVEL 8 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 8 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-07 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-11-14 | 2025-11-17 | 2025-11-19 |  | 2025-11-19 | DATES MISALIGNED | 2025-12-01 | [5 empty] | Kerri Pandolfi | 112 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 112-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 516 | INSTALL - LEVEL 8 - TELCOM BNDS | PF.112 | 9000103 |  | PF.112 | PF.112 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[8 empty] | 9000103 | 113 | 320001TUR | Stephen Yee | LEVEL 9 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 9 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-14 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-11-21 | 2025-11-23 | 2025-11-25 |  | 2025-11-25 | DATES MISALIGNED | 2025-12-08 | [5 empty] | Kerri Pandolfi | 113 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 113-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 558 | INSTALL - LEVEL 9 - TELCOM BNDS | PF.113 | 9000103 |  | PF.113 | PF.113 | 0% |  |  | 2025-11-07 |  | 2025-10-05 | 36
[8 empty] | 9000103 | 114 | 320001TUR | Stephen Yee | LEVEL 10 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 10 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-21 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-11-28 | 2025-12-01 | 2025-12-03 |  | 2025-12-03 | DATES MISALIGNED | 2025-12-12 | [5 empty] | Kerri Pandolfi | 114 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 114-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 589 | INSTALL - LEVEL 10 - TELCOM BNDS | PF.114 | 9000103 |  | PF.114 | PF.114 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[8 empty] | 9000103 | 115 | 320001TUR | Stephen Yee | LEVEL 11 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 11 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-28 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-12-05 | 2025-12-08 | 2025-12-10 |  | 2025-12-10 | DATES MISALIGNED | 2025-12-19 | [5 empty] | Kerri Pandolfi | 115 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 115-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 630 | INSTALL - LEVEL 11 - TELCOM BNDS | PF.115 | 9000103 |  | PF.115 | PF.115 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[8 empty] | 9000103 | 116 | 320001TUR | Stephen Yee | LEVEL 12 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 12 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-12-12 | 2025-12-15 | 2025-12-17 |  | 2025-12-17 | DATES MISALIGNED | 2025-12-29 | [5 empty] | Kerri Pandolfi | 116 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 116-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 674 | INSTALL - LEVEL 12 - TELCOM BNDS | PF.116 | 9000103 |  | PF.116 | PF.116 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000103 | 117 | 320001TUR | Stephen Yee | LEVEL 13 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 13 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-12 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-12-19 | 2025-12-21 | 2025-12-23 |  | 2025-12-23 | DATES MISALIGNED | 2026-01-06 | [5 empty] | Kerri Pandolfi | 117 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 117-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 715 | INSTALL - LEVEL 13 - TELCOM BNDS | PF.117 | 9000103 |  | PF.117 | PF.117 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[8 empty] | 9000103 | 118 | 320001TUR | Stephen Yee | LEVEL 14 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 14 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-19 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-12-26 | 2025-12-28 | 2025-12-30 |  | 2025-12-30 | DATES MISALIGNED | 2026-01-12 | [5 empty] | Kerri Pandolfi | 118 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 118-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 763 | INSTALL - LEVEL 14 - TELCOM BNDS | PF.118 | 9000103 |  | PF.118 | PF.118 | 0% |  |  | 2025-12-12 |  | 2025-10-05 | 61
[8 empty] | 9000103 | 119 | 320001TUR | Stephen Yee | LEVEL 15 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 15 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-26 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-02 | 2026-01-05 | 2026-01-07 |  | 2026-01-07 | DATES MISALIGNED | 2026-01-16 | [5 empty] | Kerri Pandolfi | 119 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 119-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 788 | INSTALL - LEVEL 15 - TELCOM BNDS | PF.119 | 9000103 |  | PF.119 | PF.119 | 0% |  |  | 2025-12-19 |  | 2025-10-05 | 66
[8 empty] | 9000103 | 120 | 320001TUR | Stephen Yee | LEVEL 16 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 16 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-09 | 2026-01-12 | 2026-01-14 |  | 2026-01-14 | DATES MISALIGNED | 2026-01-26 | [5 empty] | Kerri Pandolfi | 120 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 120-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 839 | INSTALL - LEVEL 16 - TELCOM BNDS | PF.120 | 9000103 |  | PF.120 | PF.120 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[8 empty] | 9000103 | 121 | 320001TUR | Stephen Yee | LEVEL 17 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 17 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-09 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-16 | 2026-01-19 | 2026-01-21 |  | 2026-01-21 | DATES MISALIGNED | 2026-02-02 | [5 empty] | Kerri Pandolfi | 121 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 121-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 887 | INSTALL - LEVEL 17 - TELCOM BNDS | PF.121 | 9000103 |  | PF.121 | PF.121 | 0% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[8 empty] | 9000103 | 122 | 320001TUR | Stephen Yee | LEVEL 18 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 18 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-16 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-23 | 2026-01-26 | 2026-01-28 |  | 2026-01-28 | DATES MISALIGNED | 2026-02-06 | [5 empty] | Kerri Pandolfi | 122 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 122-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 926 | INSTALL - LEVEL 18 - TELCOM BNDS | PF.122 | 9000103 |  | PF.122 | PF.122 | 0% |  |  | 2026-01-09 |  | 2025-10-05 | 81
[8 empty] | 9000103 | 123 | 320001TUR | Stephen Yee | LEVEL 19 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 19 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-23 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-30 | 2026-02-02 | 2026-02-04 |  | 2026-02-04 | DATES MISALIGNED | 2026-02-13 | [5 empty] | Kerri Pandolfi | 123 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 123-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 964 | INSTALL - LEVEL 19 - TELCOM BNDS | PF.123 | 9000103 |  | PF.123 | PF.123 | 0% |  |  | 2026-01-16 |  | 2025-10-05 | 86
[8 empty] | 9000103 | 124 | 320001TUR | Stephen Yee | LEVEL 20 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 20 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-30 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-02-06 | 2026-02-09 | 2026-02-11 |  | 2026-02-11 | DATES MISALIGNED | 2026-02-23 | [5 empty] | Kerri Pandolfi | 124 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 124-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1009 | INSTALL - LEVEL 20 - TELCOM BNDS | PF.124 | 9000103 |  | PF.124 | PF.124 | 0% |  |  | 2026-01-23 |  | 2025-10-05 | 91
[8 empty] | 9000103 | 125 | 320001TUR | Stephen Yee | LEVEL 21 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 21 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-06 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-02-13 | 2026-02-16 | 2026-02-18 |  | 2026-02-18 | DATES MISALIGNED | 2026-03-02 | [5 empty] | Kerri Pandolfi | 125 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 125-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1053 | INSTALL - LEVEL 21 - TELCOM BNDS | PF.125 | 9000103 |  | PF.125 | PF.125 | 0% |  |  | 2026-01-30 |  | 2025-10-05 | 96
[8 empty] | 9000103 | 126 | 320001TUR | Stephen Yee | LEVEL 22 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 22 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-13 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-02-20 | 2026-02-23 | 2026-02-25 |  | 2026-02-25 | DATES MISALIGNED | 2026-03-06 | [5 empty] | Kerri Pandolfi | 126 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 126-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1093 | INSTALL - LEVEL 22 - TELCOM BNDS | PF.126 | 9000103 |  | PF.126 | PF.126 | 0% |  |  | 2026-02-06 |  | 2025-10-05 | 101
[8 empty] | 9000103 | 127 | 320001TUR | Stephen Yee | LEVEL 23 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 23 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-20 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-02-27 | 2026-03-02 | 2026-03-04 |  | 2026-03-04 | DATES MISALIGNED | 2026-03-13 | [5 empty] | Kerri Pandolfi | 127 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 127-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1139 | INSTALL - LEVEL 23 - TELCOM BNDS | PF.127 | 9000103 |  | PF.127 | PF.127 | 0% |  |  | 2026-02-13 |  | 2025-10-05 | 106
[8 empty] | 9000103 | 128 | 320001TUR | Stephen Yee | LEVEL 24 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 24 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-27 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-03-06 | 2026-03-09 | 2026-03-11 |  | 2026-03-11 | DATES MISALIGNED | 2026-03-20 | [5 empty] | Kerri Pandolfi | 128 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 128-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1181 | INSTALL - LEVEL 24 - TELCOM BNDS | PF.128 | 9000103 |  | PF.128 | PF.128 | 0% |  |  | 2026-02-20 |  | 2025-10-05 | 111
[8 empty] | 9000103 | 129 | 320001TUR | Stephen Yee | LEVEL 25 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 25 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-06 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-03-13 | 2026-03-16 | 2026-03-18 |  | 2026-03-18 | DATES MISALIGNED | 2026-03-27 | [5 empty] | Kerri Pandolfi | 129 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 129-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1226 | INSTALL - LEVEL 25 - TELCOM BNDS | PF.129 | 9000103 |  | PF.129 | PF.129 | 0% |  |  | 2026-02-27 |  | 2025-10-05 | 116
[8 empty] | 9000103 | 130 | 320001TUR | Stephen Yee | LEVEL 26 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 26 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-16 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-03-23 | 2026-03-24 | 2026-03-26 |  | 2026-03-26 | DATES MISALIGNED | 2026-04-06 | [5 empty] | Kerri Pandolfi | 130 | 26 |  | 0.4 | 2 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0.25 | 0 | 26 | 130-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1269 | INSTALL - LEVEL 26 - TELCOM BNDS | PF.130 | 9000103 |  | PF.130 | PF.130 | 75% |  |  | 2026-03-09 |  | 2025-10-05 | 122
[8 empty] | 9000103 | 131 | 320001TUR | Stephen Yee | LEVEL 27 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 27 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-20 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-03-27 | 2026-03-30 | 2026-04-01 |  | 2026-04-01 | DATES MISALIGNED | 2026-04-10 | [5 empty] | Kerri Pandolfi | 131 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 131-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1307 | INSTALL - LEVEL 27 - TELCOM BNDS | PF.131 | 9000103 |  | PF.131 | PF.131 | 0% |  |  | 2026-03-13 |  | 2025-10-05 | 126
[8 empty] | 9000103 | 132 | 320001TUR | Stephen Yee | LEVEL 28 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 28 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-27 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-04-03 | 2026-04-06 | 2026-04-08 |  | 2026-04-08 | DATES MISALIGNED | 2026-04-17 | [5 empty] | Kerri Pandolfi | 132 | 26 |  | 0.2 | 1 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0.2 | -0.05 | 26 | 132-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1350 | INSTALL - LEVEL 28 - TELCOM BNDS | PF.132 | 9000103 |  | PF.132 | PF.132 | 75% |  |  | 2026-03-20 |  | 2025-10-05 | 131
[8 empty] | 9000103 | 133 | 320001TUR | Stephen Yee | LEVEL 29 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 29 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-03 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-04-10 | 2026-04-13 | 2026-04-15 |  | 2026-04-15 | DATES MISALIGNED | 2026-04-27 | [5 empty] | Kerri Pandolfi | 133 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 133-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1391 | INSTALL - LEVEL 29 - TELCOM BNDS | PF.133 | 9000103 |  | PF.133 | PF.133 | 0% |  |  | 2026-03-27 |  | 2025-10-05 | 136
[8 empty] | 9000103 | 134 | 320001TUR | Stephen Yee | LEVEL 30 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 30 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-13 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-04-20 | 2026-04-21 | 2026-04-23 |  | 2026-04-23 | DATES MISALIGNED | 2026-05-04 | [5 empty] | Kerri Pandolfi | 134 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 134-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1431 | INSTALL - LEVEL 30 - TELCOM BNDS | PF.134 | 9000103 |  | PF.134 | PF.134 | 0% |  |  | 2026-04-06 |  | 2025-10-05 | 142
[8 empty] | 9000103 | 135 | 320001TUR | Stephen Yee | LEVEL 31 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 31 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-20 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-04-27 | 2026-04-28 | 2026-04-30 |  | 2026-04-30 | DATES MISALIGNED | 2026-05-11 | [5 empty] | Kerri Pandolfi | 135 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 135-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1470 | INSTALL - LEVEL 31 - TELCOM BNDS | PF.135 | 9000103 |  | PF.135 | PF.135 | 0% |  |  | 2026-04-13 |  | 2025-10-05 | 147
[8 empty] | 9000103 | 136 | 320001TUR | Stephen Yee | LEVEL 32 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 32 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-27 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-05-04 | 2026-05-05 | 2026-05-07 |  | 2026-05-07 | DATES MISALIGNED | 2026-05-18 | [5 empty] | Kerri Pandolfi | 136 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 136-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1512 | INSTALL - LEVEL 32 - TELCOM BNDS | PF.136 | 9000103 |  | PF.136 | PF.136 | 0% |  |  | 2026-04-20 |  | 2025-10-05 | 152
[8 empty] | 9000103 | 137 | 320001TUR | Stephen Yee | LEVEL 33 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 33 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-04 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-05-11 | 2026-05-12 | 2026-05-14 |  | 2026-05-14 | DATES MISALIGNED | 2026-05-26 | [5 empty] | Kerri Pandolfi | 137 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 137-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1550 | INSTALL - LEVEL 33 - TELCOM BNDS | PF.137 | 9000103 |  | PF.137 | PF.137 | 0% |  |  | 2026-04-27 |  | 2025-10-05 | 157
[8 empty] | 9000103 | 138 | 320001TUR | Stephen Yee | LEVEL 34 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 34 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-11 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-05-18 | 2026-05-19 | 2026-05-21 |  | 2026-05-21 | DATES MISALIGNED | 2026-06-02 | [5 empty] | Kerri Pandolfi | 138 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 138-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1582 | INSTALL - LEVEL 34 - TELCOM BNDS | PF.138 | 9000103 |  | PF.138 | PF.138 | 0% |  |  | 2026-05-04 |  | 2025-10-05 | 162
[8 empty] | 9000103 | 139 | 320001TUR | Stephen Yee | LEVEL 35 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 35 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-19 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-05-26 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | DATES MISALIGNED | 2026-06-09 | [5 empty] | Kerri Pandolfi | 139 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 139-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1620 | INSTALL - LEVEL 35 - TELCOM BNDS | PF.139 | 9000103 |  | PF.139 | PF.139 | 0% |  |  | 2026-05-12 |  | 2025-10-05 | 168
[8 empty] | 9000103 | 140 | 320001TUR | Stephen Yee | LEVEL 36 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 36 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-26 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-06-02 | 2026-06-03 | 2026-06-05 |  | 2026-06-05 | DATES MISALIGNED | 2026-06-16 | [5 empty] | Kerri Pandolfi | 140 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 140-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1653 | INSTALL - LEVEL 36 - TELCOM BNDS | PF.140 | 9000103 |  | PF.140 | PF.140 | 0% |  |  | 2026-05-19 |  | 2025-10-05 | 173
[8 empty] | 9000103 | 141 | 320001TUR | Stephen Yee | LEVEL 37 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 37 - AMENITY/MEP PH PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 50 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-06-19 | [7 empty] | 12.5 | 0.78125 | 1 | 2 | 2026-06-26 | 2026-06-28 | 2026-06-30 |  | 2026-06-30 |  | 2026-06-30 | [5 empty] | Kerri Pandolfi | 141 | 26 |  | 0 | 0 | 0.25 | 12.5 | 1.74 | 87 | 0.25 | 1.49 | 0 | -0.25 | 26 | 141-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1688 | INSTALL - LEVEL 37 - TELCOM BNDS | PF.141 | 9000103 |  | PF.141 | PF.141 | 0% |  |  | 2026-06-12 |  | 2025-10-05 | 191
[8 empty] | 9000103 | 142 | 320001TUR | Stephen Yee | LEVEL 38 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 38 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 25 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-06-26 | [7 empty] | 6.25 | 0.39062 | 1 | 2 | 2026-07-03 | 2026-07-04 | 2026-07-06 |  | 2026-07-06 |  | 2026-07-06 | [5 empty] | Kerri Pandolfi | 142 | 26 |  | 0 | 0 | 0.25 | 6.25 | 1.74 | 43.5 | 0.25 | 1.49 | 0 | -0.25 | 26 | 142-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1714 | INSTALL - LEVEL 38 - TELCOM BNDS | PF.142 | 9000103 |  | PF.142 | PF.142 | 0% |  |  | 2026-06-19 |  | 2025-10-05 | 196
[8 empty] | 9000020 | 143 | 320001TUR | Stephen Yee | LEVEL B1 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL B1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID OPERATION | [7 empty] | 3.9 | 0.24375 | 1 | 2 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 143 | #INVALID VALUE |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | LE | 143-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | #NO MATCH | #NO MATCH | PF.143 | 9000020 |  | PF.143 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[8 empty] | 9000020 | 144 | 320001TUR | Stephen Yee | LEVEL 1 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-21 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-28 | 2026-08-30 | 2026-09-01 |  | 2026-09-01 |  | 2026-09-01 | [5 empty] | Kerri Pandolfi | 144 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 144-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1851 | INSTALL - LEVEL 1 - LIGHTING CNTRL | PF.144 | 9000020 |  | PF.144 | PF.144 | 0% |  |  | 2026-08-14 |  | 2025-10-05 | 236
[8 empty] | 9000020 | 145 | 320001TUR | Stephen Yee | LEVEL 2 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 20 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2025-11-07 | [7 empty] | 15.6 | 0.975 | 1 | 2 | 2025-11-14 | 2025-11-15 | 2025-11-17 |  | 2025-11-17 |  | 2025-11-17 | [5 empty] | Kerri Pandolfi | 145 | 25 |  | 0 | 0 | 0.78 | 15.6 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 25 | 145-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 428 | INSTALL - LEVEL 2 - LIGHTING CNTRL | PF.145 | 9000020 |  | PF.145 | PF.145 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[8 empty] | 9000020 | 146 | 320001TUR | Stephen Yee | LEVEL 3 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 3 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2025-11-07 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2025-11-14 | 2025-11-15 | 2025-11-17 |  | 2026-03-11 |  | 2026-03-12 | [5 empty] | Kerri Pandolfi | 146 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 146-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1104 | INSTALL - LEVEL 3 - LIGHTING CNTRL | PF.146 | 9000020 |  | PF.146 | PF.146 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[8 empty] | 9000020 | 147 | 320001TUR | Stephen Yee | LEVEL 4 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 4 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-02 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-03-09 | 2026-03-10 | 2026-03-12 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | Kerri Pandolfi | 147 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 147-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1145 | INSTALL - LEVEL 4 - LIGHTING CNTRL | PF.147 | 9000020 |  | PF.147 | PF.147 | 0% |  |  | 2026-02-23 |  | 2025-10-05 | 112
[8 empty] | 9000020 | 148 | 320001TUR | Stephen Yee | LEVEL 5 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 5 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-09 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-03-16 | 2026-03-17 | 2026-03-19 |  | 2026-03-25 |  | 2026-03-25 | [5 empty] | Kerri Pandolfi | 148 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 148-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1186 | INSTALL - LEVEL 5 - LIGHTING CNTRL | PF.148 | 9000020 |  | PF.148 | PF.148 | 0% |  |  | 2026-03-02 |  | 2025-10-05 | 117
[8 empty] | 9000020 | 149 | 320001TUR | Stephen Yee | LEVEL 6 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 6 LEVEL 6 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 20 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-13 | [7 empty] | 15.6 | 0.975 | 1 | 2 | 2026-03-20 | 2026-03-23 | 2026-03-25 |  | 2026-04-01 |  | 2026-04-01 | [5 empty] | Kerri Pandolfi | 149 | 26 |  | 0 | 0 | 0.78 | 15.6 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 149-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1225 | INSTALL - LEVEL 6 - LIGHTING CNTRL | PF.149 | 9000020 |  | PF.149 | PF.149 | 0% |  |  | 2026-03-06 |  | 2025-10-05 | 121
[8 empty] | 9000020 | 150 | 320001TUR | Stephen Yee | LEVEL 7 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 7 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-20 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-03-27 | 2026-03-30 | 2026-04-01 |  | 2026-04-01 |  | 2026-04-01 | [5 empty] | Kerri Pandolfi | 150 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 150-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1231 | INSTALL - LEVEL 7 - LIGHTING CNTRL | PF.150 | 9000020 |  | PF.150 | PF.150 | 0% |  |  | 2026-03-13 |  | 2025-10-05 | 126
[8 empty] | 9000020 | 151 | 320001TUR | Stephen Yee | LEVEL 8 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 8 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-20 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-03-27 | 2026-03-30 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-08 | [5 empty] | Kerri Pandolfi | 151 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 151-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1268 | INSTALL - LEVEL 8 - LIGHTING CNTRL | PF.151 | 9000020 |  | PF.151 | PF.151 | 0% |  |  | 2026-03-13 |  | 2025-10-05 | 126
[8 empty] | 9000020 | 152 | 320001TUR | Stephen Yee | LEVEL 9 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 9 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-27 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-04-03 | 2026-04-06 | 2026-04-08 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | Kerri Pandolfi | 152 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 152-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1316 | INSTALL - LEVEL 9 - LIGHTING CNTRL | PF.152 | 9000020 |  | PF.152 | PF.152 | 0% |  |  | 2026-03-20 |  | 2025-10-05 | 131
[8 empty] | 9000020 | 153 | 320001TUR | Stephen Yee | LEVEL 10 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 10 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-04-03 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-04-10 | 2026-04-13 | 2026-04-15 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | Kerri Pandolfi | 153 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 153-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1356 | INSTALL - LEVEL 10 - LIGHTING CNTRL | PF.153 | 9000020 |  | PF.153 | PF.153 | 0% |  |  | 2026-03-27 |  | 2025-10-05 | 136
[8 empty] | 9000020 | 154 | 320001TUR | Stephen Yee | LEVEL 11 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 11 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-04-13 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-04-20 | 2026-04-21 | 2026-04-23 |  | 2026-04-29 |  | 2026-04-30 | [5 empty] | Kerri Pandolfi | 154 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 154-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1395 | INSTALL - LEVEL 11 - LIGHTING CNTRL | PF.154 | 9000020 |  | PF.154 | PF.154 | 0% |  |  | 2026-04-06 |  | 2025-10-05 | 142
[8 empty] | 9000020 | 155 | 320001TUR | Stephen Yee | LEVEL 12 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 12 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-04-20 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-04-27 | 2026-04-28 | 2026-04-30 |  | 2026-05-06 |  | 2026-05-07 | [5 empty] | Kerri Pandolfi | 155 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 155-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1436 | INSTALL - LEVEL 12 - LIGHTING CNTRL | PF.155 | 9000020 |  | PF.155 | PF.155 | 0% |  |  | 2026-04-13 |  | 2025-10-05 | 147
[8 empty] | 9000020 | 156 | 320001TUR | Stephen Yee | LEVEL 13 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 13 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-04-27 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-05-04 | 2026-05-05 | 2026-05-07 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | Kerri Pandolfi | 156 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 156-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1474 | INSTALL - LEVEL 13 - LIGHTING CNTRL | PF.156 | 9000020 |  | PF.156 | PF.156 | 0% |  |  | 2026-04-20 |  | 2025-10-05 | 152
[8 empty] | 9000020 | 157 | 320001TUR | Stephen Yee | LEVEL 14 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 14 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-05-04 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-05-11 | 2026-05-12 | 2026-05-14 |  | 2026-05-19 |  | 2026-05-21 | [5 empty] | Kerri Pandolfi | 157 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 157-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1519 | INSTALL - LEVEL 14 - LIGHTING CNTRL | PF.157 | 9000020 |  | PF.157 | PF.157 | 0% |  |  | 2026-04-27 |  | 2025-10-05 | 157
[8 empty] | 9000020 | 158 | 320001TUR | Stephen Yee | LEVEL 15 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 15 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-05-11 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-05-18 | 2026-05-19 | 2026-05-21 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | Kerri Pandolfi | 158 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 158-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1549 | INSTALL - LEVEL 15 - LIGHTING CNTRL | PF.158 | 9000020 |  | PF.158 | PF.158 | 0% |  |  | 2026-05-04 |  | 2025-10-05 | 162
[8 empty] | 9000020 | 159 | 320001TUR | Stephen Yee | LEVEL 16 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 16 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-05-18 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-05-25 | 2026-05-26 | 2026-05-28 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | Kerri Pandolfi | 159 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 159-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1581 | INSTALL - LEVEL 16 - LIGHTING CNTRL | PF.159 | 9000020 |  | PF.159 | PF.159 | 0% |  |  | 2026-05-11 |  | 2025-10-05 | 167
[8 empty] | 9000020 | 160 | 320001TUR | Stephen Yee | LEVEL 17 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 17 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-05-25 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-01 | 2026-06-02 | 2026-06-04 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | Kerri Pandolfi | 160 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 160-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1619 | INSTALL - LEVEL 17 - LIGHTING CNTRL | PF.160 | 9000020 |  | PF.160 | PF.160 | 0% |  |  | 2026-05-18 |  | 2025-10-05 | 172
[8 empty] | 9000020 | 161 | 320001TUR | Stephen Yee | LEVEL 18 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 18 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-01 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-08 | 2026-06-09 | 2026-06-11 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | Kerri Pandolfi | 161 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 161-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1652 | INSTALL - LEVEL 18 - LIGHTING CNTRL | PF.161 | 9000020 |  | PF.161 | PF.161 | 0% |  |  | 2026-05-25 |  | 2025-10-05 | 177
[8 empty] | 9000020 | 162 | 320001TUR | Stephen Yee | LEVEL 19 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 19 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-08 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-15 | 2026-06-16 | 2026-06-18 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | Kerri Pandolfi | 162 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 162-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1683 | INSTALL - LEVEL 19 - LIGHTING CNTRL | PF.162 | 9000020 |  | PF.162 | PF.162 | 0% |  |  | 2026-06-01 |  | 2025-10-05 | 182
[8 empty] | 9000020 | 163 | 320001TUR | Stephen Yee | LEVEL 20 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 20 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-15 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-22 | 2026-06-23 | 2026-06-25 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | Kerri Pandolfi | 163 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 163-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1712 | INSTALL - LEVEL 20 - LIGHTING CNTRL | PF.163 | 9000020 |  | PF.163 | PF.163 | 0% |  |  | 2026-06-08 |  | 2025-10-05 | 187
[8 empty] | 9000020 | 164 | 320001TUR | Stephen Yee | LEVEL 21 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 21 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-19 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-26 | 2026-06-29 | 2026-07-01 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | Kerri Pandolfi | 164 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 164-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1739 | INSTALL - LEVEL 21 - LIGHTING CNTRL | PF.164 | 9000020 |  | PF.164 | PF.164 | 0% |  |  | 2026-06-12 |  | 2025-10-05 | 191
[8 empty] | 9000020 | 165 | 320001TUR | Stephen Yee | LEVEL 22 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 22 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-29 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-06 | 2026-07-07 | 2026-07-09 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | Kerri Pandolfi | 165 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 165-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1760 | INSTALL - LEVEL 22 - LIGHTING CNTRL | PF.165 | 9000020 |  | PF.165 | PF.165 | 0% |  |  | 2026-06-22 |  | 2025-10-05 | 197
[8 empty] | 9000020 | 166 | 320001TUR | Stephen Yee | LEVEL 23 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 23 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-06 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-13 | 2026-07-14 | 2026-07-16 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | Kerri Pandolfi | 166 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 166-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1778 | INSTALL - LEVEL 23 - LIGHTING CNTRL | PF.166 | 9000020 |  | PF.166 | PF.166 | 0% |  |  | 2026-06-29 |  | 2025-10-05 | 202
[8 empty] | 9000020 | 167 | 320001TUR | Stephen Yee | LEVEL 24 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 24 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-13 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-20 | 2026-07-21 | 2026-07-23 |  | 2026-07-29 |  | 2026-07-30 | [5 empty] | Kerri Pandolfi | 167 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 167-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1795 | INSTALL - LEVEL 24 - LIGHTING CNTRL | PF.167 | 9000020 |  | PF.167 | PF.167 | 0% |  |  | 2026-07-06 |  | 2025-10-05 | 207
[8 empty] | 9000020 | 168 | 320001TUR | Stephen Yee | LEVEL 25 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 25 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-20 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-27 | 2026-07-28 | 2026-07-30 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | Kerri Pandolfi | 168 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 168-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1811 | INSTALL - LEVEL 25 - LIGHTING CNTRL | PF.168 | 9000020 |  | PF.168 | PF.168 | 0% |  |  | 2026-07-13 |  | 2025-10-05 | 212
[8 empty] | 9000020 | 169 | 320001TUR | Stephen Yee | LEVEL 26 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 26 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-27 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-03 | 2026-08-04 | 2026-08-06 |  | 2026-08-12 |  | 2026-08-12 | [5 empty] | Kerri Pandolfi | 169 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 169-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1819 | INSTALL - LEVEL 26 - LIGHTING CNTRL | PF.169 | 9000020 |  | PF.169 | PF.169 | 0% |  |  | 2026-07-20 |  | 2025-10-05 | 217
[8 empty] | 9000020 | 170 | 320001TUR | Stephen Yee | LEVEL 27 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 27 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-31 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-07 | 2026-08-10 | 2026-08-12 |  | 2026-08-19 |  | 2026-08-19 | [5 empty] | Kerri Pandolfi | 170 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 170-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1832 | INSTALL - LEVEL 27 - LIGHTING CNTRL | PF.170 | 9000020 |  | PF.170 | PF.170 | 0% |  |  | 2026-07-24 |  | 2025-10-05 | 221
[8 empty] | 9000020 | 171 | 320001TUR | Stephen Yee | LEVEL 28 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 28 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-07 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-14 | 2026-08-17 | 2026-08-19 |  | 2026-08-26 |  | 2026-08-26 | [5 empty] | Kerri Pandolfi | 171 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 171-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1845 | INSTALL - LEVEL 28 - LIGHTING CNTRL | PF.171 | 9000020 |  | PF.171 | PF.171 | 0% |  |  | 2026-07-31 |  | 2025-10-05 | 226
[8 empty] | 9000020 | 172 | 320001TUR | Stephen Yee | LEVEL 29 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 29 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-14 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-21 | 2026-08-24 | 2026-08-26 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | Kerri Pandolfi | 172 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 172-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1858 | INSTALL - LEVEL 29 - LIGHTING CNTRL | PF.172 | 9000020 |  | PF.172 | PF.172 | 0% |  |  | 2026-08-07 |  | 2025-10-05 | 231
[8 empty] | 9000020 | 173 | 320001TUR | Stephen Yee | LEVEL 30 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 30 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-21 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-28 | 2026-08-31 | 2026-09-02 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | Kerri Pandolfi | 173 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 173-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1870 | INSTALL - LEVEL 30 - LIGHTING CNTRL | PF.173 | 9000020 |  | PF.173 | PF.173 | 0% |  |  | 2026-08-14 |  | 2025-10-05 | 236
[8 empty] | 9000020 | 174 | 320001TUR | Stephen Yee | LEVEL 31 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 31 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-31 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-09-07 | 2026-09-08 | 2026-09-10 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | Kerri Pandolfi | 174 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 174-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1880 | INSTALL - LEVEL 31 - LIGHTING CNTRL | PF.174 | 9000020 |  | PF.174 | PF.174 | 0% |  |  | 2026-08-24 |  | 2025-10-05 | 242
[8 empty] | 9000020 | 175 | 320001TUR | Stephen Yee | LEVEL 32 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 32 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-09-07 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-09-14 | 2026-09-15 | 2026-09-17 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | Kerri Pandolfi | 175 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 175-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1888 | INSTALL - LEVEL 32 - LIGHTING CNTRL | PF.175 | 9000020 |  | PF.175 | PF.175 | 0% |  |  | 2026-08-31 |  | 2025-10-05 | 247
[8 empty] | 9000020 | 176 | 320001TUR | Stephen Yee | LEVEL 33 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 33 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-09-14 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-09-21 | 2026-09-22 | 2026-09-24 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | Kerri Pandolfi | 176 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 176-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1895 | INSTALL - LEVEL 33 - LIGHTING CNTRL | PF.176 | 9000020 |  | PF.176 | PF.176 | 0% |  |  | 2026-09-07 |  | 2025-10-05 | 252
[8 empty] | 9000020 | 177 | 320001TUR | Stephen Yee | LEVEL 34 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 34 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-09-21 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-09-28 | 2026-09-29 | 2026-10-01 |  | 2026-10-06 |  | 2026-10-08 | [5 empty] | Kerri Pandolfi | 177 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 177-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1901 | INSTALL - LEVEL 34 - LIGHTING CNTRL | PF.177 | 9000020 |  | PF.177 | PF.177 | 0% |  |  | 2026-09-14 |  | 2025-10-05 | 257
[8 empty] | 9000020 | 178 | 320001TUR | Stephen Yee | LEVEL 35 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 35 - TIER 3 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-09-28 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-10-05 | 2026-10-06 | 2026-10-08 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | Kerri Pandolfi | 178 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 178-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1906 | INSTALL - LEVEL 35 - LIGHTING CNTRL | PF.178 | 9000020 |  | PF.178 | PF.178 | 0% |  |  | 2026-09-21 |  | 2025-10-05 | 262
[8 empty] | 9000020 | 179 | 320001TUR | Stephen Yee | LEVEL 36 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 36 - TIER 3 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-10-05 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-10-12 | 2026-10-13 | 2026-10-15 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | Kerri Pandolfi | 179 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 179-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1910 | INSTALL - LEVEL 36 - LIGHTING CNTRL | PF.179 | 9000020 |  | PF.179 | PF.179 | 0% |  |  | 2026-09-28 |  | 2025-10-05 | 267
[8 empty] | 9000020 | 180 | 320001TUR | Stephen Yee | LEVEL 37 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 37 - AMENITY/MEP PH LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 20 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-10-12 | [7 empty] | 15.6 | 0.975 | 1 | 2 | 2026-10-19 | 2026-10-20 | 2026-10-22 |  | 2026-10-22 | [7 empty] | Kerri Pandolfi | 180 | 26 |  | 0 | 0 | 0.78 | 15.6 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 180-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1967 | INSTALL - LEVEL 37 - LIGHTING CNTRL | PF.180 | 9000020 |  | PF.180 | PF.180 | 0% |  |  | 2026-10-05 |  | 2025-10-05 | 272
[8 empty] | 9000020 | 181 | 320001TUR | Stephen Yee | LEVEL 38 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 38 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-26 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-03 | 2026-07-04 | 2026-07-06 |  | 2026-07-06 | [7 empty] | Kerri Pandolfi | 181 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 181-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1970 | INSTALL - LEVEL 38 - LIGHTING CNTRL | PF.181 | 9000020 |  | PF.181 | PF.181 | 0% |  |  | 2026-06-19 |  | 2025-10-05 | 196
[8 empty] | 9000020 | 182 | 320001TUR | Stephen Yee | LEVEL 39 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 39 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-26 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-03 | 2026-07-04 | 2026-07-06 |  | 2026-07-06 | [7 empty] | Kerri Pandolfi | 182 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 182-320001TUR | PRE-FAB - LEVEL 39 - LEVEL 39 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1973 | INSTALL - LEVEL 39 - LIGHTING CNTRL | PF.182 | 9000020 |  | PF.182 | PF.182 | 0% |  |  | 2026-06-19 |  | 2025-10-05 | 196
[8 empty] | 9000021 | 183 | 320001TUR | Stephen Yee | LEVEL B1 | LIGHTING CONTROL PANEL ASSEMBLY WIRED | LIGHTING CONTROL PANEL ASSEMBLY WIRED | 2 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID OPERATION | [7 empty] | 16 | 1 | 1 | 2 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 183 | #INVALID VALUE |  | 0 | 0 | 8 | 16 | 11.25 | 22.5 | 8 | 3.25 | 0 | -8 | LE | 183-320001TUR | PRE-FAB - LEVEL B1 - LIGHTING CONTROL PANEL ASSEMBLY WIRED | #NO MATCH | #NO MATCH | PF.183 | 9000021 |  | PF.183 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[8 empty] | 9000031 | 184 | 320001TUR | Stephen Yee | LEVEL B1 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL B1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 4 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo, Eddie Velez | 2025-08-22 | [7 empty] | 2.1193 | 0.13246 | 1 | 2 | 2025-08-29 | 2025-08-30 | 2025-09-01 |  | 2025-09-01 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 184 | 25 |  | 0 | 0 | 0.52983 | 2.1193 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 184-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | #NO MATCH | #NO MATCH | PF.184 | 9000031 |  | PF.184 | DELETED | 100% |  |  | 2025-08-15 |  | 2025-10-05 | -26
[8 empty] | 9000031 | 185 | 320001TUR | Stephen Yee | LEVEL 1 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 9 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-05 | 2025-08-28 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4.7684 | 0.29803 | 1 | 2 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-14 | DATES MISALIGNED | 2025-08-25 |  |  | Image 2025-09-22 08-57-43.jpeg |  | 8 | Kerri Pandolfi | 185 | 25 |  | 0.44444 | 4 | 0.52983 | 4.7684 |  | 0 | 0.52983 | -0.52983 | 0.44444 | -0.085383 | 25 | 185-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 114 | INSTALL - LEVEL 1 - D&B HR JB | PF.185 | 9000031 |  | PF.185 | PF.185 | 99% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000031 | 186 | 320001TUR | Stephen Yee | LEVEL 2 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 8 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 4.2386 | 0.26491 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | DATES MISALIGNED | 2025-09-10 | [5 empty] | Kerri Pandolfi | 186 | 25 |  | 0 | 0 | 0.52983 | 4.2386 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 186-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 163 | LEVEL 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.186 | 9000031 |  | PF.186 | PF.186 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000031 | 187 | 320001TUR | Stephen Yee | LEVEL 3 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 3 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-14 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-10-21 | 2025-10-22 | 2025-10-24 |  | 2025-10-24 |  | 2025-10-24 | TRUE |  | X |  |  | Kerri Pandolfi | 187 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 187-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 321 | INSTALL - LEVEL 3 - D&B HR JB | PF.187 | 9000031 |  | PF.187 | DELETED | 100% |  |  | 2025-10-07 |  | 2025-10-05 | 13
[8 empty] | 9000031 | 188 | 320001TUR | Stephen Yee | LEVEL 4 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 4 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-21 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-10-28 | 2025-10-29 | 2025-10-31 |  | 2025-10-31 |  | 2025-10-31 | TRUE |  | X |  |  | Kerri Pandolfi | 188 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 188-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 365 | INSTALL - LEVEL 4 - D&B HR JB | PF.188 | 9000031 |  | PF.188 | DELETED | 100% |  |  | 2025-10-14 |  | 2025-10-05 | 18
[8 empty] | 9000031 | 189 | 320001TUR | Stephen Yee | LEVEL 5 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 5 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-28 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-11-04 | 2025-11-05 | 2025-11-07 |  | 2025-11-07 |  | 2025-11-07 | TRUE |  | X |  |  | Kerri Pandolfi | 189 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 189-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 398 | INSTALL - LEVEL 5 - D&B HR JB | PF.189 | 9000031 |  | PF.189 | DELETED | 100% |  |  | 2025-10-21 |  | 2025-10-05 | 23
[8 empty] | 9000031 | 190 | 320001TUR | Stephen Yee | LEVEL 6 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 6 LEVEL 6 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 8 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-12 | [7 empty] | 4.2386 | 0.26491 | 1 | 2 | 2025-09-19 | 2025-09-22 | 2025-09-24 |  | 2025-09-24 |  | 2025-11-14 | TRUE |  | x |  |  | Kerri Pandolfi | 190 | 25 |  | 0 | 0 | 0.52983 | 4.2386 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 190-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 425 | INSTALL - LEVEL 6 - D&B HR JB | PF.190 | 9000031 |  | PF.190 | DELETED | 100% |  |  | 2025-09-05 |  | 2025-10-05 | -11
[8 empty] | 9000031 | 191 | 320001TUR | Stephen Yee | LEVEL 7 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 7 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-11 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-11-18 | 2025-11-19 | 2025-11-21 |  | 2025-11-21 |  | 2025-11-21 | [5 empty] | Kerri Pandolfi | 191 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 191-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 473 | INSTALL - LEVEL 7 - D&B HR JB | PF.191 | 9000031 |  | PF.191 | PF.191 | 0% |  |  | 2025-11-04 |  | 2025-10-05 | 33
[8 empty] | 9000031 | 192 | 320001TUR | Stephen Yee | LEVEL 8 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 8 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-21 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-11-28 | 2025-11-29 | 2025-12-01 |  | 2025-12-01 |  | 2025-12-01 | [5 empty] | Kerri Pandolfi | 192 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 192-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 510 | INSTALL - LEVEL 8 - D&B HR JB | PF.192 | 9000031 |  | PF.192 | PF.192 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[8 empty] | 9000031 | 193 | 320001TUR | Stephen Yee | LEVEL 9 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 9 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-28 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-12-05 | 2025-12-06 | 2025-12-08 |  | 2025-12-08 |  | 2025-12-08 | [5 empty] | Kerri Pandolfi | 193 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 193-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 550 | INSTALL - LEVEL 9 - D&B HR JB | PF.193 | 9000031 |  | PF.193 | PF.193 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[8 empty] | 9000031 | 194 | 320001TUR | Stephen Yee | LEVEL 10 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 10 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 |  | 2025-12-15 | [5 empty] | Kerri Pandolfi | 194 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 194-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 584 | INSTALL - LEVEL 10 - D&B HR JB | PF.194 | 9000031 |  | PF.194 | PF.194 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000031 | 195 | 320001TUR | Stephen Yee | LEVEL 11 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 11 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-12 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-12-19 | 2025-12-20 | 2025-12-22 |  | 2025-12-22 |  | 2025-12-22 | [5 empty] | Kerri Pandolfi | 195 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 195-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 624 | INSTALL - LEVEL 11 - D&B HR JB | PF.195 | 9000031 |  | PF.195 | PF.195 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[8 empty] | 9000031 | 196 | 320001TUR | Stephen Yee | LEVEL 12 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 12 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-19 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-12-26 | 2025-12-28 | 2025-12-30 |  | 2025-12-30 |  | 2025-12-30 | [5 empty] | Kerri Pandolfi | 196 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 196-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 667 | INSTALL - LEVEL 12 - D&B HR JB | PF.196 | 9000031 |  | PF.196 | PF.196 | 0% |  |  | 2025-12-12 |  | 2025-10-05 | 61
[8 empty] | 9000031 | 197 | 320001TUR | Stephen Yee | LEVEL 13 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 13 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-26 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-01-02 | 2026-01-05 | 2026-01-07 |  | 2026-01-07 |  | 2026-01-07 | [5 empty] | Kerri Pandolfi | 197 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 197-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 709 | INSTALL - LEVEL 13 - D&B HR JB | PF.197 | 9000031 |  | PF.197 | PF.197 | 0% |  |  | 2025-12-19 |  | 2025-10-05 | 66
[8 empty] | 9000031 | 198 | 320001TUR | Stephen Yee | LEVEL 14 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 14 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-01-09 | 2026-01-12 | 2026-01-14 |  | 2026-01-14 |  | 2026-01-14 | [5 empty] | Kerri Pandolfi | 198 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 198-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 764 | INSTALL - LEVEL 14 - D&B HR JB | PF.198 | 9000031 |  | PF.198 | PF.198 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[8 empty] | 9000031 | 199 | 320001TUR | Stephen Yee | LEVEL 15 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 15 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-12 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-01-19 | 2026-01-20 | 2026-01-22 |  | 2026-01-22 |  | 2026-01-22 | [5 empty] | Kerri Pandolfi | 199 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 199-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 814 | INSTALL - LEVEL 15 - D&B HR JB | PF.199 | 9000031 |  | PF.199 | PF.199 | 0% |  |  | 2026-01-05 |  | 2025-10-05 | 77
[8 empty] | 9000031 | 200 | 320001TUR | Stephen Yee | LEVEL 16 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 16 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-19 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-01-26 | 2026-01-27 | 2026-01-29 |  | 2026-01-29 |  | 2026-01-29 | [5 empty] | Kerri Pandolfi | 200 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 200-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 866 | INSTALL - LEVEL 16 - D&B HR JB | PF.200 | 9000031 |  | PF.200 | PF.200 | 0% |  |  | 2026-01-12 |  | 2025-10-05 | 82
[8 empty] | 9000031 | 201 | 320001TUR | Stephen Yee | LEVEL 17 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 17 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-26 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-02-02 | 2026-02-03 | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 | [5 empty] | Kerri Pandolfi | 201 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 201-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 913 | INSTALL - LEVEL 17 - D&B HR JB | PF.201 | 9000031 |  | PF.201 | PF.201 | 0% |  |  | 2026-01-19 |  | 2025-10-05 | 87
[8 empty] | 9000031 | 202 | 320001TUR | Stephen Yee | LEVEL 18 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 18 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-02 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-02-09 | 2026-02-10 | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 | [5 empty] | Kerri Pandolfi | 202 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 202-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 955 | INSTALL - LEVEL 18 - D&B HR JB | PF.202 | 9000031 |  | PF.202 | PF.202 | 0% |  |  | 2026-01-26 |  | 2025-10-05 | 92
[8 empty] | 9000031 | 203 | 320001TUR | Stephen Yee | LEVEL 19 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 19 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-10 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-02-17 | 2026-02-18 | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 | [5 empty] | Kerri Pandolfi | 203 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 203-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1000 | INSTALL - LEVEL 19 - D&B HR JB | PF.203 | 9000031 |  | PF.203 | PF.203 | 0% |  |  | 2026-02-03 |  | 2025-10-05 | 98
[8 empty] | 9000031 | 204 | 320001TUR | Stephen Yee | LEVEL 20 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 20 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-17 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-02-24 | 2026-02-25 | 2026-02-27 |  | 2026-02-27 |  | 2026-02-27 | [5 empty] | Kerri Pandolfi | 204 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 204-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1040 | INSTALL - LEVEL 20 - D&B HR JB | PF.204 | 9000031 |  | PF.204 | PF.204 | 0% |  |  | 2026-02-10 |  | 2025-10-05 | 103
[8 empty] | 9000031 | 205 | 320001TUR | Stephen Yee | LEVEL 21 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 21 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-24 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-03 | 2026-03-04 | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 | [5 empty] | Kerri Pandolfi | 205 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 205-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1085 | INSTALL - LEVEL 21 - D&B HR JB | PF.205 | 9000031 |  | PF.205 | PF.205 | 0% |  |  | 2026-02-17 |  | 2025-10-05 | 108
[8 empty] | 9000031 | 206 | 320001TUR | Stephen Yee | LEVEL 22 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 22 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-03 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-10 | 2026-03-11 | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 | [5 empty] | Kerri Pandolfi | 206 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 206-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1133 | INSTALL - LEVEL 22 - D&B HR JB | PF.206 | 9000031 |  | PF.206 | PF.206 | 0% |  |  | 2026-02-24 |  | 2025-10-05 | 113
[8 empty] | 9000031 | 207 | 320001TUR | Stephen Yee | LEVEL 23 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 23 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-10 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-17 | 2026-03-18 | 2026-03-20 |  | 2026-03-20 |  | 2026-03-20 | [5 empty] | Kerri Pandolfi | 207 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 207-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1174 | INSTALL - LEVEL 23 - D&B HR JB | PF.207 | 9000031 |  | PF.207 | PF.207 | 0% |  |  | 2026-03-03 |  | 2025-10-05 | 118
[8 empty] | 9000031 | 208 | 320001TUR | Stephen Yee | LEVEL 24 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 24 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-17 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-24 | 2026-03-25 | 2026-03-27 |  | 2026-03-27 |  | 2026-03-27 | [5 empty] | Kerri Pandolfi | 208 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 208-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1221 | INSTALL - LEVEL 24 - D&B HR JB | PF.208 | 9000031 |  | PF.208 | PF.208 | 0% |  |  | 2026-03-10 |  | 2025-10-05 | 123
[8 empty] | 9000031 | 209 | 320001TUR | Stephen Yee | LEVEL 25 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 25 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-03-24 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-31 | 2026-04-01 | 2026-04-03 |  | 2026-04-03 |  | 2026-04-03 | [5 empty] | Kerri Pandolfi | 209 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 209-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1261 | INSTALL - LEVEL 25 - D&B HR JB | PF.209 | 9000031 |  | PF.209 | PF.209 | 0% |  |  | 2026-03-17 |  | 2025-10-05 | 128
[8 empty] | 9000031 | 210 | 320001TUR | Stephen Yee | LEVEL 26 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 26 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-03-31 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-04-07 | 2026-04-08 | 2026-04-10 |  | 2026-04-10 |  | 2026-04-10 | [5 empty] | Kerri Pandolfi | 210 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 210-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1302 | INSTALL - LEVEL 26 - D&B HR JB | PF.210 | 9000031 |  | PF.210 | PF.210 | 0% |  |  | 2026-03-24 |  | 2025-10-05 | 133
[8 empty] | 9000031 | 211 | 320001TUR | Stephen Yee | LEVEL 27 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 27 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-04-07 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-04-14 | 2026-04-15 | 2026-04-17 |  | 2026-04-17 |  | 2026-04-17 | [5 empty] | Kerri Pandolfi | 211 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 211-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1346 | INSTALL - LEVEL 27 - D&B HR JB | PF.211 | 9000031 |  | PF.211 | PF.211 | 0% |  |  | 2026-03-31 |  | 2025-10-05 | 138
[8 empty] | 9000031 | 212 | 320001TUR | Stephen Yee | LEVEL 28 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 28 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-04-17 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-04-24 | 2026-04-25 | 2026-04-27 |  | 2026-04-27 |  | 2026-04-27 | [5 empty] | Kerri Pandolfi | 212 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 212-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1383 | INSTALL - LEVEL 28 - D&B HR JB | PF.212 | 9000031 |  | PF.212 | PF.212 | 0% |  |  | 2026-04-10 |  | 2025-10-05 | 146
[8 empty] | 9000031 | 213 | 320001TUR | Stephen Yee | LEVEL 29 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 29 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-04-24 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-01 | 2026-05-02 | 2026-05-04 |  | 2026-05-04 |  | 2026-05-04 | [5 empty] | Kerri Pandolfi | 213 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 213-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1425 | INSTALL - LEVEL 29 - D&B HR JB | PF.213 | 9000031 |  | PF.213 | PF.213 | 0% |  |  | 2026-04-17 |  | 2025-10-05 | 151
[8 empty] | 9000031 | 214 | 320001TUR | Stephen Yee | LEVEL 30 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 30 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-01 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-08 | 2026-05-09 | 2026-05-11 |  | 2026-05-11 |  | 2026-05-11 | [5 empty] | Kerri Pandolfi | 214 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 214-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1463 | INSTALL - LEVEL 30 - D&B HR JB | PF.214 | 9000031 |  | PF.214 | PF.214 | 0% |  |  | 2026-04-24 |  | 2025-10-05 | 156
[8 empty] | 9000031 | 215 | 320001TUR | Stephen Yee | LEVEL 31 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 31 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-08 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-15 | 2026-05-16 | 2026-05-18 |  | 2026-05-18 |  | 2026-05-18 | [5 empty] | Kerri Pandolfi | 215 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 215-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1505 | INSTALL - LEVEL 31 - D&B HR JB | PF.215 | 9000031 |  | PF.215 | PF.215 | 0% |  |  | 2026-05-01 |  | 2025-10-05 | 161
[8 empty] | 9000031 | 216 | 320001TUR | Stephen Yee | LEVEL 32 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 32 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-15 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-22 | 2026-05-24 | 2026-05-26 |  | 2026-05-26 |  | 2026-05-26 | [5 empty] | Kerri Pandolfi | 216 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 216-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1546 | INSTALL - LEVEL 32 - D&B HR JB | PF.216 | 9000031 |  | PF.216 | PF.216 | 0% |  |  | 2026-05-08 |  | 2025-10-05 | 166
[8 empty] | 9000031 | 217 | 320001TUR | Stephen Yee | LEVEL 33 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 33 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-22 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-29 | 2026-05-31 | 2026-06-02 |  | 2026-06-02 |  | 2026-06-02 | [5 empty] | Kerri Pandolfi | 217 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 217-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1572 | INSTALL - LEVEL 33 - D&B HR JB | PF.217 | 9000031 |  | PF.217 | PF.217 | 0% |  |  | 2026-05-15 |  | 2025-10-05 | 171
[8 empty] | 9000031 | 218 | 320001TUR | Stephen Yee | LEVEL 34 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 34 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-29 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-06-05 | 2026-06-07 | 2026-06-09 |  | 2026-06-09 |  | 2026-06-09 | [5 empty] | Kerri Pandolfi | 218 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 218-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1609 | INSTALL - LEVEL 34 - D&B HR JB | PF.218 | 9000031 |  | PF.218 | PF.218 | 0% |  |  | 2026-05-22 |  | 2025-10-05 | 176
[8 empty] | 9000031 | 219 | 320001TUR | Stephen Yee | LEVEL 35 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 35 - TIER 3 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-06-05 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-06-12 | 2026-06-14 | 2026-06-16 |  | 2026-06-16 |  | 2026-06-16 | [5 empty] | Kerri Pandolfi | 219 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 219-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1642 | INSTALL - LEVEL 35 - D&B HR JB | PF.219 | 9000031 |  | PF.219 | PF.219 | 0% |  |  | 2026-05-29 |  | 2025-10-05 | 181
[8 empty] | 9000031 | 220 | 320001TUR | Stephen Yee | LEVEL 36 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 36 - TIER 3 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-06-12 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-06-19 | 2026-06-22 | 2026-06-24 |  | 2026-06-24 |  | 2026-06-24 | [5 empty] | Kerri Pandolfi | 220 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 220-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1682 | INSTALL - LEVEL 36 - D&B HR JB | PF.220 | 9000031 |  | PF.220 | PF.220 | 0% |  |  | 2026-06-05 |  | 2025-10-05 | 186
[8 empty] | 9000031 | 221 | 320001TUR | Stephen Yee | LEVEL 37 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 37 - AMENITY/MEP PH JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 15 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-15 | [7 empty] | 7.9474 | 0.49671 | 1 | 2 | 2026-05-22 | 2026-05-24 | 2026-05-26 |  | 2026-07-07 |  | 2026-07-01 | [5 empty] | Kerri Pandolfi | 221 | 26 |  | 0 | 0 | 0.52983 | 7.9474 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 221-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1710 | INSTALL - LEVEL 37 - D&B HR JB | PF.221 | 9000031 |  | PF.221 | PF.221 | 0% |  |  | 2026-05-08 |  | 2025-10-05 | 166
[8 empty] | 9000031 | 222 | 320001TUR | Stephen Yee | LEVEL 38 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 38 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 8 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-22 | [7 empty] | 4.2386 | 0.26491 | 1 | 2 | 2026-05-29 | 2026-05-31 | 2026-06-02 |  | 2026-07-07 |  | 2026-07-01 | [5 empty] | Kerri Pandolfi | 222 | 26 |  | 0 | 0 | 0.52983 | 4.2386 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 222-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1711 | INSTALL - LEVEL 38 - D&B HR JB | PF.222 | 9000031 |  | PF.222 | PF.222 | 0% |  |  | 2026-05-15 |  | 2025-10-05 | 171
[8 empty] | 9000051 | 223 | 320001TUR | Stephen Yee | LEVEL B1 | HANGER STRUT (POWER) | LEVEL B1 HANGER STRUT (POWER) | 50 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | #INVALID OPERATION | [7 empty] | 13.701 | 1.7126 | 2 | 1 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 223 | #INVALID VALUE |  | 0 | 0 | 0.27402 | 13.701 | 1.08 | 54 | 0.27402 | 0.80598 | 0 | -0.27402 | LE | 223-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 HANGER STRUT (POWER) | #NO MATCH | #NO MATCH | PF.223 | 9000051 |  | PF.223 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[8 empty] | 9000051 | 224 | 320001TUR | Stephen Yee | LEVEL 1 | HANGER STRUT (POWER) | LEVEL 1 HANGER STRUT (POWER) | 50 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-03-21 | [7 empty] | 13.701 | 1.7126 | 2 | 1 | 2025-03-28 | 2025-04-01 | 2025-04-03 |  | 2025-04-03 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 224 | 25 |  | 0 | 0 | 0.27402 | 13.701 | 1.08 | 54 | 0.27402 | 0.80598 | 0 | -0.27402 | 25 | 224-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 HANGER STRUT (POWER) | #NO MATCH | #NO MATCH | PF.224 | 9000051 |  | PF.224 | DELETED | 100% |  |  | 2025-03-14 |  | 2025-10-05 | -136
[8 empty] | 9000051 | 225 | 320001TUR | Stephen Yee | LEVEL 2 | HANGER STRUT (POWER) | LEVEL 2 HANGER STRUT (POWER) | 88 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez, Steve D'Entremont | 2025-09-02 | 2025-09-09 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 24.1137 | 3.0142 | 4 | 1 | 2025-09-09 | 2025-09-13 | 2025-09-15 |  | 2025-09-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-09-16 12-35-27.jpeg | YES | 3 | Kerri Pandolfi | 225 | 25 |  | 0.80682 | 71 | 0.27402 | 24.1137 | 1.08 | 95.04 | 0.27402 | 0.80598 | 0.27402 | 0 | 25 | 225-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 HANGER STRUT (POWER) | #NO MATCH | #NO MATCH | PF.225 | 9000051 |  | PF.225 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-08-26 |  | 2025-10-05 | -19 | TRUE
[8 empty] | 9000051 | 226 | 320001TUR | Stephen Yee | LEVEL 6 | HANGER STRUT (POWER) | LEVEL 6 HANGER STRUT (POWER) - WEST SIDE | 50 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-07-17 | 2025-07-30 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 13.701 | 1.7126 | 2 | 1 | 2025-07-24 | 2025-07-28 | 2025-07-30 |  | 2025-08-04 |  | 2025-05-19 | TRUE |  | Image 2025-08-01 08-26-35.jpeg |  | 9 | Kerri Pandolfi | 226 | 25 |  | 0.3 | 15 | 0.27402 | 13.701 | 1.08 | 54 | 0.27402 | 0.80598 | 0.27402 | 0 | 25 | 226-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 HANGER STRUT (POWER) - WEST SIDE | 8 | INSTALL - LEVEL 6 - CONDUIT HANGERS | PF.226 | 9000051 |  | PF.226 | PF.226 | 100% | TRUE |  | 2025-07-10 |  | 2025-10-05 | -52 | TRUE
[8 empty] | 9000051 | 227 | 320001TUR | Stephen Yee | LEVEL 36 | HANGER STRUT (POWER) | LEVEL 36 - TIER 3 HANGER STRUT (POWER) | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-11-28 | [7 empty] | 2.7402 | 0.34252 | 1 | 1 | 2025-12-05 | 2025-12-07 | 2025-12-09 |  | 2025-12-09 | DATES MISALIGNED | 2026-01-09 | [5 empty] | Kerri Pandolfi | 227 | 25 |  | 0 | 0 | 0.27402 | 2.7402 | 1.08 | 10.8 | 0.27402 | 0.80598 | 0 | -0.27402 | 25 | 227-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 HANGER STRUT (POWER) | 718 | INSTALL - LEVEL 36 - CONDUIT HANGERS | PF.227 | 9000051 |  | PF.227 | PF.227 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[8 empty] | 9000051 | 228 | 320001TUR | Stephen Yee | LEVEL 37 | HANGER STRUT (POWER) | LEVEL 37 - AMENITY/MEP PH HANGER STRUT (POWER) | 150 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-09 | [7 empty] | 41.1029 | 5.1379 | 6 | 1 | 2025-12-16 | 2025-12-24 | 2025-12-26 |  | 2025-12-26 | DATES MISALIGNED | 2026-01-15 | [5 empty] | Kerri Pandolfi | 228 | 25 |  | 0 | 0 | 0.27402 | 41.1029 | 1.08 | 162 | 0.27402 | 0.80598 | 0 | -0.27402 | 25 | 228-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH HANGER STRUT (POWER) | 713 | INSTALL - LEVEL 37 - CONDUIT HANGERS | PF.228 | 9000051 |  | PF.228 | PF.228 | 0% |  |  | 2025-12-02 |  | 2025-10-05 | 53
[8 empty] | 9000051 | 229 | 320001TUR | Stephen Yee | LEVEL 38 | HANGER STRUT (POWER) | LEVEL 38 HANGER STRUT (POWER) | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-30 | [7 empty] | 2.7402 | 0.34252 | 1 | 1 | 2026-01-06 | 2026-01-07 | 2026-01-09 |  | 2026-01-09 | DATES MISALIGNED | 2026-01-22 | [5 empty] | Kerri Pandolfi | 229 | 26 |  | 0 | 0 | 0.27402 | 2.7402 | 1.08 | 10.8 | 0.27402 | 0.80598 | 0 | -0.27402 | 26 | 229-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 HANGER STRUT (POWER) | 813 | INSTALL - LEVEL 38 - CONDUIT HANGERS | PF.229 | 9000051 |  | PF.229 | PF.229 | 0% |  |  | 2025-12-23 |  | 2025-10-05 | 68
[8 empty] | 9000050 | 230 | 320001TUR | Stephen Yee | LEVEL B1 | PIPE BENDS (LARGE) POWER | LEVEL B1 PIPE BENDS (LARGE) POWER | 15 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | #INVALID OPERATION | [7 empty] | 12.3549 | 1.5444 | 2 | 1 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 230 | #INVALID VALUE |  | 0 | 0 | 0.82366 | 12.3549 | 0.72 | 10.8 | 0.72 | 0 | 0 | -0.82366 | LE | 230-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 PIPE BENDS (LARGE) POWER | #NO MATCH | #NO MATCH | PF.230 | 9000050 |  | PF.230 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[8 empty] | 9000050 | 231 | 320001TUR | Stephen Yee | LEVEL 1 | PIPE BENDS (LARGE) POWER | LEVEL 1 PIPE BENDS (LARGE) POWER | 15 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-03-28 | [7 empty] | 12.3549 | 1.5444 | 2 | 1 | 2025-04-04 | 2025-04-08 | 2025-04-10 |  | 2025-04-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 231 | 25 |  | 0 | 0 | 0.82366 | 12.3549 | 0.72 | 10.8 | 0.72 | 0 | 0 | -0.82366 | 25 | 231-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 PIPE BENDS (LARGE) POWER | #NO MATCH | #NO MATCH | PF.231 | 9000050 |  | PF.231 | DELETED | 100% |  |  | 2025-03-21 |  | 2025-10-05 | -131
[8 empty] | 9000050 | 232 | 320001TUR | Stephen Yee | LEVEL 2 | PIPE BENDS (LARGE) POWER | LEVEL 2 PIPE BENDS (LARGE) POWER | 30 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-04-08 | [7 empty] | 24.7098 | 3.0887 | 4 | 1 | 2025-04-15 | 2025-04-20 | 2025-04-22 |  | 2025-04-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 232 | 25 |  | 0 | 0 | 0.82366 | 24.7098 | 0.72 | 21.6 | 0.72 | 0 | 0 | -0.82366 | 25 | 232-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 PIPE BENDS (LARGE) POWER | #NO MATCH | #NO MATCH | PF.232 | 9000050 |  | PF.232 | DELETED | 100% |  |  | 2025-04-01 |  | 2025-10-05 | -124
[8 empty] | 9000050 | 233 | 320001TUR | Stephen Yee | LEVEL 6 | PIPE BENDS (LARGE) POWER | LEVEL 6 LEVEL 6 PIPE BENDS (LARGE) POWER | 30 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-05-13 |  |  |  |  | TRUE | True |  | 24.7098 | 3.0887 | 4 | 1 | 2025-05-20 | 2025-05-26 | 2025-05-28 |  | 2025-05-28 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 233 | 25 |  | 0 | 0 | 0.82366 | 24.7098 | 0.72 | 21.6 | 0.72 | 0 | 0 | -0.82366 | 25 | 233-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 PIPE BENDS (LARGE) POWER | #NO MATCH | #NO MATCH | PF.233 | 9000050 |  | PF.233 | DELETED | 100% |  |  | 2025-05-06 |  | 2025-10-05 | -99
[8 empty] | 9000050 | 234 | 320001TUR | Stephen Yee | LEVEL 36 | PIPE BENDS (LARGE) POWER | LEVEL 36 - TIER 3 PIPE BENDS (LARGE) POWER | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-05 | [7 empty] | 2.471 | 0.30887 | 1 | 1 | 2025-12-12 | 2025-12-15 | 2025-12-17 |  | 2025-12-17 | DATES MISALIGNED | 2026-01-13 | [5 empty] | Kerri Pandolfi | 234 | 25 |  | 0 | 0 | 0.82366 | 2.471 | 0.72 | 2.16 | 0.72 | 0 | 0 | -0.82366 | 25 | 234-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 PIPE BENDS (LARGE) POWER | 732 | INSTALL - LEVEL 36 - CONDUIT BENDS | PF.234 | 9000050 |  | PF.234 | PF.234 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000050 | 235 | 320001TUR | Stephen Yee | LEVEL 37 | PIPE BENDS (LARGE) POWER | LEVEL 37 - AMENITY/MEP PH PIPE BENDS (LARGE) POWER | 45 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-22 | [7 empty] | 37.0647 | 4.6331 | 5 | 1 | 2025-12-29 | 2026-01-04 | 2026-01-06 |  | 2026-01-06 | DATES MISALIGNED | 2026-01-20 | [5 empty] | Kerri Pandolfi | 235 | 26 |  | 0 | 0 | 0.82366 | 37.0647 | 0.72 | 32.4 | 0.72 | 0 | 0 | -0.82366 | 26 | 235-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH PIPE BENDS (LARGE) POWER | 728 | INSTALL - LEVEL 37 - CONDUIT BENDS | PF.235 | 9000050 |  | PF.235 | PF.235 | 0% |  |  | 2025-12-15 |  | 2025-10-05 | 62
[8 empty] | 9000050 | 236 | 320001TUR | Stephen Yee | LEVEL 38 | PIPE BENDS (LARGE) POWER | LEVEL 38 PIPE BENDS (LARGE) POWER | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2026-01-09 | [7 empty] | 2.471 | 0.30887 | 1 | 1 | 2026-01-16 | 2026-01-18 | 2026-01-20 |  | 2026-01-20 |  | 2026-01-26 | [5 empty] | Kerri Pandolfi | 236 | 26 |  | 0 | 0 | 0.82366 | 2.471 | 0.72 | 2.16 | 0.72 | 0 | 0 | -0.82366 | 26 | 236-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 PIPE BENDS (LARGE) POWER | 827 | INSTALL - LEVEL 38 - CONDUIT BENDS | PF.236 | 9000050 |  | PF.236 | PF.236 | 0% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[8 empty] | 9000052 | 237 | 320001TUR | Stephen Yee | LEVEL B1 | MODULAR EMT (5) LARGE | LEVEL B1 MODULAR EMT (5) LARGE | 2 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | #INVALID OPERATION | [7 empty] | 5.34 | 0.6675 | 1 | 1 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 237 | #INVALID VALUE |  | 0 | 0 | 2.67 | 5.34 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | LE | 237-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 MODULAR EMT (5) LARGE | #NO MATCH | #NO MATCH | PF.237 | 9000052 |  | PF.237 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[8 empty] | 9000052 | 238 | 320001TUR | Stephen Yee | LEVEL 1 | MODULAR EMT (5) LARGE | LEVEL 1 MODULAR EMT (5) LARGE | 10 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-03-26 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2025-04-02 | 2025-04-08 | 2025-04-10 |  | 2025-04-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 238 | 25 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 25 | 238-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 MODULAR EMT (5) LARGE | #NO MATCH | #NO MATCH | PF.238 | 9000052 |  | PF.238 | DELETED | 100% |  |  | 2025-03-19 |  | 2025-10-05 | -133
[8 empty] | 9000052 | 239 | 320001TUR | Stephen Yee | LEVEL 35 | MODULAR EMT (5) LARGE | LEVEL 35 - TIER 3 - MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-11-19 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2025-11-26 | 2025-12-02 | 2025-12-04 |  | 2025-12-04 | DATES MISALIGNED | 2026-01-02 | [5 empty] | Kerri Pandolfi | 239 | 25 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 25 | 239-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 - MODULAR EMT (5) LARGE | 639 | INSTALL - LEVEL 35 - CONDUIT MODULES | PF.239 | 9000052 |  | PF.239 | PF.239 | 0% |  |  | 2025-11-12 |  | 2025-10-05 | 39
[8 empty] | 9000052 | 240 | 320001TUR | Stephen Yee | LEVEL 36 | MODULAR EMT (5) LARGE | LEVEL 36 - TIER 3 - MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-02 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2025-12-09 | 2025-12-15 | 2025-12-17 |  | 2025-12-17 | DATES MISALIGNED | 2026-01-15 | [5 empty] | Kerri Pandolfi | 240 | 25 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 25 | 240-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 - MODULAR EMT (5) LARGE | 726 | INSTALL - LEVEL 36 - CONDUIT MODULES | PF.240 | 9000052 |  | PF.240 | PF.240 | 0% |  |  | 2025-11-25 |  | 2025-10-05 | 48
[8 empty] | 9000052 | 241 | 320001TUR | Stephen Yee | LEVEL 37 | MODULAR EMT (5) LARGE | LEVEL 37 - AMENITY/MEP PH - MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-23 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2025-12-30 | 2026-01-04 | 2026-01-06 |  | 2026-01-06 | DATES MISALIGNED | 2026-01-22 | [5 empty] | Kerri Pandolfi | 241 | 26 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 26 | 241-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - MODULAR EMT (5) LARGE | 773 | INSTALL - LEVEL 37 - CONDUIT MODULES | PF.241 | 9000052 |  | PF.241 | PF.241 | 0% |  |  | 2025-12-16 |  | 2025-10-05 | 63
[8 empty] | 9000052 | 242 | 320001TUR | Stephen Yee | LEVEL 38 | MODULAR EMT (5) LARGE | LEVEL 38 MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-25 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2026-01-01 | 2026-01-07 | 2026-01-09 |  | 2026-01-20 | DATES MISALIGNED | 2026-01-28 | [5 empty] | Kerri Pandolfi | 242 | 26 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 26 | 242-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 MODULAR EMT (5) LARGE | 821 | INSTALL - LEVEL 38 - CONDUIT MODULES | PF.242 | 9000052 |  | PF.242 | PF.242 | 0% |  |  | 2025-12-18 |  | 2025-10-05 | 65
[8 empty] | 9000052 | 243 | 320001TUR | Stephen Yee | LEVEL 39 | MODULAR EMT (5) LARGE | LEVEL 39 MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-31 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2026-01-07 | 2026-01-13 | 2026-01-15 |  | 2026-01-21 |  | 2026-01-27 | [5 empty] | Kerri Pandolfi | 243 | 26 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 26 | 243-320001TUR | PRE-FAB - LEVEL 39 - LEVEL 39 MODULAR EMT (5) LARGE | 811 | INSTALL - LEVEL 39 - CONDUIT MODULES | PF.243 | 9000052 |  | PF.243 | PF.243 | 0% |  |  | 2025-12-24 |  | 2025-10-05 | 69
[8 empty] | 9000054 | 244 | 320001TUR | Stephen Yee | LEVEL B1 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL B1 RISER (STICK BUILD) (POWER) (PLACEHOLDER) |  | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-14 | [7 empty] | 0 | 0 | 0 | 1 | 2026-03-21 | 2026-03-21 | 2026-03-23 |  | 2026-03-23 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 244 | 26 |  | #DIVIDE BY ZERO | 0 | 2.225 | 0 |  | 0 | 2.225 | -2.225 | #DIVIDE BY ZERO | #DIVIDE BY ZERO | 26 | 244-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.244 | 9000054 |  | PF.244 | DELETED | 100% |  |  | 2026-03-07 |  | 2025-10-05 | 121
[8 empty] | 9000054 | 245 | 320001TUR | Stephen Yee | LEVEL 1 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 1 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-04 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 245 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 245-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.245 | 9000054 |  | PF.245 | DELETED | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[8 empty] | 9000054 | 246 | 320001TUR | Stephen Yee | LEVEL 2 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 2 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-12 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 246 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 246-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.246 | 9000054 |  | PF.246 | DELETED | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[8 empty] | 9000054 | 247 | 320001TUR | Stephen Yee | LEVEL 3 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 3 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-22 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-29 | 2025-08-31 | 2025-09-02 |  | 2025-09-02 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 247 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 247-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.247 | 9000054 |  | PF.247 | DELETED | 100% |  |  | 2025-08-15 |  | 2025-10-05 | -26
[8 empty] | 9000054 | 248 | 320001TUR | Stephen Yee | LEVEL 4 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 4 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-29 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-05 | 2025-09-08 | 2025-09-10 |  | 2025-09-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 248 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 248-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.248 | 9000054 |  | PF.248 | DELETED | 100% |  |  | 2025-08-22 |  | 2025-10-05 | -21
[8 empty] | 9000054 | 249 | 320001TUR | Stephen Yee | LEVEL 5 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 5 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-12 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 249 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 249-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.249 | 9000054 |  | PF.249 | DELETED | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[8 empty] | 9000054 | 250 | 320001TUR | Stephen Yee | LEVEL 6 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 6 LEVEL 6 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-22 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-29 | 2025-08-31 | 2025-09-02 |  | 2025-09-02 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 250 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 250-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.250 | 9000054 |  | PF.250 | DELETED | 100% |  |  | 2025-08-15 |  | 2025-10-05 | -26
[8 empty] | 9000054 | 251 | 320001TUR | Stephen Yee | LEVEL 7 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 7 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-29 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-05 | 2025-09-08 | 2025-09-10 |  | 2025-09-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 251 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 251-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.251 | 9000054 |  | PF.251 | DELETED | 100% |  |  | 2025-08-22 |  | 2025-10-05 | -21
[8 empty] | 9000054 | 252 | 320001TUR | Stephen Yee | LEVEL 8 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 8 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-08 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 252 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 252-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.252 | 9000054 |  | PF.252 | DELETED | 100% |  |  | 2025-09-01 |  | 2025-10-05 | -15
[8 empty] | 9000054 | 253 | 320001TUR | Stephen Yee | LEVEL 9 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 9 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-09 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-16 | 2025-09-17 | 2025-09-19 |  | 2025-09-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 253 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 253-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.253 | 9000054 |  | PF.253 | DELETED | 100% |  |  | 2025-09-02 |  | 2025-10-05 | -14
[8 empty] | 9000054 | 254 | 320001TUR | Stephen Yee | LEVEL 10 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 10 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-16 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-09-26 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 254 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 254-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.254 | 9000054 |  | PF.254 | DELETED | 100% |  |  | 2025-09-09 |  | 2025-10-05 | -9
[8 empty] | 9000054 | 255 | 320001TUR | Stephen Yee | LEVEL 11 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 11 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-23 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-30 | 2025-10-01 | 2025-10-03 |  | 2025-10-03 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 255 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 255-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.255 | 9000054 |  | PF.255 | DELETED | 100% |  |  | 2025-09-16 |  | 2025-10-05 | -4
[8 empty] | 9000054 | 256 | 320001TUR | Stephen Yee | LEVEL 12 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 12 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-30 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-10-07 | 2025-10-08 | 2025-10-10 |  | 2025-10-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 256 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 256-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.256 | 9000054 |  | PF.256 | DELETED | 100% |  |  | 2025-09-23 |  | 2025-10-05 | 3
[8 empty] | 9000054 | 257 | 320001TUR | Stephen Yee | LEVEL 13 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 13 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-07 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-10-14 | 2025-10-15 | 2025-10-17 |  | 2025-10-17 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 257 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 257-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.257 | 9000054 |  | PF.257 | DELETED | 100% |  |  | 2025-09-30 |  | 2025-10-05 | 8
[8 empty] | 9000054 | 258 | 320001TUR | Stephen Yee | LEVEL 14 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 14 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-14 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-10-21 | 2025-10-22 | 2025-10-24 |  | 2025-10-24 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 258 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 258-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.258 | 9000054 |  | PF.258 | DELETED | 100% |  |  | 2025-10-07 |  | 2025-10-05 | 13
[8 empty] | 9000054 | 259 | 320001TUR | Stephen Yee | LEVEL 15 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 15 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-10-31 | 2025-11-01 | 2025-11-03 |  | 2025-11-03 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 259 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 259-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.259 | 9000054 |  | PF.259 | DELETED | 100% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[8 empty] | 9000054 | 260 | 320001TUR | Stephen Yee | LEVEL 16 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 16 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 260 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 260-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.260 | 9000054 |  | PF.260 | DELETED | 100% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[8 empty] | 9000054 | 261 | 320001TUR | Stephen Yee | LEVEL 17 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 17 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-04 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-11-11 | 2025-11-12 | 2025-11-14 |  | 2025-11-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 261 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 261-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.261 | 9000054 |  | PF.261 | DELETED | 100% |  |  | 2025-10-28 |  | 2025-10-05 | 28
[8 empty] | 9000054 | 262 | 320001TUR | Stephen Yee | LEVEL 18 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 18 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-11 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-11-18 | 2025-11-19 | 2025-11-21 |  | 2025-11-21 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 262 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 262-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.262 | 9000054 |  | PF.262 | DELETED | 100% |  |  | 2025-11-04 |  | 2025-10-05 | 33
[8 empty] | 9000054 | 263 | 320001TUR | Stephen Yee | LEVEL 19 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 19 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-18 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-11-25 | 2025-11-26 | 2025-11-28 |  | 2025-11-28 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 263 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 263-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.263 | 9000054 |  | PF.263 | DELETED | 100% |  |  | 2025-11-11 |  | 2025-10-05 | 38
[8 empty] | 9000054 | 264 | 320001TUR | Stephen Yee | LEVEL 20 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 20 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-25 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-12-02 | 2025-12-03 | 2025-12-05 |  | 2025-12-05 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 264 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 264-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.264 | 9000054 |  | PF.264 | DELETED | 100% |  |  | 2025-11-18 |  | 2025-10-05 | 43
[8 empty] | 9000054 | 265 | 320001TUR | Stephen Yee | LEVEL 21 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 21 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-02 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-12-09 | 2025-12-10 | 2025-12-12 |  | 2025-12-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 265 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 265-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.265 | 9000054 |  | PF.265 | DELETED | 100% |  |  | 2025-11-25 |  | 2025-10-05 | 48
[8 empty] | 9000054 | 266 | 320001TUR | Stephen Yee | LEVEL 22 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 22 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-12 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-19 | 2026-01-20 | 2026-01-22 |  | 2026-01-22 |  | 2026-01-21 | TRUE |  | X |  |  | Kerri Pandolfi | 266 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 266-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 785 | INSTALL - LEVEL 22 - FEEDER RISERS | PF.266 | 9000054 |  | PF.266 | DELETED | 100% |  |  | 2026-01-05 |  | 2025-10-05 | 77
[8 empty] | 9000054 | 267 | 320001TUR | Stephen Yee | LEVEL 23 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 23 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-16 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-12-23 | 2025-12-24 | 2025-12-26 |  | 2025-12-26 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 267 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 267-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.267 | 9000054 |  | PF.267 | DELETED | 100% |  |  | 2025-12-09 |  | 2025-10-05 | 58
[8 empty] | 9000054 | 268 | 320001TUR | Stephen Yee | LEVEL 24 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 24 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-23 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-12-30 | 2025-12-31 | 2026-01-02 |  | 2026-01-02 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 268 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 268-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.268 | 9000054 |  | PF.268 | DELETED | 100% |  |  | 2025-12-16 |  | 2025-10-05 | 63
[8 empty] | 9000054 | 269 | 320001TUR | Stephen Yee | LEVEL 25 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 25 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-30 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-06 | 2026-01-07 | 2026-01-09 |  | 2026-01-09 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 269 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 269-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.269 | 9000054 |  | PF.269 | DELETED | 100% |  |  | 2025-12-23 |  | 2025-10-05 | 68
[8 empty] | 9000054 | 270 | 320001TUR | Stephen Yee | LEVEL 26 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 26 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-09 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-16 | 2026-01-18 | 2026-01-20 |  | 2026-01-20 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 270 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 270-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.270 | 9000054 |  | PF.270 | DELETED | 100% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[8 empty] | 9000054 | 271 | 320001TUR | Stephen Yee | LEVEL 27 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 27 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-16 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-23 | 2026-01-26 | 2026-01-28 |  | 2026-01-28 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 271 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 271-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.271 | 9000054 |  | PF.271 | DELETED | 100% |  |  | 2026-01-09 |  | 2025-10-05 | 81
[8 empty] | 9000054 | 272 | 320001TUR | Stephen Yee | LEVEL 28 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 28 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-20 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-27 | 2026-01-28 | 2026-01-30 |  | 2026-01-30 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 272 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 272-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.272 | 9000054 |  | PF.272 | DELETED | 100% |  |  | 2026-01-13 |  | 2025-10-05 | 83
[8 empty] | 9000054 | 273 | 320001TUR | Stephen Yee | LEVEL 29 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 29 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 273 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 273-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.273 | 9000054 |  | PF.273 | DELETED | 100% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[8 empty] | 9000054 | 274 | 320001TUR | Stephen Yee | LEVEL 30 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 30 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-03 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-02-10 | 2026-02-11 | 2026-02-13 |  | 2026-02-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 274 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 274-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.274 | 9000054 |  | PF.274 | DELETED | 100% |  |  | 2026-01-27 |  | 2025-10-05 | 93
[8 empty] | 9000054 | 275 | 320001TUR | Stephen Yee | LEVEL 31 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 31 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-10 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-02-17 | 2026-02-18 | 2026-02-20 |  | 2026-02-20 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 275 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 275-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.275 | 9000054 |  | PF.275 | DELETED | 100% |  |  | 2026-02-03 |  | 2025-10-05 | 98
[8 empty] | 9000054 | 276 | 320001TUR | Stephen Yee | LEVEL 32 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 32 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-17 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-02-24 | 2026-02-25 | 2026-02-27 |  | 2026-02-27 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 276 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 276-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.276 | 9000054 |  | PF.276 | DELETED | 100% |  |  | 2026-02-10 |  | 2025-10-05 | 103
[8 empty] | 9000054 | 277 | 320001TUR | Stephen Yee | LEVEL 33 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 33 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-24 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-03 | 2026-03-04 | 2026-03-06 |  | 2026-03-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 277 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 277-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.277 | 9000054 |  | PF.277 | DELETED | 100% |  |  | 2026-02-17 |  | 2025-10-05 | 108
[8 empty] | 9000054 | 278 | 320001TUR | Stephen Yee | LEVEL 34 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 34 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-03 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-10 | 2026-03-11 | 2026-03-13 |  | 2026-03-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 278 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 278-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.278 | 9000054 |  | PF.278 | DELETED | 100% |  |  | 2026-02-24 |  | 2025-10-05 | 113
[8 empty] | 9000054 | 279 | 320001TUR | Stephen Yee | LEVEL 35 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 35 - TIER 3 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-06 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-13 | 2026-03-14 | 2026-03-16 |  | 2026-03-16 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 279 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 279-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.279 | 9000054 |  | PF.279 | DELETED | 100% |  |  | 2026-02-27 |  | 2025-10-05 | 116
[8 empty] | 9000054 | 280 | 320001TUR | Stephen Yee | LEVEL 36 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 36 - TIER 3 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-06 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-13 | 2026-03-15 | 2026-03-17 |  | 2026-03-17 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 280 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 280-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.280 | 9000054 |  | PF.280 | DELETED | 100% |  |  | 2026-02-27 |  | 2025-10-05 | 116
[8 empty] | 9000054 | 281 | 320001TUR | Stephen Yee | LEVEL 37 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 37 - AMENITY/MEP PH - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-06 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-13 | 2026-03-16 | 2026-03-18 |  | 2026-03-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 281 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 281-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.281 | 9000054 |  | PF.281 | DELETED | 100% |  |  | 2026-02-27 |  | 2025-10-05 | 116
[8 empty] | 9000054 | 282 | 320001TUR | Stephen Yee | LEVEL 38 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 38 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-09 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-16 | 2026-03-17 | 2026-03-19 |  | 2026-03-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 282 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 282-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.282 | 9000054 |  | PF.282 | DELETED | 100% |  |  | 2026-03-02 |  | 2025-10-05 | 117
[8 empty] | 9000054 | 283 | 320001TUR | Stephen Yee | LEVEL 39 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 39 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-10 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-17 | 2026-03-18 | 2026-03-20 |  | 2026-03-20 |  |  | TRUE |  | X |  |  | Kerri Pandolfi | 283 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 283-320001TUR | PRE-FAB - LEVEL 39 - LEVEL 39 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1974 | INSTALL - LEVEL 39 - FEEDER RISERS | PF.283 | 9000054 |  | PF.283 | DELETED | 100% |  |  | 2026-03-03 |  | 2025-10-05 | 118
[8 empty] | 9000060 | 284 | 320001TUR | Stephen Yee | LEVEL 1 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 1 PANEL ASSEMBLY (STRUT BUILD) DH1, EDH1, EL1, LH1, MH1, PL1, SDP1, SP1, LRH1 | 5 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-12 | [7 empty] | 2.5 | 0.3125 | 1 | 1 | 2026-01-19 | 2026-01-20 | 2026-01-22 |  | 2026-07-30 |  | 2026-07-30 | [5 empty] | Kerri Pandolfi | 284 | 26 |  | 0 | 0 | 0.5 | 2.5 | 0.7 | 3.5 | 0.5 | 0.2 | 0 | -0.5 | 26 | 284-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 PANEL ASSEMBLY (STRUT BUILD) DH1, EDH1, EL1, LH1, MH1, PL1, SDP1, SP1, LRH1 | 1794 | LEVEL 1 TRANSFORMER PREP LUG ONLY | PF.284 | 9000060 |  | PF.284 | PF.284 | 0% |  |  | 2026-01-05 |  | 2025-10-05 | 77
[8 empty] | 9000060 | 285 | 320001TUR | Stephen Yee | LEVEL 2 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 2 PANEL ASSEMBLY (STRUT BUILD) LH2, MH2, PL2, SP2 | 5 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-10 | [7 empty] | 2.5 | 0.3125 | 1 | 1 | 2025-10-17 | 2025-10-18 | 2025-10-20 |  | 2025-10-20 | DATES MISALIGNED | 2025-10-07 | [5 empty] | Kerri Pandolfi | 285 | 25 |  | 0 | 0 | 0.5 | 2.5 | 0.7 | 3.5 | 0.5 | 0.2 | 0 | -0.5 | 25 | 285-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 PANEL ASSEMBLY (STRUT BUILD) LH2, MH2, PL2, SP2 | 252 | LEVEL 3 - PODIUM - HPH3 PANEL ASSEMBLY (STRUT BUILD) | PF.285 | 9000060 |  | PF.285 | PF.285 | 0% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[8 empty] | 9000060 | 286 | 320001TUR | Stephen Yee | LEVEL 4 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 4 - PODIUM - PL4 PANEL ASSEMBLY | 1 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-25 | 2025-08-28 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8.51 | 1.0637 | 2 | 1 | 2025-10-02 | 2025-10-05 | 2025-10-07 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-07 |  |  |  |  | 8 | Kerri Pandolfi | 286 | 25 |  | 20 | 20 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 8.51 | 0 | 25 | 286-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM - PL4 PANEL ASSEMBLY | 250 | LEVEL 4 - PODIUM - PANEL EPH4,EPL4 | PF.286 | 9000060 |  | PF.286 | PF.286 | 75% |  |  | 2025-09-18 |  | 2025-10-05 | -2 | TRUE
[8 empty] | 9000060 | 287 | 320001TUR | Stephen Yee | LEVEL 5 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 5 - PODIUM -HPH5,EPH5,EPL5 PANEL ASSEMBLY (STRUT BUILD) | 3 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-29 | 2025-09-25 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 1.5 | 0.1875 | 1 | 1 | 2025-10-06 | 2025-10-07 | 2025-10-09 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 8 | Kerri Pandolfi | 287 | 25 |  | 1.3333 | 4 | 0.5 | 1.5 | 0.7 | 2.1 | 0.5 | 0.2 | 0.5 | 0 | 25 | 287-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM -HPH5,EPH5,EPL5 PANEL ASSEMBLY (STRUT BUILD) | 274 | INSTALL - LEVEL 5 - DISTRIBUTION EQUIP | PF.287 | 9000060 |  | PF.287 | PF.287 | 75% |  |  | 2025-09-22 |  | 2025-10-05 | 2 | TRUE
[8 empty] | 9000060 | 288 | 320001TUR | Stephen Yee | LEVEL 6 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 6 - PANEL ASSEMBLY (STRUT BUILD) DH6, LH6, PLM6, PL6 | 4 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-29 | 2025-10-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.25 | 1 | 1 | 2025-10-06 | 2025-10-07 | 2025-10-09 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 8 | Kerri Pandolfi | 288 | 25 |  | 2 | 8 | 0.5 | 2 | 0.7 | 2.8 | 0.5 | 0.2 | 0.5 | 0 | 25 | 288-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 - PANEL ASSEMBLY (STRUT BUILD) DH6, LH6, PLM6, PL6 | 268 | INSTALL - LEVEL 6 - DISTRIBUTION EQUIP | PF.288 | 9000060 |  | PF.288 | PF.288 | 75% |  |  | 2025-09-22 |  | 2025-10-05 | 2 | TRUE
[8 empty] | 9000060 | 289 | 320001TUR | Stephen Yee | LEVEL 6 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 6 - PODIUM - PL6 PANEL ASSEMBLY | 1 | Gray | 121 BROADWAY MXD TOWER | Eddie Velez | 2025-09-26 | 2025-10-01 |  | TRUE | true | TRUE | True |  | 8.51 | 1.0637 | 2 | 1 | 2025-10-03 | 2025-10-07 | 2025-10-09 |  | 2025-11-03 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  | 14 | Kerri Pandolfi | 289 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 289-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 - PODIUM - PL6 PANEL ASSEMBLY | #NO MATCH | #NO MATCH | PF.289 | 9000060 |  | PF.289 | DELETED | 100% |  |  | 2025-09-19 |  | 2025-10-05 | -1
[8 empty] | 9000060 | 290 | 320001TUR | Stephen Yee | LEVEL 10 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 10 - EPH10,EPL10 PANEL ASSEMBLY (STRUT BUILD) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-04 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2025-11-11 | 2025-11-12 | 2025-11-14 |  | 2025-11-14 |  | 2025-11-14 | [5 empty] | Kerri Pandolfi | 290 | 25 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 25 | 290-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - EPH10,EPL10 PANEL ASSEMBLY (STRUT BUILD) | 427 | INSTALL - LEVEL 10 - DISTRIBUTION EQUIP | PF.290 | 9000060 |  | PF.290 | PF.290 | 0% |  |  | 2025-10-28 |  | 2025-10-05 | 28
[8 empty] | 9000060 | 291 | 320001TUR | Stephen Yee | LEVEL 11 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 11 - TIER 1 - PANEL ASSEMBLY (STRUT BUILD) | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-10-14 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-21 | 2025-10-22 | 2025-10-24 |  | 2025-10-24 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 291 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 291-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 - PANEL ASSEMBLY (STRUT BUILD) | #NO MATCH | #NO MATCH | PF.291 | 9000060 |  | PF.291 | DELETED | 100% |  |  | 2025-10-07 |  | 2025-10-05 | 13
[8 empty] | 9000060 | 292 | 320001TUR | Stephen Yee | LEVEL 14 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 14 - TIER 1 - PL14 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-11 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-12-18 | 2025-12-20 | 2025-12-22 |  | 2025-12-22 |  | 2025-12-22 | [5 empty] | Kerri Pandolfi | 292 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 292-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 - PL14 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 604 | INSTALL - LEVEL 14 - DISTRIBUTION EQUIP | PF.292 | 9000060 |  | PF.292 | PF.292 | 0% |  |  | 2025-12-04 |  | 2025-10-05 | 55
[8 empty] | 9000060 | 293 | 320001TUR | Stephen Yee | LEVEL 15 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 15 - TIER 2 -EPH15,EPL15 PANEL ASSEMBLY (STRUT BUILD) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-12 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2025-12-19 | 2025-12-21 | 2025-12-23 |  | 2025-12-23 |  | 2025-12-23 | [5 empty] | Kerri Pandolfi | 293 | 25 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 25 | 293-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 -EPH15,EPL15 PANEL ASSEMBLY (STRUT BUILD) | 629 | INSTALL - LEVEL 15 - DISTRIBUTION EQUIP | PF.293 | 9000060 |  | PF.293 | PF.293 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[8 empty] | 9000060 | 294 | 320001TUR | Stephen Yee | LEVEL 17 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 17 - TIER 2 -HPH17 PANEL ASSEMBLY (STRUT BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-21 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-11-28 | 2025-11-29 | 2025-12-01 |  | 2025-12-12 |  | 2025-12-18 | [5 empty] | Kerri Pandolfi | 294 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 294-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 -HPH17 PANEL ASSEMBLY (STRUT BUILD) | 599 | LEVEL 17 - TIER 2 - PL17 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | PF.294 | 9000060 |  | PF.294 | PF.294 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[8 empty] | 9000060 | 295 | 320001TUR | Stephen Yee | LEVEL 20 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 20 - TIER 2 -EPH20,EPL20 PANEL ASSEMBLY (STRUT BUILD) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-19 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2025-12-26 | 2025-12-27 | 2025-12-29 |  | 2026-01-21 |  | 2026-01-26 | [5 empty] | Kerri Pandolfi | 295 | 26 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 26 | 295-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 -EPH20,EPL20 PANEL ASSEMBLY (STRUT BUILD) | 826 | LEVEL 20 - TIER 2 - PL20 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | PF.295 | 9000060 |  | PF.295 | PF.295 | 0% |  |  | 2025-12-12 |  | 2025-10-05 | 61
[8 empty] | 9000060 | 296 | 320001TUR | Stephen Yee | LEVEL 22 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 22 - TIER 2 - PL22 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-22 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-12-29 | 2025-12-31 | 2026-01-02 |  | 2026-01-26 |  | 2026-01-29 | [5 empty] | Kerri Pandolfi | 296 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 296-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 - PL22 | 837 | INSTALL - LEVEL 22 - DISTRIBUTION EQUIP | PF.296 | 9000060 |  | PF.296 | PF.296 | 0% |  |  | 2025-12-15 |  | 2025-10-05 | 62
[8 empty] | 9000060 | 297 | 320001TUR | Stephen Yee | LEVEL 24 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 24 - TIER 2 - PANEL ASSEMBLY (STRUT BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-05 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-12 | 2026-01-13 | 2026-01-15 |  | 2026-03-03 |  | 2026-03-06 | [5 empty] | Kerri Pandolfi | 297 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 297-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - PANEL ASSEMBLY (STRUT BUILD) | 1086 | INSTALL - LEVEL 24 - DISTRIBUTION EQUIP | PF.297 | 9000060 |  | PF.297 | PF.297 | 0% |  |  | 2025-12-29 |  | 2025-10-05 | 72
[8 empty] | 9000060 | 298 | 320001TUR | Stephen Yee | LEVEL 25 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 25 - TIER 2 - PANEL PL25 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-09 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2026-01-16 | 2026-01-20 | 2026-01-22 |  | 2026-03-03 |  | 2026-03-06 | [5 empty] | Kerri Pandolfi | 298 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 298-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 - PANEL PL25 | 1057 | INSTALL - LEVEL 25 - DISTRIBUTION EQUIP | PF.298 | 9000060 |  | PF.298 | PF.298 | 0% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[8 empty] | 9000060 | 299 | 320001TUR | Stephen Yee | LEVEL 28 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 28 - TIER 2 - PANEL PL28 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-15 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2026-01-22 | 2026-01-26 | 2026-01-28 |  | 2026-04-07 |  | 2026-04-10 | [5 empty] | Kerri Pandolfi | 299 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 299-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 - PANEL PL28 | 1271 | INSTALL - LEVEL 28 - DISTRIBUTION EQUIP | PF.299 | 9000060 |  | PF.299 | PF.299 | 0% |  |  | 2026-01-08 |  | 2025-10-05 | 80
[8 empty] | 9000060 | 300 | 320001TUR | Stephen Yee | LEVEL 29 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 29 - TIER 2 - PANEL HPH29,EPH29,EPL29 | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-16 | 2025-09-16 | [6 empty] | 1.5 | 0.1875 | 1 | 1 | 2026-01-23 | 2026-01-25 | 2026-01-27 |  | 2026-04-07 |  | 2026-04-10 | [5 empty] | Kerri Pandolfi | 300 | 26 |  | 0 | 0 | 0.5 | 1.5 | 0.7 | 2.1 | 0.5 | 0.2 | 0 | -0.5 | 26 | 300-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 - PANEL HPH29,EPH29,EPL29 | 1301 | INSTALL - LEVEL 29 - DISTRIBUTION EQUIP | PF.300 | 9000060 |  | PF.300 | PF.300 | 0% |  |  | 2026-01-09 |  | 2025-10-05 | 81
[8 empty] | 9000060 | 301 | 320001TUR | Stephen Yee | LEVEL 31 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 31 - TIER 2 - PANEL PL31 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-03-12 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2026-03-19 | 2026-03-21 | 2026-03-23 |  | 2026-04-07 |  | 2026-04-10 | [5 empty] | Kerri Pandolfi | 301 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 301-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 - PANEL PL31 | 1272 | INSTALL - LEVEL 31 - DISTRIBUTION EQUIP | PF.301 | 9000060 |  | PF.301 | PF.301 | 0% |  |  | 2026-03-05 |  | 2025-10-05 | 120
[8 empty] | 9000060 | 302 | 320001TUR | Stephen Yee | LEVEL 34 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 34 - TIER 2 - PANEL PL34 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-03-12 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2026-03-19 | 2026-03-21 | 2026-03-23 |  | 2026-05-13 |  | 2026-05-18 | [5 empty] | Kerri Pandolfi | 302 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 302-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 - PANEL PL34 | 1475 | INSTALL - LEVEL 34 - DISTRIBUTION EQUIP | PF.302 | 9000060 |  | PF.302 | PF.302 | 0% |  |  | 2026-03-05 |  | 2025-10-05 | 120
[8 empty] | 9000060 | 303 | 320001TUR | Stephen Yee | LEVEL 37 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 37 - AMENITY/MEP PH - PANEL ASSEMBLY (STRUT BUILD) | 5 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-02-17 | [7 empty] | 2.5 | 0.3125 | 1 | 1 | 2026-02-24 | 2026-02-25 | 2026-02-27 |  | 2026-02-27 | DATES MISALIGNED | 2026-05-18 | [5 empty] | Kerri Pandolfi | 303 | 26 |  | 0 | 0 | 0.5 | 2.5 | 0.7 | 3.5 | 0.5 | 0.2 | 0 | -0.5 | 26 | 303-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - PANEL ASSEMBLY (STRUT BUILD) | 1504 | INSTALL - LEVEL 37 - DISTRIBUTION EQUIP | PF.303 | 9000060 |  | PF.303 | PF.303 | 0% |  |  | 2026-02-10 |  | 2025-10-05 | 103
[8 empty] | 9000060 | 304 | 320001TUR | Stephen Yee | LEVEL 3 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 3 - PODIUM - HPH3 PANEL ASSEMBLY (STRUT BUILD) | 1 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-29 | 2025-08-28 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 0.5 | 0.0625 | 1 | 1 | 2025-10-06 | 2025-10-07 | 2025-10-09 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 8 | Kerri Pandolfi | 304 | 25 |  | 8 | 8 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0.5 | 0 | 25 | 304-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM - HPH3 PANEL ASSEMBLY (STRUT BUILD) | 269 | INSTALL - LEVEL 3 - DISTRIBUTION EQUIP | PF.304 | 9000060 |  | PF.304 | PF.304 | 75% |  |  | 2025-09-22 |  | 2025-10-05 | 2 | TRUE
[8 empty] | 9000060 | 305 | 320001TUR | Stephen Yee | LEVEL 4 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 4 - PODIUM - PANEL EPH4,EPL4 | 2 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-26 | 2025-09-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 1 | 0.125 | 1 | 1 | 2025-10-03 | 2025-10-05 | 2025-10-07 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 8 | Kerri Pandolfi | 305 | 25 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 25 | 305-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM - PANEL EPH4,EPL4 | 270 | INSTALL - LEVEL 4 - DISTRIBUTION EQUIP | PF.305 | 9000060 |  | PF.305 | PF.305 | 0% |  |  | 2025-09-19 |  | 2025-10-05 | -1 | TRUE
[8 empty] | 9000060 | 306 | 320001TUR | Stephen Yee | LEVEL 5 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 5 - PODIUM - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-19 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-08-26 | 2025-08-27 | 2025-08-29 |  | 2025-08-29 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 306 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 306-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM - METER STACK | #NO MATCH | #NO MATCH | PF.306 | 9000060 |  | PF.306 | DELETED | 100% |  |  | 2025-08-12 |  | 2025-10-05 | -29
[8 empty] | 9000060 | 307 | 320001TUR | Stephen Yee | LEVEL 6 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 6 LEVEL 6 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-19 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-08-26 | 2025-08-27 | 2025-08-29 |  | 2025-08-29 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 307 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 307-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 - METER STACK | #NO MATCH | #NO MATCH | PF.307 | 9000060 |  | PF.307 | DELETED | 100% |  |  | 2025-08-12 |  | 2025-10-05 | -29
[8 empty] | 9000060 | 308 | 320001TUR | Stephen Yee | LEVEL 7 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 7 - TIER 1 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-16 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-09-26 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 308 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 308-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 - METER STACK | #NO MATCH | #NO MATCH | PF.308 | 9000060 |  | PF.308 | DELETED | 100% |  |  | 2025-09-09 |  | 2025-10-05 | -9
[8 empty] | 9000060 | 309 | 320001TUR | Stephen Yee | LEVEL 8 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 8 - PL8 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-30 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-11-06 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 |  | 2025-11-14 | [5 empty] | Kerri Pandolfi | 309 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 309-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - PL8 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 438 | INSTALL - LEVEL 8 - DISTRIBUTION EQUIP | PF.309 | 9000060 |  | PF.309 | PF.309 | 0% |  |  | 2025-10-23 |  | 2025-10-05 | 25
[8 empty] | 9000060 | 310 | 320001TUR | Stephen Yee | LEVEL 9 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 9 -HPH9 PANEL ASSEMBLY (STRUT BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-14 |  | 2025-11-14 | [5 empty] | Kerri Pandolfi | 310 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 310-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 -HPH9 PANEL ASSEMBLY (STRUT BUILD) | 429 | INSTALL - LEVEL 9 - DISTRIBUTION EQUIP | PF.310 | 9000060 |  | PF.310 | PF.310 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[8 empty] | 9000060 | 311 | 320001TUR | Stephen Yee | LEVEL 10 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 10 - TIER 1 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-15 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-09-25 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 311 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 311-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 - METER STACK | #NO MATCH | #NO MATCH | PF.311 | 9000060 |  | PF.311 | DELETED | 100% |  |  | 2025-09-08 |  | 2025-10-05 | -10
[8 empty] | 9000060 | 312 | 320001TUR | Stephen Yee | LEVEL 11 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 11 - PL11 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-30 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-11-06 | 2025-11-10 | 2025-11-12 |  | 2025-11-18 |  | 2025-11-14 | [5 empty] | Kerri Pandolfi | 312 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 312-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - PL11 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 439 | INSTALL - LEVEL 11 - DISTRIBUTION EQUIP | PF.312 | 9000060 |  | PF.312 | PF.312 | 0% |  |  | 2025-10-23 |  | 2025-10-05 | 25
[8 empty] | 9000060 | 313 | 320001TUR | Stephen Yee | LEVEL 12 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 12 - TIER 1 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-10-14 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-21 | 2025-10-22 | 2025-10-24 |  | 2025-10-24 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 313 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 313-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 - METER STACK | #NO MATCH | #NO MATCH | PF.313 | 9000060 |  | PF.313 | DELETED | 100% |  |  | 2025-10-07 |  | 2025-10-05 | 13
[8 empty] | 9000060 | 314 | 320001TUR | Stephen Yee | LEVEL 13 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 13 - TIER 1 - HPH13 PANEL ASSEMBLY (STRUT BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-24 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-31 | 2025-11-01 | 2025-11-03 |  | 2025-12-17 |  | 2025-12-22 | [5 empty] | Kerri Pandolfi | 314 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 314-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 - HPH13 PANEL ASSEMBLY (STRUT BUILD) | 625 | INSTALL - LEVEL 13 - DISTRIBUTION EQUIP | PF.314 | 9000060 |  | PF.314 | PF.314 | 0% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[8 empty] | 9000060 | 315 | 320001TUR | Stephen Yee | LEVEL 14 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 14 - TIER 1 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-10-13 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-20 | 2025-10-21 | 2025-10-23 |  | 2025-10-23 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 315 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 315-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 - METER STACK | #NO MATCH | #NO MATCH | PF.315 | 9000060 |  | PF.315 | DELETED | 100% |  |  | 2025-10-06 |  | 2025-10-05 | 12
[8 empty] | 9000060 | 316 | 320001TUR | Stephen Yee | LEVEL 15 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 15 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-10-10 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-17 | 2025-10-20 | 2025-10-22 |  | 2025-10-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 316 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 316-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.316 | 9000060 |  | PF.316 | DELETED | 100% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[8 empty] | 9000060 | 317 | 320001TUR | Stephen Yee | LEVEL 16 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 16 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-11-11 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-11-18 | 2025-11-19 | 2025-11-21 |  | 2025-11-21 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 317 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 317-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.317 | 9000060 |  | PF.317 | DELETED | 100% |  |  | 2025-11-04 |  | 2025-10-05 | 33
[8 empty] | 9000060 | 318 | 320001TUR | Stephen Yee | LEVEL 17 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 17 - TIER 2 - PL17 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-20 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-11-27 | 2025-11-29 | 2025-12-01 |  | 2025-12-17 |  | 2025-12-23 | [5 empty] | Kerri Pandolfi | 318 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 318-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 - PL17 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 623 | INSTALL - LEVEL 17 - DISTRIBUTION EQUIP | PF.318 | 9000060 |  | PF.318 | PF.318 | 0% |  |  | 2025-11-13 |  | 2025-10-05 | 40
[8 empty] | 9000060 | 319 | 320001TUR | Stephen Yee | LEVEL 18 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 18 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-11-11 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-11-18 | 2025-11-19 | 2025-11-21 |  | 2025-11-21 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 319 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 319-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.319 | 9000060 |  | PF.319 | DELETED | 100% |  |  | 2025-11-04 |  | 2025-10-05 | 33
[8 empty] | 9000060 | 320 | 320001TUR | Stephen Yee | LEVEL 19 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 19 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-12-09 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-12-16 | 2025-12-17 | 2025-12-19 |  | 2025-12-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 320 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 320-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.320 | 9000060 |  | PF.320 | DELETED | 100% |  |  | 2025-12-02 |  | 2025-10-05 | 53
[8 empty] | 9000060 | 321 | 320001TUR | Stephen Yee | LEVEL 20 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 20 - TIER 2 - PL20 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-18 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-12-25 | 2025-12-27 | 2025-12-29 |  | 2026-01-26 |  | 2026-01-29 | [5 empty] | Kerri Pandolfi | 321 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 321-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 - PL20 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 836 | INSTALL - LEVEL 20 - DISTRIBUTION EQUIP | PF.321 | 9000060 |  | PF.321 | PF.321 | 0% |  |  | 2025-12-11 |  | 2025-10-05 | 60
[8 empty] | 9000060 | 322 | 320001TUR | Stephen Yee | LEVEL 21 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 21 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-12-09 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-12-16 | 2025-12-17 | 2025-12-19 |  | 2025-12-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 322 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 322-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.322 | 9000060 |  | PF.322 | DELETED | 100% |  |  | 2025-12-02 |  | 2025-10-05 | 53
[8 empty] | 9000060 | 323 | 320001TUR | Stephen Yee | LEVEL 22 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 22 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-12-08 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-12-15 | 2025-12-16 | 2025-12-18 |  | 2025-12-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 323 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 323-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.323 | 9000060 |  | PF.323 | DELETED | 100% |  |  | 2025-12-01 |  | 2025-10-05 | 52
[8 empty] | 9000060 | 324 | 320001TUR | Stephen Yee | LEVEL 23 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 23 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-01-06 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-13 | 2026-01-14 | 2026-01-16 |  | 2026-01-16 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 324 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 324-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.324 | 9000060 |  | PF.324 | DELETED | 100% |  |  | 2025-12-30 |  | 2025-10-05 | 73
[8 empty] | 9000060 | 325 | 320001TUR | Stephen Yee | LEVEL 24 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 24 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-01-05 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-12 | 2026-01-13 | 2026-01-15 |  | 2026-01-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 325 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 325-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.325 | 9000060 |  | PF.325 | DELETED | 100% |  |  | 2025-12-29 |  | 2025-10-05 | 72
[8 empty] | 9000060 | 326 | 320001TUR | Stephen Yee | LEVEL 25 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 25 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-01-05 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-12 | 2026-01-13 | 2026-01-15 |  | 2026-01-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 326 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 326-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.326 | 9000060 |  | PF.326 | DELETED | 100% |  |  | 2025-12-29 |  | 2025-10-05 | 72
[8 empty] | 9000060 | 327 | 320001TUR | Stephen Yee | LEVEL 26 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 26 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-01-06 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-13 | 2026-01-14 | 2026-01-16 |  | 2026-01-16 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 327 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 327-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.327 | 9000060 |  | PF.327 | DELETED | 100% |  |  | 2025-12-30 |  | 2025-10-05 | 73
[8 empty] | 9000060 | 328 | 320001TUR | Stephen Yee | LEVEL 27 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 27 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-02-03 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-10 | 2026-02-11 | 2026-02-13 |  | 2026-02-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 328 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 328-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.328 | 9000060 |  | PF.328 | DELETED | 100% |  |  | 2026-01-27 |  | 2025-10-05 | 93
[8 empty] | 9000060 | 329 | 320001TUR | Stephen Yee | LEVEL 28 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 28 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-02-02 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-09 | 2026-02-10 | 2026-02-12 |  | 2026-02-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 329 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 329-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.329 | 9000060 |  | PF.329 | DELETED | 100% |  |  | 2026-01-26 |  | 2025-10-05 | 92
[8 empty] | 9000060 | 330 | 320001TUR | Stephen Yee | LEVEL 29 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 29 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-02-02 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-09 | 2026-02-10 | 2026-02-12 |  | 2026-02-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 330 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 330-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.330 | 9000060 |  | PF.330 | DELETED | 100% |  |  | 2026-01-26 |  | 2025-10-05 | 92
[8 empty] | 9000060 | 331 | 320001TUR | Stephen Yee | LEVEL 30 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 30 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-02-03 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-10 | 2026-02-11 | 2026-02-13 |  | 2026-02-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 331 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 331-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.331 | 9000060 |  | PF.331 | DELETED | 100% |  |  | 2026-01-27 |  | 2025-10-05 | 93
[8 empty] | 9000060 | 332 | 320001TUR | Stephen Yee | LEVEL 31 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 31 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-02 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-03-09 | 2026-03-10 | 2026-03-12 |  | 2026-03-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 332 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 332-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.332 | 9000060 |  | PF.332 | DELETED | 100% |  |  | 2026-02-23 |  | 2025-10-05 | 112
[8 empty] | 9000060 | 333 | 320001TUR | Stephen Yee | LEVEL 32 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 32 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-03 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-03-10 | 2026-03-11 | 2026-03-13 |  | 2026-03-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 333 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 333-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.333 | 9000060 |  | PF.333 | DELETED | 100% |  |  | 2026-02-24 |  | 2025-10-05 | 113
[8 empty] | 9000060 | 334 | 320001TUR | Stephen Yee | LEVEL 33 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 33 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-03 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-03-10 | 2026-03-11 | 2026-03-13 |  | 2026-03-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 334 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 334-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.334 | 9000060 |  | PF.334 | DELETED | 100% |  |  | 2026-02-24 |  | 2025-10-05 | 113
[8 empty] | 9000060 | 335 | 320001TUR | Stephen Yee | LEVEL 34 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 34 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-02 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-03-09 | 2026-03-10 | 2026-03-12 |  | 2026-03-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 335 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 335-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.335 | 9000060 |  | PF.335 | DELETED | 100% |  |  | 2026-02-23 |  | 2025-10-05 | 112
[8 empty] | 9000060 | 336 | 320001TUR | Stephen Yee | LEVEL 35 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 35 - TIER 3 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-31 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-04-07 | 2026-04-08 | 2026-04-10 |  | 2026-04-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 336 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 336-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 - METER STACK | #NO MATCH | #NO MATCH | PF.336 | 9000060 |  | PF.336 | DELETED | 100% |  |  | 2026-03-24 |  | 2025-10-05 | 133
[8 empty] | 9000060 | 337 | 320001TUR | Stephen Yee | LEVEL 36 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 36 - TIER 3 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-31 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-04-07 | 2026-04-08 | 2026-04-10 |  | 2026-04-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 337 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 337-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 - METER STACK | #NO MATCH | #NO MATCH | PF.337 | 9000060 |  | PF.337 | DELETED | 100% |  |  | 2026-03-24 |  | 2025-10-05 | 133
[8 empty] | 9000060 | 338 | 320001TUR | Stephen Yee | LEVEL 1 | TRANSFORMER PREP LUGGING / PUNCHING PER (1) TRANSFORMER | LEVEL 1 TRANSFORMER T4 | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-07-24 | [7 empty] | 3.3333 | 0.41667 | 1 | 1 | 2026-07-31 | 2026-08-01 | 2026-08-03 |  | 2026-08-03 |  | 2026-08-03 | [5 empty] | Kerri Pandolfi | 338 | 26 |  | 0 | 0 | 1.6667 | 3.3333 | 1.67 | 3.34 | 1.6667 | 0.0033333 | 0 | -1.6667 | 26 | 338-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 TRANSFORMER T4 | 1796 | INSTALL - LEVEL 1 - DISTRIBUTION EQUIP | PF.338 | 9000060 |  | PF.338 | PF.338 | 0% |  |  | 2026-07-17 |  | 2025-10-05 | 216
[8 empty] | 9000060 | 339 | 320001TUR | Stephen Yee | LEVEL 6 | TRANSFORMER PREP LUGGING / PUNCHING PER (1) TRANSFORMER | LEVEL 6 - TRANSFORMER T5 & T4 | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | [7 empty] | 3.3333 | 0.41667 | 1 | 1 | 2025-10-31 | 2025-11-01 | 2025-11-03 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-07 | [5 empty] | Kerri Pandolfi | 339 | 25 |  | 0 | 0 | 1.6667 | 3.3333 | 1.67 | 3.34 | 1.6667 | 0.0033333 | 0 | -1.6667 | 25 | 339-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 - TRANSFORMER T5 & T4 | 257 | LEVEL 6 LEVEL 6 - PANEL ASSEMBLY (STRUT BUILD) | PF.339 | 9000060 |  | PF.339 | PF.339 | 0% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[8 empty] | 9000061 | 340 | 320001TUR | Stephen Yee | LEVEL 37 | MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2026-01-19 | [7 empty] | 80 | 5 | 5 | 2 | 2026-01-26 | 2026-02-02 | 2026-02-04 |  | 2026-02-04 | DATES MISALIGNED | 2026-02-26 | [5 empty] | Kerri Pandolfi | 340 | 26 |  | 0 | 0 | 40 | 80 | 53.8 | 107.6 | 40 | 13.8 | 0 | -40 | 26 | 340-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | 920 | LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | PF.340 | 9000061 |  | PF.340 | PF.340 | 0% |  |  | 2026-01-12 |  | 2025-10-05 | 82
[8 empty] | 9000061 | 341 | 320001TUR | Stephen Yee | LEVEL 37 | MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2026-02-09 | [7 empty] | 80 | 5 | 5 | 2 | 2026-02-16 | 2026-02-23 | 2026-02-25 |  | 2026-02-25 | DATES MISALIGNED | 2026-03-18 | [5 empty] | Kerri Pandolfi | 341 | 26 |  | 0 | 0 | 40 | 80 | 53.8 | 107.6 | 40 | 13.8 | 0 | -40 | 26 | 341-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | 1044 | INSTALL - LEVEL 37 - MODULAR DIST EQUIP | PF.341 | 9000061 |  | PF.341 | PF.341 | 0% |  |  | 2026-02-02 |  | 2025-10-05 | 97
[8 empty] | 9000150 | 342 | 320001TUR | Stephen Yee | LEVEL 1 | CHIEF BOXES (A/V) (2 RECEPTACLES) | LEVEL 1 CHIEF BOXES (A/V) (1 RECEPTACLE) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-12 | 2025-09-15 | Chris Gauvin | TRUE | true | TRUE | True | APPROVED | 2.6 | 0.1625 | 1 | 2 | 2025-09-19 | 2025-09-20 | 2025-09-22 |  | 2025-10-14 | DATES MISALIGNED | 2025-08-18 |  |  | Image 2025-09-22 08-57-15.jpeg |  | 8 | Kerri Pandolfi | 342 | 25 |  | 2 | 2 | 2.6 | 2.6 |  | 0 | 2.6 | -2.6 | 2 | -0.6 | 25 | 342-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 CHIEF BOXES (A/V) (1 RECEPTACLE) | 90 | LEVEL 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.342 | 9000150 |  | PF.342 | PF.342 | 99% | TRUE |  | 2025-09-05 |  | 2025-10-05 | -11 | TRUE
[8 empty] | 9000150 | 343 | 320001TUR | Stephen Yee | LEVEL 2 | CHIEF BOXES (A/V) (2 RECEPTACLES) | LEVEL 2 CHIEF BOXES (A/V) (2 RECEPTACLES) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 13 | 0.8125 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | DATES MISALIGNED | 2025-08-28 | [5 empty] | Kerri Pandolfi | 343 | 25 |  | 0 | 0 | 2.6 | 13 |  | 0 | 2.6 | -2.6 | 0 | -2.6 | 25 | 343-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 CHIEF BOXES (A/V) (2 RECEPTACLES) | 126 | LEVEL 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | PF.343 | 9000150 |  | PF.343 | PF.343 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000150 | 344 | 320001TUR | Stephen Yee | LEVEL 6 | CHIEF BOXES (A/V) (1 RECEPTACLE) | LEVEL 6 - CHIEF BOXES (A/V) (1 RECEPTACLE) | 11 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-18 | Chris Gauvin | TRUE | true | TRUE | True | APPROVED | 8.9007 | 0.55629 | 1 | 2 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-28 | DATES MISALIGNED | 2025-09-16 |  |  | Image 2025-10-03 07-27-23.jpeg |  | 2 | Kerri Pandolfi | 344 | 25 |  | 1.4091 | 15.5 | 0.80915 | 8.9007 | 2.8 | 30.8 | 0.80915 | 1.9909 | 0.80915 | 0 | 25 | 344-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 - CHIEF BOXES (A/V) (1 RECEPTACLE) | 176 | LEVEL 6 LEVEL 6 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.344 | 9000150 |  | PF.344 | PF.344 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000150 | 345 | 320001TUR | Stephen Yee | LEVEL 37 | CHIEF BOXES (A/V) (2 RECEPTACLES) | LEVEL 37 - AMENITY/MEP PH - CHIEF BOXES (A/V) (2 RECEPTACLES) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-06-15 | [7 empty] | 26 | 1.625 | 2 | 2 | 2026-06-22 | 2026-06-24 | 2026-06-26 |  | 2026-06-26 |  | 2026-06-26 | [5 empty] | Kerri Pandolfi | 345 | 26 |  | 0 | 0 | 2.6 | 26 |  | 0 | 2.6 | -2.6 | 0 | -2.6 | 26 | 345-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - CHIEF BOXES (A/V) (2 RECEPTACLES) | 1680 | LEVEL 37 - AMENITY/MEP PH PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.345 | 9000150 |  | PF.345 | PF.345 | 0% |  |  | 2026-06-08 |  | 2025-10-05 | 187
[8 empty] | 9000220 | 346 | 320001TUR | Stephen Yee | LEVEL 1 | TEMPS (LARGE) | LEVEL 1 TEMPS (LARGE) | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 8 | 1 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 346 |  |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 |  | 346-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 TEMPS (LARGE) | #NO MATCH | #NO MATCH | PF.346 | 9000220 |  | PF.346 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 347 | 320001TUR | Stephen Yee | LEVEL 7 | TEMPS (LARGE) | LEVEL 7 - TIER 1 - TEMPS (LARGE) | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 8 | 1 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 347 |  |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 |  | 347-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 - TEMPS (LARGE) | #NO MATCH | #NO MATCH | PF.347 | 9000220 |  | PF.347 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 348 | 320001TUR | Stephen Yee | LEVEL 18 | TEMPS (LARGE) | LEVEL 18 - TIER 2 - 45KVA PDU | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-18 | 2025-07-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-07-25 | 2025-07-28 | 2025-07-30 |  | 2025-08-04 |  |  | TRUE |  | Image 2025-08-01 08-34-04.jpeg |  | 4 | Kerri Pandolfi | 348 | 25 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 25 | 348-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 - 45KVA PDU | 1934 |  | PF.348 | 9000220 |  | PF.348 | PF.348 | 100% |  |  | 2025-07-11 |  | 2025-10-05 | -51 | TRUE
[8 empty] | 9000220 | 349 | 320001TUR | Stephen Yee | LEVEL 24 | TEMPS (LARGE) | LEVEL 24 - TIER 2 - 45KVA PDU # 082 | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-07-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-22 |  |  | TRUE |  | Image 2025-09-19 10-37-51.jpeg |  |  | Kerri Pandolfi | 349 | 25 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 25 | 349-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - 45KVA PDU # 082 | 1941 | INSTALL - LEVEL 22 - TEMP WIRING | PF.349 | 9000220 |  | PF.349 | PF.349 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15
[8 empty] | 9000220 | 350 | 320001TUR | Stephen Yee | LEVEL 30 | TEMPS (LARGE) | LEVEL 30 - TIER 2 - 75KVA PDU#068 | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | [7 empty] | 8 | 1 | 1 | 1 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-09-30 |  |  | TRUE |  | Image 2025-09-19 10-39-05.jpeg |  |  | Kerri Pandolfi | 350 | 25 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 25 | 350-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 - 75KVA PDU#068 | 1952 | INSTALL - LEVEL 28 - TEMP WIRING | PF.350 | 9000220 |  | PF.350 | PF.350 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6
[8 empty] | 9000220 | 351 | 320001TUR | Stephen Yee | LEVEL 37 | TEMPS (LARGE) | LEVEL 37 - TIER 2 - 75KVA PDU | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-12 | [7 empty] | 8 | 1 | 1 | 1 | 2025-12-19 | 2025-12-22 | 2025-12-24 |  | 2025-12-24 | [7 empty] | Kerri Pandolfi | 351 | 25 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 25 | 351-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - TIER 2 - 75KVA PDU | 1968 | INSTALL - LEVEL 33 - TEMP WIRING | PF.351 | 9000220 |  | PF.351 | PF.351 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[8 empty] | 9000220 | 352 | 320001TUR | Stephen Yee | LEVEL 38 | TEMPS (LARGE) | LEVEL 38 - 75KVA PDU | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-02 | [7 empty] | 8 | 1 | 1 | 1 | 2026-01-09 | 2026-01-10 | 2026-01-12 |  | 2026-01-12 | [7 empty] | Kerri Pandolfi | 352 | 26 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 26 | 352-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 - 75KVA PDU | 1971 | INSTALL - LEVEL 38 - TEMP WIRING | PF.352 | 9000220 |  | PF.352 | PF.352 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[8 empty] | 9000220 | 353 | 320001TUR | Stephen Yee | LEVEL B1 | TEMPS (SMALL) | LEVEL B1 TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 353 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 353-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.353 | 9000220 |  | PF.353 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 354 | 320001TUR | Stephen Yee | LEVEL 1 | TEMPS (SMALL) | LEVEL 1 TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 354 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 354-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.354 | 9000220 |  | PF.354 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 355 | 320001TUR | Stephen Yee | LEVEL 2 | TEMPS (SMALL) | LEVEL 2 TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 355 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 355-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.355 | 9000220 |  | PF.355 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 356 | 320001TUR | Stephen Yee | LEVEL 3 | TEMPS (SMALL) | LEVEL 3 - PODIUM - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 356 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 356-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.356 | 9000220 |  | PF.356 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 357 | 320001TUR | Stephen Yee | LEVEL 4 | TEMPS (SMALL) | LEVEL 4 - PODIUM - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 357 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 357-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.357 | 9000220 |  | PF.357 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 358 | 320001TUR | Stephen Yee | LEVEL 5 | TEMPS (SMALL) | LEVEL 5 - PODIUM - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 358 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 358-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.358 | 9000220 |  | PF.358 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 359 | 320001TUR | Stephen Yee | LEVEL 6 | TEMPS (SMALL) | LEVEL 6 LEVEL 6 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 359 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 359-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.359 | 9000220 |  | PF.359 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 360 | 320001TUR | Stephen Yee | LEVEL 7 | TEMPS (SMALL) | LEVEL 7 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 360 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 360-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.360 | 9000220 |  | PF.360 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 361 | 320001TUR | Stephen Yee | LEVEL 8 | TEMPS (SMALL) | LEVEL 8 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 361 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 361-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.361 | 9000220 |  | PF.361 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 362 | 320001TUR | Stephen Yee | LEVEL 9 | TEMPS (SMALL) | LEVEL 9 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 362 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 362-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.362 | 9000220 |  | PF.362 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 363 | 320001TUR | Stephen Yee | LEVEL 10 | TEMPS (SMALL) | LEVEL 10 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 363 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 363-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.363 | 9000220 |  | PF.363 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 364 | 320001TUR | Stephen Yee | LEVEL 11 | TEMPS (SMALL) | LEVEL 11 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 364 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 364-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.364 | 9000220 |  | PF.364 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 365 | 320001TUR | Stephen Yee | LEVEL 12 | TEMPS (SMALL) | LEVEL 12 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 365 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 365-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.365 | 9000220 |  | PF.365 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 366 | 320001TUR | Stephen Yee | LEVEL 13 | TEMPS (SMALL) | LEVEL 13 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 366 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 366-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.366 | 9000220 |  | PF.366 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 367 | 320001TUR | Stephen Yee | LEVEL 14 | TEMPS (SMALL) | LEVEL 14 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 367 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 367-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.367 | 9000220 |  | PF.367 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 368 | 320001TUR | Stephen Yee | LEVEL 15 | TEMPS (SMALL) | LEVEL 15 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 368 |  |  | 0.66667 | 2 | 1 | 3 | 2 | 6 | 1 | 1 | 0.66667 | -0.33333 |  | 368-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.368 | 9000220 |  | PF.368 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 369 | 320001TUR | Stephen Yee | LEVEL 16 | TEMPS (SMALL) | LEVEL 16 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 369 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 369-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.369 | 9000220 |  | PF.369 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 370 | 320001TUR | Stephen Yee | LEVEL 17 | TEMPS (SMALL) | LEVEL 17 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 370 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 370-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.370 | 9000220 |  | PF.370 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 371 | 320001TUR | Stephen Yee | LEVEL 18 | TEMPS (SMALL) | LEVEL 18 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 371 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 371-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.371 | 9000220 |  | PF.371 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 372 | 320001TUR | Stephen Yee | LEVEL 19 | TEMPS (SMALL) | LEVEL 19 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 372 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 372-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.372 | 9000220 |  | PF.372 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 373 | 320001TUR | Stephen Yee | LEVEL 20 | TEMPS (SMALL) | LEVEL 20 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 373 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 373-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.373 | 9000220 |  | PF.373 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[8 empty] | 9000220 | 374 | 320001TUR | Stephen Yee | LEVEL 21 | TEMPS (SMALL) | LEVEL 21 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-22 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-08-29 | 2025-08-30 | 2025-09-01 |  | 2025-09-01 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 374 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 374-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.374 | 9000220 |  | PF.374 | DELETED | 100% |  |  | 2025-08-15 |  | 2025-10-05 | -26
[8 empty] | 9000220 | 375 | 320001TUR | Stephen Yee | LEVEL 22 | TEMPS (SMALL) | LEVEL 22 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-29 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-09-05 | 2025-09-06 | 2025-09-08 |  | 2025-09-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 375 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 375-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.375 | 9000220 |  | PF.375 | DELETED | 100% |  |  | 2025-08-22 |  | 2025-10-05 | -21
[8 empty] | 9000220 | 376 | 320001TUR | Stephen Yee | LEVEL 23 | TEMPS (SMALL) | LEVEL 23 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-05 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-09-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 376 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 376-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.376 | 9000220 |  | PF.376 | DELETED | 100% |  |  | 2025-08-29 |  | 2025-10-05 | -16
[8 empty] | 9000220 | 377 | 320001TUR | Stephen Yee | LEVEL 24 | TEMPS (SMALL) | LEVEL 24 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-12 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-09-19 | 2025-09-20 | 2025-09-22 |  | 2025-09-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 377 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 377-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.377 | 9000220 |  | PF.377 | DELETED | 100% |  |  | 2025-09-05 |  | 2025-10-05 | -11
[8 empty] | 9000220 | 378 | 320001TUR | Stephen Yee | LEVEL 25 | TEMPS (SMALL) | LEVEL 25 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-19 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-09-26 | 2025-09-27 | 2025-09-29 |  | 2025-09-29 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 378 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 378-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.378 | 9000220 |  | PF.378 | DELETED | 100% |  |  | 2025-09-12 |  | 2025-10-05 | -6
[8 empty] | 9000220 | 379 | 320001TUR | Stephen Yee | LEVEL 26 | TEMPS (SMALL) | LEVEL 26 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-23 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3 | 0.375 | 1 | 1 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-09-30 |  |  |  |  | Image 2025-09-26 10-11-15.jpeg |  | 14 | Kerri Pandolfi | 379 | 25 |  | 0.66667 | 2 | 1 | 3 | 2 | 6 | 1 | 1 | 0.66667 | -0.33333 | 25 | 379-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 - SPIDER BOXES | 1944 | INSTALL - LEVEL 26 - TEMP WIRING | PF.379 | 9000220 |  | PF.379 | PF.379 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000220 | 380 | 320001TUR | Stephen Yee | LEVEL 27 | TEMPS (SMALL) | LEVEL 27 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-23 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3 | 0.375 | 1 | 1 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-09-30 |  |  |  |  | Image 2025-09-26 10-11-51.jpeg |  | 14 | Kerri Pandolfi | 380 | 25 |  | 0.66667 | 2 | 1 | 3 | 2 | 6 | 1 | 1 | 0.66667 | -0.33333 | 25 | 380-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 - SPIDER BOXES | 1946 | INSTALL - LEVEL 27 - TEMP WIRING | PF.380 | 9000220 |  | PF.380 | PF.380 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000220 | 381 | 320001TUR | Stephen Yee | LEVEL 28 | TEMPS (SMALL) | LEVEL 28 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-26 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3 | 0.375 | 1 | 1 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-09-30 |  |  |  |  | Image 2025-09-26 10-12-29.jpeg |  |  | Kerri Pandolfi | 381 | 25 |  | 0.66667 | 2 | 1 | 3 | 2 | 6 | 1 | 1 | 0.66667 | -0.33333 | 25 | 381-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 - SPIDER BOXES | 1948 | LEVEL 30 - TIER 2 - 75KVA PDU | PF.381 | 9000220 |  | PF.381 | PF.381 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6
[8 empty] | 9000220 | 382 | 320001TUR | Stephen Yee | LEVEL 29 | TEMPS (SMALL) | LEVEL 29 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-17 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-10-24 | 2025-10-25 | 2025-10-27 |  | 2025-10-27 | [7 empty] | Kerri Pandolfi | 382 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 382-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 - SPIDER BOXES | 1950 |  | PF.382 | 9000220 |  | PF.382 | PF.382 | 0% |  |  | 2025-10-10 |  | 2025-10-05 | 16
[8 empty] | 9000220 | 383 | 320001TUR | Stephen Yee | LEVEL 30 | TEMPS (SMALL) | LEVEL 30 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-09 | [7 empty] | 3 | 0.375 | 1 | 1 | 2026-01-16 | 2026-01-19 | 2026-01-21 | OVER DUE | 2025-10-27 | [7 empty] | Kerri Pandolfi | 383 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 383-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 - SPIDER BOXES | 1953 |  | PF.383 | 9000220 |  | PF.383 | PF.383 | 0% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[8 empty] | 9000220 | 384 | 320001TUR | Stephen Yee | LEVEL 31 | TEMPS (SMALL) | LEVEL 31 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-31 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-11-07 | 2025-11-08 | 2025-11-10 |  | 2025-11-10 | [7 empty] | Kerri Pandolfi | 384 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 384-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 - SPIDER BOXES | 1955 |  | PF.384 | 9000220 |  | PF.384 | PF.384 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[8 empty] | 9000220 | 385 | 320001TUR | Stephen Yee | LEVEL 32 | TEMPS (SMALL) | LEVEL 32 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-07 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-11-14 | 2025-11-15 | 2025-11-17 |  | 2025-11-17 | [7 empty] | Kerri Pandolfi | 385 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 385-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 - SPIDER BOXES | 1957 | INSTALL - LEVEL 32 - TEMP WIRING | PF.385 | 9000220 |  | PF.385 | PF.385 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[8 empty] | 9000220 | 386 | 320001TUR | Stephen Yee | LEVEL 33 | TEMPS (SMALL) | LEVEL 33 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-14 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-11-21 | 2025-11-22 | 2025-11-24 |  | 2025-11-24 | [7 empty] | Kerri Pandolfi | 386 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 386-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 - SPIDER BOXES | 1959 | LEVEL 37 - TIER 2 - 75KVA PDU | PF.386 | 9000220 |  | PF.386 | PF.386 | 0% |  |  | 2025-11-07 |  | 2025-10-05 | 36
[8 empty] | 9000220 | 387 | 320001TUR | Stephen Yee | LEVEL 34 | TEMPS (SMALL) | LEVEL 34 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-21 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-11-28 | 2025-11-29 | 2025-12-01 |  | 2025-12-01 | [7 empty] | Kerri Pandolfi | 387 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 387-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 - SPIDER BOXES | 1961 | INSTALL - LEVEL 34 - TEMP WIRING | PF.387 | 9000220 |  | PF.387 | PF.387 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[8 empty] | 9000220 | 388 | 320001TUR | Stephen Yee | LEVEL 35 | TEMPS (SMALL) | LEVEL 35 - TIER 3 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-28 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-12-05 | 2025-12-06 | 2025-12-08 |  | 2025-12-08 | [7 empty] | Kerri Pandolfi | 388 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 388-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 - SPIDER BOXES | 1963 | INSTALL - LEVEL 35 - TEMP WIRING | PF.388 | 9000220 |  | PF.388 | PF.388 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[8 empty] | 9000220 | 389 | 320001TUR | Stephen Yee | LEVEL 36 | TEMPS (SMALL) | LEVEL 36 - TIER 3 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-05 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | [7 empty] | Kerri Pandolfi | 389 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 389-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 - SPIDER BOXES | 1965 | INSTALL - LEVEL 36 - TEMP WIRING | PF.389 | 9000220 |  | PF.389 | PF.389 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000220 | 390 | 320001TUR | Stephen Yee | LEVEL 37 | TEMPS (SMALL) | LEVEL 37 - AMENITY/MEP PH - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-12 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-12-19 | 2025-12-22 | 2025-12-24 |  | 2025-12-24 | [7 empty] | Kerri Pandolfi | 390 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 390-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - SPIDER BOXES | 1969 |  | PF.390 | 9000220 |  | PF.390 | PF.390 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[8 empty] | 9000220 | 391 | 320001TUR | Stephen Yee | LEVEL 38 | TEMPS (SMALL) | LEVEL 38 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 3 | 0.375 | 1 | 1 | 2026-01-09 | 2026-01-10 | 2026-01-12 |  | 2026-01-12 | [7 empty] | Kerri Pandolfi | 391 | 26 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 26 | 391-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 - SPIDER BOXES | 1972 | LEVEL 38 - 75KVA PDU | PF.391 | 9000220 |  | PF.391 | PF.391 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[8 empty] | 9000220 | 392 | 320001TUR | Stephen Yee | LEVEL 39 | TEMPS (SMALL) | LEVEL 39 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-02-02 | [7 empty] | 3 | 0.375 | 1 | 1 | 2026-02-09 | 2026-02-10 | 2026-02-12 |  | 2026-02-12 | [7 empty] | Kerri Pandolfi | 392 | 26 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 26 | 392-320001TUR | PRE-FAB - LEVEL 39 - LEVEL 39 - SPIDER BOXES | 1975 | INSTALL - LEVEL 39 - TEMP WIRING | PF.392 | 9000220 |  | PF.392 | PF.392 | 0% |  |  | 2026-01-26 |  | 2025-10-05 | 92
[8 empty] | 9000063 | 001 | 320001TUR | Stephen Yee | LEVEL 3 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 3 - Load Centers 125A | 8 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-02 | 2025-08-13 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 55.28 | 3.455 | 4 | 2 | 2025-09-09 | 2025-09-15 | 2025-09-17 |  | 2025-10-14 |  | 2025-09-17 | TRUE |  | Image 2025-09-10 13-03-36.jpeg |  | 1 | Kerri Pandolfi | 1 | 25 |  | 7.625 | 61 | 6.91 | 55.28 |  | 0 | 6.91 | -6.91 | 6.91 | 0 | 25 | 001-320001TUR | PRE-FAB - LEVEL 3 - Level 3 - Load Centers 125A | 189 | Level 3 - Load Centers 150A | PF.001 | 9000063 |  | PF.001 | PF.001 | 100% | TRUE |  | 2025-08-26 |  | 2025-10-05 | -19 | TRUE
[8 empty] | 9000063 | 002 | 320001TUR | Stephen Yee | LEVEL 3 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 3 - Load Centers 150A | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-05 | 2025-08-13 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-09-12 | 2025-09-17 | 2025-09-19 |  | 2025-10-20 |  | 2025-09-19 | TRUE |  | Image 2025-09-10 13-04-02.jpeg |  | 1 | Kerri Pandolfi | 2 | 25 |  | 9.8 | 49 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 7.92 | 0 | 25 | 002-320001TUR | PRE-FAB - LEVEL 3 - Level 3 - Load Centers 150A | 205 | Level 4 - Load Centers 125A | PF.002 | 9000063 |  | PF.002 | PF.002 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000063 | 003 | 320001TUR | Stephen Yee | LEVEL 4 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 4 - Load Centers 125A | 8 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-09 | 2025-08-27 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 55.28 | 3.455 | 4 | 2 | 2025-09-16 | 2025-09-21 | 2025-09-23 |  | 2025-10-27 |  | 2025-09-23 | TRUE |  | Image 2025-09-10 13-05-07.jpeg |  | 1 | Kerri Pandolfi | 3 | 25 |  | 5.125 | 41 | 6.91 | 55.28 |  | 0 | 6.91 | -6.91 | 5.125 | -1.785 | 25 | 003-320001TUR | PRE-FAB - LEVEL 4 - Level 4 - Load Centers 125A | 212 | Level 4 - Load Centers 150A | PF.003 | 9000063 |  | PF.003 | PF.003 | 100% | TRUE |  | 2025-09-02 |  | 2025-10-05 | -14 | TRUE
[8 empty] | 9000063 | 004 | 320001TUR | Stephen Yee | LEVEL 4 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 4 - Load Centers 150A | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-11 | 2025-08-27 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-09-18 | 2025-09-23 | 2025-09-25 |  | 2025-11-07 |  | 2025-09-25 | TRUE |  | Image 2025-09-10 13-05-43.jpeg |  | 1 | Kerri Pandolfi | 4 | 25 |  | 6.2 | 31 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 6.2 | -1.72 | 25 | 004-320001TUR | PRE-FAB - LEVEL 4 - Level 4 - Load Centers 150A | 222 | Level 5 - Load Centers 125A | PF.004 | 9000063 |  | PF.004 | PF.004 | 100% | TRUE |  | 2025-09-04 |  | 2025-10-05 | -12 | TRUE
[8 empty] | 9000063 | 005 | 320001TUR | Stephen Yee | LEVEL 5 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 5 - Load Centers 125A | 8 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-16 | 2025-09-09 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 55.28 | 3.455 | 4 | 2 | 2025-09-23 | 2025-09-28 | 2025-09-30 |  | 2025-11-17 |  | 2025-09-30 | TRUE |  | Image 2025-09-29 13-51-21.jpeg |  | 1 | Kerri Pandolfi | 5 | 25 |  | 3.9375 | 31.5 | 6.91 | 55.28 |  | 0 | 6.91 | -6.91 | 3.9375 | -2.9725 | 25 | 005-320001TUR | PRE-FAB - LEVEL 5 - Level 5 - Load Centers 125A | 229 | Level 5 - Load Centers 150A | PF.005 | 9000063 |  | PF.005 | PF.005 | 100% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000063 | 006 | 320001TUR | Stephen Yee | LEVEL 5 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 5 - Load Centers 150A | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-17 | 2025-09-09 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-09-24 | 2025-09-29 | 2025-10-01 |  | 2025-11-24 |  | 2025-10-01 | TRUE |  | Image 2025-09-29 13-52-00.jpeg |  | 1 | Kerri Pandolfi | 6 | 25 |  | 6.8 | 34 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 6.8 | -1.12 | 25 | 006-320001TUR | PRE-FAB - LEVEL 5 - Level 5 - Load Centers 150A | 241 | Level 7 - Load Centers 125A | PF.006 | 9000063 |  | PF.006 | PF.006 | 100% | TRUE |  | 2025-09-10 |  | 2025-10-05 | -8 | TRUE
[8 empty] | 9000063 | 007 | 320001TUR | Stephen Yee | LEVEL 7 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 7 - Load Centers 125A | 8 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-23 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 55.28 | 3.455 | 4 | 2 | 2025-09-30 | 2025-10-04 | 2025-10-06 |  | 2025-12-01 | DATES MISALIGNED | 2025-10-06 |  |  | 2025-10-01 |  | 1 | Kerri Pandolfi | 7 | 25 |  | 4.625 | 37 | 6.91 | 55.28 |  | 0 | 6.91 | -6.91 | 4.625 | -2.285 | 25 | 007-320001TUR | PRE-FAB - LEVEL 7 - Level 7 - Load Centers 125A | 247 | Level 7 - Load Centers 150A | PF.007 | 9000063 |  | PF.007 | PF.007 | 99% |  |  | 2025-09-16 |  | 2025-10-05 | -4 | TRUE
[8 empty] | 9000063 | 008 | 320001TUR | Stephen Yee | LEVEL 7 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 7 - Load Centers 150A | 4 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-25 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 31.68 | 1.98 | 2 | 2 | 2025-10-02 | 2025-10-05 | 2025-10-07 |  | 2025-12-08 | DATES MISALIGNED | 2025-10-07 |  |  | 2025-10-01 |  | 1 | Kerri Pandolfi | 8 | 25 |  | 6.625 | 26.5 | 7.92 | 31.68 |  | 0 | 7.92 | -7.92 | 6.625 | -1.295 | 25 | 008-320001TUR | PRE-FAB - LEVEL 7 - Level 7 - Load Centers 150A | 256 | Level 8 - Load Centers 125A | PF.008 | 9000063 |  | PF.008 | PF.008 | 99% |  |  | 2025-09-18 |  | 2025-10-05 | -2 | TRUE
[8 empty] | 9000063 | 009 | 320001TUR | Stephen Yee | LEVEL 8 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 8 - Load Centers 125A | 7 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-24 | 2025-09-30 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 48.37 | 3.0231 | 4 | 2 | 2025-10-01 | 2025-10-07 | 2025-10-09 |  | 2025-12-15 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 1 | Kerri Pandolfi | 9 | 25 |  | 4.5714 | 32 | 6.91 | 48.37 |  | 0 | 6.91 | -6.91 | 4.5714 | -2.3386 | 25 | 009-320001TUR | PRE-FAB - LEVEL 8 - Level 8 - Load Centers 125A | 267 | Level 8 - Load Centers 150A | PF.009 | 9000063 |  | PF.009 | PF.009 | 75% |  |  | 2025-09-17 |  | 2025-10-05 | -3 | TRUE
[8 empty] | 9000063 | 010 | 320001TUR | Stephen Yee | LEVEL 8 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 8 - Load Centers 150A | 5 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-01 | 2025-10-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-08 | 2025-10-12 | 2025-10-14 |  | 2025-12-22 | DATES MISALIGNED | 2025-10-14 |  |  |  |  | 1 | Kerri Pandolfi | 10 | 25 |  | 2.8 | 14 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 2.8 | -5.12 | 25 | 010-320001TUR | PRE-FAB - LEVEL 8 - Level 8 - Load Centers 150A | 276 | Level 9 - Load Centers 125A | PF.010 | 9000063 |  | PF.010 | PF.010 | 35.35% |  |  | 2025-09-24 |  | 2025-10-05 | 4 | TRUE
[8 empty] | 9000063 | 011 | 320001TUR | Stephen Yee | LEVEL 9 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 9 - Load Centers 125A | 7 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-01 | 2025-10-02 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 48.37 | 3.0231 | 4 | 2 | 2025-10-08 | 2025-10-14 | 2025-10-16 |  | 2025-12-29 | DATES MISALIGNED | 2025-10-16 |  |  |  |  | 1 | Kerri Pandolfi | 11 | 25 |  | 0.57143 | 4 | 6.91 | 48.37 |  | 0 | 6.91 | -6.91 | 0.57143 | -6.3386 | 25 | 011-320001TUR | PRE-FAB - LEVEL 9 - Level 9 - Load Centers 125A | 287 | Level 9 - Load Centers 150A | PF.011 | 9000063 |  | PF.011 | PF.011 | 8.27% |  |  | 2025-09-24 |  | 2025-10-05 | 4 | TRUE
[8 empty] | 9000063 | 012 | 320001TUR | Stephen Yee | LEVEL 9 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 9 - Load Centers 150A | 5 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-03 | 2025-10-02 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-10 | 2025-10-15 | 2025-10-17 |  | 2026-01-05 | DATES MISALIGNED | 2025-10-17 |  |  |  |  | 1 | Kerri Pandolfi | 12 | 26 |  | 0.2 | 1 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.2 | -7.72 | 26 | 012-320001TUR | PRE-FAB - LEVEL 9 - Level 9 - Load Centers 150A | 298 | Level 10 - Load Centers 125A | PF.012 | 9000063 |  | PF.012 | PF.012 | 2.525% |  |  | 2025-09-26 |  | 2025-10-05 | 6 | TRUE
[8 empty] | 9000063 | 013 | 320001TUR | Stephen Yee | LEVEL 10 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 10 - Load Centers 125A | 9 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-07 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 62.19 | 3.8869 | 4 | 2 | 2025-10-14 | 2025-10-20 | 2025-10-22 |  | 2026-01-12 | DATES MISALIGNED | 2025-10-22 |  |  |  |  | 1 | Kerri Pandolfi | 13 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 013-320001TUR | PRE-FAB - LEVEL 10 - Level 10 - Load Centers 125A | 303 | Level 10 - Load Centers 150A | PF.013 | 9000063 |  | PF.013 | PF.013 | 4.824% |  |  | 2025-09-30 |  | 2025-10-05 | 8 | TRUE
[8 empty] | 9000063 | 014 | 320001TUR | Stephen Yee | LEVEL 10 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 10 - Load Centers 150A | 5 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-10 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-17 | 2025-10-22 | 2025-10-24 |  | 2026-01-20 | DATES MISALIGNED | 2025-10-24 |  |  |  |  | 1 | Kerri Pandolfi | 14 | 26 |  | 0.7 | 3.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.7 | -7.22 | 26 | 014-320001TUR | PRE-FAB - LEVEL 10 - Level 10 - Load Centers 150A | 320 | Level 11 - Load Centers 125A | PF.014 | 9000063 |  | PF.014 | PF.014 | 8.838% |  |  | 2025-10-03 |  | 2025-10-05 | 11 | TRUE
[8 empty] | 9000063 | 015 | 320001TUR | Stephen Yee | LEVEL 11 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 11 - Load Centers 125A | 9 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-14 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 62.19 | 3.8869 | 4 | 2 | 2025-10-21 | 2025-10-26 | 2025-10-28 |  | 2026-01-26 | DATES MISALIGNED | 2025-10-28 |  |  |  |  | 1 | Kerri Pandolfi | 15 | 26 |  | 0.44444 | 4 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.44444 | -6.4656 | 26 | 015-320001TUR | PRE-FAB - LEVEL 11 - Level 11 - Load Centers 125A | 330 | Level 11 - Load Centers 150A | PF.015 | 9000063 |  | PF.015 | PF.015 | 6.432% |  |  | 2025-10-07 |  | 2025-10-05 | 13 | TRUE
[8 empty] | 9000063 | 016 | 320001TUR | Stephen Yee | LEVEL 11 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 11 - Load Centers 150A | 5 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-16 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-23 | 2025-10-28 | 2025-10-30 |  | 2026-02-02 | DATES MISALIGNED | 2025-10-30 |  |  |  |  | 1 | Kerri Pandolfi | 16 | 26 |  | 0.7 | 3.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.7 | -7.22 | 26 | 016-320001TUR | PRE-FAB - LEVEL 11 - Level 11 - Load Centers 150A | 345 | Level 12 - Load Centers 125A | PF.016 | 9000063 |  | PF.016 | PF.016 | 8.838% |  |  | 2025-10-09 |  | 2025-10-05 | 15 | TRUE
[8 empty] | 9000063 | 017 | 320001TUR | Stephen Yee | LEVEL 12 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 12 - Load Centers 125A | 9 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-21 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 62.19 | 3.8869 | 4 | 2 | 2025-10-28 | 2025-11-02 | 2025-11-04 |  | 2026-02-09 | DATES MISALIGNED | 2025-11-04 |  |  |  |  | 1 | Kerri Pandolfi | 17 | 26 |  | 0.44444 | 4 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.44444 | -6.4656 | 26 | 017-320001TUR | PRE-FAB - LEVEL 12 - Level 12 - Load Centers 125A | 370 | Level 12 - Load Centers 150A | PF.017 | 9000063 |  | PF.017 | PF.017 | 6.432% |  |  | 2025-10-14 |  | 2025-10-05 | 18 | TRUE
[8 empty] | 9000063 | 018 | 320001TUR | Stephen Yee | LEVEL 12 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 12 - Load Centers 150A | 5 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-22 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-29 | 2025-11-03 | 2025-11-05 |  | 2026-02-17 | DATES MISALIGNED | 2025-11-05 |  |  |  |  | 1 | Kerri Pandolfi | 18 | 26 |  | 0.7 | 3.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.7 | -7.22 | 26 | 018-320001TUR | PRE-FAB - LEVEL 12 - Level 12 - Load Centers 150A | 382 | Level 13 - Load Centers 125A | PF.018 | 9000063 |  | PF.018 | PF.018 | 8.838% |  |  | 2025-10-15 |  | 2025-10-05 | 19 | TRUE
[8 empty] | 9000063 | 019 | 320001TUR | Stephen Yee | LEVEL 13 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 13 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-28 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-04 | 2025-11-08 | 2025-11-10 |  | 2026-02-23 | DATES MISALIGNED | 2025-11-10 |  |  |  |  | 1 | Kerri Pandolfi | 19 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 019-320001TUR | PRE-FAB - LEVEL 13 - Level 13 - Load Centers 125A | 399 | Level 13 - Load Centers 150A | PF.019 | 9000063 |  | PF.019 | PF.019 | 4.02% |  |  | 2025-10-21 |  | 2025-10-05 | 23 | TRUE
[8 empty] | 9000063 | 020 | 320001TUR | Stephen Yee | LEVEL 13 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 13 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-30 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-11-06 | 2025-11-11 | 2025-11-13 |  | 2026-03-02 | DATES MISALIGNED | 2025-11-13 |  |  |  |  | 1 | Kerri Pandolfi | 20 | 26 |  | 1 | 5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 1 | -6.92 | 26 | 020-320001TUR | PRE-FAB - LEVEL 13 - Level 13 - Load Centers 150A | 409 | Level 14 - Load Centers 125A | PF.020 | 9000063 |  | PF.020 | PF.020 | 12.63% |  |  | 2025-10-23 |  | 2025-10-05 | 25 | TRUE
[8 empty] | 9000063 | 021 | 320001TUR | Stephen Yee | LEVEL 14 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 14 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-04 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-11 | 2025-11-15 | 2025-11-17 |  | 2026-03-09 | DATES MISALIGNED | 2025-11-17 |  |  |  |  | 1 | Kerri Pandolfi | 21 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 021-320001TUR | PRE-FAB - LEVEL 14 - Level 14 - Load Centers 125A | 433 | Level 14 - Load Centers 150A | PF.021 | 9000063 |  | PF.021 | PF.021 | 4.02% |  |  | 2025-10-28 |  | 2025-10-05 | 28 | TRUE
[8 empty] | 9000063 | 022 | 320001TUR | Stephen Yee | LEVEL 14 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 14 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-05 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-11-12 | 2025-11-17 | 2025-11-19 |  | 2026-03-16 | DATES MISALIGNED | 2025-11-19 |  |  |  |  | 1 | Kerri Pandolfi | 22 | 26 |  | 0.5 | 2.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.5 | -7.42 | 26 | 022-320001TUR | PRE-FAB - LEVEL 14 - Level 14 - Load Centers 150A | 451 | Level 15 - Load Centers 125A | PF.022 | 9000063 |  | PF.022 | PF.022 | 6.313% |  |  | 2025-10-29 |  | 2025-10-05 | 29 | TRUE
[8 empty] | 9000063 | 023 | 320001TUR | Stephen Yee | LEVEL 15 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 15 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-11 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-18 | 2025-11-22 | 2025-11-24 |  | 2026-03-23 | DATES MISALIGNED | 2025-11-24 |  |  |  |  | 1 | Kerri Pandolfi | 23 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 023-320001TUR | PRE-FAB - LEVEL 15 - Level 15 - Load Centers 125A | 471 | Level 15 - Load Centers 150A | PF.023 | 9000063 |  | PF.023 | PF.023 | 4.02% |  |  | 2025-11-04 |  | 2025-10-05 | 33 | TRUE
[8 empty] | 9000063 | 024 | 320001TUR | Stephen Yee | LEVEL 15 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 15 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-12 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-11-19 | 2025-11-23 | 2025-11-25 |  | 2026-03-30 | DATES MISALIGNED | 2025-11-25 |  |  |  |  | 1 | Kerri Pandolfi | 24 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 024-320001TUR | PRE-FAB - LEVEL 15 - Level 15 - Load Centers 150A | 489 | Level 16 - Load Centers 125A | PF.024 | 9000063 |  | PF.024 | PF.024 | 5.051% |  |  | 2025-11-05 |  | 2025-10-05 | 34 | TRUE
[8 empty] | 9000063 | 025 | 320001TUR | Stephen Yee | LEVEL 16 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 16 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-18 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-25 | 2025-11-29 | 2025-12-01 |  | 2026-04-06 | DATES MISALIGNED | 2025-12-01 |  |  |  |  | 1 | Kerri Pandolfi | 25 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 025-320001TUR | PRE-FAB - LEVEL 16 - Level 16 - Load Centers 125A | 491 | Level 16 - Load Centers 150A | PF.025 | 9000063 |  | PF.025 | PF.025 | 4.02% |  |  | 2025-11-11 |  | 2025-10-05 | 38 | TRUE
[8 empty] | 9000063 | 026 | 320001TUR | Stephen Yee | LEVEL 16 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 16 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-19 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-11-26 | 2025-12-01 | 2025-12-03 |  | 2026-04-13 | DATES MISALIGNED | 2025-12-03 |  |  |  |  | 1 | Kerri Pandolfi | 26 | 26 |  | 0.6 | 3 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.6 | -7.32 | 26 | 026-320001TUR | PRE-FAB - LEVEL 16 - Level 16 - Load Centers 150A | 513 | Level 17 - Load Centers 125A | PF.026 | 9000063 |  | PF.026 | PF.026 | 7.576% |  |  | 2025-11-12 |  | 2025-10-05 | 39 | TRUE
[8 empty] | 9000063 | 027 | 320001TUR | Stephen Yee | LEVEL 17 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 17 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-20 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-27 | 2025-12-03 | 2025-12-05 |  | 2026-04-21 | DATES MISALIGNED | 2025-12-05 |  |  |  |  | 1 | Kerri Pandolfi | 27 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 027-320001TUR | PRE-FAB - LEVEL 17 - Level 17 - Load Centers 125A | 526 | Level 17 - Load Centers 150A | PF.027 | 9000063 |  | PF.027 | PF.027 | 4.02% |  |  | 2025-11-13 |  | 2025-10-05 | 40 | TRUE
[8 empty] | 9000063 | 028 | 320001TUR | Stephen Yee | LEVEL 17 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 17 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-26 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-03 | 2025-12-07 | 2025-12-09 |  | 2026-04-28 | DATES MISALIGNED | 2025-12-09 |  |  |  |  | 1 | Kerri Pandolfi | 28 | 26 |  | 0.7 | 3.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.7 | -7.22 | 26 | 028-320001TUR | PRE-FAB - LEVEL 17 - Level 17 - Load Centers 150A | 555 | Level 18 - Load Centers 125A | PF.028 | 9000063 |  | PF.028 | PF.028 | 8.838% |  |  | 2025-11-19 |  | 2025-10-05 | 44 | TRUE
[8 empty] | 9000063 | 029 | 320001TUR | Stephen Yee | LEVEL 18 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 18 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-27 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-04 | 2025-12-10 | 2025-12-12 |  | 2026-05-05 | DATES MISALIGNED | 2025-12-12 |  |  |  |  | 1 | Kerri Pandolfi | 29 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 029-320001TUR | PRE-FAB - LEVEL 18 - Level 18 - Load Centers 125A | 563 | Level 18 - Load Centers 150A | PF.029 | 9000063 |  | PF.029 | PF.029 | 4.02% |  |  | 2025-11-20 |  | 2025-10-05 | 45 | TRUE
[8 empty] | 9000063 | 030 | 320001TUR | Stephen Yee | LEVEL 18 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 18 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-03 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-10 | 2025-12-13 | 2025-12-15 |  | 2026-05-12 | DATES MISALIGNED | 2025-12-15 |  |  |  |  | 1 | Kerri Pandolfi | 30 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 030-320001TUR | PRE-FAB - LEVEL 18 - Level 18 - Load Centers 150A | 585 | Level 19 - Load Centers 125A | PF.030 | 9000063 |  | PF.030 | PF.030 | 5.051% |  |  | 2025-11-26 |  | 2025-10-05 | 49 | TRUE
[8 empty] | 9000063 | 031 | 320001TUR | Stephen Yee | LEVEL 19 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 19 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-03 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-10 | 2025-12-16 | 2025-12-18 |  | 2026-05-19 | DATES MISALIGNED | 2025-12-18 |  |  |  |  | 1 | Kerri Pandolfi | 31 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 031-320001TUR | PRE-FAB - LEVEL 19 - Level 19 - Load Centers 125A | 595 | Level 19 - Load Centers 150A | PF.031 | 9000063 |  | PF.031 | PF.031 | 4.824% |  |  | 2025-11-26 |  | 2025-10-05 | 49 | TRUE
[8 empty] | 9000063 | 032 | 320001TUR | Stephen Yee | LEVEL 19 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 19 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-10 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-17 | 2025-12-20 | 2025-12-22 |  | 2026-05-27 | DATES MISALIGNED | 2025-12-22 |  |  |  |  | 1 | Kerri Pandolfi | 32 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 032-320001TUR | PRE-FAB - LEVEL 19 - Level 19 - Load Centers 150A | 622 | Level 20 - Load Centers 125A | PF.032 | 9000063 |  | PF.032 | PF.032 | 5.051% |  |  | 2025-12-03 |  | 2025-10-05 | 54 | TRUE
[8 empty] | 9000063 | 033 | 320001TUR | Stephen Yee | LEVEL 20 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 20 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-09 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-16 | 2025-12-22 | 2025-12-24 |  | 2026-06-03 | DATES MISALIGNED | 2025-12-24 |  |  |  |  | 1 | Kerri Pandolfi | 33 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 033-320001TUR | PRE-FAB - LEVEL 20 - Level 20 - Load Centers 125A | 633 | Level 20 - Load Centers 150A | PF.033 | 9000063 |  | PF.033 | PF.033 | 4.824% |  |  | 2025-12-02 |  | 2025-10-05 | 53 | TRUE
[8 empty] | 9000063 | 034 | 320001TUR | Stephen Yee | LEVEL 20 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 20 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-17 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-24 | 2025-12-27 | 2025-12-29 |  | 2026-01-02 |  | 2025-12-29 |  |  |  |  | 1 | Kerri Pandolfi | 34 | 26 |  | 0.25 | 1.25 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.25 | -7.67 | 26 | 034-320001TUR | PRE-FAB - LEVEL 20 - Level 20 - Load Centers 150A | 648 | Level 21 - Load Centers 125A | PF.034 | 9000063 |  | PF.034 | PF.034 | 3.157% |  |  | 2025-12-10 |  | 2025-10-05 | 59 | TRUE
[8 empty] | 9000063 | 035 | 320001TUR | Stephen Yee | LEVEL 21 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 21 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-18 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-25 | 2025-12-31 | 2026-01-02 |  | 2026-01-07 |  | 2026-01-02 |  |  |  |  | 1 | Kerri Pandolfi | 35 | 26 |  | 0.36111 | 3.25 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.36111 | -6.5489 | 26 | 035-320001TUR | PRE-FAB - LEVEL 21 - Level 21 - Load Centers 125A | 672 | Level 21 - Load Centers 150A | PF.035 | 9000063 |  | PF.035 | PF.035 | 5.226% |  |  | 2025-12-11 |  | 2025-10-05 | 60 | TRUE
[8 empty] | 9000063 | 036 | 320001TUR | Stephen Yee | LEVEL 21 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 21 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-24 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-31 | 2026-01-04 | 2026-01-06 |  | 2026-01-07 |  | 2026-01-06 |  |  |  |  | 1 | Kerri Pandolfi | 36 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 036-320001TUR | PRE-FAB - LEVEL 21 - Level 21 - Load Centers 150A | 687 | Level 22 - Load Centers 125A | PF.036 | 9000063 |  | PF.036 | PF.036 | 5.051% |  |  | 2025-12-17 |  | 2025-10-05 | 64 | TRUE
[8 empty] | 9000063 | 037 | 320001TUR | Stephen Yee | LEVEL 22 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 22 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-24 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-31 | 2026-01-06 | 2026-01-08 |  | 2026-01-12 |  | 2026-01-08 |  |  |  |  | 1 | Kerri Pandolfi | 37 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 037-320001TUR | PRE-FAB - LEVEL 22 - Level 22 - Load Centers 125A | 712 | Level 22 - Load Centers 150A | PF.037 | 9000063 |  | PF.037 | PF.037 | 4.02% |  |  | 2025-12-17 |  | 2025-10-05 | 64 | TRUE
[8 empty] | 9000063 | 038 | 320001TUR | Stephen Yee | LEVEL 22 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 22 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-31 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-07 | 2026-01-10 | 2026-01-12 |  | 2026-01-12 |  | 2026-01-12 |  |  |  |  | 1 | Kerri Pandolfi | 38 | 26 |  | 0.3 | 1.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.3 | -7.62 | 26 | 038-320001TUR | PRE-FAB - LEVEL 22 - Level 22 - Load Centers 150A | 727 | Level 23 - Load Centers 125A | PF.038 | 9000063 |  | PF.038 | PF.038 | 3.788% |  |  | 2025-12-24 |  | 2025-10-05 | 69 | TRUE
[8 empty] | 9000063 | 039 | 320001TUR | Stephen Yee | LEVEL 23 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 23 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-30 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-01-06 | 2026-01-12 | 2026-01-14 |  | 2026-01-15 |  | 2026-01-14 |  |  |  |  | 1 | Kerri Pandolfi | 39 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 039-320001TUR | PRE-FAB - LEVEL 23 - Level 23 - Load Centers 125A | 760 | Level 23 - Load Centers 150A | PF.039 | 9000063 |  | PF.039 | PF.039 | 4.02% |  |  | 2025-12-23 |  | 2025-10-05 | 68 | TRUE
[8 empty] | 9000063 | 040 | 320001TUR | Stephen Yee | LEVEL 23 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 23 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-09 | 2026-01-14 | 2026-01-16 | OVER DUE | 2026-01-15 |  | 2026-01-16 |  |  |  |  | 1 | Kerri Pandolfi | 40 | 26 |  | 0.3 | 1.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.3 | -7.62 | 26 | 040-320001TUR | PRE-FAB - LEVEL 23 - Level 23 - Load Centers 150A | 774 | Level 24 - Load Centers 125A | PF.040 | 9000063 |  | PF.040 | PF.040 | 3.788% |  |  | 2025-12-26 |  | 2025-10-05 | 71 | TRUE
[8 empty] | 9000063 | 041 | 320001TUR | Stephen Yee | LEVEL 24 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 24 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-07 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-01-14 | 2026-01-20 | 2026-01-22 | OVER DUE | 2026-01-21 |  | 2026-01-22 |  |  |  |  | 1 | Kerri Pandolfi | 41 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 041-320001TUR | PRE-FAB - LEVEL 24 - Level 24 - Load Centers 125A | 787 | Level 24 - Load Centers 150A | PF.041 | 9000063 |  | PF.041 | PF.041 | 4.824% |  |  | 2025-12-31 |  | 2025-10-05 | 74 | TRUE
[8 empty] | 9000063 | 042 | 320001TUR | Stephen Yee | LEVEL 24 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 24 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-14 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-21 | 2026-01-24 | 2026-01-26 | OVER DUE | 2026-01-21 |  | 2026-01-26 |  |  |  |  | 1 | Kerri Pandolfi | 42 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 042-320001TUR | PRE-FAB - LEVEL 24 - Level 24 - Load Centers 150A | 825 | Level 25 - Load Centers 125A | PF.042 | 9000063 |  | PF.042 | PF.042 | 5.051% |  |  | 2026-01-07 |  | 2025-10-05 | 79 | TRUE
[8 empty] | 9000063 | 043 | 320001TUR | Stephen Yee | LEVEL 25 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 25 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-13 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-01-20 | 2026-01-26 | 2026-01-28 | OVER DUE | 2026-01-26 |  | 2026-01-28 |  |  |  |  | 1 | Kerri Pandolfi | 43 | 26 |  | 0.44444 | 4 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.44444 | -6.4656 | 26 | 043-320001TUR | PRE-FAB - LEVEL 25 - Level 25 - Load Centers 125A | 833 | Level 25 - Load Centers 150A | PF.043 | 9000063 |  | PF.043 | PF.043 | 6.432% |  |  | 2026-01-06 |  | 2025-10-05 | 78 | TRUE
[8 empty] | 9000063 | 044 | 320001TUR | Stephen Yee | LEVEL 25 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 25 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-16 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-23 | 2026-01-28 | 2026-01-30 | OVER DUE | 2026-01-26 |  | 2026-01-30 |  |  |  |  | 1 | Kerri Pandolfi | 44 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 044-320001TUR | PRE-FAB - LEVEL 25 - Level 25 - Load Centers 150A | 871 | Level 26 - Load Centers 125A | PF.044 | 9000063 |  | PF.044 | PF.044 | 5.051% |  |  | 2026-01-09 |  | 2025-10-05 | 81 | TRUE
[8 empty] | 9000063 | 045 | 320001TUR | Stephen Yee | LEVEL 26 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 26 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-20 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-01-27 | 2026-02-01 | 2026-02-03 | OVER DUE | 2026-01-29 |  | 2026-02-03 |  |  |  |  | 1 | Kerri Pandolfi | 45 | 26 |  | 0.55556 | 5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.55556 | -6.3544 | 26 | 045-320001TUR | PRE-FAB - LEVEL 26 - Level 26 - Load Centers 125A | 883 | Level 26 - Load Centers 150A | PF.045 | 9000063 |  | PF.045 | PF.045 | 8.04% |  |  | 2026-01-13 |  | 2025-10-05 | 83 | TRUE
[8 empty] | 9000063 | 046 | 320001TUR | Stephen Yee | LEVEL 26 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 26 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-22 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-29 | 2026-02-03 | 2026-02-05 | OVER DUE | 2026-01-29 | DATES MISALIGNED | 2026-02-05 |  |  |  |  | 1 | Kerri Pandolfi | 46 | 26 |  | 0.1 | 0.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.1 | -7.82 | 26 | 046-320001TUR | PRE-FAB - LEVEL 26 - Level 26 - Load Centers 150A | 914 | Level 27 - Load Centers 125A | PF.046 | 9000063 |  | PF.046 | PF.046 | 1.263% |  |  | 2026-01-15 |  | 2025-10-05 | 85 | TRUE
[8 empty] | 9000063 | 047 | 320001TUR | Stephen Yee | LEVEL 27 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 27 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-03 | 2026-02-08 | 2026-02-10 | OVER DUE | 2026-02-03 | DATES MISALIGNED | 2026-02-10 |  |  |  |  | 1 | Kerri Pandolfi | 47 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 047-320001TUR | PRE-FAB - LEVEL 27 - Level 27 - Load Centers 125A | 919 | Level 27 - Load Centers 150A | PF.047 | 9000063 |  | PF.047 | PF.047 | 4.824% |  |  | 2026-01-20 |  | 2025-10-05 | 88 | TRUE
[8 empty] | 9000063 | 048 | 320001TUR | Stephen Yee | LEVEL 27 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 27 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-29 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-02-05 | 2026-02-10 | 2026-02-12 | OVER DUE | 2026-02-03 | DATES MISALIGNED | 2026-02-12 |  |  |  |  | 1 | Kerri Pandolfi | 48 | 26 |  | 0.15 | 0.75 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.15 | -7.77 | 26 | 048-320001TUR | PRE-FAB - LEVEL 27 - Level 27 - Load Centers 150A | 953 | Level 28 - Load Centers 125A | PF.048 | 9000063 |  | PF.048 | PF.048 | 1.894% |  |  | 2026-01-22 |  | 2025-10-05 | 90 | TRUE
[8 empty] | 9000063 | 049 | 320001TUR | Stephen Yee | LEVEL 28 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 28 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-03 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-10 | 2026-02-15 | 2026-02-17 | OVER DUE | 2026-02-06 | DATES MISALIGNED | 2026-02-17 |  |  |  |  | 1 | Kerri Pandolfi | 49 | 26 |  | 0.22222 | 2 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.22222 | -6.6878 | 26 | 049-320001TUR | PRE-FAB - LEVEL 28 - Level 28 - Load Centers 125A | 959 | Level 28 - Load Centers 150A | PF.049 | 9000063 |  | PF.049 | PF.049 | 3.216% |  |  | 2026-01-27 |  | 2025-10-05 | 93 | TRUE
[8 empty] | 9000063 | 050 | 320001TUR | Stephen Yee | LEVEL 28 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 28 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-05 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-02-12 | 2026-02-17 | 2026-02-19 | OVER DUE | 2026-02-06 | DATES MISALIGNED | 2026-02-19 |  |  |  |  | 1 | Kerri Pandolfi | 50 | 26 |  | 0.3 | 1.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.3 | -7.62 | 26 | 050-320001TUR | PRE-FAB - LEVEL 28 - Level 28 - Load Centers 150A | 967 | Level 29 - Load Centers 125A | PF.050 | 9000063 |  | PF.050 | PF.050 | 3.788% |  |  | 2026-01-29 |  | 2025-10-05 | 95 | TRUE
[8 empty] | 9000063 | 051 | 320001TUR | Stephen Yee | LEVEL 29 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 29 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-10 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-17 | 2026-02-21 | 2026-02-23 | OVER DUE | 2026-02-11 | DATES MISALIGNED | 2026-02-23 |  |  |  |  | 1 | Kerri Pandolfi | 51 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 051-320001TUR | PRE-FAB - LEVEL 29 - Level 29 - Load Centers 125A | 1003 | Level 29 - Load Centers 150A | PF.051 | 9000063 |  | PF.051 | PF.051 | 4.824% |  |  | 2026-02-03 |  | 2025-10-05 | 98 | TRUE
[8 empty] | 9000063 | 052 | 320001TUR | Stephen Yee | LEVEL 29 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 29 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-11 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-02-18 | 2026-02-23 | 2026-02-25 | OVER DUE | 2026-02-11 | DATES MISALIGNED | 2026-02-25 |  |  |  |  | 1 | Kerri Pandolfi | 52 | 26 |  | 0.3 | 1.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.3 | -7.62 | 26 | 052-320001TUR | PRE-FAB - LEVEL 29 - Level 29 - Load Centers 150A | 1010 | Level 30 - Load Centers 125A | PF.052 | 9000063 |  | PF.052 | PF.052 | 3.788% |  |  | 2026-02-04 |  | 2025-10-05 | 99 | TRUE
[8 empty] | 9000063 | 053 | 320001TUR | Stephen Yee | LEVEL 30 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 30 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-17 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-24 | 2026-02-28 | 2026-03-02 | OVER DUE | 2026-02-17 | DATES MISALIGNED | 2026-03-02 |  |  |  |  | 1 | Kerri Pandolfi | 53 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 053-320001TUR | PRE-FAB - LEVEL 30 - Level 30 - Load Centers 125A | 1039 | Level 30 - Load Centers 150A | PF.053 | 9000063 |  | PF.053 | PF.053 | 4.824% |  |  | 2026-02-10 |  | 2025-10-05 | 103 | TRUE
[8 empty] | 9000063 | 054 | 320001TUR | Stephen Yee | LEVEL 30 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 30 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-18 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-02-25 | 2026-03-02 | 2026-03-04 | OVER DUE | 2026-02-17 | DATES MISALIGNED | 2026-03-04 |  |  |  |  | 1 | Kerri Pandolfi | 54 | 26 |  | 0.35 | 1.75 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.35 | -7.57 | 26 | 054-320001TUR | PRE-FAB - LEVEL 30 - Level 30 - Load Centers 150A | 1050 | Level 31 - Load Centers 125A | PF.054 | 9000063 |  | PF.054 | PF.054 | 4.419% |  |  | 2026-02-11 |  | 2025-10-05 | 104 | TRUE
[8 empty] | 9000063 | 055 | 320001TUR | Stephen Yee | LEVEL 31 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 31 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-19 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-26 | 2026-03-04 | 2026-03-06 | OVER DUE | 2026-02-20 | DATES MISALIGNED | 2026-03-06 |  |  |  |  | 1 | Kerri Pandolfi | 55 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 055-320001TUR | PRE-FAB - LEVEL 31 - Level 31 - Load Centers 125A | 1083 | Level 31 - Load Centers 150A | PF.055 | 9000063 |  | PF.055 | PF.055 | 4.824% |  |  | 2026-02-12 |  | 2025-10-05 | 105 | TRUE
[8 empty] | 9000063 | 056 | 320001TUR | Stephen Yee | LEVEL 31 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 31 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-25 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-03-04 | 2026-03-08 | 2026-03-10 | OVER DUE | 2026-02-20 | DATES MISALIGNED | 2026-03-10 |  |  |  |  | 1 | Kerri Pandolfi | 56 | 26 |  | 0.15 | 0.75 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.15 | -7.77 | 26 | 056-320001TUR | PRE-FAB - LEVEL 31 - Level 31 - Load Centers 150A | 1091 | Level 32 - Load Centers 125A | PF.056 | 9000063 |  | PF.056 | PF.056 | 1.894% |  |  | 2026-02-18 |  | 2025-10-05 | 109 | TRUE
[8 empty] | 9000063 | 057 | 320001TUR | Stephen Yee | LEVEL 32 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 32 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-25 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-03-04 | 2026-03-10 | 2026-03-12 | OVER DUE | 2026-02-25 | DATES MISALIGNED | 2026-03-12 |  |  |  |  | 1 | Kerri Pandolfi | 57 | 26 |  | 0 | 0 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0 | -6.91 | 26 | 057-320001TUR | PRE-FAB - LEVEL 32 - Level 32 - Load Centers 125A | 1103 | Level 32 - Load Centers 150A | PF.057 | 9000063 |  | PF.057 | PF.057 | 0% |  |  | 2026-02-18 |  | 2025-10-05 | 109 | TRUE
[8 empty] | 9000063 | 058 | 320001TUR | Stephen Yee | LEVEL 32 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 32 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-04 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-03-11 | 2026-03-14 | 2026-03-16 | OVER DUE | 2026-02-25 | DATES MISALIGNED | 2026-03-16 |  |  |  |  | 1 | Kerri Pandolfi | 58 | 26 |  | 0 | 0 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 058-320001TUR | PRE-FAB - LEVEL 32 - Level 32 - Load Centers 150A | 1134 | Level 33 - Load Centers 125A | PF.058 | 9000063 |  | PF.058 | PF.058 | 0% |  |  | 2026-02-25 |  | 2025-10-05 | 114 | TRUE
[8 empty] | 9000063 | 059 | 320001TUR | Stephen Yee | LEVEL 33 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 33 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-04 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-03-11 | 2026-03-17 | 2026-03-19 | OVER DUE | 2026-03-02 | DATES MISALIGNED | 2026-03-19 |  |  |  |  | 1 | Kerri Pandolfi | 59 | 26 |  | 0 | 0 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0 | -6.91 | 26 | 059-320001TUR | PRE-FAB - LEVEL 33 - Level 33 - Load Centers 125A | 1143 | Level 33 - Load Centers 150A | PF.059 | 9000063 |  | PF.059 | PF.059 | 0% |  |  | 2026-02-25 |  | 2025-10-05 | 114 | TRUE
[8 empty] | 9000063 | 060 | 320001TUR | Stephen Yee | LEVEL 33 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 33 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-11 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-03-18 | 2026-03-21 | 2026-03-23 | OVER DUE | 2026-03-02 | DATES MISALIGNED | 2026-03-23 |  |  |  |  | 1 | Kerri Pandolfi | 60 | 26 |  | 0 | 0 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 060-320001TUR | PRE-FAB - LEVEL 33 - Level 33 - Load Centers 150A | 1176 | Level 34 - Load Centers 125A | PF.060 | 9000063 |  | PF.060 | PF.060 | 0% |  |  | 2026-03-04 |  | 2025-10-05 | 119 | TRUE
[8 empty] | 9000063 | 061 | 320001TUR | Stephen Yee | LEVEL 34 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 34 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-10 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-03-17 | 2026-03-23 | 2026-03-25 | OVER DUE | 2026-03-05 | DATES MISALIGNED | 2026-03-25 |  |  |  |  | 1 | Kerri Pandolfi | 61 | 26 |  | 0 | 0 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0 | -6.91 | 26 | 061-320001TUR | PRE-FAB - LEVEL 34 - Level 34 - Load Centers 125A | 1185 | Level 34 - Load Centers 150A | PF.061 | 9000063 |  | PF.061 | PF.061 | 0% |  |  | 2026-03-03 |  | 2025-10-05 | 118 | TRUE
[8 empty] | 9000063 | 062 | 320001TUR | Stephen Yee | LEVEL 34 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 34 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-13 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-03-20 | 2026-03-25 | 2026-03-27 | OVER DUE | 2026-03-05 | DATES MISALIGNED | 2026-03-27 |  |  |  |  | 1 | Kerri Pandolfi | 62 | 26 |  | 0 | 0 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 062-320001TUR | PRE-FAB - LEVEL 34 - Level 34 - Load Centers 150A | 1220 | Level 35 - Load Centers 150A | PF.062 | 9000063 |  | PF.062 | PF.062 | 0% |  |  | 2026-03-06 |  | 2025-10-05 | 121 | TRUE
[8 empty] | 9000063 | 063 | 320001TUR | Stephen Yee | LEVEL 35 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 35 - Load Centers 150A | 7 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-17 | [7 empty] | 55.44 | 3.465 | 4 | 2 | 2026-03-24 | 2026-03-29 | 2026-03-31 | OVER DUE | 2026-03-10 | DATES MISALIGNED | 2026-03-31 |  |  |  |  | 1 | Kerri Pandolfi | 63 | 26 |  | 0 | 0 | 7.92 | 55.44 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 063-320001TUR | PRE-FAB - LEVEL 35 - Level 35 - Load Centers 150A | 1223 | Level 36 - Load Centers 150A | PF.063 | 9000063 |  | PF.063 | PF.063 | 0% |  |  | 2026-03-10 |  | 2025-10-05 | 123 | TRUE
[8 empty] | 9000063 | 064 | 320001TUR | Stephen Yee | LEVEL 36 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 36 - Load Centers 150A | 7 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-19 | [7 empty] | 55.44 | 3.465 | 4 | 2 | 2026-03-26 | 2026-04-01 | 2026-04-03 | OVER DUE | 2026-03-13 | DATES MISALIGNED | 2026-04-03 |  |  |  |  | 1 | Kerri Pandolfi | 64 | 26 |  | 0 | 0 | 7.92 | 55.44 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 064-320001TUR | PRE-FAB - LEVEL 36 - Level 36 - Load Centers 150A | 1257 |  | PF.064 | 9000063 |  | PF.064 | PF.064 | 0% |  |  | 2026-03-12 |  | 2025-10-05 | 125 | TRUE
[8 empty] | 9000030 | 065 | 320001TUR | Stephen Yee | LEVEL B1 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL B1 LAUNDRY/BATHROOM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 15 | Gray | 121 BROADWAY MXD TOWER | Eddie Velez | 2025-09-19 | 2025-09-19 | JOHN CORSO | TRUE | true | TRUE | True | APPROVED | 2.733 | 0.17081 | 1 | 2 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET |  |  | Image 2025-09-30 09-46-35.jpeg |  | 3 | Kerri Pandolfi | 65 | 25 |  | 0.33333 | 5 | 0.1822 | 2.733 | 1.15 | 17.25 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 065-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 LAUNDRY/BATHROOM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | #NO MATCH | #NO MATCH | PF.065 | 9000030 |  | PF.065 | NOT ON PROJECT SCHEDULE | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000030 | 066 | 320001TUR | Stephen Yee | LEVEL 1 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 47 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-26 | 2025-08-21 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8.5634 | 0.53521 | 1 | 2 | 2025-09-02 | 2025-09-03 | 2025-09-05 |  | 2025-10-14 | DATES MISALIGNED | 2025-08-21 |  |  |  |  | 2 | Kerri Pandolfi | 66 | 25 |  | 0.2234 | 10.5 | 0.1822 | 8.5634 | 1.15 | 54.05 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 066-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 99 | LEVEL 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.066 | 9000030 |  | PF.066 | PF.066 | 75% | TRUE |  | 2025-08-19 |  | 2025-10-05 | -24 | TRUE
[8 empty] | 9000030 | 067 | 320001TUR | Stephen Yee | LEVEL 2 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 50 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 9.11 | 0.56938 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | DATES MISALIGNED | 2025-09-03 | [5 empty] | Kerri Pandolfi | 67 | 25 |  | 0 | 0 | 0.1822 | 9.11 | 1.15 | 57.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 067-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 139 | LEVEL 2 CHIEF BOXES (A/V) (2 RECEPTACLES) | PF.067 | 9000030 |  | PF.067 | PF.067 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000030 | 068 | 320001TUR | Stephen Yee | LEVEL 3 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 3 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-10 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-17 | 2025-10-19 | 2025-10-21 |  | 2025-10-27 |  | 2025-10-24 | TRUE |  | X |  |  | Kerri Pandolfi | 68 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 068-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 332 | LEVEL 3 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.068 | 9000030 |  | PF.068 | DELETED | 100% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[8 empty] | 9000030 | 069 | 320001TUR | Stephen Yee | LEVEL 4 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 4 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-07 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-14 | 2025-10-15 | 2025-10-17 |  | 2025-11-03 |  | 2025-10-31 | [5 empty] | Kerri Pandolfi | 69 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 069-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 373 | LEVEL 4 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.069 | 9000030 |  | PF.069 | PF.069 | 0% |  |  | 2025-09-30 |  | 2025-10-05 | 8
[8 empty] | 9000030 | 070 | 320001TUR | Stephen Yee | LEVEL 5 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 5 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-17 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-24 | 2025-10-26 | 2025-10-28 |  | 2025-11-04 |  | 2025-11-07 | [5 empty] | Kerri Pandolfi | 70 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 070-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 401 | LEVEL 5 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.070 | 9000030 |  | PF.070 | PF.070 | 0% |  |  | 2025-10-10 |  | 2025-10-05 | 16
[8 empty] | 9000030 | 071 | 320001TUR | Stephen Yee | LEVEL 6 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 6 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 98 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-26 | 2025-09-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 17.8556 | 1.116 | 2 | 2 | 2025-10-03 | 2025-10-07 | 2025-10-09 |  | 2025-10-28 | DATES MISALIGNED | 2025-09-10 |  |  |  |  | 2 | Kerri Pandolfi | 71 | 25 |  | 0.14796 | 14.5 | 0.1822 | 17.8556 | 1.15 | 112.7 | 0.1822 | 0.9678 | 0.14796 | -0.034241 | 25 | 071-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 175 | LEVEL 6 LEVEL 6 - CHIEF BOXES (A/V) (2 RECEPTACLES) | PF.071 | 9000030 |  | PF.071 | PF.071 | 75% | TRUE |  | 2025-09-19 |  | 2025-10-05 | -1 | TRUE
[8 empty] | 9000030 | 072 | 320001TUR | Stephen Yee | LEVEL 7 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 7 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-21 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-28 | 2025-10-29 | 2025-10-31 |  | 2025-11-07 | DATES MISALIGNED | 2025-11-21 | [5 empty] | Kerri Pandolfi | 72 | 25 |  | 0.5 | 5 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 072-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 482 | LEVEL 7 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.072 | 9000030 |  | PF.072 | PF.072 | 75% |  |  | 2025-10-14 |  | 2025-10-05 | 18
[8 empty] | 9000030 | 073 | 320001TUR | Stephen Yee | LEVEL 8 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 8 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-31 | 2025-11-03 | 2025-11-05 |  | 2025-11-18 | DATES MISALIGNED | 2025-12-01 | [5 empty] | Kerri Pandolfi | 73 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 073-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 515 | LEVEL 8 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.073 | 9000030 |  | PF.073 | PF.073 | 0% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[8 empty] | 9000030 | 074 | 320001TUR | Stephen Yee | LEVEL 9 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 9 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-07 | 2025-11-08 | 2025-11-10 |  | 2025-11-18 | DATES MISALIGNED | 2025-12-08 | [5 empty] | Kerri Pandolfi | 74 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 074-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 557 | LEVEL 9 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.074 | 9000030 |  | PF.074 | PF.074 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[8 empty] | 9000030 | 075 | 320001TUR | Stephen Yee | LEVEL 10 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 10 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-04 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-11 | 2025-11-12 | 2025-11-14 |  | 2025-11-21 | DATES MISALIGNED | 2025-12-12 | [5 empty] | Kerri Pandolfi | 75 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 075-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 587 | LEVEL 10 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.075 | 9000030 |  | PF.075 | PF.075 | 0% |  |  | 2025-10-28 |  | 2025-10-05 | 28
[8 empty] | 9000030 | 076 | 320001TUR | Stephen Yee | LEVEL 11 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 11 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-07 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-14 | 2025-11-17 | 2025-11-19 |  | 2025-11-26 | DATES MISALIGNED | 2025-12-19 | [5 empty] | Kerri Pandolfi | 76 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 076-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 628 | LEVEL 11 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.076 | 9000030 |  | PF.076 | PF.076 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[8 empty] | 9000030 | 077 | 320001TUR | Stephen Yee | LEVEL 12 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 12 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-14 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-21 | 2025-11-22 | 2025-11-24 |  | 2025-12-02 | DATES MISALIGNED | 2025-12-29 | [5 empty] | Kerri Pandolfi | 77 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 077-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 673 | LEVEL 12 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.077 | 9000030 |  | PF.077 | PF.077 | 0% |  |  | 2025-11-07 |  | 2025-10-05 | 36
[8 empty] | 9000030 | 078 | 320001TUR | Stephen Yee | LEVEL 13 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 13 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-18 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-25 | 2025-11-26 | 2025-11-28 |  | 2025-12-05 | DATES MISALIGNED | 2026-01-06 | [5 empty] | Kerri Pandolfi | 78 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 078-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 714 | LEVEL 13 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.078 | 9000030 |  | PF.078 | PF.078 | 0% |  |  | 2025-11-11 |  | 2025-10-05 | 38
[8 empty] | 9000030 | 079 | 320001TUR | Stephen Yee | LEVEL 14 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 14 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-21 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-28 | 2025-12-01 | 2025-12-03 |  | 2025-12-10 | DATES MISALIGNED | 2026-01-12 | [5 empty] | Kerri Pandolfi | 79 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 079-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 762 | LEVEL 14 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.079 | 9000030 |  | PF.079 | PF.079 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[8 empty] | 9000030 | 080 | 320001TUR | Stephen Yee | LEVEL 15 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 15 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-28 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-05 | 2025-12-06 | 2025-12-08 |  | 2025-12-15 | DATES MISALIGNED | 2026-01-16 | [5 empty] | Kerri Pandolfi | 80 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 080-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 786 | LEVEL 15 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.080 | 9000030 |  | PF.080 | PF.080 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[8 empty] | 9000030 | 081 | 320001TUR | Stephen Yee | LEVEL 16 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 16 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-01 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-08 | 2025-12-09 | 2025-12-11 |  | 2025-12-23 | DATES MISALIGNED | 2026-01-26 | [5 empty] | Kerri Pandolfi | 81 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 081-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 835 | LEVEL 16 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.081 | 9000030 |  | PF.081 | PF.081 | 0% |  |  | 2025-11-24 |  | 2025-10-05 | 47
[8 empty] | 9000030 | 082 | 320001TUR | Stephen Yee | LEVEL 17 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 17 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-12 | 2025-12-14 | 2025-12-16 |  | 2025-12-29 | DATES MISALIGNED | 2026-02-02 | [5 empty] | Kerri Pandolfi | 82 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 082-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 886 | LEVEL 17 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.082 | 9000030 |  | PF.082 | PF.082 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[8 empty] | 9000030 | 083 | 320001TUR | Stephen Yee | LEVEL 18 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 18 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-09 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-16 | 2025-12-17 | 2025-12-19 |  | 2026-01-02 | DATES MISALIGNED | 2026-02-06 | [5 empty] | Kerri Pandolfi | 83 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 083-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 925 | LEVEL 18 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.083 | 9000030 |  | PF.083 | PF.083 | 0% |  |  | 2025-12-02 |  | 2025-10-05 | 53
[8 empty] | 9000030 | 084 | 320001TUR | Stephen Yee | LEVEL 19 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 19 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-12 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-19 | 2025-12-22 | 2025-12-24 |  | 2026-01-07 | DATES MISALIGNED | 2026-02-13 | [5 empty] | Kerri Pandolfi | 84 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 084-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 963 | LEVEL 19 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.084 | 9000030 |  | PF.084 | PF.084 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[8 empty] | 9000030 | 085 | 320001TUR | Stephen Yee | LEVEL 20 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 20 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-19 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-26 | 2025-12-28 | 2025-12-30 |  | 2026-01-12 | DATES MISALIGNED | 2026-02-23 | [5 empty] | Kerri Pandolfi | 85 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 085-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1008 | LEVEL 20 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.085 | 9000030 |  | PF.085 | PF.085 | 0% |  |  | 2025-12-12 |  | 2025-10-05 | 61
[8 empty] | 9000030 | 086 | 320001TUR | Stephen Yee | LEVEL 21 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 21 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-26 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-02 | 2026-01-03 | 2026-01-05 |  | 2026-01-15 | DATES MISALIGNED | 2026-03-02 | [5 empty] | Kerri Pandolfi | 86 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 086-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1051 | LEVEL 21 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.086 | 9000030 |  | PF.086 | PF.086 | 0% |  |  | 2025-12-19 |  | 2025-10-05 | 66
[8 empty] | 9000030 | 087 | 320001TUR | Stephen Yee | LEVEL 22 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 22 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-29 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-05 | 2026-01-06 | 2026-01-08 |  | 2026-01-15 | DATES MISALIGNED | 2026-03-06 | [5 empty] | Kerri Pandolfi | 87 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 087-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1092 | LEVEL 22 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.087 | 9000030 |  | PF.087 | PF.087 | 0% |  |  | 2025-12-22 |  | 2025-10-05 | 67
[8 empty] | 9000030 | 088 | 320001TUR | Stephen Yee | LEVEL 23 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 23 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-09 | 2026-01-11 | 2026-01-13 |  | 2026-01-21 | DATES MISALIGNED | 2026-03-13 | [5 empty] | Kerri Pandolfi | 88 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 088-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1138 | LEVEL 23 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.088 | 9000030 |  | PF.088 | PF.088 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[8 empty] | 9000030 | 089 | 320001TUR | Stephen Yee | LEVEL 24 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 24 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-06 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-13 | 2026-01-14 | 2026-01-16 |  | 2026-01-26 | DATES MISALIGNED | 2026-03-20 | [5 empty] | Kerri Pandolfi | 89 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 089-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1180 | LEVEL 24 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.089 | 9000030 |  | PF.089 | PF.089 | 0% |  |  | 2025-12-30 |  | 2025-10-05 | 73
[8 empty] | 9000030 | 090 | 320001TUR | Stephen Yee | LEVEL 25 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 25 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-12 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-19 | 2026-01-20 | 2026-01-22 |  | 2026-02-06 | DATES MISALIGNED | 2026-03-27 | [5 empty] | Kerri Pandolfi | 90 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 090-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1224 | LEVEL 25 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.090 | 9000030 |  | PF.090 | PF.090 | 0% |  |  | 2026-01-05 |  | 2025-10-05 | 77
[8 empty] | 9000030 | 091 | 320001TUR | Stephen Yee | LEVEL 26 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 26 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-04-06 | [5 empty] | Kerri Pandolfi | 91 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 091-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1267 | LEVEL 26 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.091 | 9000030 |  | PF.091 | PF.091 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[8 empty] | 9000030 | 092 | 320001TUR | Stephen Yee | LEVEL 27 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 27 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-20 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-27 | 2026-01-28 | 2026-01-30 |  | 2026-02-06 | DATES MISALIGNED | 2026-04-10 | [5 empty] | Kerri Pandolfi | 92 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 092-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1306 | LEVEL 27 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.092 | 9000030 |  | PF.092 | PF.092 | 0% |  |  | 2026-01-13 |  | 2025-10-05 | 83
[8 empty] | 9000030 | 093 | 320001TUR | Stephen Yee | LEVEL 28 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 28 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-23 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-30 | 2026-02-02 | 2026-02-04 |  | 2026-02-06 | DATES MISALIGNED | 2026-04-17 | [5 empty] | Kerri Pandolfi | 93 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 093-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1349 | LEVEL 28 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.093 | 9000030 |  | PF.093 | PF.093 | 0% |  |  | 2026-01-16 |  | 2025-10-05 | 86
[8 empty] | 9000030 | 094 | 320001TUR | Stephen Yee | LEVEL 29 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 29 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-04-27 | [5 empty] | Kerri Pandolfi | 94 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 094-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1390 | LEVEL 29 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.094 | 9000030 |  | PF.094 | PF.094 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[8 empty] | 9000030 | 095 | 320001TUR | Stephen Yee | LEVEL 30 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 30 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-05-04 | [5 empty] | Kerri Pandolfi | 95 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 095-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1430 | LEVEL 30 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.095 | 9000030 |  | PF.095 | PF.095 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[8 empty] | 9000030 | 096 | 320001TUR | Stephen Yee | LEVEL 31 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 31 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-05-11 | [5 empty] | Kerri Pandolfi | 96 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 096-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1469 | LEVEL 31 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.096 | 9000030 |  | PF.096 | PF.096 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[8 empty] | 9000030 | 097 | 320001TUR | Stephen Yee | LEVEL 32 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 32 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-05-18 | [5 empty] | Kerri Pandolfi | 97 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 097-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1511 | LEVEL 32 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.097 | 9000030 |  | PF.097 | PF.097 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[8 empty] | 9000030 | 098 | 320001TUR | Stephen Yee | LEVEL 33 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 33 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-05-26 | [5 empty] | Kerri Pandolfi | 98 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 098-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1548 | LEVEL 33 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.098 | 9000030 |  | PF.098 | PF.098 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[8 empty] | 9000030 | 099 | 320001TUR | Stephen Yee | LEVEL 34 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 34 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-20 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-27 | 2026-03-01 | 2026-03-03 |  | 2026-03-10 | DATES MISALIGNED | 2026-06-02 | [5 empty] | Kerri Pandolfi | 99 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 099-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1580 | LEVEL 34 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.099 | 9000030 |  | PF.099 | PF.099 | 0% |  |  | 2026-02-13 |  | 2025-10-05 | 106
[8 empty] | 9000040 | 393 | 320001TUR | Stephen Yee | LEVEL 39 | VFD ASSEMBLY (1) | ROOFTOP DISCONNECTS | 25 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-13 | [7 empty] | 75 | 4.6875 | 5 | 2 | 2026-05-20 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | [7 empty] | Kerri Pandolfi | 393 | 26 |  | 0 | 0 | 3 | 75 | 4.1 | 102.5 | 3 | 1.1 | 0 | -3 | 26 | 393-320001TUR | PRE-FAB - LEVEL 39 - ROOFTOP DISCONNECTS | 1976 | INSTALL - LEVEL 40 DISCONNECTS | PF.393 | 9000040 |  | PF.393 | PF.393 | 0% |  |  | 2026-05-06 |  | 2025-10-05 | 164
[8 empty] | 9000062 | 394 | 320001TUR | Stephen Yee | LEVEL 1 | PIPE NIPPLES | 5" and 4" RIGID NIPPLES | 24 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-23 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 21.6 | 2.7 | 3 | 1 | 2025-06-30 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-35-52.jpeg |  | 8 | Kerri Pandolfi | 394 | 25 |  | 0.66667 | 16 | 0.9 | 21.6 | 1 | 24 | 0.9 | 0.1 | 0.66667 | -0.23333 | 25 | 394-320001TUR | PRE-FAB - LEVEL 1 - 5" and 4" RIGID NIPPLES | #NO MATCH | #NO MATCH | PF.394 | 9000062 |  | PF.394 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-16 |  | 2025-10-05 | -70
[8 empty] | 9000056 | 395 | 320001TUR | Stephen Yee | LEVEL 13 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-13 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-06-20 | 2025-06-21 | 2025-06-23 |  | 2025-06-23 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-06-23 07-25-29.jpeg |  |  | Kerri Pandolfi | 395 | 25 |  | 0.17647 | 3 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.17647 | -0.17353 | 25 | 395-320001TUR | PRE-FAB - LEVEL 13 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.395 | 9000056 |  | PF.395 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-06 |  | 2025-10-05 | -76
[8 empty] | 9000056 | 396 | 320001TUR | Stephen Yee | LEVEL 14 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-13 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-06-20 | 2025-06-23 | 2025-06-25 |  | 2025-06-25 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-06-25 13-32-13.jpeg |  | 9 | Kerri Pandolfi | 396 | 25 |  | 0.58824 | 10 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 396-320001TUR | PRE-FAB - LEVEL 14 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.396 | 9000056 |  | PF.396 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-06 |  | 2025-10-05 | -76
[8 empty] | 9000056 | 397 | 320001TUR | Stephen Yee | LEVEL 15 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-36-22.jpeg |  | 14 | Kerri Pandolfi | 397 | 25 |  | 0.11765 | 2 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.11765 | -0.23235 | 25 | 397-320001TUR | PRE-FAB - LEVEL 15 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.397 | 9000056 |  | PF.397 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-18 |  | 2025-10-05 | -68
[8 empty] | 9000056 | 398 | 320001TUR | Stephen Yee | LEVEL 16 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-36-40.jpeg |  | 14 | Kerri Pandolfi | 398 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 398-320001TUR | PRE-FAB - LEVEL 16 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.398 | 9000056 |  | PF.398 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-18 |  | 2025-10-05 | -68
[8 empty] | 9000056 | 399 | 320001TUR | Stephen Yee | LEVEL 17 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-36-58.jpeg |  | 8 | Kerri Pandolfi | 399 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 399-320001TUR | PRE-FAB - LEVEL 17 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.399 | 9000056 |  | PF.399 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-18 |  | 2025-10-05 | -68
[8 empty] | 9000056 | 400 | 320001TUR | Stephen Yee | LEVEL 18 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-37-25.jpeg |  | 8 | Kerri Pandolfi | 400 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 400-320001TUR | PRE-FAB - LEVEL 18 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.400 | 9000056 |  | PF.400 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-18 |  | 2025-10-05 | -68
[8 empty] | 9000056 | 401 | 320001TUR | Stephen Yee | LEVEL 19 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-07 07-32-09.jpeg |  | 8 | Kerri Pandolfi | 401 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 401-320001TUR | PRE-FAB - LEVEL 19 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.401 | 9000056 |  | PF.401 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-06-18 |  | 2025-10-05 | -68
[8 empty] | 9000056 | 402 | 320001TUR | Stephen Yee | LEVEL 20 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-07 07-32-28.jpeg |  | 8 | Kerri Pandolfi | 402 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 402-320001TUR | PRE-FAB - LEVEL 20 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.402 | 9000056 |  | PF.402 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-06-18 |  | 2025-10-05 | -68
[8 empty] | 9000220 | 403 | 320001TUR | Stephen Yee | MULTI LEVEL | TEMPS (SMALL) | temp power quad outlets | 31 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-03 | 2025-07-11 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 31 | 3.875 | 4 | 1 | 2025-07-10 | 2025-07-16 | 2025-07-18 |  | 2025-07-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-16 10-59-22.jpeg |  | 5 | Kerri Pandolfi | 403 | 25 |  | 1.129 | 35 | 1 | 31 | 2 | 62 | 1 | 1 | 1 | 0 | 25 | 403-320001TUR | PRE-FAB - MULTI LEVEL - temp power quad outlets | #NO MATCH | #NO MATCH | PF.403 | 9000220 |  | PF.403 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-26 |  | 2025-10-05 | -62
[8 empty] | 9000220 | 404 | 320001TUR | Stephen Yee | MULTI LEVEL | TEMPS (SMALL) | temp power quad outlets | 31 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-16 | 2025-07-11 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 31 | 3.875 | 4 | 1 | 2025-07-23 | 2025-07-29 | 2025-07-31 |  | 2025-08-05 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-25 10-26-49.jpeg |  | 6 | Kerri Pandolfi | 404 | 25 |  | 0.35484 | 11 | 1 | 31 | 2 | 62 | 1 | 1 | 0.35484 | -0.64516 | 25 | 404-320001TUR | PRE-FAB - MULTI LEVEL - temp power quad outlets | #NO MATCH | #NO MATCH | PF.404 | 9000220 |  | PF.404 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-09 |  | 2025-10-05 | -53
[8 empty] | 9000056 | 405 | 320001TUR | Stephen Yee | LEVEL 21 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-21-52.jpeg |  | 8 | Kerri Pandolfi | 405 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 405-320001TUR | PRE-FAB - LEVEL 21 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.405 | 9000056 |  | PF.405 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[8 empty] | 9000056 | 406 | 320001TUR | Stephen Yee | LEVEL 22 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-22-14.jpeg |  | 8 | Kerri Pandolfi | 406 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 406-320001TUR | PRE-FAB - LEVEL 22 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.406 | 9000056 |  | PF.406 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[8 empty] | 9000056 | 407 | 320001TUR | Stephen Yee | LEVEL 23 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-22-39.jpeg |  | 8 | Kerri Pandolfi | 407 | 25 |  | 0 | 0 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0 | -0.35 | 25 | 407-320001TUR | PRE-FAB - LEVEL 23 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.407 | 9000056 |  | PF.407 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[8 empty] | 9000056 | 408 | 320001TUR | Stephen Yee | LEVEL 24 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-23-07.jpeg |  | 8 | Kerri Pandolfi | 408 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 408-320001TUR | PRE-FAB - LEVEL 24 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.408 | 9000056 |  | PF.408 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[8 empty] | 9000056 | 409 | 320001TUR | Stephen Yee | LEVEL 25 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-23-39.jpeg |  | 8 | Kerri Pandolfi | 409 | 25 |  | 0.70588 | 12 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 409-320001TUR | PRE-FAB - LEVEL 25 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.409 | 9000056 |  | PF.409 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[8 empty] | 9000056 | 410 | 320001TUR | Stephen Yee | LEVEL 26 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-46-21.jpeg |  | 9 | Kerri Pandolfi | 410 | 25 |  | 1.1176 | 19 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 410-320001TUR | PRE-FAB - LEVEL 26 - DECK SLEEVES | 183 |  | PF.410 | 9000056 |  | PF.410 | PF.410 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 411 | 320001TUR | Stephen Yee | LEVEL 27 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-46-45.jpeg |  | 9 | Kerri Pandolfi | 411 | 25 |  | 0.29412 | 5 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.29412 | -0.055882 | 25 | 411-320001TUR | PRE-FAB - LEVEL 27 - DECK SLEEVES | 184 |  | PF.411 | 9000056 |  | PF.411 | PF.411 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 412 | 320001TUR | Stephen Yee | LEVEL 28 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-47-16.jpeg |  | 9 | Kerri Pandolfi | 412 | 25 |  | 0.058824 | 1 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.058824 | -0.29118 | 25 | 412-320001TUR | PRE-FAB - LEVEL 28 - DECK SLEEVES | 185 |  | PF.412 | 9000056 |  | PF.412 | PF.412 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 413 | 320001TUR | Stephen Yee | LEVEL 29 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-45-47.jpeg |  | 9 | Kerri Pandolfi | 413 | 25 |  | 0.058824 | 1 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.058824 | -0.29118 | 25 | 413-320001TUR | PRE-FAB - LEVEL 29 - DECK SLEEVES | 186 |  | PF.413 | 9000056 |  | PF.413 | PF.413 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 414 | 320001TUR | Stephen Yee | LEVEL 30 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-44-39.jpeg |  | 9 | Kerri Pandolfi | 414 | 25 |  | 0 | 0 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0 | -0.35 | 25 | 414-320001TUR | PRE-FAB - LEVEL 30 - DECK SLEEVES | 187 |  | PF.414 | 9000056 |  | PF.414 | PF.414 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 415 | 320001TUR | Stephen Yee | LEVEL 31 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-49-30.jpeg |  | 9 | Kerri Pandolfi | 415 | 25 |  | 0.35294 | 6 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 415-320001TUR | PRE-FAB - LEVEL 31 - DECK SLEEVES | 335 |  | PF.415 | 9000056 |  | PF.415 | PF.415 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 416 | 320001TUR | Stephen Yee | LEVEL 32 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-49-53.jpeg |  | 9 | Kerri Pandolfi | 416 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 416-320001TUR | PRE-FAB - LEVEL 32 - DECK SLEEVES | 336 |  | PF.416 | 9000056 |  | PF.416 | PF.416 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 417 | 320001TUR | Stephen Yee | LEVEL 33 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-50-21.jpeg |  | 9 | Kerri Pandolfi | 417 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 417-320001TUR | PRE-FAB - LEVEL 33 - DECK SLEEVES | 337 |  | PF.417 | 9000056 |  | PF.417 | PF.417 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 418 | 320001TUR | Stephen Yee | LEVEL 34 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-50-55.jpeg |  | 9 | Kerri Pandolfi | 418 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 418-320001TUR | PRE-FAB - LEVEL 34 - DECK SLEEVES | 338 |  | PF.418 | 9000056 |  | PF.418 | PF.418 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 419 | 320001TUR | Stephen Yee | LEVEL 35 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-51-17.jpeg |  | 9 | Kerri Pandolfi | 419 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 419-320001TUR | PRE-FAB - LEVEL 35 - DECK SLEEVES | 339 |  | PF.419 | 9000056 |  | PF.419 | PF.419 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000056 | 420 | 320001TUR | Stephen Yee | LEVEL 36 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-07-07 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 |  | 2025-11-24 |  |  | Image 2025-09-26 09-44-02.jpeg |  | 2 | Kerri Pandolfi | 420 | 25 |  | 0.51471 | 8.75 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 420-320001TUR | PRE-FAB - LEVEL 36 - DECK SLEEVES | 476 |  | PF.420 | 9000056 |  | PF.420 | PF.420 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000056 | 421 | 320001TUR | Stephen Yee | LEVEL 37 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-07-07 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 |  | 2025-11-24 |  |  | Image 2025-09-26 09-44-29.jpeg |  | 2 | Kerri Pandolfi | 421 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 421-320001TUR | PRE-FAB - LEVEL 37 - DECK SLEEVES | 477 |  | PF.421 | 9000056 |  | PF.421 | PF.421 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000056 | 422 | 320001TUR | Stephen Yee | LEVEL 38 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-07-07 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 |  | 2025-11-24 |  |  | Image 2025-09-26 09-45-15.jpeg |  | 2 | Kerri Pandolfi | 422 | 25 |  | 0.44118 | 7.5 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 422-320001TUR | PRE-FAB - LEVEL 38 - DECK SLEEVES | 478 |  | PF.422 | 9000056 |  | PF.422 | PF.422 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000056 | 423 | 320001TUR | Stephen Yee | LEVEL 39 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-07-07 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 |  | 2025-11-24 |  |  | Image 2025-09-26 09-45-42.jpeg |  | 2 | Kerri Pandolfi | 423 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 423-320001TUR | PRE-FAB - LEVEL 39 - DECK SLEEVES | 479 |  | PF.423 | 9000056 |  | PF.423 | PF.423 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000056 | 424 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 30 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-03 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 10.5 | 1.3125 | 2 | 1 | 2025-07-10 | 2025-07-12 | 2025-07-14 |  | 2025-07-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-11 11-14-44.jpeg |  | 5 | Kerri Pandolfi | 424 | 25 |  | 0 | 0 | 0.35 | 10.5 |  | 0 | 0.35 | -0.35 | 0 | -0.35 | 25 | 424-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | #NO MATCH | #NO MATCH | PF.424 | 9000056 |  | PF.424 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-26 |  | 2025-10-05 | -62
[8 empty] | 9000056 | 425 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 30 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 10.5 | 1.3125 | 2 | 1 | 2025-08-08 | 2025-08-12 | 2025-08-14 |  | 2025-08-18 |  | 2025-08-15 | TRUE |  | Image 2025-08-13 12-43-01.jpeg |  | 8 | Kerri Pandolfi | 425 | 25 |  | 0.26667 | 8 | 0.35 | 10.5 |  | 0 | 0.35 | -0.35 | 0.26667 | -0.083333 | 25 | 425-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | 86 |  | PF.425 | 9000056 |  | PF.425 | PF.425 | 100% | TRUE |  | 2025-07-25 |  | 2025-10-05 | -41 | TRUE
[8 empty] | 9000056 | 426 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 30 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 10.5 | 1.3125 | 2 | 1 | 2025-08-08 | 2025-08-12 | 2025-08-14 |  | 2025-09-22 |  | 2025-09-19 | TRUE |  | Image 2025-08-13 13-17-41.jpeg |  | 8 | Kerri Pandolfi | 426 | 25 |  | 0.26667 | 8 | 0.35 | 10.5 |  | 0 | 0.35 | -0.35 | 0.26667 | -0.083333 | 25 | 426-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | 196 |  | PF.426 | 9000056 |  | PF.426 | PF.426 | 100% | TRUE |  | 2025-07-25 |  | 2025-10-05 | -41 | TRUE
[8 empty] | 9000056 | 427 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 28 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 9.8 | 1.225 | 2 | 1 | 2025-08-08 | 2025-08-12 | 2025-08-14 |  | 2025-10-27 |  | 2025-10-24 | TRUE |  | Image 2025-08-13 13-19-46.jpeg |  | 8 | Kerri Pandolfi | 427 | 25 |  | 0.57143 | 16 | 0.35 | 9.8 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 427-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | 307 |  | PF.427 | 9000056 |  | PF.427 | PF.427 | 100% | TRUE |  | 2025-07-25 |  | 2025-10-05 | -41 | TRUE
[8 empty] | 9000056 | 428 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 11 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3.85 | 0.48125 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-12-01 |  | 2025-12-02 | TRUE |  | Image 2025-08-13 13-33-53.jpeg |  | 8 | Kerri Pandolfi | 428 | 25 |  | 0.45455 | 5 | 0.35 | 3.85 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 428-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | 511 |  | PF.428 | 9000056 |  | PF.428 | PF.428 | 100% | TRUE |  | 2025-07-28 |  | 2025-10-05 | -40 | TRUE
[8 empty] | 9000060 | 429 | 320001TUR | Stephen Yee | LEVEL 21 | PANEL ASSEMBLY (STRUT BUILD) | PANEL HPH21 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-16 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-23 | 2026-01-24 | 2026-01-26 |  | 2026-01-26 |  | 2026-01-29 | [5 empty] | Kerri Pandolfi | 429 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 429-320001TUR | PRE-FAB - LEVEL 21 - PANEL HPH21 | 867 | INSTALL - LEVEL 21 - DISTRIBUTION EQUIP | PF.429 | 9000060 |  | PF.429 | PF.429 | 0% |  |  | 2026-01-09 |  | 2025-10-05 | 81
[8 empty] | 9000060 | 430 | 320001TUR | Stephen Yee | LEVEL 24 | PANEL ASSEMBLY (STRUT BUILD) | PANEL EPH24,EPL24 | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-02-17 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2026-02-24 | 2026-02-25 | 2026-02-27 |  | 2026-02-27 |  | 2026-03-04 | [5 empty] | Kerri Pandolfi | 430 | 26 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 26 | 430-320001TUR | PRE-FAB - LEVEL 24 - PANEL EPH24,EPL24 | 1052 | LEVEL 24 - TIER 2 - PANEL ASSEMBLY (STRUT BUILD) | PF.430 | 9000060 |  | PF.430 | PF.430 | 0% |  |  | 2026-02-10 |  | 2025-10-05 | 103
[8 empty] | 9000060 | 431 | 320001TUR | Stephen Yee | LEVEL 25 | PANEL ASSEMBLY (STRUT BUILD) | PANEL HPH25 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-02-16 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-23 | 2026-02-24 | 2026-02-26 |  | 2026-02-26 |  | 2026-03-03 | [5 empty] | Kerri Pandolfi | 431 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 431-320001TUR | PRE-FAB - LEVEL 25 - PANEL HPH25 | 1047 | LEVEL 25 - TIER 2 - PANEL PL25 | PF.431 | 9000060 |  | PF.431 | PF.431 | 0% |  |  | 2026-02-09 |  | 2025-10-05 | 102
[8 empty] | 9000060 | 432 | 320001TUR | Stephen Yee | LEVEL 33 | PANEL ASSEMBLY (STRUT BUILD) | PANEL HPH33 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-01 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-05-08 | 2026-05-11 | 2026-05-13 |  | 2026-05-13 |  | 2026-05-18 | [5 empty] | Kerri Pandolfi | 432 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 432-320001TUR | PRE-FAB - LEVEL 33 - PANEL HPH33 | 1506 | INSTALL - LEVEL 33 - DISTRIBUTION EQUIP | PF.432 | 9000060 |  | PF.432 | PF.432 | 0% |  |  | 2026-04-24 |  | 2025-10-05 | 156
[8 empty] | 9000060 | 433 | 320001TUR | Stephen Yee | LEVEL 34 | PANEL ASSEMBLY (STRUT BUILD) | PANELS EPH34,EPL34 | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-04-28 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2026-05-05 | 2026-05-06 | 2026-05-08 |  | 2026-05-08 |  | 2026-05-13 | [5 empty] | Kerri Pandolfi | 433 | 26 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 26 | 433-320001TUR | PRE-FAB - LEVEL 34 - PANELS EPH34,EPL34 | 1468 | LEVEL 34 - TIER 2 - PANEL PL34 | PF.433 | 9000060 |  | PF.433 | PF.433 | 0% |  |  | 2026-04-21 |  | 2025-10-05 | 153
[8 empty] | 9000056 | 434 | 320001TUR | Stephen Yee | LEVEL 18 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC X 8" LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-01 | 2025-08-04 | 2025-08-06 |  | 2025-08-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-13-22.jpeg |  | 9 | Kerri Pandolfi | 434 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 434-320001TUR | PRE-FAB - LEVEL 18 - 6" PVC X 8" LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.434 | 9000056 |  | PF.434 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[8 empty] | 9000056 | 435 | 320001TUR | Stephen Yee | LEVEL 19 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC X 8" LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-01 | 2025-08-04 | 2025-08-06 |  | 2025-08-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-13-45.jpeg |  | 9 | Kerri Pandolfi | 435 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 435-320001TUR | PRE-FAB - LEVEL 19 - 6" PVC X 8" LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.435 | 9000056 |  | PF.435 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[8 empty] | 9000056 | 436 | 320001TUR | Stephen Yee | LEVEL 20 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC X 8" LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-01 | 2025-08-04 | 2025-08-06 |  | 2025-08-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-14-11.jpeg |  | 9 | Kerri Pandolfi | 436 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 436-320001TUR | PRE-FAB - LEVEL 20 - 6" PVC X 8" LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.436 | 9000056 |  | PF.436 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[8 empty] | 9000056 | 437 | 320001TUR | Stephen Yee | LEVEL 21 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-01 | 2025-08-04 | 2025-08-06 |  | 2025-08-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-14-32.jpeg |  | 9 | Kerri Pandolfi | 437 | 25 |  | 0.4375 | 3.5 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.4375 | -0.5625 | 25 | 437-320001TUR | PRE-FAB - LEVEL 21 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.437 | 9000056 |  | PF.437 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[8 empty] | 9000056 | 438 | 320001TUR | Stephen Yee | LEVEL 22 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-08 | 2025-08-09 | 2025-08-11 |  | 2025-08-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-18-00.jpeg |  | 9 | Kerri Pandolfi | 438 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 438-320001TUR | PRE-FAB - LEVEL 22 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.438 | 9000056 |  | PF.438 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-25 |  | 2025-10-05 | -41
[8 empty] | 9000056 | 439 | 320001TUR | Stephen Yee | LEVEL 23 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-08 | 2025-08-09 | 2025-08-11 |  | 2025-08-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-18-25.jpeg |  | 9 | Kerri Pandolfi | 439 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 439-320001TUR | PRE-FAB - LEVEL 23 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.439 | 9000056 |  | PF.439 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-25 |  | 2025-10-05 | -41
[8 empty] | 9000056 | 440 | 320001TUR | Stephen Yee | LEVEL 24 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-08 | 2025-08-09 | 2025-08-11 |  | 2025-08-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-18-45.jpeg |  | 9 | Kerri Pandolfi | 440 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 440-320001TUR | PRE-FAB - LEVEL 24 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.440 | 9000056 |  | PF.440 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-25 |  | 2025-10-05 | -41
[8 empty] | 9000056 | 441 | 320001TUR | Stephen Yee | LEVEL 25 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-08 | 2025-08-09 | 2025-08-11 |  | 2025-08-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-19-16.jpeg |  | 9 | Kerri Pandolfi | 441 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 441-320001TUR | PRE-FAB - LEVEL 25 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.441 | 9000056 |  | PF.441 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-25 |  | 2025-10-05 | -41
[8 empty] | 9000056 | 442 | 320001TUR | Stephen Yee | LEVEL 26 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-28-20.jpeg |  | 9 | Kerri Pandolfi | 442 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 442-320001TUR | PRE-FAB - LEVEL 26 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.442 | 9000056 |  | PF.442 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[8 empty] | 9000056 | 443 | 320001TUR | Stephen Yee | LEVEL 27 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-28-39.jpeg |  | 9 | Kerri Pandolfi | 443 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 443-320001TUR | PRE-FAB - LEVEL 27 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.443 | 9000056 |  | PF.443 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[8 empty] | 9000056 | 444 | 320001TUR | Stephen Yee | LEVEL 28 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-28-59.jpeg |  | 9 | Kerri Pandolfi | 444 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 444-320001TUR | PRE-FAB - LEVEL 28 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.444 | 9000056 |  | PF.444 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[8 empty] | 9000056 | 445 | 320001TUR | Stephen Yee | LEVEL 29 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-29-17.jpeg |  | 9 | Kerri Pandolfi | 445 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 445-320001TUR | PRE-FAB - LEVEL 29 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.445 | 9000056 |  | PF.445 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[8 empty] | 9000056 | 446 | 320001TUR | Stephen Yee | LEVEL 30 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-15 | 2025-08-17 | 2025-08-19 |  | 2025-08-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-32-39.jpeg |  | 9 | Kerri Pandolfi | 446 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 446-320001TUR | PRE-FAB - LEVEL 30 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.446 | 9000056 |  | PF.446 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-01 |  | 2025-10-05 | -36
[8 empty] | 9000056 | 447 | 320001TUR | Stephen Yee | LEVEL 31 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-15 | 2025-08-17 | 2025-08-19 |  | 2025-08-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-32-01.jpeg |  | 9 | Kerri Pandolfi | 447 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 447-320001TUR | PRE-FAB - LEVEL 31 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.447 | 9000056 |  | PF.447 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-01 |  | 2025-10-05 | -36
[8 empty] | 9000056 | 448 | 320001TUR | Stephen Yee | LEVEL 32 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-15 | 2025-08-17 | 2025-08-19 |  | 2025-08-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-31-35.jpeg |  | 9 | Kerri Pandolfi | 448 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 448-320001TUR | PRE-FAB - LEVEL 32 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.448 | 9000056 |  | PF.448 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-01 |  | 2025-10-05 | -36
[8 empty] | 9000056 | 449 | 320001TUR | Stephen Yee | LEVEL 33 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-15 | 2025-08-17 | 2025-08-19 |  | 2025-08-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-31-07.jpeg |  | 9 | Kerri Pandolfi | 449 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 449-320001TUR | PRE-FAB - LEVEL 33 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.449 | 9000056 |  | PF.449 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-01 |  | 2025-10-05 | -36
[8 empty] | 9000056 | 450 | 320001TUR | Stephen Yee | LEVEL 34 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-12 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-30-45.jpeg |  |  | Kerri Pandolfi | 450 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 450-320001TUR | PRE-FAB - LEVEL 34 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.450 | 9000056 |  | PF.450 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[8 empty] | 9000056 | 451 | 320001TUR | Stephen Yee | LEVEL 35 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-12 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-30-09.jpeg |  |  | Kerri Pandolfi | 451 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 451-320001TUR | PRE-FAB - LEVEL 35 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.451 | 9000056 |  | PF.451 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[8 empty] | 9000056 | 452 | 320001TUR | Stephen Yee | LEVEL 36 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-12 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-29-49.jpeg |  |  | Kerri Pandolfi | 452 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 452-320001TUR | PRE-FAB - LEVEL 36 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.452 | 9000056 |  | PF.452 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[8 empty] | 9000056 | 453 | 320001TUR | Stephen Yee | LEVEL 37 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET |  |  | Image 2025-08-13 13-25-13.jpeg |  | 9 | Kerri Pandolfi | 453 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 453-320001TUR | PRE-FAB - LEVEL 37 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.453 | 9000056 |  | PF.453 | NOT ON PROJECT SCHEDULE | 99% | TRUE |  | 2025-07-28 |  | 2025-10-05 | -40 | TRUE
[8 empty] | 9000056 | 454 | 320001TUR | Stephen Yee | LEVEL 38 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-04 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-27 |  | NOT LINKED IN PROJECT SCHEDULE SHEET |  |  | Image 2025-08-13 13-25-57.jpeg |  | 9 | Kerri Pandolfi | 454 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 454-320001TUR | PRE-FAB - LEVEL 38 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.454 | 9000056 |  | PF.454 | NOT ON PROJECT SCHEDULE | 99% | TRUE |  | 2025-07-28 |  | 2025-10-05 | -40 | TRUE
[8 empty] | 9000056 | 455 | 320001TUR | Stephen Yee | LEVEL 39 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-04 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-27 |  | NOT LINKED IN PROJECT SCHEDULE SHEET |  |  | Image 2025-08-13 13-27-15.jpeg |  | 9 | Kerri Pandolfi | 455 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 455-320001TUR | PRE-FAB - LEVEL 39 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.455 | 9000056 |  | PF.455 | NOT ON PROJECT SCHEDULE | 99% | TRUE |  | 2025-07-28 |  | 2025-10-05 | -40 | TRUE
[8 empty] | 9000150 | 456 | 320001TUR | Stephen Yee | LEVEL 1 | IN-WALL ASSEMBLIES (AV) | shallow box, beam mockup | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-04 | james campbell | TRUE | true | TRUE | True | APPROVED | 0.27316 | 0.034145 | 1 | 1 | 2025-08-01 | 2025-08-02 | 2025-08-04 |  | 2025-08-04 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 07-22-27.jpeg |  |  | Kerri Pandolfi | 456 | 25 |  | 0 | 0 | 0.27316 | 0.27316 | 0.4 | 0.4 | 0.27316 | 0.12684 | 0 | -0.27316 | 25 | 456-320001TUR | PRE-FAB - LEVEL 1 - shallow box, beam mockup | #NO MATCH | #NO MATCH | PF.456 | 9000150 |  | PF.456 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[8 empty] | 9000220 | 457 | 320001TUR | Stephen Yee | MULTI LEVEL | TEMPS (SMALL) | SPIDER BOXES / 15FT - FEMAILE WHIPS | 40 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo, Doug Durand | 2025-07-29 | 2025-08-13 | Arthur Mayo | TRUE | true | TRUE | True | APPROVED | 40 | 5 | 5 | 1 | 2025-08-05 | 2025-08-12 | 2025-08-14 |  | 2025-08-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-15 06-42-52.jpeg |  | 14 | Kerri Pandolfi | 457 | 25 |  | 0.4375 | 17.5 | 1 | 40 | 2 | 80 | 1 | 1 | 0.4375 | -0.5625 | 25 | 457-320001TUR | PRE-FAB - MULTI LEVEL - SPIDER BOXES / 15FT - FEMAILE WHIPS | #NO MATCH | #NO MATCH | PF.457 | 9000220 |  | PF.457 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[8 empty] | 9000220 | 458 | 320001TUR | Stephen Yee | SITE | TEMPS (LARGE) | TEMP PANELS | 2 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-13 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 16 | 2 | 2 | 1 | 2025-08-15 | 2025-08-19 | 2025-08-21 |  | 2025-08-21 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-18 13-07-35.jpeg |  |  | Kerri Pandolfi | 458 | 25 |  | 17.75 | 35.5 | 8 | 16 |  | 0 | 8 | -8 | 8 | 0 | 25 | 458-320001TUR | PRE-FAB - SITE - TEMP PANELS | #NO MATCH | #NO MATCH | PF.458 | 9000220 |  | PF.458 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-08-01 |  | 2025-10-05 | -36
[8 empty] | 9000104 | 459 | 320001TUR | Stephen Yee | LEVEL 3 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 2 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-26 | 2025-08-15 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.0005814 | 1 | 430 | 2025-09-02 | 2025-09-03 | 2025-09-05 |  | 2025-09-05 |  | 2025-11-14 | TRUE |  | 2025-09-02 |  | 14 | Kerri Pandolfi | 459 | 25 |  | 2 | 4 | 1 | 2 | 1.8 | 3.6 | 1 | 0.8 | 1 | 0 | 25 | 459-320001TUR | PRE-FAB - LEVEL 3 - HILTI WALL SLEEVES | 426 | INSTALL - LEVEL 3 - HILTI WALL SLEEVES | PF.459 | 9000104 |  | PF.459 | PF.459 | 100% | TRUE |  | 2025-08-19 |  | 2025-10-05 | -24 | TRUE
[8 empty] | 9000104 | 460 | 320001TUR | Stephen Yee | LEVEL 4 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0016722 | 1 | 299 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-11-21 | TRUE |  | Image 2025-09-19 10-24-31.jpeg |  | 2 | Kerri Pandolfi | 460 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 460-320001TUR | PRE-FAB - LEVEL 4 - HILTI WALL SLEEVES | 470 | INSTALL - LEVEL 4 - HILTI WALL SLEEVES | PF.460 | 9000104 |  | PF.460 | PF.460 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[8 empty] | 9000104 | 461 | 320001TUR | Stephen Yee | LEVEL 5 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0016667 | 1 | 300 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-01 | TRUE |  | Image 2025-09-19 10-24-56.jpeg |  | 2 | Kerri Pandolfi | 461 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 461-320001TUR | PRE-FAB - LEVEL 5 - HILTI WALL SLEEVES | 509 | INSTALL - LEVEL 5 - HILTI WALL SLEEVES | PF.461 | 9000104 |  | PF.461 | PF.461 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[8 empty] | 9000104 | 462 | 320001TUR | Stephen Yee | LEVEL 6 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0016556 | 1 | 302 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-08 | TRUE |  | Image 2025-09-19 10-27-06.jpeg |  | 2 | Kerri Pandolfi | 462 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 462-320001TUR | PRE-FAB - LEVEL 6 - HILTI WALL SLEEVES | 549 | INSTALL - LEVEL 6 - HILTI WALL SLEEVES | PF.462 | 9000104 |  | PF.462 | PF.462 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[8 empty] | 9000104 | 463 | 320001TUR | Stephen Yee | LEVEL 7 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0011574 | 1 | 432 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-15 | TRUE |  | Image 2025-09-19 10-27-31.jpeg |  | 2 | Kerri Pandolfi | 463 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 463-320001TUR | PRE-FAB - LEVEL 7 - HILTI WALL SLEEVES | 583 | INSTALL - LEVEL 7 - HILTI WALL SLEEVES | PF.463 | 9000104 |  | PF.463 | PF.463 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[8 empty] | 9000104 | 464 | 320001TUR | Stephen Yee | LEVEL 8 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0017544 | 1 | 285 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-22 | TRUE |  | Image 2025-09-19 10-29-33.jpeg |  | 2 | Kerri Pandolfi | 464 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 464-320001TUR | PRE-FAB - LEVEL 8 - HILTI WALL SLEEVES | 621 | INSTALL - LEVEL 8 - HILTI WALL SLEEVES | PF.464 | 9000104 |  | PF.464 | PF.464 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[8 empty] | 9000104 | 465 | 320001TUR | Stephen Yee | LEVEL 9 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.002381 | 1 | 210 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-30 | TRUE |  | Image 2025-09-19 10-29-12.jpeg |  | 2 | Kerri Pandolfi | 465 | 25 |  | 1.1875 | 4.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 1 | 0 | 25 | 465-320001TUR | PRE-FAB - LEVEL 9 - HILTI WALL SLEEVES | 666 | INSTALL - LEVEL 9 - HILTI WALL SLEEVES | PF.465 | 9000104 |  | PF.465 | PF.465 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[8 empty] | 9000104 | 466 | 320001TUR | Stephen Yee | LEVEL 10 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0023585 | 1 | 212 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-01-07 | TRUE |  | Image 2025-09-19 10-28-51.jpeg |  | 2 | Kerri Pandolfi | 466 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 466-320001TUR | PRE-FAB - LEVEL 10 - HILTI WALL SLEEVES | 707 | INSTALL - LEVEL 10 - HILTI WALL SLEEVES | PF.466 | 9000104 |  | PF.466 | PF.466 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[8 empty] | 9000104 | 467 | 320001TUR | Stephen Yee | LEVEL 11 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0023364 | 1 | 214 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-01-14 | TRUE |  | Image 2025-09-19 10-28-23.jpeg |  | 2 | Kerri Pandolfi | 467 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 467-320001TUR | PRE-FAB - LEVEL 11 - HILTI WALL SLEEVES | 761 | INSTALL - LEVEL 11 - HILTI WALL SLEEVES | PF.467 | 9000104 |  | PF.467 | PF.467 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[8 empty] | 9000104 | 468 | 320001TUR | Stephen Yee | LEVEL 12 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0023256 | 1 | 215 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-01-22 | TRUE |  | Image 2025-09-19 10-34-11.jpeg |  | 2 | Kerri Pandolfi | 468 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 468-320001TUR | PRE-FAB - LEVEL 12 - HILTI WALL SLEEVES | 812 | INSTALL - LEVEL 12 - HILTI WALL SLEEVES | PF.468 | 9000104 |  | PF.468 | PF.468 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[8 empty] | 9000104 | 469 | 320001TUR | Stephen Yee | LEVEL 13 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0016502 | 1 | 303 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-01-29 | TRUE |  | Image 2025-09-19 10-33-47.jpeg |  | 2 | Kerri Pandolfi | 469 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 469-320001TUR | PRE-FAB - LEVEL 13 - HILTI WALL SLEEVES | 865 | INSTALL - LEVEL 13 - HILTI WALL SLEEVES | PF.469 | 9000104 |  | PF.469 | PF.469 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[8 empty] | 9000104 | 470 | 320001TUR | Stephen Yee | LEVEL 14 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0022523 | 1 | 222 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-02-05 | TRUE |  | Image 2025-09-19 10-33-22.jpeg |  | 2 | Kerri Pandolfi | 470 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 470-320001TUR | PRE-FAB - LEVEL 14 - HILTI WALL SLEEVES | 912 | INSTALL - LEVEL 14 - HILTI WALL SLEEVES | PF.470 | 9000104 |  | PF.470 | PF.470 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[8 empty] | 9000104 | 471 | 320001TUR | Stephen Yee | LEVEL 15 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-02-12 | TRUE |  | Image 2025-09-19 10-32-57.jpeg |  | 2 | Kerri Pandolfi | 471 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 471-320001TUR | PRE-FAB - LEVEL 15 - HILTI WALL SLEEVES | 954 | INSTALL - LEVEL 15 - HILTI WALL SLEEVES | PF.471 | 9000104 |  | PF.471 | PF.471 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 472 | 320001TUR | Stephen Yee | LEVEL 16 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-02-20 | TRUE |  | Image 2025-09-19 10-32-32.jpeg |  | 2 | Kerri Pandolfi | 472 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 472-320001TUR | PRE-FAB - LEVEL 16 - HILTI WALL SLEEVES | 999 | INSTALL - LEVEL 16 - HILTI WALL SLEEVES | PF.472 | 9000104 |  | PF.472 | PF.472 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 473 | 320001TUR | Stephen Yee | LEVEL 17 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-02-27 | TRUE |  | Image 2025-09-19 10-32-07.jpeg |  | 2 | Kerri Pandolfi | 473 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 473-320001TUR | PRE-FAB - LEVEL 17 - HILTI WALL SLEEVES | 1038 | INSTALL - LEVEL 17 - HILTI WALL SLEEVES | PF.473 | 9000104 |  | PF.473 | PF.473 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 474 | 320001TUR | Stephen Yee | LEVEL 18 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-03-06 | TRUE |  | Image 2025-09-19 10-31-19.jpeg |  | 2 | Kerri Pandolfi | 474 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 474-320001TUR | PRE-FAB - LEVEL 18 - HILTI WALL SLEEVES | 1084 | INSTALL - LEVEL 18 - HILTI WALL SLEEVES | PF.474 | 9000104 |  | PF.474 | PF.474 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 475 | 320001TUR | Stephen Yee | LEVEL 19 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-03-13 | TRUE |  | Image 2025-09-19 10-31-46.jpeg |  | 2 | Kerri Pandolfi | 475 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 475-320001TUR | PRE-FAB - LEVEL 19 - HILTI WALL SLEEVES | 1132 | INSTALL - LEVEL 19 - HILTI WALL SLEEVES | PF.475 | 9000104 |  | PF.475 | PF.475 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 476 | 320001TUR | Stephen Yee | LEVEL 20 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-03-20 | TRUE |  | Image 2025-09-24 06-16-22.jpeg |  | 2 | Kerri Pandolfi | 476 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 476-320001TUR | PRE-FAB - LEVEL 20 - HILTI WALL SLEEVES | 1173 | INSTALL - LEVEL 20 - HILTI WALL SLEEVES | PF.476 | 9000104 |  | PF.476 | PF.476 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 477 | 320001TUR | Stephen Yee | LEVEL 21 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-03-27 | TRUE |  | Image 2025-09-24 06-15-57.jpeg |  | 2 | Kerri Pandolfi | 477 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 477-320001TUR | PRE-FAB - LEVEL 21 - HILTI WALL SLEEVES | 1219 | INSTALL - LEVEL 21 - HILTI WALL SLEEVES | PF.477 | 9000104 |  | PF.477 | PF.477 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 478 | 320001TUR | Stephen Yee | LEVEL 22 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-04-03 | TRUE |  | Image 2025-09-24 06-15-29.jpeg |  | 2 | Kerri Pandolfi | 478 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 478-320001TUR | PRE-FAB - LEVEL 22 - HILTI WALL SLEEVES | 1260 | INSTALL - LEVEL 22 - HILTI WALL SLEEVES | PF.478 | 9000104 |  | PF.478 | PF.478 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 479 | 320001TUR | Stephen Yee | LEVEL 23 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-04-10 | TRUE |  | Image 2025-09-24 06-15-09.jpeg |  | 2 | Kerri Pandolfi | 479 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 479-320001TUR | PRE-FAB - LEVEL 23 - HILTI WALL SLEEVES | 1300 | INSTALL - LEVEL 23 - HILTI WALL SLEEVES | PF.479 | 9000104 |  | PF.479 | PF.479 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 480 | 320001TUR | Stephen Yee | LEVEL 24 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-04-17 | TRUE |  | Image 2025-09-24 06-13-58.jpeg |  | 2 | Kerri Pandolfi | 480 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 480-320001TUR | PRE-FAB - LEVEL 24 - HILTI WALL SLEEVES | 1345 | INSTALL - LEVEL 24 - HILTI WALL SLEEVES | PF.480 | 9000104 |  | PF.480 | PF.480 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 481 | 320001TUR | Stephen Yee | LEVEL 25 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-04-27 | TRUE |  | Image 2025-09-24 06-13-33.jpeg |  | 2 | Kerri Pandolfi | 481 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 481-320001TUR | PRE-FAB - LEVEL 25 - HILTI WALL SLEEVES | 1382 | INSTALL - LEVEL 25 - HILTI WALL SLEEVES | PF.481 | 9000104 |  | PF.481 | PF.481 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 482 | 320001TUR | Stephen Yee | LEVEL 26 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-05-04 | TRUE |  | Image 2025-09-24 06-13-10.jpeg |  | 2 | Kerri Pandolfi | 482 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 482-320001TUR | PRE-FAB - LEVEL 26 - HILTI WALL SLEEVES | 1424 | INSTALL - LEVEL 26 - HILTI WALL SLEEVES | PF.482 | 9000104 |  | PF.482 | PF.482 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 483 | 320001TUR | Stephen Yee | LEVEL 27 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-05-11 | TRUE |  | Image 2025-09-24 06-12-50.jpeg |  | 2 | Kerri Pandolfi | 483 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 483-320001TUR | PRE-FAB - LEVEL 27 - HILTI WALL SLEEVES | 1462 | INSTALL - LEVEL 27 - HILTI WALL SLEEVES | PF.483 | 9000104 |  | PF.483 | PF.483 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 484 | 320001TUR | Stephen Yee | LEVEL 28 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-05-18 | TRUE |  | Image 2025-09-24 07-44-28.jpeg |  | 2 | Kerri Pandolfi | 484 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 484-320001TUR | PRE-FAB - LEVEL 28 - HILTI WALL SLEEVES | 1503 | INSTALL - LEVEL 28 - HILTI WALL SLEEVES | PF.484 | 9000104 |  | PF.484 | PF.484 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 485 | 320001TUR | Stephen Yee | LEVEL 29 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-05-26 | TRUE |  | Image 2025-09-24 07-44-55.jpeg |  | 2 | Kerri Pandolfi | 485 | 25 |  | 0.125 | 0.5 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.125 | -0.875 | 25 | 485-320001TUR | PRE-FAB - LEVEL 29 - HILTI WALL SLEEVES | 1545 | INSTALL - LEVEL 29 - HILTI WALL SLEEVES | PF.485 | 9000104 |  | PF.485 | PF.485 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 486 | 320001TUR | Stephen Yee | LEVEL 30 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-06-02 | TRUE |  | Image 2025-09-24 07-45-14.jpeg |  | 2 | Kerri Pandolfi | 486 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 486-320001TUR | PRE-FAB - LEVEL 30 - HILTI WALL SLEEVES | 1571 | INSTALL - LEVEL 30 - HILTI WALL SLEEVES | PF.486 | 9000104 |  | PF.486 | PF.486 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 487 | 320001TUR | Stephen Yee | LEVEL 31 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-06-09 | TRUE |  | Image 2025-09-24 07-47-01.jpeg |  | 2 | Kerri Pandolfi | 487 | 25 |  | 1.125 | 4.5 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 1 | 0 | 25 | 487-320001TUR | PRE-FAB - LEVEL 31 - HILTI WALL SLEEVES | 1608 | INSTALL - LEVEL 31 - HILTI WALL SLEEVES | PF.487 | 9000104 |  | PF.487 | PF.487 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 488 | 320001TUR | Stephen Yee | LEVEL 32 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-06-17 | TRUE |  | Image 2025-09-24 07-47-23.jpeg |  | 2 | Kerri Pandolfi | 488 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 488-320001TUR | PRE-FAB - LEVEL 32 - HILTI WALL SLEEVES | 1650 | INSTALL - LEVEL 32 - HILTI WALL SLEEVES | PF.488 | 9000104 |  | PF.488 | PF.488 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 489 | 320001TUR | Stephen Yee | LEVEL 33 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-06-24 | TRUE |  | Image 2025-09-24 07-47-46.jpeg |  | 2 | Kerri Pandolfi | 489 | 25 |  | 0.125 | 0.5 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.125 | -0.875 | 25 | 489-320001TUR | PRE-FAB - LEVEL 33 - HILTI WALL SLEEVES | 1681 | INSTALL - LEVEL 33 - HILTI WALL SLEEVES | PF.489 | 9000104 |  | PF.489 | PF.489 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 490 | 320001TUR | Stephen Yee | LEVEL 34 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-07-01 | TRUE |  | Image 2025-09-24 07-46-36.jpeg |  | 2 | Kerri Pandolfi | 490 | 25 |  | 0.5 | 2 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.5 | -0.5 | 25 | 490-320001TUR | PRE-FAB - LEVEL 34 - HILTI WALL SLEEVES | 1709 | INSTALL - LEVEL 34 - HILTI WALL SLEEVES | PF.490 | 9000104 |  | PF.490 | PF.490 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 491 | 320001TUR | Stephen Yee | LEVEL 35 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-07-09 | TRUE |  | Image 2025-09-24 07-46-12.jpeg |  | 2 | Kerri Pandolfi | 491 | 25 |  | 0.5 | 2 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.5 | -0.5 | 25 | 491-320001TUR | PRE-FAB - LEVEL 35 - HILTI WALL SLEEVES | 1738 | INSTALL - LEVEL 35 - HILTI WALL SLEEVES | PF.491 | 9000104 |  | PF.491 | PF.491 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 492 | 320001TUR | Stephen Yee | LEVEL 36 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-07-16 | TRUE |  | Image 2025-09-24 07-45-50.jpeg |  | 2 | Kerri Pandolfi | 492 | 25 |  | 0.5 | 2 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.5 | -0.5 | 25 | 492-320001TUR | PRE-FAB - LEVEL 36 - HILTI WALL SLEEVES | 1759 | INSTALL - LEVEL 36 - HILTI WALL SLEEVES | PF.492 | 9000104 |  | PF.492 | PF.492 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[8 empty] | 9000104 | 493 | 320001TUR | Stephen Yee | LEVEL 3 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | CONDUIT RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-26 | [7 empty] | 1 | 0.125 | 1 | 1 | 2025-09-02 | 2025-09-03 | 2025-09-05 |  | 2025-09-05 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 493 | 25 |  | 0 | 0 | 1 | 1 | 1.8 | 1.8 | 1 | 0.8 | 0 | -1 | 25 | 493-320001TUR | PRE-FAB - LEVEL 3 - CONDUIT RISER SLEEVES | #NO MATCH | #NO MATCH | PF.493 | 9000104 |  | PF.493 | DELETED | 100% |  |  | 2025-08-19 |  | 2025-10-05 | -24
[8 empty] | 9000104 | 494 | 320001TUR | Stephen Yee | LEVEL 4 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-02 | [7 empty] | 2 | 0.25 | 1 | 1 | 2025-09-09 | 2025-09-10 | 2025-09-12 |  | 2025-09-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 494 | 25 |  | 0 | 0 | 2 | 2 |  | 0 | 2 | -2 | 0 | -2 | 25 | 494-320001TUR | PRE-FAB - LEVEL 4 - HILTI RISER SLEEVES | #NO MATCH | #NO MATCH | PF.494 | 9000104 |  | PF.494 | DELETED | 100% |  |  | 2025-08-26 |  | 2025-10-05 | -19
[8 empty] | 9000104 | 495 | 320001TUR | Stephen Yee | LEVEL 5 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.25 | 1 | 1 | 2025-08-22 | 2025-08-23 | 2025-08-25 |  | 2025-08-25 |  | 2025-08-25 | TRUE |  | Image 2025-08-26 07-30-43.jpeg |  | 3 | Kerri Pandolfi | 495 | 25 |  | 2 | 2 | 2 | 2 |  | 0 | 2 | -2 | 2 | 0 | 25 | 495-320001TUR | PRE-FAB - LEVEL 5 - HILTI RISER SLEEVES | 112 |  | PF.495 | 9000104 |  | PF.495 | PF.495 | 100% | TRUE |  | 2025-08-08 |  | 2025-10-05 | -31 | TRUE
[8 empty] | 9000104 | 496 | 320001TUR | Stephen Yee | LEVEL 6 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 1 | 0.125 | 1 | 1 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-03 |  | 2025-08-27 | TRUE |  | Image 2025-09-03 09-24-58.jpeg |  | 3 | Kerri Pandolfi | 496 | 25 |  | 3 | 3 | 1 | 1 | 1.8 | 1.8 | 1 | 0.8 | 1 | 0 | 25 | 496-320001TUR | PRE-FAB - LEVEL 6 - HILTI RISER SLEEVES | 120 | PRE-FAB - LEVEL 5 - HILTI RISER SLEEVES | PF.496 | 9000104 |  | PF.496 | PF.496 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 497 | 320001TUR | Stephen Yee | LEVEL 7 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00047259 | 1 | 529 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-03 |  | 2025-08-27 | TRUE |  | Image 2025-09-03 09-25-33.jpeg |  | 3 | Kerri Pandolfi | 497 | 25 |  | 3 | 3 | 2 | 2 |  | 0 | 2 | -2 | 2 | 0 | 25 | 497-320001TUR | PRE-FAB - LEVEL 7 - HILTI RISER SLEEVES | 121 | PRE-FAB - LEVEL 5 - HILTI RISER SLEEVES | PF.497 | 9000104 |  | PF.497 | PF.497 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 498 | 320001TUR | Stephen Yee | LEVEL 8 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00032595 | 1 | 767 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-03 |  | 2025-08-29 | TRUE |  | Image 2025-09-03 09-26-21.jpeg |  | 3 | Kerri Pandolfi | 498 | 25 |  | 2 | 2 | 2 | 2 |  | 0 | 2 | -2 | 2 | 0 | 25 | 498-320001TUR | PRE-FAB - LEVEL 8 - HILTI RISER SLEEVES | 134 | PRE-FAB - LEVEL 7 - HILTI RISER SLEEVES | PF.498 | 9000104 |  | PF.498 | PF.498 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 499 | 320001TUR | Stephen Yee | LEVEL 9 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-25 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00065445 | 1 | 382 | 2025-09-01 | 2025-09-02 | 2025-09-04 |  | 2025-09-04 |  | 2025-09-04 | TRUE |  | Image 2025-09-03 09-26-54.jpeg |  | 3 | Kerri Pandolfi | 499 | 25 |  | 2 | 2 | 2 | 2 |  | 0 | 2 | -2 | 2 | 0 | 25 | 499-320001TUR | PRE-FAB - LEVEL 9 - HILTI RISER SLEEVES | 142 | PRE-FAB - LEVEL 8 - HILTI RISER SLEEVES | PF.499 | 9000104 |  | PF.499 | PF.499 | 100% | TRUE |  | 2025-08-18 |  | 2025-10-05 | -25 | TRUE
[8 empty] | 9000104 | 500 | 320001TUR | Stephen Yee | LEVEL 10 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00080906 | 1 | 309 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-08 |  | 2025-09-08 | TRUE |  | Image 2025-09-03 09-40-36.jpeg |  | 3 | Kerri Pandolfi | 500 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 500-320001TUR | PRE-FAB - LEVEL 10 - HILTI RISER SLEEVES | 154 | PRE-FAB - LEVEL 9 - HILTI RISER SLEEVES | PF.500 | 9000104 |  | PF.500 | PF.500 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 501 | 320001TUR | Stephen Yee | LEVEL 11 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00085616 | 1 | 292 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-10 |  | 2025-09-10 | TRUE |  | Image 2025-09-03 09-41-04.jpeg |  | 3 | Kerri Pandolfi | 501 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 501-320001TUR | PRE-FAB - LEVEL 11 - HILTI RISER SLEEVES | 165 | PRE-FAB - LEVEL 10 - HILTI RISER SLEEVES | PF.501 | 9000104 |  | PF.501 | PF.501 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 502 | 320001TUR | Stephen Yee | LEVEL 12 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00079618 | 1 | 314 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-15 |  | 2025-09-15 | TRUE |  | Image 2025-09-03 09-42-43.jpeg |  | 3 | Kerri Pandolfi | 502 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 502-320001TUR | PRE-FAB - LEVEL 12 - HILTI RISER SLEEVES | 174 | PRE-FAB - LEVEL 11 - HILTI RISER SLEEVES | PF.502 | 9000104 |  | PF.502 | PF.502 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 503 | 320001TUR | Stephen Yee | LEVEL 13 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00065274 | 1 | 383 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-17 |  | 2025-09-17 | TRUE |  | Image 2025-09-03 11-24-21.jpeg |  | 3 | Kerri Pandolfi | 503 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 503-320001TUR | PRE-FAB - LEVEL 13 - HILTI RISER SLEEVES | 188 | PRE-FAB - LEVEL 12 - HILTI RISER SLEEVES | PF.503 | 9000104 |  | PF.503 | PF.503 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 504 | 320001TUR | Stephen Yee | LEVEL 14 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.25 | 1 | 1 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-19 |  | 2025-09-19 | TRUE |  | Image 2025-09-03 11-25-07.jpeg |  | 3 | Kerri Pandolfi | 504 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 504-320001TUR | PRE-FAB - LEVEL 14 - HILTI RISER SLEEVES | 204 | PRE-FAB - LEVEL 13 - HILTI RISER SLEEVES | PF.504 | 9000104 |  | PF.504 | PF.504 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 505 | 320001TUR | Stephen Yee | LEVEL 15 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064935 | 1 | 385 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-23 |  | 2025-09-23 | TRUE |  | Image 2025-09-03 11-24-49.jpeg |  | 3 | Kerri Pandolfi | 505 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 505-320001TUR | PRE-FAB - LEVEL 15 - HILTI RISER SLEEVES | 211 | PRE-FAB - LEVEL 14 - HILTI RISER SLEEVES | PF.505 | 9000104 |  | PF.505 | PF.505 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[8 empty] | 9000104 | 506 | 320001TUR | Stephen Yee | LEVEL 16 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00080128 | 1 | 312 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-10-03 |  | 2025-09-26 | TRUE |  | Image 2025-09-24 12-46-20.jpeg |  | 2 | Kerri Pandolfi | 506 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 506-320001TUR | PRE-FAB - LEVEL 16 - HILTI RISER SLEEVES | 221 | PRE-FAB - LEVEL 15 - HILTI RISER SLEEVES | PF.506 | 9000104 |  | PF.506 | PF.506 | 100% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 507 | 320001TUR | Stephen Yee | LEVEL 17 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064767 | 1 | 386 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-07 |  | 2025-09-30 | TRUE |  | Image 2025-09-24 12-46-51.jpeg |  | 2 | Kerri Pandolfi | 507 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 507-320001TUR | PRE-FAB - LEVEL 17 - HILTI RISER SLEEVES | 231 | PRE-FAB - LEVEL 16 - HILTI RISER SLEEVES | PF.507 | 9000104 |  | PF.507 | PF.507 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[8 empty] | 9000104 | 508 | 320001TUR | Stephen Yee | LEVEL 18 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00078616 | 1 | 318 | 2025-09-29 | 2025-09-30 | 2025-10-02 |  | 2025-10-14 |  | 2025-10-02 | TRUE |  | Image 2025-09-24 12-47-12.jpeg |  | 2 | Kerri Pandolfi | 508 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 508-320001TUR | PRE-FAB - LEVEL 18 - HILTI RISER SLEEVES | 242 | PRE-FAB - LEVEL 17 - HILTI RISER SLEEVES | PF.508 | 9000104 |  | PF.508 | PF.508 | 100% | TRUE |  | 2025-09-15 |  | 2025-10-05 | -5 | TRUE
[8 empty] | 9000104 | 509 | 320001TUR | Stephen Yee | LEVEL 19 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00085324 | 1 | 293 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-07 |  | 2025-10-07 | TRUE |  | Image 2025-09-24 12-47-32.jpeg |  | 2 | Kerri Pandolfi | 509 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 509-320001TUR | PRE-FAB - LEVEL 19 - HILTI RISER SLEEVES | 251 | PRE-FAB - LEVEL 18 - HILTI RISER SLEEVES | PF.509 | 9000104 |  | PF.509 | PF.509 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[8 empty] | 9000104 | 510 | 320001TUR | Stephen Yee | LEVEL 20 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00085034 | 1 | 294 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-10-10 |  | 2025-10-09 | TRUE |  | Image 2025-09-24 12-48-03.jpeg |  | 2 | Kerri Pandolfi | 510 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 510-320001TUR | PRE-FAB - LEVEL 20 - HILTI RISER SLEEVES | 266 | PRE-FAB - LEVEL 19 - HILTI RISER SLEEVES | PF.510 | 9000104 |  | PF.510 | PF.510 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000104 | 511 | 320001TUR | Stephen Yee | LEVEL 21 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064599 | 1 | 387 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-10-14 |  | 2025-10-14 | TRUE |  | Image 2025-09-24 12-48-43.jpeg |  | 2 | Kerri Pandolfi | 511 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 511-320001TUR | PRE-FAB - LEVEL 21 - HILTI RISER SLEEVES | 275 | PRE-FAB - LEVEL 20 - HILTI RISER SLEEVES | PF.511 | 9000104 |  | PF.511 | PF.511 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000104 | 512 | 320001TUR | Stephen Yee | LEVEL 22 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064433 | 1 | 388 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-10-16 |  | 2025-10-16 | TRUE |  | Image 2025-09-24 12-49-16.jpeg |  | 2 | Kerri Pandolfi | 512 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 512-320001TUR | PRE-FAB - LEVEL 22 - HILTI RISER SLEEVES | 288 | PRE-FAB - LEVEL 21 - HILTI RISER SLEEVES | PF.512 | 9000104 |  | PF.512 | PF.512 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000104 | 513 | 320001TUR | Stephen Yee | LEVEL 23 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064267 | 1 | 389 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-10-21 |  | 2025-10-21 | TRUE |  | Image 2025-09-24 12-45-25.jpeg |  | 2 | Kerri Pandolfi | 513 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 513-320001TUR | PRE-FAB - LEVEL 23 - HILTI RISER SLEEVES | 299 | PRE-FAB - LEVEL 22 - HILTI RISER SLEEVES | PF.513 | 9000104 |  | PF.513 | PF.513 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000104 | 514 | 320001TUR | Stephen Yee | LEVEL 24 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-31 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064103 | 1 | 390 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 | DATES MISALIGNED | 2025-10-23 |  |  | Image 2025-09-26 10-06-53.jpeg |  | 2 | Kerri Pandolfi | 514 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 514-320001TUR | PRE-FAB - LEVEL 24 - HILTI RISER SLEEVES | 309 | PRE-FAB - LEVEL 23 - HILTI RISER SLEEVES | PF.514 | 9000104 |  | PF.514 | PF.514 | 99% | TRUE |  | 2025-10-24 |  | 2025-10-05 | 26 | TRUE
[8 empty] | 9000104 | 515 | 320001TUR | Stephen Yee | LEVEL 25 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00077882 | 1 | 321 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-12 | DATES MISALIGNED | 2025-10-27 |  |  | Image 2025-09-26 09-53-03.jpeg |  | 2 | Kerri Pandolfi | 515 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 515-320001TUR | PRE-FAB - LEVEL 25 - HILTI RISER SLEEVES | 325 | PRE-FAB - LEVEL 24 - HILTI RISER SLEEVES | PF.515 | 9000104 |  | PF.515 | PF.515 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 516 | 320001TUR | Stephen Yee | LEVEL 26 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00084459 | 1 | 296 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-12 | DATES MISALIGNED | 2025-10-30 |  |  | Image 2025-09-26 09-54-08.jpeg |  | 2 | Kerri Pandolfi | 516 | 25 |  | 1.5 | 1.5 | 2 | 2 |  | 0 | 2 | -2 | 1.5 | -0.5 | 25 | 516-320001TUR | PRE-FAB - LEVEL 26 - HILTI RISER SLEEVES | 343 | PRE-FAB - LEVEL 25 - HILTI RISER SLEEVES | PF.516 | 9000104 |  | PF.516 | PF.516 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 517 | 320001TUR | Stephen Yee | LEVEL 27 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00084746 | 1 | 295 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-03 |  | 2025-11-03 |  |  | Image 2025-09-26 09-54-34.jpeg |  | 2 | Kerri Pandolfi | 517 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 517-320001TUR | PRE-FAB - LEVEL 27 - HILTI RISER SLEEVES | 369 | PRE-FAB - LEVEL 26 - HILTI RISER SLEEVES | PF.517 | 9000104 |  | PF.517 | PF.517 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 518 | 320001TUR | Stephen Yee | LEVEL 28 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00058275 | 1 | 429 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-05 |  | 2025-11-05 |  |  | Image 2025-09-26 09-55-07.jpeg |  | 2 | Kerri Pandolfi | 518 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 518-320001TUR | PRE-FAB - LEVEL 28 - HILTI RISER SLEEVES | 378 | PRE-FAB - LEVEL 27 - HILTI RISER SLEEVES | PF.518 | 9000104 |  | PF.518 | PF.518 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 519 | 320001TUR | Stephen Yee | LEVEL 29 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00083893 | 1 | 298 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-07 |  | 2025-11-12 |  |  | Image 2025-09-26 10-01-41.jpeg |  | 2 | Kerri Pandolfi | 519 | 25 |  | 1.5 | 1.5 | 2 | 2 |  | 0 | 2 | -2 | 1.5 | -0.5 | 25 | 519-320001TUR | PRE-FAB - LEVEL 29 - HILTI RISER SLEEVES | 402 | PRE-FAB - LEVEL 28 - HILTI RISER SLEEVES | PF.519 | 9000104 |  | PF.519 | PF.519 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 520 | 320001TUR | Stephen Yee | LEVEL 30 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00084175 | 1 | 297 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-13 |  | 2025-11-17 |  |  | Image 2025-09-26 10-03-56.jpeg |  | 2 | Kerri Pandolfi | 520 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 520-320001TUR | PRE-FAB - LEVEL 30 - HILTI RISER SLEEVES | 435 | PRE-FAB - LEVEL 29 - HILTI RISER SLEEVES | PF.520 | 9000104 |  | PF.520 | PF.520 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 521 | 320001TUR | Stephen Yee | LEVEL 31 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00058005 | 1 | 431 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-18 |  | 2025-11-21 |  |  | Image 2025-09-26 10-04-21.jpeg |  | 2 | Kerri Pandolfi | 521 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 521-320001TUR | PRE-FAB - LEVEL 31 - HILTI RISER SLEEVES | 472 | PRE-FAB - LEVEL 30 - HILTI RISER SLEEVES | PF.521 | 9000104 |  | PF.521 | PF.521 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 522 | 320001TUR | Stephen Yee | LEVEL 32 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00063776 | 1 | 392 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 | DATES MISALIGNED | 2025-12-04 |  |  | Image 2025-09-26 10-05-11.jpeg |  | 2 | Kerri Pandolfi | 522 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 522-320001TUR | PRE-FAB - LEVEL 32 - HILTI RISER SLEEVES | 521 | INSTALL - LEVEL 32 - HILTI RISER SLEEVES | PF.522 | 9000104 |  | PF.522 | PF.522 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 523 | 320001TUR | Stephen Yee | LEVEL 33 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00083056 | 1 | 301 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-12-05 | DATES MISALIGNED | 2025-12-16 |  |  | Image 2025-09-26 10-05-37.jpeg |  | 2 | Kerri Pandolfi | 523 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 523-320001TUR | PRE-FAB - LEVEL 33 - HILTI RISER SLEEVES | 588 | INSTALL - LEVEL 33 - HILTI RISER SLEEVES | PF.523 | 9000104 |  | PF.523 | PF.523 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 524 | 320001TUR | Stephen Yee | LEVEL 34 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00057737 | 1 | 433 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-12-17 | DATES MISALIGNED | 2025-12-29 |  |  | Image 2025-09-26 10-07-16.jpeg |  | 2 | Kerri Pandolfi | 524 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 524-320001TUR | PRE-FAB - LEVEL 34 - HILTI RISER SLEEVES | 647 | INSTALL - LEVEL 34 - HILTI RISER SLEEVES | PF.524 | 9000104 |  | PF.524 | PF.524 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 525 | 320001TUR | Stephen Yee | LEVEL 35 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.0011962 | 1 | 209 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-12-30 |  | 2026-01-05 |  |  | Image 2025-09-26 10-07-40.jpeg |  | 2 | Kerri Pandolfi | 525 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 525-320001TUR | PRE-FAB - LEVEL 35 - HILTI RISER SLEEVES | 682 | INSTALL - LEVEL 35 - HILTI RISER SLEEVES | PF.525 | 9000104 |  | PF.525 | PF.525 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 526 | 320001TUR | Stephen Yee | LEVEL 36 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.0011848 | 1 | 211 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2026-01-06 |  | 2026-01-09 |  |  | Image 2025-09-26 10-03-13.jpeg |  | 2 | Kerri Pandolfi | 526 | 26 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 26 | 526-320001TUR | PRE-FAB - LEVEL 36 - HILTI RISER SLEEVES | 719 | INSTALL - LEVEL 36 - HILTI RISER SLEEVES | PF.526 | 9000104 |  | PF.526 | PF.526 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[8 empty] | 9000104 | 527 | 320001TUR | Stephen Yee | LEVEL 37 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | CONDUIT RISER SLEEVES | 1 | Yellow | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-04 | 2025-08-19 | Stephen Yee | TRUE | true |  |  |  | 1 | 0.00058685 | 1 | 213 | 2026-05-11 | 2026-05-12 | 2026-05-14 | OVER DUE |  |  | 2026-01-15 | [5 empty] | Kerri Pandolfi | 527 |  |  | 0 | 0 | 1 | 1 | 1.8 | 1.8 | 1 | 0.8 | 0 | -1 |  | 527-320001TUR | PRE-FAB - LEVEL 37 - CONDUIT RISER SLEEVES | 766 | INSTALL - LEVEL 37 - CONDUIT RISER SLEEVES | PF.527 | 9000104 |  | PF.527 | PF.527 | 0% |  |  | 2026-04-27 |  | 2025-10-05 | 157
[8 empty] | 9000104 | 528 | 320001TUR | Stephen Yee | LEVEL 38 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | CONDUIT RISER SLEEVES | 1 | Yellow | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-18 | 2025-08-19 | Stephen Yee | TRUE | true |  |  |  | 1 | 0.00031807 | 1 | 393 | 2026-05-25 | 2026-05-26 | 2026-05-28 | OVER DUE |  |  | 2026-01-28 | [5 empty] | Kerri Pandolfi | 528 |  |  | 0 | 0 | 1 | 1 | 1.8 | 1.8 | 1 | 0.8 | 0 | -1 |  | 528-320001TUR | PRE-FAB - LEVEL 38 - CONDUIT RISER SLEEVES | 838 | INSTALL - LEVEL 38 - CONDUIT RISER SLEEVES | PF.528 | 9000104 |  | PF.528 | PF.528 | 0% |  |  | 2026-05-11 |  | 2025-10-05 | 167
[8 empty] | 9000220 | 529 | 320001TUR | Stephen Yee | MULTI LEVEL | TEMPS (SMALL) | SPIDER BOXES | 30 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-12 | 2025-08-21 | Arthur Mayo | TRUE | true | TRUE | True | APPROVED | 30 | 3.75 | 4 | 1 | 2025-08-19 | 2025-08-25 | 2025-08-27 |  | 2025-08-27 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-25 13-11-08.jpeg |  | 3 | Kerri Pandolfi | 529 | 25 |  | 0.16667 | 5 | 1 | 30 | 2 | 60 | 1 | 1 | 0.16667 | -0.83333 | 25 | 529-320001TUR | PRE-FAB - MULTI LEVEL - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.529 | 9000220 |  | PF.529 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-08-05 |  | 2025-10-05 | -34 | TRUE
[8 empty] | 9000010 | 530 | 320001TUR | Stephen Yee | LEVEL 2 | LIGHT FIXTURE WIRED ASSEMBLY (1) LUMINARY WHIP | S50 - THREADED ROD CEILING MOUNT - VAULT | 20 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-26 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2.8 | 0.35 | 1 | 1 | 2025-09-26 | 2025-09-27 | 2025-09-29 |  | 2025-10-06 |  |  | TRUE |  | Image 2025-09-24 06-11-02.jpeg |  | 13 | Kerri Pandolfi | 530 | 25 |  | 0.575 | 11.5 | 0.14 | 2.8 | 0.15 | 3 | 0.14 | 0.01 | 0.14 | 0 | 25 | 530-320001TUR | PRE-FAB - LEVEL 2 - S50 - THREADED ROD CEILING MOUNT - VAULT | 1917 |  | PF.530 | 9000010 |  | PF.530 | PF.530 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000010 | 531 | 320001TUR | Stephen Yee | LEVEL 2 | LIGHT FIXTURE WIRED ASSEMBLY (1) LUMINARY WHIP | S50 - WALL MOUNT VAULT+L2.5 | 25 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-27 | 2025-08-26 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3.5 | 0.4375 | 1 | 1 | 2025-09-03 | 2025-09-04 | 2025-09-06 |  | 2025-09-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-09-08 09-58-27.jpeg |  | 2 | Kerri Pandolfi | 531 | 25 |  | 0.88 | 22 | 0.14 | 3.5 | 0.15 | 3.75 | 0.14 | 0.01 | 0.14 | 0 | 25 | 531-320001TUR | PRE-FAB - LEVEL 2 - S50 - WALL MOUNT VAULT+L2.5 | #NO MATCH | #NO MATCH | PF.531 | 9000010 |  | PF.531 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-08-20 |  | 2025-10-05 | -23 | TRUE
[8 empty] | 9000030 | 532 | 320001TUR | Stephen Yee | MULTI LEVEL | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | EUH HEATER PREWIRE | 29 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-01 | [7 empty] | 5.2838 | 0.66048 | 1 | 1 | 2025-09-08 | 2025-09-09 | 2025-09-11 |  | 2025-09-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 532 | 25 |  | 0 | 0 | 0.1822 | 5.2838 | 1.15 | 33.35 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 532-320001TUR | PRE-FAB - MULTI LEVEL - EUH HEATER PREWIRE | #NO MATCH | #NO MATCH | PF.532 | 9000030 |  | PF.532 | DELETED | 100% |  |  | 2025-08-25 |  | 2025-10-05 | -20
[8 empty] | 9000034 | 533 | 320001TUR | Stephen Yee | LEVEL 1 | SPECIAL CONTROL ASSEMBLY (BRANCH) | UNIT HEATERS (INSTALL MOUNTING HARDWARE) | 12 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-03 | [7 empty] | 48 | 6 | 6 | 1 | 2025-10-10 | 2025-10-18 | 2025-10-20 |  | 2025-10-20 | [7 empty] | Kerri Pandolfi | 533 | 25 |  | 0 | 0 | 4 | 48 | 4.25 | 51 | 4 | 0.25 | 0 | -4 | 25 | 533-320001TUR | PRE-FAB - LEVEL 1 - UNIT HEATERS (INSTALL MOUNTING HARDWARE) | 1915 |  | PF.533 | 9000034 |  | PF.533 | PF.533 | 0% |  |  | 2025-09-26 |  | 2025-10-05 | 6
[8 empty] | 9000030 | 534 | 320001TUR | Stephen Yee | LEVEL 13 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 483 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-10 | [7 empty] | 43.6101 | 2.7256 | 3 | 2 | 2025-12-17 | 2025-12-21 | 2025-12-23 |  | 2025-12-29 | DATES MISALIGNED | 2026-01-06 | [6 empty] | 534 | 25 |  | 0 | 0 | 0.09029 | 43.6101 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 534-320001TUR | PRE-FAB - LEVEL 13 - UNITS INWALL | 671 | LEVEL 13 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.534 | 9000030 |  | PF.534 | PF.534 | 0% |  |  | 2025-12-03 |  | 2025-10-05 | 54
[8 empty] | 9000030 | 535 | 320001TUR | Stephen Yee | LEVEL 22 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-11 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-02-18 | 2026-02-23 | 2026-02-25 |  | 2026-03-02 |  | 2026-03-06 | [6 empty] | 535 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 535-320001TUR | PRE-FAB - LEVEL 22 - UNITS INWALL | 1045 | LEVEL 22 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.535 | 9000030 |  | PF.535 | PF.535 | 0% |  |  | 2026-02-04 |  | 2025-10-05 | 99
[8 empty] | 9000030 | 536 | 320001TUR | Stephen Yee | LEVEL 23 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-18 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-02-25 | 2026-03-02 | 2026-03-04 |  | 2026-03-09 |  | 2026-03-13 | [6 empty] | 536 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 536-320001TUR | PRE-FAB - LEVEL 23 - UNITS INWALL | 1090 | LEVEL 23 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.536 | 9000030 |  | PF.536 | PF.536 | 0% |  |  | 2026-02-11 |  | 2025-10-05 | 104
[8 empty] | 9000030 | 537 | 320001TUR | Stephen Yee | LEVEL 24 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-25 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-03-04 | 2026-03-09 | 2026-03-11 |  | 2026-03-16 |  | 2026-03-20 | [6 empty] | 537 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 537-320001TUR | PRE-FAB - LEVEL 24 - UNITS INWALL | 1137 | LEVEL 24 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.537 | 9000030 |  | PF.537 | PF.537 | 0% |  |  | 2026-02-18 |  | 2025-10-05 | 109
[8 empty] | 9000030 | 538 | 320001TUR | Stephen Yee | LEVEL 25 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-04 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-03-11 | 2026-03-16 | 2026-03-18 |  | 2026-03-23 |  | 2026-03-27 | [6 empty] | 538 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 538-320001TUR | PRE-FAB - LEVEL 25 - UNITS INWALL | 1178 | LEVEL 25 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.538 | 9000030 |  | PF.538 | PF.538 | 0% |  |  | 2026-02-25 |  | 2025-10-05 | 114
[8 empty] | 9000030 | 539 | 320001TUR | Stephen Yee | LEVEL 26 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-11 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-03-18 | 2026-03-21 | 2026-03-23 |  | 2026-03-30 | DATES MISALIGNED | 2026-04-06 | [6 empty] | 539 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 539-320001TUR | PRE-FAB - LEVEL 26 - UNITS INWALL | 1230 | LEVEL 26 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.539 | 9000030 |  | PF.539 | PF.539 | 0% |  |  | 2026-03-04 |  | 2025-10-05 | 119
[8 empty] | 9000030 | 540 | 320001TUR | Stephen Yee | LEVEL 27 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-18 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-03-25 | 2026-03-30 | 2026-04-01 |  | 2026-04-06 |  | 2026-04-10 | [6 empty] | 540 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 540-320001TUR | PRE-FAB - LEVEL 27 - UNITS INWALL | 1264 | LEVEL 27 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.540 | 9000030 |  | PF.540 | PF.540 | 0% |  |  | 2026-03-11 |  | 2025-10-05 | 124
[8 empty] | 9000030 | 541 | 320001TUR | Stephen Yee | LEVEL 31 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-16 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-23 | 2026-04-28 | 2026-04-30 |  | 2026-05-05 |  | 2026-05-11 | [6 empty] | 541 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 541-320001TUR | PRE-FAB - LEVEL 31 - UNITS INWALL | 1429 | LEVEL 31 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.541 | 9000030 |  | PF.541 | PF.541 | 0% |  |  | 2026-04-09 |  | 2025-10-05 | 145
[8 empty] | 9000030 | 542 | 320001TUR | Stephen Yee | LEVEL 28 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-25 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-01 | 2026-04-06 | 2026-04-08 |  | 2026-04-13 |  | 2026-04-17 | [6 empty] | 542 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 542-320001TUR | PRE-FAB - LEVEL 28 - UNITS INWALL | 1304 | LEVEL 28 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.542 | 9000030 |  | PF.542 | PF.542 | 0% |  |  | 2026-03-18 |  | 2025-10-05 | 129
[8 empty] | 9000030 | 543 | 320001TUR | Stephen Yee | LEVEL 32 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-23 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-30 | 2026-05-05 | 2026-05-07 |  | 2026-05-12 |  | 2026-05-18 | [6 empty] | 543 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 543-320001TUR | PRE-FAB - LEVEL 32 - UNITS INWALL | 1467 | LEVEL 32 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.543 | 9000030 |  | PF.543 | PF.543 | 0% |  |  | 2026-04-16 |  | 2025-10-05 | 150
[8 empty] | 9000030 | 544 | 320001TUR | Stephen Yee | LEVEL 29 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-01 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-08 | 2026-04-13 | 2026-04-15 |  | 2026-04-21 |  | 2026-04-27 | [6 empty] | 544 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 544-320001TUR | PRE-FAB - LEVEL 29 - UNITS INWALL | 1348 | LEVEL 29 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.544 | 9000030 |  | PF.544 | PF.544 | 0% |  |  | 2026-03-25 |  | 2025-10-05 | 134
[8 empty] | 9000030 | 545 | 320001TUR | Stephen Yee | LEVEL 33 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-30 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-05-07 | 2026-05-12 | 2026-05-14 |  | 2026-05-19 | DATES MISALIGNED | 2026-05-26 | [6 empty] | 545 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 545-320001TUR | PRE-FAB - LEVEL 33 - UNITS INWALL | 1510 | LEVEL 33 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.545 | 9000030 |  | PF.545 | PF.545 | 0% |  |  | 2026-04-23 |  | 2025-10-05 | 155
[8 empty] | 9000030 | 546 | 320001TUR | Stephen Yee | LEVEL 34 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 386 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-07 | [7 empty] | 34.8519 | 2.1782 | 3 | 2 | 2026-05-14 | 2026-05-19 | 2026-05-21 |  | 2026-05-27 |  | 2026-06-02 | [6 empty] | 546 | 26 |  | 0 | 0 | 0.09029 | 34.8519 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 546-320001TUR | PRE-FAB - LEVEL 34 - UNITS INWALL | 1554 | LEVEL 34 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.546 | 9000030 |  | PF.546 | PF.546 | 0% |  |  | 2026-04-30 |  | 2025-10-05 | 160
[8 empty] | 9000030 | 547 | 320001TUR | Stephen Yee | LEVEL 30 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-09 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-16 | 2026-04-21 | 2026-04-23 |  | 2026-04-28 |  | 2026-05-04 | [6 empty] | 547 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 547-320001TUR | PRE-FAB - LEVEL 30 - UNITS INWALL | 1389 | LEVEL 30 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.547 | 9000030 |  | PF.547 | PF.547 | 0% |  |  | 2026-04-02 |  | 2025-10-05 | 140
[8 empty] | 9000030 | 548 | 320001TUR | Stephen Yee | LEVEL 35 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 386 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-15 | [7 empty] | 34.8519 | 2.1782 | 3 | 2 | 2026-05-22 | 2026-05-27 | 2026-05-29 |  | 2026-06-03 |  | 2026-06-09 | [6 empty] | 548 | 26 |  | 0 | 0 | 0.09029 | 34.8519 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 548-320001TUR | PRE-FAB - LEVEL 35 - UNITS INWALL | 1586 | LEVEL 35 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.548 | 9000030 |  | PF.548 | PF.548 | 0% |  |  | 2026-05-08 |  | 2025-10-05 | 166
[8 empty] | 9000030 | 549 | 320001TUR | Stephen Yee | LEVEL 36 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-22 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-05-29 | 2026-06-03 | 2026-06-05 |  | 2026-06-10 |  | 2026-06-16 | [6 empty] | 549 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 549-320001TUR | PRE-FAB - LEVEL 36 - UNITS INWALL | 1617 | LEVEL 36 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.549 | 9000030 |  | PF.549 | PF.549 | 0% |  |  | 2026-05-15 |  | 2025-10-05 | 171
[8 empty] | 9000030 | 550 | 320001TUR | Stephen Yee | LEVEL 3 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-01 | 2025-09-30 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 42.0751 | 2.6297 | 3 | 2 | 2025-10-08 | 2025-10-13 | 2025-10-15 |  | 2025-10-27 |  | 2025-10-24 |  |  |  |  | 2 |  | 550 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 550-320001TUR | PRE-FAB - LEVEL 3 - UNITS INWALL | 302 | LEVEL 3 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.550 | 9000030 |  | PF.550 | PF.550 | 0% |  |  | 2025-09-24 |  | 2025-10-05 | 4 | TRUE
[8 empty] | 9000030 | 551 | 320001TUR | Stephen Yee | LEVEL 4 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-08 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-10-15 | 2025-10-20 | 2025-10-22 |  | 2025-11-03 |  | 2025-10-31 | [6 empty] | 551 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 551-320001TUR | PRE-FAB - LEVEL 4 - UNITS INWALL | 331 | LEVEL 4 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.551 | 9000030 |  | PF.551 | PF.551 | 0% |  |  | 2025-10-01 |  | 2025-10-05 | 9
[8 empty] | 9000030 | 552 | 320001TUR | Stephen Yee | LEVEL 5 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-22 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-10-29 | 2025-11-02 | 2025-11-04 |  | 2025-11-07 |  | 2025-11-07 | [6 empty] | 552 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 552-320001TUR | PRE-FAB - LEVEL 5 - UNITS INWALL | 372 | LEVEL 5 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.552 | 9000030 |  | PF.552 | PF.552 | 0% |  |  | 2025-10-15 |  | 2025-10-05 | 19
[8 empty] | 9000030 | 553 | 320001TUR | Stephen Yee | LEVEL 6 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-29 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-11-05 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 553 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 553-320001TUR | PRE-FAB - LEVEL 6 - UNITS INWALL | #NO MATCH | #NO MATCH | PF.553 | 9000030 |  | PF.553 | NOT ON PROJECT SCHEDULE | 0% |  |  | 2025-10-22 |  | 2025-10-05 | 24
[8 empty] | 9000030 | 554 | 320001TUR | Stephen Yee | LEVEL 7 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-29 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-11-05 | 2025-11-10 | 2025-11-12 |  | 2025-11-17 |  | 2025-11-21 | [6 empty] | 554 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 554-320001TUR | PRE-FAB - LEVEL 7 - UNITS INWALL | 440 | LEVEL 7 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.554 | 9000030 |  | PF.554 | PF.554 | 0% |  |  | 2025-10-22 |  | 2025-10-05 | 24
[8 empty] | 9000030 | 555 | 320001TUR | Stephen Yee | LEVEL 8 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-05 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-11-12 | 2025-11-17 | 2025-11-19 |  | 2025-11-24 | DATES MISALIGNED | 2025-12-01 | [6 empty] | 555 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 555-320001TUR | PRE-FAB - LEVEL 8 - UNITS INWALL | 481 | LEVEL 8 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.555 | 9000030 |  | PF.555 | PF.555 | 0% |  |  | 2025-10-29 |  | 2025-10-05 | 29
[8 empty] | 9000030 | 556 | 320001TUR | Stephen Yee | LEVEL 9 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 491 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-12 | [7 empty] | 44.3324 | 2.7708 | 3 | 2 | 2025-11-19 | 2025-11-23 | 2025-11-25 |  | 2025-12-01 | DATES MISALIGNED | 2025-12-08 | [6 empty] | 556 | 25 |  | 0 | 0 | 0.09029 | 44.3324 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 556-320001TUR | PRE-FAB - LEVEL 9 - UNITS INWALL | 514 | LEVEL 9 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.556 | 9000030 |  | PF.556 | PF.556 | 0% |  |  | 2025-11-05 |  | 2025-10-05 | 34
[8 empty] | 9000030 | 557 | 320001TUR | Stephen Yee | LEVEL 10 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 491 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-19 | [7 empty] | 44.3324 | 2.7708 | 3 | 2 | 2025-11-26 | 2025-12-01 | 2025-12-03 |  | 2025-12-08 |  | 2025-12-12 | [6 empty] | 557 | 25 |  | 0 | 0 | 0.09029 | 44.3324 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 557-320001TUR | PRE-FAB - LEVEL 10 - UNITS INWALL | 553 | LEVEL 10 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.557 | 9000030 |  | PF.557 | PF.557 | 0% |  |  | 2025-11-12 |  | 2025-10-05 | 39
[8 empty] | 9000030 | 558 | 320001TUR | Stephen Yee | LEVEL 11 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 491 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-26 | [7 empty] | 44.3324 | 2.7708 | 3 | 2 | 2025-12-03 | 2025-12-08 | 2025-12-10 |  | 2025-12-15 |  | 2025-12-19 | [6 empty] | 558 | 25 |  | 0 | 0 | 0.09029 | 44.3324 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 558-320001TUR | PRE-FAB - LEVEL 11 - UNITS INWALL | 586 | LEVEL 11 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.558 | 9000030 |  | PF.558 | PF.558 | 0% |  |  | 2025-11-19 |  | 2025-10-05 | 44
[8 empty] | 9000030 | 559 | 320001TUR | Stephen Yee | LEVEL 12 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 491 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-03 | [7 empty] | 44.3324 | 2.7708 | 3 | 2 | 2025-12-10 | 2025-12-15 | 2025-12-17 |  | 2025-12-22 | DATES MISALIGNED | 2025-12-29 | [6 empty] | 559 | 25 |  | 0 | 0 | 0.09029 | 44.3324 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 559-320001TUR | PRE-FAB - LEVEL 12 - UNITS INWALL | 627 | LEVEL 12 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.559 | 9000030 |  | PF.559 | PF.559 | 0% |  |  | 2025-11-26 |  | 2025-10-05 | 49
[8 empty] | 9000030 | 560 | 320001TUR | Stephen Yee | LEVEL 14 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 483 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-17 | [7 empty] | 43.6101 | 2.7256 | 3 | 2 | 2025-12-24 | 2025-12-28 | 2025-12-30 |  | 2026-01-05 | DATES MISALIGNED | 2026-01-12 | [6 empty] | 560 | 26 |  | 0 | 0 | 0.09029 | 43.6101 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 560-320001TUR | PRE-FAB - LEVEL 14 - UNITS INWALL | 708 | LEVEL 14 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.560 | 9000030 |  | PF.560 | PF.560 | 0% |  |  | 2025-12-10 |  | 2025-10-05 | 59
[8 empty] | 9000030 | 561 | 320001TUR | Stephen Yee | LEVEL 15 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-24 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2025-12-31 | 2026-01-05 | 2026-01-07 |  | 2026-01-12 |  | 2026-01-16 | [6 empty] | 561 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 561-320001TUR | PRE-FAB - LEVEL 15 - UNITS INWALL | 731 | LEVEL 15 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.561 | 9000030 |  | PF.561 | PF.561 | 0% |  |  | 2025-12-17 |  | 2025-10-05 | 64
[8 empty] | 9000030 | 562 | 320001TUR | Stephen Yee | LEVEL 16 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-31 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-01-07 | 2026-01-12 | 2026-01-14 |  | 2026-01-20 |  | 2026-01-26 | [6 empty] | 562 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 562-320001TUR | PRE-FAB - LEVEL 16 - UNITS INWALL | 784 | LEVEL 16 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.562 | 9000030 |  | PF.562 | PF.562 | 0% |  |  | 2025-12-24 |  | 2025-10-05 | 69
[8 empty] | 9000030 | 563 | 320001TUR | Stephen Yee | LEVEL 17 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-07 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-01-14 | 2026-01-19 | 2026-01-21 |  | 2026-01-26 | DATES MISALIGNED | 2026-02-02 | [6 empty] | 563 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 563-320001TUR | PRE-FAB - LEVEL 17 - UNITS INWALL | 834 | LEVEL 17 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.563 | 9000030 |  | PF.563 | PF.563 | 0% |  |  | 2025-12-31 |  | 2025-10-05 | 74
[8 empty] | 9000030 | 564 | 320001TUR | Stephen Yee | LEVEL 18 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-14 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-01-21 | 2026-01-26 | 2026-01-28 |  | 2026-02-02 |  | 2026-02-06 | [6 empty] | 564 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 564-320001TUR | PRE-FAB - LEVEL 18 - UNITS INWALL | 884 | LEVEL 18 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.564 | 9000030 |  | PF.564 | PF.564 | 0% |  |  | 2026-01-07 |  | 2025-10-05 | 79
[8 empty] | 9000030 | 565 | 320001TUR | Stephen Yee | LEVEL 19 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-21 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-01-28 | 2026-02-02 | 2026-02-04 |  | 2026-02-09 |  | 2026-02-13 | [6 empty] | 565 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 565-320001TUR | PRE-FAB - LEVEL 19 - UNITS INWALL | 924 | LEVEL 19 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.565 | 9000030 |  | PF.565 | PF.565 | 0% |  |  | 2026-01-14 |  | 2025-10-05 | 84
[8 empty] | 9000030 | 566 | 320001TUR | Stephen Yee | LEVEL 20 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-28 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-02-04 | 2026-02-09 | 2026-02-11 |  | 2026-02-17 |  | 2026-02-23 | [6 empty] | 566 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 566-320001TUR | PRE-FAB - LEVEL 20 - UNITS INWALL | 962 | LEVEL 20 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.566 | 9000030 |  | PF.566 | PF.566 | 0% |  |  | 2026-01-21 |  | 2025-10-05 | 89
[8 empty] | 9000030 | 567 | 320001TUR | Stephen Yee | LEVEL 21 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-04 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-02-11 | 2026-02-16 | 2026-02-18 |  | 2026-02-23 | DATES MISALIGNED | 2026-03-02 | [6 empty] | 567 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 567-320001TUR | PRE-FAB - LEVEL 21 - UNITS INWALL | 1007 | LEVEL 21 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.567 | 9000030 |  | PF.567 | PF.567 | 0% |  |  | 2026-01-28 |  | 2025-10-05 | 94
[8 empty] | 9000010 | 568 | 320001TUR | Chris Gauvin, Stephen Yee | LEVEL 1 | LIGHT FIXTURE WIRED ASSEMBLY (2) LUMINARY WHIPS | (LOADING DOCK) S50 FIXTURE STRUT ASSEMBLIES | 19 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-10 | Chris Gauvin | TRUE | true | TRUE | True | APPROVED | 5.32 | 0.665 | 1 | 1 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-27 |  |  |  |  | Image 2025-09-29 13-53-41.jpeg |  | 13 | Kerri Pandolfi | 568 | 25 |  | 1.3158 | 25 | 0.28 | 5.32 | 0.29 | 5.51 | 0.28 | 0.01 | 0.28 | 0 | 25 | 568-320001TUR | PRE-FAB - LEVEL 1 - (LOADING DOCK) S50 FIXTURE STRUT ASSEMBLIES | 1916 |  | PF.568 | 9000010 |  | PF.568 | PF.568 | 99% |  |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[8 empty] | 9000030 | 569 | 320001TUR | Stephen Yee | LEVEL 3 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 3 - MOCK UP UNIT (S-2) INWALL | 24 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-09 | 2025-09-17 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4.3728 | 0.5466 | 1 | 1 | 2025-09-16 | 2025-09-17 | 2025-09-19 |  | 2025-09-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | 2025-10-01 |  | 2 | Kerri Pandolfi | 569 | 25 |  | 0.25 | 6 | 0.1822 | 4.3728 | 1.15 | 27.6 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 569-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - MOCK UP UNIT (S-2) INWALL | #NO MATCH | #NO MATCH | PF.569 | 9000030 |  | PF.569 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-09-02 |  | 2025-10-05 | -14 | TRUE
[8 empty] | 9000030 | 570 | 320001TUR | Stephen Yee | LEVEL 3 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 3 - MOCK UP UNIT (A-1) INWALL | 31 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-09 | 2025-09-17 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.6482 | 0.70603 | 1 | 1 | 2025-09-16 | 2025-09-17 | 2025-09-19 |  | 2025-09-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | 2025-10-01 |  | 2 | Kerri Pandolfi | 570 | 25 |  | 0.30645 | 9.5 | 0.1822 | 5.6482 | 1.15 | 35.65 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 570-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - MOCK UP UNIT (A-1) INWALL | #NO MATCH | #NO MATCH | PF.570 | 9000030 |  | PF.570 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-09-02 |  | 2025-10-05 | -14 | TRUE
[8 empty] | 9000220 | 571 | 320001TUR | Stephen Yee | LEVEL 3 | TEMPS (SMALL) | CORE HOLE (PLYWOOD) PLUG | 60 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-05 | 2025-09-18 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 60 | 7.5 | 8 | 1 | 2025-09-12 | 2025-09-24 | 2025-09-26 |  | 2025-09-26 |  |  |  |  | 2025-09-29 |  |  | Kerri Pandolfi | 571 | 25 |  | 0 | 0 | 1 | 60 | 2 | 120 | 1 | 1 | 0 | -1 | 25 | 571-320001TUR | PRE-FAB - LEVEL 3 - CORE HOLE (PLYWOOD) PLUG | 1918 |  | PF.571 | 9000220 |  | PF.571 | PF.571 | 99% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16
[8 empty] | 9000140 | 572 | 320001TUR | Stephen Yee | LEVEL 3 | SITE LIGHTING ASSEMBLY | L3 - UNITS TEMP LIGHTING (STRINGERS) | 13 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-03 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 7.8 | 0.975 | 1 | 1 | 2025-10-10 | 2025-10-13 | 2025-10-15 |  | 2025-10-27 | [6 empty] | 2 | Kerri Pandolfi | 572 | 25 |  | 0 | 0 | 0.6 | 7.8 | 1.104 | 14.352 | 0.6 | 0.504 | 0 | -0.6 | 25 | 572-320001TUR | PRE-FAB - LEVEL 3 - L3 - UNITS TEMP LIGHTING (STRINGERS) | 1919 |  | PF.572 | 9000140 |  | PF.572 | PF.572 | 0% |  |  | 2025-09-26 |  | 2025-10-05 | 6 | TRUE
[8 empty] | 9000140 | 573 | 320001TUR | Stephen Yee | LEVEL 4 | SITE LIGHTING ASSEMBLY | L4 - UNITS TEMP LIGHTING (STRINGERS) | 13 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-10 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 7.8 | 0.975 | 1 | 1 | 2025-10-17 | 2025-10-20 | 2025-10-22 |  | 2025-10-27 | [7 empty] | Kerri Pandolfi | 573 | 25 |  | 0 | 0 | 0.6 | 7.8 | 1.104 | 14.352 | 0.6 | 0.504 | 0 | -0.6 | 25 | 573-320001TUR | PRE-FAB - LEVEL 4 - L4 - UNITS TEMP LIGHTING (STRINGERS) | 1920 |  | PF.573 | 9000140 |  | PF.573 | PF.573 | 0% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[8 empty] | 9000140 | 574 | 320001TUR | Stephen Yee | LEVEL 5 | SITE LIGHTING ASSEMBLY | L5 - UNITS TEMP LIGHTING (STRINGERS) | 13 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 7.8 | 0.975 | 1 | 1 | 2025-10-31 | 2025-11-02 | 2025-11-04 |  | 2025-11-07 | [7 empty] | Kerri Pandolfi | 574 | 25 |  | 0 | 0 | 0.6 | 7.8 | 1.104 | 14.352 | 0.6 | 0.504 | 0 | -0.6 | 25 | 574-320001TUR | PRE-FAB - LEVEL 5 - L5 - UNITS TEMP LIGHTING (STRINGERS) | 1921 |  | PF.574 | 9000140 |  | PF.574 | PF.574 | 0% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[8 empty] | 9000140 | 575 | 320001TUR | Stephen Yee | LEVEL 7 | SITE LIGHTING ASSEMBLY | L7 - UNITS TEMP LIGHTING (STRINGERS) | 12 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | [7 empty] | 7.2 | 0.9 | 1 | 1 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-17 | [7 empty] | Kerri Pandolfi | 575 | 25 |  | 0 | 0 | 0.6 | 7.2 | 1.104 | 13.248 | 0.6 | 0.504 | 0 | -0.6 | 25 | 575-320001TUR | PRE-FAB - LEVEL 7 - L7 - UNITS TEMP LIGHTING (STRINGERS) | 1922 |  | PF.575 | 9000140 |  | PF.575 | PF.575 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[8 empty] | 9000140 | 576 | 320001TUR | Stephen Yee | LEVEL 8 | SITE LIGHTING ASSEMBLY | L8 - UNITS TEMP LIGHTING (STRINGERS) | 12 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-07 | [7 empty] | 7.2 | 0.9 | 1 | 1 | 2025-11-14 | 2025-11-17 | 2025-11-19 |  | 2025-11-24 | [7 empty] | Kerri Pandolfi | 576 | 25 |  | 0 | 0 | 0.6 | 7.2 | 1.104 | 13.248 | 0.6 | 0.504 | 0 | -0.6 | 25 | 576-320001TUR | PRE-FAB - LEVEL 8 - L8 - UNITS TEMP LIGHTING (STRINGERS) | 1923 |  | PF.576 | 9000140 |  | PF.576 | PF.576 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[8 empty] | 9000140 | 577 | 320001TUR | Stephen Yee | LEVEL 9 | SITE LIGHTING ASSEMBLY | L9 - UNITS TEMP LIGHTING (STRINGERS) | 12 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-14 | [7 empty] | 7.2 | 0.9 | 1 | 1 | 2025-11-21 | 2025-11-23 | 2025-11-25 |  | 2025-12-01 | [7 empty] | Kerri Pandolfi | 577 | 25 |  | 0 | 0 | 0.6 | 7.2 | 1.104 | 13.248 | 0.6 | 0.504 | 0 | -0.6 | 25 | 577-320001TUR | PRE-FAB - LEVEL 9 - L9 - UNITS TEMP LIGHTING (STRINGERS) | 1924 |  | PF.577 | 9000140 |  | PF.577 | PF.577 | 0% |  |  | 2025-11-07 |  | 2025-10-05 | 36
[8 empty] | 9000140 | 578 | 320001TUR | Stephen Yee | LEVEL 10 | SITE LIGHTING ASSEMBLY | L10 - UNITS TEMP LIGHTING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-20 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-11-27 | 2025-12-01 | 2025-12-03 |  | 2025-12-08 | [7 empty] | Kerri Pandolfi | 578 | 25 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 25 | 578-320001TUR | PRE-FAB - LEVEL 10 - L10 - UNITS TEMP LIGHTING (STRINGERS) | 1925 |  | PF.578 | 9000140 |  | PF.578 | PF.578 | 0% |  |  | 2025-11-13 |  | 2025-10-05 | 40
[8 empty] | 9000140 | 579 | 320001TUR | Stephen Yee | LEVEL 11 | SITE LIGHTING ASSEMBLY | L11 - UNITS TEMP LIGHTING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-27 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-12-04 | 2025-12-08 | 2025-12-10 |  | 2025-12-15 | [7 empty] | Kerri Pandolfi | 579 | 25 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 25 | 579-320001TUR | PRE-FAB - LEVEL 11 - L11 - UNITS TEMP LIGHTING (STRINGERS) | 1926 |  | PF.579 | 9000140 |  | PF.579 | PF.579 | 0% |  |  | 2025-11-20 |  | 2025-10-05 | 45
[8 empty] | 9000140 | 580 | 320001TUR | Stephen Yee | LEVEL 12 | SITE LIGHTING ASSEMBLY | L12 - UNITS TEMP LIGHTING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-04 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-12-11 | 2025-12-15 | 2025-12-17 |  | 2025-12-22 | [7 empty] | Kerri Pandolfi | 580 | 25 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 25 | 580-320001TUR | PRE-FAB - LEVEL 12 - L12 - UNITS TEMP LIGHTING (STRINGERS) | 1928 |  | PF.580 | 9000140 |  | PF.580 | PF.580 | 0% |  |  | 2025-11-27 |  | 2025-10-05 | 50
[8 empty] | 9000140 | 581 | 320001TUR | Stephen Yee | LEVEL 13 | SITE LIGHTING ASSEMBLY | L13 - UNITS TEMP LIGHTING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-11 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-12-18 | 2025-12-21 | 2025-12-23 |  | 2025-12-29 | [7 empty] | Kerri Pandolfi | 581 | 25 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 25 | 581-320001TUR | PRE-FAB - LEVEL 13 - L13 - UNITS TEMP LIGHTING (STRINGERS) | 1929 |  | PF.581 | 9000140 |  | PF.581 | PF.581 | 0% |  |  | 2025-12-04 |  | 2025-10-05 | 55
[8 empty] | 9000140 | 582 | 320001TUR | Stephen Yee | LEVEL 14 | SITE LIGHTING ASSEMBLY | L14 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-18 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-12-25 | 2025-12-28 | 2025-12-30 |  | 2026-01-05 | [7 empty] | Kerri Pandolfi | 582 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 582-320001TUR | PRE-FAB - LEVEL 14 - L14 - UNITS TEMP LIGHTHING (STRINGERS) | 1930 |  | PF.582 | 9000140 |  | PF.582 | PF.582 | 0% |  |  | 2025-12-11 |  | 2025-10-05 | 60
[8 empty] | 9000140 | 583 | 320001TUR | Stephen Yee | LEVEL 15 | SITE LIGHTING ASSEMBLY | L15 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-25 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-01 | 2026-01-05 | 2026-01-07 |  | 2026-01-12 | [7 empty] | Kerri Pandolfi | 583 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 583-320001TUR | PRE-FAB - LEVEL 15 - L15 - UNITS TEMP LIGHTHING (STRINGERS) | 1931 |  | PF.583 | 9000140 |  | PF.583 | PF.583 | 0% |  |  | 2025-12-18 |  | 2025-10-05 | 65
[8 empty] | 9000140 | 584 | 320001TUR | Stephen Yee | LEVEL 16 | SITE LIGHTING ASSEMBLY | L16 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-01 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-08 | 2026-01-12 | 2026-01-14 |  | 2026-01-20 | [7 empty] | Kerri Pandolfi | 584 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 584-320001TUR | PRE-FAB - LEVEL 16 - L16 - UNITS TEMP LIGHTHING (STRINGERS) | 1932 |  | PF.584 | 9000140 |  | PF.584 | PF.584 | 0% |  |  | 2025-12-25 |  | 2025-10-05 | 70
[8 empty] | 9000140 | 585 | 320001TUR | Stephen Yee | LEVEL 17 | SITE LIGHTING ASSEMBLY | L17 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-08 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-15 | 2026-01-19 | 2026-01-21 |  | 2026-01-26 | [7 empty] | Kerri Pandolfi | 585 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 585-320001TUR | PRE-FAB - LEVEL 17 - L17 - UNITS TEMP LIGHTHING (STRINGERS) | 1933 |  | PF.585 | 9000140 |  | PF.585 | PF.585 | 0% |  |  | 2026-01-01 |  | 2025-10-05 | 75
[8 empty] | 9000140 | 586 | 320001TUR | Stephen Yee | LEVEL 18 | SITE LIGHTING ASSEMBLY | L18 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-15 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-22 | 2026-01-26 | 2026-01-28 |  | 2026-02-02 | [7 empty] | Kerri Pandolfi | 586 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 586-320001TUR | PRE-FAB - LEVEL 18 - L18 - UNITS TEMP LIGHTHING (STRINGERS) | 1935 |  | PF.586 | 9000140 |  | PF.586 | PF.586 | 0% |  |  | 2026-01-08 |  | 2025-10-05 | 80
[8 empty] | 9000140 | 587 | 320001TUR | Stephen Yee | LEVEL 19 | SITE LIGHTING ASSEMBLY | L19 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-22 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-29 | 2026-02-02 | 2026-02-04 |  | 2026-02-09 | [7 empty] | Kerri Pandolfi | 587 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 587-320001TUR | PRE-FAB - LEVEL 19 - L19 - UNITS TEMP LIGHTHING (STRINGERS) | 1936 |  | PF.587 | 9000140 |  | PF.587 | PF.587 | 0% |  |  | 2026-01-15 |  | 2025-10-05 | 85
[8 empty] | 9000140 | 588 | 320001TUR | Stephen Yee | LEVEL 20 | SITE LIGHTING ASSEMBLY | L20 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-29 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-02-05 | 2026-02-09 | 2026-02-11 |  | 2026-02-17 | [7 empty] | Kerri Pandolfi | 588 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 588-320001TUR | PRE-FAB - LEVEL 20 - L20 - UNITS TEMP LIGHTHING (STRINGERS) | 1937 |  | PF.588 | 9000140 |  | PF.588 | PF.588 | 0% |  |  | 2026-01-22 |  | 2025-10-05 | 90
[8 empty] | 9000140 | 589 | 320001TUR | Stephen Yee | LEVEL 21 | SITE LIGHTING ASSEMBLY | L21 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-05 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-02-12 | 2026-02-16 | 2026-02-18 |  | 2026-02-23 | [7 empty] | Kerri Pandolfi | 589 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 589-320001TUR | PRE-FAB - LEVEL 21 - L21 - UNITS TEMP LIGHTHING (STRINGERS) | 1938 |  | PF.589 | 9000140 |  | PF.589 | PF.589 | 0% |  |  | 2026-01-29 |  | 2025-10-05 | 95
[8 empty] | 9000140 | 590 | 320001TUR | Stephen Yee | LEVEL 22 | SITE LIGHTING ASSEMBLY | L22 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-12 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-02-19 | 2026-02-23 | 2026-02-25 |  | 2026-03-02 | [7 empty] | Kerri Pandolfi | 590 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 590-320001TUR | PRE-FAB - LEVEL 22 - L22 - UNITS TEMP LIGHTHING (STRINGERS) | 1939 |  | PF.590 | 9000140 |  | PF.590 | PF.590 | 0% |  |  | 2026-02-05 |  | 2025-10-05 | 100
[8 empty] | 9000140 | 591 | 320001TUR | Stephen Yee | LEVEL 23 | SITE LIGHTING ASSEMBLY | L23 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-19 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-02-26 | 2026-03-02 | 2026-03-04 |  | 2026-03-09 | [7 empty] | Kerri Pandolfi | 591 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 591-320001TUR | PRE-FAB - LEVEL 23 - L23 - UNITS TEMP LIGHTHING (STRINGERS) | 1940 |  | PF.591 | 9000140 |  | PF.591 | PF.591 | 0% |  |  | 2026-02-12 |  | 2025-10-05 | 105
[8 empty] | 9000140 | 592 | 320001TUR | Stephen Yee | LEVEL 24 | SITE LIGHTING ASSEMBLY | L24 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-26 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-03-05 | 2026-03-09 | 2026-03-11 |  | 2026-03-16 | [7 empty] | Kerri Pandolfi | 592 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 592-320001TUR | PRE-FAB - LEVEL 24 - L24 - UNITS TEMP LIGHTHING (STRINGERS) | 1942 |  | PF.592 | 9000140 |  | PF.592 | PF.592 | 0% |  |  | 2026-02-19 |  | 2025-10-05 | 110
[8 empty] | 9000140 | 593 | 320001TUR | Stephen Yee | LEVEL 25 | SITE LIGHTING ASSEMBLY | L25 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-05 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-03-12 | 2026-03-16 | 2026-03-18 |  | 2026-03-23 | [7 empty] | Kerri Pandolfi | 593 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 593-320001TUR | PRE-FAB - LEVEL 25 - L25 - UNITS TEMP LIGHTHING (STRINGERS) | 1943 |  | PF.593 | 9000140 |  | PF.593 | PF.593 | 0% |  |  | 2026-02-26 |  | 2025-10-05 | 115
[8 empty] | 9000140 | 594 | 320001TUR | Stephen Yee | LEVEL 26 | SITE LIGHTING ASSEMBLY | L26 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-13 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-03-20 | 2026-03-24 | 2026-03-26 |  | 2026-03-30 | [7 empty] | Kerri Pandolfi | 594 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 594-320001TUR | PRE-FAB - LEVEL 26 - L26 - UNITS TEMP LIGHTHING (STRINGERS) | 1945 |  | PF.594 | 9000140 |  | PF.594 | PF.594 | 0% |  |  | 2026-03-06 |  | 2025-10-05 | 121
[8 empty] | 9000140 | 595 | 320001TUR | Stephen Yee | LEVEL 27 | SITE LIGHTING ASSEMBLY | L27 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-19 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-03-26 | 2026-03-30 | 2026-04-01 |  | 2026-04-06 | [7 empty] | Kerri Pandolfi | 595 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 595-320001TUR | PRE-FAB - LEVEL 27 - L27 - UNITS TEMP LIGHTHING (STRINGERS) | 1947 |  | PF.595 | 9000140 |  | PF.595 | PF.595 | 0% |  |  | 2026-03-12 |  | 2025-10-05 | 125
[8 empty] | 9000140 | 596 | 320001TUR | Stephen Yee | LEVEL 28 | SITE LIGHTING ASSEMBLY | L28 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-26 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-04-02 | 2026-04-06 | 2026-04-08 |  | 2026-04-13 | [7 empty] | Kerri Pandolfi | 596 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 596-320001TUR | PRE-FAB - LEVEL 28 - L28 - UNITS TEMP LIGHTHING (STRINGERS) | 1949 |  | PF.596 | 9000140 |  | PF.596 | PF.596 | 0% |  |  | 2026-03-19 |  | 2025-10-05 | 130
[8 empty] | 9000140 | 597 | 320001TUR | Stephen Yee | LEVEL 29 | SITE LIGHTING ASSEMBLY | L29 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-02 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-04-09 | 2026-04-13 | 2026-04-15 |  | 2026-04-21 | [7 empty] | Kerri Pandolfi | 597 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 597-320001TUR | PRE-FAB - LEVEL 29 - L29 - UNITS TEMP LIGHTHING (STRINGERS) | 1951 |  | PF.597 | 9000140 |  | PF.597 | PF.597 | 0% |  |  | 2026-03-26 |  | 2025-10-05 | 135
[8 empty] | 9000140 | 598 | 320001TUR | Stephen Yee | LEVEL 30 | SITE LIGHTING ASSEMBLY | L30 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-10 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-04-17 | 2026-04-21 | 2026-04-23 |  | 2026-04-28 | [7 empty] | Kerri Pandolfi | 598 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 598-320001TUR | PRE-FAB - LEVEL 30 - L30 - UNITS TEMP LIGHTHING (STRINGERS) | 1954 |  | PF.598 | 9000140 |  | PF.598 | PF.598 | 0% |  |  | 2026-04-03 |  | 2025-10-05 | 141
[8 empty] | 9000140 | 599 | 320001TUR | Stephen Yee | LEVEL 31 | SITE LIGHTING ASSEMBLY | L31 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-17 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-04-24 | 2026-04-28 | 2026-04-30 |  | 2026-05-05 | [7 empty] | Kerri Pandolfi | 599 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 599-320001TUR | PRE-FAB - LEVEL 31 - L31 - UNITS TEMP LIGHTHING (STRINGERS) | 1956 |  | PF.599 | 9000140 |  | PF.599 | PF.599 | 0% |  |  | 2026-04-10 |  | 2025-10-05 | 146
[8 empty] | 9000140 | 600 | 320001TUR | Stephen Yee | LEVEL 32 | SITE LIGHTING ASSEMBLY | L32 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-24 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-05-01 | 2026-05-05 | 2026-05-07 |  | 2026-05-12 | [7 empty] | Kerri Pandolfi | 600 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 600-320001TUR | PRE-FAB - LEVEL 32 - L32 - UNITS TEMP LIGHTHING (STRINGERS) | 1958 |  | PF.600 | 9000140 |  | PF.600 | PF.600 | 0% |  |  | 2026-04-17 |  | 2025-10-05 | 151
[8 empty] | 9000140 | 601 | 320001TUR | Stephen Yee | LEVEL 33 | SITE LIGHTING ASSEMBLY | L33 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-01 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-05-08 | 2026-05-12 | 2026-05-14 |  | 2026-05-19 | [7 empty] | Kerri Pandolfi | 601 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 601-320001TUR | PRE-FAB - LEVEL 33 - L33 - UNITS TEMP LIGHTHING (STRINGERS) | 1960 |  | PF.601 | 9000140 |  | PF.601 | PF.601 | 0% |  |  | 2026-04-24 |  | 2025-10-05 | 156
[8 empty] | 9000140 | 602 | 320001TUR | Stephen Yee | LEVEL 34 | SITE LIGHTING ASSEMBLY | L34 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-08 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-05-15 | 2026-05-19 | 2026-05-21 |  | 2026-05-27 | [7 empty] | Kerri Pandolfi | 602 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 602-320001TUR | PRE-FAB - LEVEL 34 - L34 - UNITS TEMP LIGHTHING (STRINGERS) | 1962 |  | PF.602 | 9000140 |  | PF.602 | PF.602 | 0% |  |  | 2026-05-01 |  | 2025-10-05 | 161
[8 empty] | 9000140 | 603 | 320001TUR | Stephen Yee | LEVEL 35 | SITE LIGHTING ASSEMBLY | L35 - UNITS TEMP LIGHTHING (STRINGERS) | 7 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-19 | [7 empty] | 4.2 | 0.525 | 1 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-29 |  | 2026-06-03 | [7 empty] | Kerri Pandolfi | 603 | 26 |  | 0 | 0 | 0.6 | 4.2 | 1.104 | 7.728 | 0.6 | 0.504 | 0 | -0.6 | 26 | 603-320001TUR | PRE-FAB - LEVEL 35 - L35 - UNITS TEMP LIGHTHING (STRINGERS) | 1964 |  | PF.603 | 9000140 |  | PF.603 | PF.603 | 0% |  |  | 2026-05-12 |  | 2025-10-05 | 168
[8 empty] | 9000140 | 604 | 320001TUR | Stephen Yee | LEVEL 36 | SITE LIGHTING ASSEMBLY | L36 - UNITS TEMP LIGHTHING (STRINGERS) | 7 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-26 | [7 empty] | 4.2 | 0.525 | 1 | 1 | 2026-06-02 | 2026-06-03 | 2026-06-05 |  | 2026-06-10 | [7 empty] | Kerri Pandolfi | 604 | 26 |  | 0 | 0 | 0.6 | 4.2 | 1.104 | 7.728 | 0.6 | 0.504 | 0 | -0.6 | 26 | 604-320001TUR | PRE-FAB - LEVEL 36 - L36 - UNITS TEMP LIGHTHING (STRINGERS) | 1966 |  | PF.604 | 9000140 |  | PF.604 | PF.604 | 0% |  |  | 2026-05-19 |  | 2025-10-05 | 173
[8 empty] | 9000010 | 605 | 320001TUR | Stephen Yee | LEVEL 11 | IN-WALL SWITCH ASSEMBLIES (LIGHTING) | BOH DEVICES (L11-L36) | 234 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-18 | 2025-09-23 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 17.55 | 1.0969 | 2 | 2 | 2025-09-25 | 2025-09-29 | 2025-10-01 |  | 2025-10-13 |  |  |  |  | Image 2025-09-29 13-53-08.jpeg |  | 14 | Kerri Pandolfi | 605 | 25 |  | 0.13248 | 31 | 0.075 | 17.55 | 0.62 | 145.08 | 0.075 | 0.545 | 0.075 | 0 | 25 | 605-320001TUR | PRE-FAB - LEVEL 11 - BOH DEVICES (L11-L36) | 1927 |  | PF.605 | 9000010 |  | PF.605 | PF.605 | 99% | TRUE |  | 2025-09-11 |  | 2025-10-05 | -7 | TRUE
[8 empty] | 9000221 | X | 320001TUR | John McCullough, Pat Cameron | LEVEL B1 | TEMP POWER DRAGO | 3000AMP DRAGO #206 | 1 | Gray | 121 BROADWAY MXD TOWER | Doug Durand, Eriberto Velez | 2023-10-30 | 2023-10-13 | Pat Cameron | TRUE | true | TRUE | True | APPROVED | 240 | 30 | 30 | 1 | 2023-11-06 | 2023-12-16 | 2023-12-18 |  | 2023-12-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE | MATTHEW C MAJESKI | Image 2023-12-07 13-45-13.jpeg | N/A | 6 | Kerri Pandolfi | #INVALID VALUE | 23 |  | #INVALID VALUE | #INVALID VALUE | 240 | 240 |  | 0 | 240 | -240 | #INVALID VALUE | #INVALID VALUE | 23 | X-320001TUR | PRE-FAB - LEVEL B1 - 3000AMP DRAGO #206 | #NO MATCH | #NO MATCH | PF.X | 9000221 |  | PF.X | NOT ON PROJECT SCHEDULE | 100% |  |  | 2023-10-23 |  | 2025-10-05 | -500

## Comments
Row 903 | NO PIPE ON L4 | Eddie Velez | 10/03/25 2:47 PM
Row 904 | NO PIPE ON L5 | Eddie Velez | 10/03/25 2:47 PM
Row 905 | @jcampbell@sullymac.com Jimbo, what date should I push this out to? | Eddie Velez | 09/25/25 5:54 AM
Row 979 | NO PREFAB OUTSIDE LAUNDRY/BATHROOM | Eddie Velez | 08/28/25 6:37 AM
Row 980 | JBs ARE DUE IN ON 9/4/25 | Eddie Velez | 09/04/25 6:13 AM
Row 982 | NO JB ON L3 | Eddie Velez | 10/03/25 2:49 PM
Row 983 | NO JB ON L4 | Eddie Velez | 10/03/25 2:49 PM
Row 984 | NO JB ON L5 | Eddie Velez | 10/03/25 2:50 PM
Row 985 | Due to open ceilings and inaccessible ceiling areas, L6 is Direct-to-Device Homeruns | Eddie Velez | 09/18/25 5:57 AM
Row 1019 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:26 PM
Row 1020 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:27 PM
| THIS CHANGED FROM ALL OF L2 TO JUST VAULT HANGERS ON 9/5/25 | Eddie Velez | 09/05/25 11:53 AM
Row 1021 | @warehouse180@sullymac.com @jcampbell@sullymac.com @syee@sullymac.com Tony/Jim, Please schedule this Fab to be picked with Fab 348 and have them both delivered to site for Monday 8/4. Thank you, | Paul Simcoe | 07/31/25 10:19 AM
Row 1026 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:26 PM
Row 1027 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:27 PM
Row 1028 | COORDINATION TIMELINE TOO TIGHT | Paul Simcoe | 08/01/25 1:19 PM
Row 1033 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:26 PM
Row 1084 | CHANGED FROM A "WIRED" ASSEMBLY TO A STRUT ONLY BUILD (ADDED TO FAB#288) | Eddie Velez | 10/02/25 12:01 PM
Row 1084 | NO PREFAB NEEDED | Arthur Mayo | 07/25/25 6:20 AM
Row 1086 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:22 AM
Row 1101 | NO PREFAB NEEDED | Arthur Mayo | 07/25/25 6:15 AM
Row 1102 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:17 AM
Row 1103 | NO PREFAB NEEDED | Arthur Mayo | 07/25/25 6:18 AM
Row 1106 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:21 AM
Row 1108 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:23 AM
Row 1110 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:24 AM
Row 1111 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:25 AM
Row 1112 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:26 AM
Row 1114 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:27 AM
Row 1115 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:27 AM
Row 1117 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:28 AM
Row 1118 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:29 AM
Row 1119 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:30 AM
Row 1120 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:30 AM
Row 1121 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:31 AM
Row 1122 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:32 AM
Row 1123 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:33 AM
Row 1124 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:34 AM
Row 1125 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:35 AM
Row 1126 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:35 AM
Row 1128 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:37 AM
Row 1129 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:38 AM
Row 1130 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:38 AM
Row 1131 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:39 AM
Row 1132 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:39 AM
Row 1137 | RFI OUT ON CHIEF PACS TEL DATA SIZE REQUIREMENTS | Eddie Velez | 09/04/25 6:14 AM
Row 1145 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 1146 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 1169 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 1170 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 1171 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 1172 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 1173 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 1252 | RFI OUT ON DEVICES FOR THIS AREA | Eddie Velez | 09/04/25 6:12 AM
Row 1255 | ROUGHED IN THE FIELD | Eddie Velez | 10/03/25 12:00 PM
Row 1351 | @amayo@sullymac.com @evelez@sullymac.com ARTY, CAN YOU PLEASE GET WITH MATT TO CONFIRM THE MATERIALS FOR THIS BUILD. | Douglas Durand | 08/12/25 7:03 AM
Row 1353 | @jcampbell@sullymac.com @syee@sullymac.com Jim, Can we squeeze in this fab today with the riser sleeves? Steve wants this onsite as a reference for the rest of the building. | Paul Simcoe | 09/02/25 8:04 AM
| ON IT | james campbell | 09/02/25 8:57 AM
Row 1387 | INSTALLED ONSITE | Paul Simcoe | 08/19/25 11:32 AM
Row 1388 | INSTALLED ONSITE FOR MOCKUP | Paul Simcoe | 08/19/25 11:32 AM
Row 1390 | @psimcoe@sullymac.com ill need a little more info on this | Warehouse Quality Control | 08/28/25 8:25 AM
Row 1427 | STEVE HAS RFI OUT ON NEED FOR FUSED DISCOS | Eddie Velez | 09/04/25 6:15 AM
Row 1465 | @evelez@sullymac.com you sent this to Purner...Right? | james campbell | 09/23/25 1:33 PM
| @jcampbell@sullymac.com No, but his handler did | Eddie Velez | 09/23/25 1:48 PM
| 😂 | james campbell | 09/23/25 1:57 PM
Row 1466 | MATERIALS BOUGHT BY PAUL COBERT PRIOR TO TRANSITION | Eddie Velez | 09/22/25 9:41 AM
Row 1500 | @ddurand@sullymac.com @evelez@sullymac.com I believe this is shipped? Just need to check the box | Shawn Leahy | 08/30/24 1:35 PM