## STRATUS PACKAGES -ALL PROJECTS
Package Name | Tracking Status | Qty Planned | Qty Complete | %Complete | Hours Estimated | Actual Hours | Division | COST CODE | FAB # | JOB# (HIDDEN) | FOREMAN CONTACT | LOCATION | CATEGORY | PRE-FAB ITEM | QUANTITY PER BUILD | STATUS (HIDDEN) | PROJECT NAME (HIDDEN) | DETAILER | DETAIL DUE BY | DETAIL COMPLETE | DETAIL APPROVAL | MATERIAL RECEIVED | MATERIAL RECEIVED HELPER (HIDDEN) | EQUIPMENT RECEIVED | EQUIPMENT RECEIVED HELPER (HIDDEN) | APPROVAL TO BEGIN FAB | ESTIMATED MAN HOURS PER BUILD (HIDDEN) | WORK DAYS (HIDDEN) | WORK DAYS | CREW | PRE-FAB BUILD START | PRE-FAB BUILD END | PROJECTED COMPLETE DATE | PROJECTED LATER THAN DUE HELPER (HIDDEN) | DUE ON SITE | DUE ONSITE-PROJECT SCHEDULE DUE ONSITE (HIDDEN) | PROJECT SCHEDULE DUE ON SITE DATE (REFERENCE) | SHIPPED TO SITE | CREW MEMBERS (HIDDEN) | PRE-FAB COMPLETE | MATERIAL TRANSFER | STATION (HIDDEN) | PROJECT MANAGER (HIDDEN) | FAB HELPER (HIDDEN) | BUILD YEAR (HIDDEN) | MATERIAL LOCATION (HIDDEN) | PRE-FAB ACTUAL BUILD TIME (PER UNIT) (HIDDEN) | PRE-FAB ACTUAL BUILD TIME (TOTAL) | PRE-FAB ESTIMATED BUILD TIME (PER UNIT) (HIDDEN) | PRE-FAB ESTIMATED BUILD TIME (TOTAL) | CONEST ESTIMATED HOURS (PER UNIT) (HIDDEN) | CONEST ESTIMATED BUILD TIME (TOTAL) (HIDDEN) | CONEST VS ACTUAL LOWEST - HELPER (HIDDEN) | CONEST LESS THAN ACTUAL - HELPER (HIDDEN) | ESTIMATED VS ACTUAL LOWEST - HELPER (HIDDEN) | ESTIMATED LOWER - HELPER (HIDDEN) | BUILD YEAR HELPER (HIDDEN) | FAB#-JOB# | ACTIVITY DESCRIPTION (HIDDEN) | PROJECT SCHEDULE ROW # (HIDDEN) | ITEM LINK TO IN PROJECT SCHEDULE | ACTIVITY ID | COST CODE HELPER (HIDDEN) | STAR (HIDDEN) | Activity ID PREFAB Helper (HIDDEN) | Activity ID Project Schedule Sheet | % Complete | QA/QC COMPLETE | BIM/CAD COORDINATOR | COORDINATION COMPLETE DUE DATE | COORDINATION COMPLETED | TODAY (HIDDEN) | DAYS FROM TODAY TO PREFAB START (HIDDEN) | STATION CONFIRMED | Last Sync From STRATUS (UTC) | STRATUS.STRATUS_INJECTED_REFERENCE_TYPE_ID | STRATUS_PackageId | STRATUS.Model | STRATUS.#Parts | STRATUS.Hours Estimated | STRATUS.#Assemblies | STRATUS.Project Number | STRATUS.Required | STRATUS.Project Name | STRATUS.Actual Hours | STRATUS.STRATUS_INJECTED_TRACKING_STATUS | STRATUS.%Complete | STRATUS.Division | STRATUS.Package Name | STRATUS.STRATUS_INJECTED_FABRICATION_PARTS_EXIST | STRATUS.Description | STRATUS.#Total Parts | STRATUS.Package Number | STRATUS.#Tasks
[9 empty] | 3193 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3193 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3193-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3193 |  |  | PF.3193 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00513-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00513-LEVEL 23-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00513-320001TUR | 0
[9 empty] | 3194 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3194 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3194-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3194 |  |  | PF.3194 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00514-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00514-LEVEL 24-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00514-320001TUR | 0
[9 empty] | 3195 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3195 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3195-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3195 |  |  | PF.3195 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00515-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00515-LEVEL 25-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00515-320001TUR | 0
[9 empty] | 3196 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3196 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3196-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3196 |  |  | PF.3196 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00516-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00516-LEVEL 26-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00516-320001TUR | 0
[9 empty] | 3197 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3197 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3197-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3197 |  |  | PF.3197 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00517-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00517-LEVEL 27-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00517-320001TUR | 0
[9 empty] | 3198 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3198 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3198-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3198 |  |  | PF.3198 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00518-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00518-LEVEL 28-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00518-320001TUR | 0
[9 empty] | 3199 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3199 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3199-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3199 |  |  | PF.3199 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00519-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00519-LEVEL 29-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00519-320001TUR | 0
[9 empty] | 3200 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3200 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3200-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3200 |  |  | PF.3200 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00520-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/13/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00520-LEVEL 30-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00520-320001TUR | 0
[9 empty] | 3201 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3201 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3201-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3201 |  |  | PF.3201 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00521-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00521-LEVEL 31-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00521-320001TUR | 0
[9 empty] | 3202 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3202 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3202-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3202 |  |  | PF.3202 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00522-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00522-LEVEL 32-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00522-320001TUR | 0
[9 empty] | 3203 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3203 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3203-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3203 |  |  | PF.3203 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00523-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00523-LEVEL 33-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00523-320001TUR | 0
[9 empty] | 3204 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3204 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3204-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3204 |  |  | PF.3204 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00524-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00524-LEVEL 34-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00524-320001TUR | 0
[9 empty] | 3205 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3205 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3205-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3205 |  |  | PF.3205 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00525-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00525-LEVEL 35-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00525-320001TUR | 0
[9 empty] | 3206 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3206 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3206-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3206 |  |  | PF.3206 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00526-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00526-LEVEL 36-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00526-320001TUR | 0
[9 empty] | 3207 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3207 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3207-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3207 |  |  | PF.3207 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00527-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00527-LEVEL 37-CND-CONDUIT RISER SLEEVES | False | CONDUIT RISER SLEEVES | 0 | FAB-00527-320001TUR | 0
[9 empty] | 3208 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3208 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3208-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3208 |  |  | PF.3208 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00528-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00528-LEVEL 38-CND-CONDUIT RISER SLEEVES | False | CONDUIT RISER SLEEVES | 0 | FAB-00528-320001TUR | 0
[9 empty] | 3209 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3209 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3209-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3209 |  |  | PF.3209 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00529-320001TUR | MXD_RESI_JAP_ELEC | 0 | 30.00 | 0 | 320001TUR | 8/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00529-MULTI LEVEL-TMP-SPIDER BOXES | False | SPIDER BOXES | 0 | FAB-00529-320001TUR | 0
[9 empty] | 3210 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3210 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3210-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3210 |  |  | PF.3210 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00530-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.80 | 0 | 320001TUR | 10/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00530-LEVEL 2-LGT-S50-THREADED ROD CEILING MOUNT-VAULT | False | S50-THREADED ROD CEILING MOUNT-VAULT | 0 | FAB-00530-320001TUR | 0
[9 empty] | 3211 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3211 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3211-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3211 |  |  | PF.3211 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00531-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.50 | 0 | 320001TUR | 9/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00531-LEVEL 2-LGT-S50-WALL MOUNT VAULT+L2.5 | False | S50-WALL MOUNT VAULT L2.5 | 0 | FAB-00531-320001TUR | 0
[9 empty] | 3212 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3212 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3212-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3212 |  |  | PF.3212 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00532-320001TUR | MXD_RESI_JAP_ELEC | 0 | 5.28 | 0 | 320001TUR | 9/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00532-MULTI LEVEL-IW-EUH HEATER PREWIRE | False | EUH HEATER PREWIRE | 0 | FAB-00532-320001TUR | 0
[9 empty] | 3213 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3213 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3213-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3213 |  |  | PF.3213 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00533-320001TUR | MXD_RESI_JAP_ELEC | 0 | 48.00 | 0 | 320001TUR | 10/20/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00533-LEVEL 1-IW-UNIT HEATERS-INSTALL MOUNTING HARDWARE | False | UNIT HEATERS INSTALL MOUNTING HARDWARE | 0 | FAB-00533-320001TUR | 0
[9 empty] | 3214 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3214 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3214-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3214 |  |  | PF.3214 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00534-320001TUR | MXD_RESI_JAP_ELEC | 0 | 43.61 | 0 | 320001TUR | 12/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00534-LEVEL 13-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00534-320001TUR | 0
[9 empty] | 3215 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3215 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3215-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3215 |  |  | PF.3215 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00535-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00535-LEVEL 22-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00535-320001TUR | 0
[9 empty] | 3216 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3216 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3216-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3216 |  |  | PF.3216 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00536-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00536-LEVEL 23-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00536-320001TUR | 0
[9 empty] | 3217 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3217 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3217-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3217 |  |  | PF.3217 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00537-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00537-LEVEL 24-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00537-320001TUR | 0
[9 empty] | 3218 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3218 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3218-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3218 |  |  | PF.3218 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00538-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00538-LEVEL 25-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00538-320001TUR | 0
[9 empty] | 3219 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3219 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3219-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3219 |  |  | PF.3219 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00539-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 3/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00539-LEVEL 26-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00539-320001TUR | 0
[9 empty] | 3220 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3220 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3220-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3220 |  |  | PF.3220 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00540-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 4/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00540-LEVEL 27-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00540-320001TUR | 0
[9 empty] | 3221 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3221 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3221-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3221 |  |  | PF.3221 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00541-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 5/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00541-LEVEL 31-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00541-320001TUR | 0
[9 empty] | 3222 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3222 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3222-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3222 |  |  | PF.3222 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00542-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 4/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00542-LEVEL 28-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00542-320001TUR | 0
[9 empty] | 3223 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3223 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3223-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3223 |  |  | PF.3223 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00543-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 5/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00543-LEVEL 32-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00543-320001TUR | 0
[9 empty] | 3224 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3224 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3224-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3224 |  |  | PF.3224 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00544-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 4/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00544-LEVEL 29-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00544-320001TUR | 0
[9 empty] | 3225 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3225 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3225-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3225 |  |  | PF.3225 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00545-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 5/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00545-LEVEL 33-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00545-320001TUR | 0
[9 empty] | 3226 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3226 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3226-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3226 |  |  | PF.3226 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00546-320001TUR | MXD_RESI_JAP_ELEC | 0 | 34.85 | 0 | 320001TUR | 5/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00546-LEVEL 34-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00546-320001TUR | 0
[9 empty] | 3227 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3227 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3227-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3227 |  |  | PF.3227 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00547-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 4/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00547-LEVEL 30-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00547-320001TUR | 0
[9 empty] | 3228 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3228 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3228-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3228 |  |  | PF.3228 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00548-320001TUR | MXD_RESI_JAP_ELEC | 0 | 34.85 | 0 | 320001TUR | 6/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00548-LEVEL 35-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00548-320001TUR | 0
[9 empty] | 3229 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3229 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3229-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3229 |  |  | PF.3229 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00549-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 6/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00549-LEVEL 36-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00549-320001TUR | 0
[9 empty] | 3230 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3230 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3230-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3230 |  |  | PF.3230 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00550-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00550-LEVEL 3-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00550-320001TUR | 0
[9 empty] | 3231 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3231 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3231-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3231 |  |  | PF.3231 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00551-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00551-LEVEL 4-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00551-320001TUR | 0
[9 empty] | 3232 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3232 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3232-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3232 |  |  | PF.3232 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00552-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00552-LEVEL 5-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00552-320001TUR | 0
[9 empty] | 3233 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3233 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3233-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3233 |  |  | PF.3233 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00553-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00553-LEVEL 6-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00553-320001TUR | 0
[9 empty] | 3234 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3234 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3234-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3234 |  |  | PF.3234 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00554-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00554-LEVEL 7-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00554-320001TUR | 0
[9 empty] | 3235 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3235 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3235-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3235 |  |  | PF.3235 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00555-320001TUR | MXD_RESI_JAP_ELEC | 0 | 42.08 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00555-LEVEL 8-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00555-320001TUR | 0
[9 empty] | 3236 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3236 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3236-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3236 |  |  | PF.3236 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00556-320001TUR | MXD_RESI_JAP_ELEC | 0 | 44.33 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00556-LEVEL 9-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00556-320001TUR | 0
[9 empty] | 3237 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3237 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3237-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3237 |  |  | PF.3237 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00557-320001TUR | MXD_RESI_JAP_ELEC | 0 | 44.33 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00557-LEVEL 10-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00557-320001TUR | 0
[9 empty] | 3238 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3238 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3238-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3238 |  |  | PF.3238 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00558-320001TUR | MXD_RESI_JAP_ELEC | 0 | 44.33 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00558-LEVEL 11-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00558-320001TUR | 0
[9 empty] | 3239 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3239 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3239-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3239 |  |  | PF.3239 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00559-320001TUR | MXD_RESI_JAP_ELEC | 0 | 44.33 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00559-LEVEL 12-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00559-320001TUR | 0
[9 empty] | 3240 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3240 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3240-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3240 |  |  | PF.3240 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00560-320001TUR | MXD_RESI_JAP_ELEC | 0 | 43.61 | 0 | 320001TUR | 1/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00560-LEVEL 14-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00560-320001TUR | 0
[9 empty] | 3241 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3241 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3241-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3241 |  |  | PF.3241 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00561-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00561-LEVEL 15-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00561-320001TUR | 0
[9 empty] | 3242 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3242 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3242-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3242 |  |  | PF.3242 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00562-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00562-LEVEL 16-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00562-320001TUR | 0
[9 empty] | 3243 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3243 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3243-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3243 |  |  | PF.3243 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00563-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00563-LEVEL 17-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00563-320001TUR | 0
[9 empty] | 3244 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3244 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3244-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3244 |  |  | PF.3244 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00564-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 2/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00564-LEVEL 18-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00564-320001TUR | 0
[9 empty] | 3245 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3245 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3245-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3245 |  |  | PF.3245 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00565-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 2/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00565-LEVEL 19-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00565-320001TUR | 0
[9 empty] | 3246 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3246 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3246-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3246 |  |  | PF.3246 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00566-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.14 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00566-LEVEL 20-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00566-320001TUR | 0
[9 empty] | 3247 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3247 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3247-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3247 |  |  | PF.3247 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00567-320001TUR | MXD_RESI_JAP_ELEC | 0 | 45.42 | 0 | 320001TUR | 2/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00567-LEVEL 21-IW-UNITS INWALL | False | UNITS INWALL | 0 | FAB-00567-320001TUR | 0
[9 empty] | 3248 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3248 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3248-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3248 |  |  | PF.3248 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00568-320001TUR | MXD_RESI_JAP_ELEC | 0 | 5.32 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00568-LEVEL 1-LGT-LOADING DOCK S50 FIXTURE STRUT ASSEMBLIES | False | LOADING DOCK S50 FIXTURE STRUT ASSEMBLIES | 0 | FAB-00568-320001TUR | 0
[9 empty] | 3249 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3249 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3249-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3249 |  |  | PF.3249 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00569-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.37 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00569-LEVEL 3-IW-MOCK UP UNIT-S-2 INWALL | False | LEVEL 3-MOCK UP UNIT S-2 INWALL | 0 | FAB-00569-320001TUR | 0
[9 empty] | 3250 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3250 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3250-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3250 |  |  | PF.3250 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00570-320001TUR | MXD_RESI_JAP_ELEC | 0 | 5.65 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00570-LEVEL 3-IW-MOCK UP UNIT-A-1 INWALL | False | LEVEL 3-MOCK UP UNIT A-1 INWALL | 0 | FAB-00570-320001TUR | 0
[9 empty] | 3251 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3251 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3251-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3251 |  |  | PF.3251 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00571-320001TUR | MXD_RESI_JAP_ELEC | 0 | 60.00 | 0 | 320001TUR | 9/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00571-LEVEL 3-TMP-CORE HOLE-PLYWOOD PLUG | False | CORE HOLE PLYWOOD PLUG | 0 | FAB-00571-320001TUR | 0
[9 empty] | 3252 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3252 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3252-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3252 |  |  | PF.3252 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00572-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.80 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00572-LEVEL 3-TMP-L3-UNITS TEMP LIGHTING-STRINGERS | False | L3-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00572-320001TUR | 0
[9 empty] | 3253 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3253 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3253-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3253 |  |  | PF.3253 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00573-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.80 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00573-LEVEL 4-TMP-L4-UNITS TEMP LIGHTING-STRINGERS | False | L4-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00573-320001TUR | 0
[9 empty] | 3254 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3254 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3254-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3254 |  |  | PF.3254 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00574-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.80 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00574-LEVEL 5-TMP-L5-UNITS TEMP LIGHTING-STRINGERS | False | L5-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00574-320001TUR | 0
[9 empty] | 3255 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3255 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3255-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3255 |  |  | PF.3255 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00575-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.20 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00575-LEVEL 7-TMP-L7-UNITS TEMP LIGHTING-STRINGERS | False | L7-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00575-320001TUR | 0
[9 empty] | 3256 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3256 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3256-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3256 |  |  | PF.3256 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00576-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.20 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00576-LEVEL 8-TMP-L8-UNITS TEMP LIGHTING-STRINGERS | False | L8-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00576-320001TUR | 0
[9 empty] | 3257 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3257 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3257-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3257 |  |  | PF.3257 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00577-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.20 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00577-LEVEL 9-TMP-L9-UNITS TEMP LIGHTING-STRINGERS | False | L9-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00577-320001TUR | 0
[9 empty] | 3258 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3258 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3258-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3258 |  |  | PF.3258 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00578-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00578-LEVEL 10-TMP-L10-UNITS TEMP LIGHTING-STRINGERS | False | L10-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00578-320001TUR | 0
[9 empty] | 3259 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3259 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3259-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3259 |  |  | PF.3259 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00579-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00579-LEVEL 11-TMP-L11-UNITS TEMP LIGHTING-STRINGERS | False | L11-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00579-320001TUR | 0
[9 empty] | 3260 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3260 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3260-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3260 |  |  | PF.3260 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00580-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00580-LEVEL 12-TMP-L12-UNITS TEMP LIGHTING-STRINGERS | False | L12-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00580-320001TUR | 0
[9 empty] | 3261 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3261 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3261-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3261 |  |  | PF.3261 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00581-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 12/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00581-LEVEL 13-TMP-L13-UNITS TEMP LIGHTING-STRINGERS | False | L13-UNITS TEMP LIGHTING STRINGERS | 0 | FAB-00581-320001TUR | 0
[9 empty] | 3262 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3262 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3262-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3262 |  |  | PF.3262 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00582-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 1/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00582-LEVEL 14-TMP-L14-UNITS TEMP LIGHTHING-STRINGERS | False | L14-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00582-320001TUR | 0
[9 empty] | 3263 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3263 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3263-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3263 |  |  | PF.3263 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00583-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00583-LEVEL 15-TMP-L15-UNITS TEMP LIGHTHING-STRINGERS | False | L15-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00583-320001TUR | 0
[9 empty] | 3264 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3264 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3264-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3264 |  |  | PF.3264 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00584-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00584-LEVEL 16-TMP-L16-UNITS TEMP LIGHTHING-STRINGERS | False | L16-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00584-320001TUR | 0
[9 empty] | 3265 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3265 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3265-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3265 |  |  | PF.3265 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00585-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00585-LEVEL 17-TMP-L17-UNITS TEMP LIGHTHING-STRINGERS | False | L17-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00585-320001TUR | 0
[9 empty] | 3266 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3266 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3266-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3266 |  |  | PF.3266 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00586-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 2/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00586-LEVEL 18-TMP-L18-UNITS TEMP LIGHTHING-STRINGERS | False | L18-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00586-320001TUR | 0
[9 empty] | 3267 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3267 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3267-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3267 |  |  | PF.3267 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00587-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 2/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00587-LEVEL 19-TMP-L19-UNITS TEMP LIGHTHING-STRINGERS | False | L19-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00587-320001TUR | 0
[9 empty] | 3268 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3268 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3268-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3268 |  |  | PF.3268 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00588-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00588-LEVEL 20-TMP-L20-UNITS TEMP LIGHTHING-STRINGERS | False | L20-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00588-320001TUR | 0
[9 empty] | 3269 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3269 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3269-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3269 |  |  | PF.3269 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00589-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 2/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00589-LEVEL 21-TMP-L21-UNITS TEMP LIGHTHING-STRINGERS | False | L21-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00589-320001TUR | 0
[9 empty] | 3270 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3270 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3270-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3270 |  |  | PF.3270 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00590-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00590-LEVEL 22-TMP-L22-UNITS TEMP LIGHTHING-STRINGERS | False | L22-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00590-320001TUR | 0
[9 empty] | 3271 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3271 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3271-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3271 |  |  | PF.3271 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00591-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00591-LEVEL 23-TMP-L23-UNITS TEMP LIGHTHING-STRINGERS | False | L23-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00591-320001TUR | 0
[9 empty] | 3272 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3272 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3272-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3272 |  |  | PF.3272 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00592-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00592-LEVEL 24-TMP-L24-UNITS TEMP LIGHTHING-STRINGERS | False | L24-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00592-320001TUR | 0
[9 empty] | 3273 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3273 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3273-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3273 |  |  | PF.3273 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00593-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00593-LEVEL 25-TMP-L25-UNITS TEMP LIGHTHING-STRINGERS | False | L25-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00593-320001TUR | 0
[9 empty] | 3274 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3274 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3274-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3274 |  |  | PF.3274 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00594-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 3/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00594-LEVEL 26-TMP-L26-UNITS TEMP LIGHTHING-STRINGERS | False | L26-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00594-320001TUR | 0
[9 empty] | 3275 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3275 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3275-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3275 |  |  | PF.3275 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00595-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 4/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00595-LEVEL 27-TMP-L27-UNITS TEMP LIGHTHING-STRINGERS | False | L27-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00595-320001TUR | 0
[9 empty] | 3276 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3276 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3276-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3276 |  |  | PF.3276 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00596-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 4/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00596-LEVEL 28-TMP-L28-UNITS TEMP LIGHTHING-STRINGERS | False | L28-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00596-320001TUR | 0
[9 empty] | 3277 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3277 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3277-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3277 |  |  | PF.3277 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00597-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 4/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00597-LEVEL 29-TMP-L29-UNITS TEMP LIGHTHING-STRINGERS | False | L29-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00597-320001TUR | 0
[9 empty] | 3278 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3278 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3278-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3278 |  |  | PF.3278 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00598-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 4/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00598-LEVEL 30-TMP-L30-UNITS TEMP LIGHTHING-STRINGERS | False | L30-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00598-320001TUR | 0
[9 empty] | 3279 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3279 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3279-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3279 |  |  | PF.3279 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00599-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 5/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00599-LEVEL 31-TMP-L31-UNITS TEMP LIGHTHING-STRINGERS | False | L31-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00599-320001TUR | 0
[9 empty] | 3280 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3280 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3280-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3280 |  |  | PF.3280 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00600-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 5/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00600-LEVEL 32-TMP-L32-UNITS TEMP LIGHTHING-STRINGERS | False | L32-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00600-320001TUR | 0
[9 empty] | 3281 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3281 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3281-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3281 |  |  | PF.3281 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00601-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 5/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00601-LEVEL 33-TMP-L33-UNITS TEMP LIGHTHING-STRINGERS | False | L33-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00601-320001TUR | 0
[9 empty] | 3282 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3282 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3282-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3282 |  |  | PF.3282 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00602-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.40 | 0 | 320001TUR | 5/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00602-LEVEL 34-TMP-L34-UNITS TEMP LIGHTHING-STRINGERS | False | L34-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00602-320001TUR | 0
[9 empty] | 3283 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3283 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3283-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3283 |  |  | PF.3283 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00603-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.20 | 0 | 320001TUR | 6/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00603-LEVEL 35-TMP-L35-UNITS TEMP LIGHTHING-STRINGERS | False | L35-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00603-320001TUR | 0
[9 empty] | 3284 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3284 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3284-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3284 |  |  | PF.3284 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00604-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.20 | 0 | 320001TUR | 6/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00604-LEVEL 36-TMP-L36-UNITS TEMP LIGHTHING-STRINGERS | False | L36-UNITS TEMP LIGHTHING STRINGERS | 0 | FAB-00604-320001TUR | 0
[9 empty] | 3285 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3285 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3285-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3285 |  |  | PF.3285 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00605-320001TUR | MXD_RESI_JAP_ELEC | 0 | 17.55 | 0 | 320001TUR | 10/13/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00605-LEVEL 11-LGT-BOH DEVICES-L11-L36 | False | BOH DEVICES L11-L36 | 0 | FAB-00605-320001TUR | 0
[9 empty] | 2793 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2793 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2793-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2793 |  |  | PF.2793 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00113-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00113-LEVEL 9-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 9-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00113-320001TUR | 0
[9 empty] | 2794 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2794 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2794-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2794 |  |  | PF.2794 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00114-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00114-LEVEL 10-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 10-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00114-320001TUR | 0
[9 empty] | 2795 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2795 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2795-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2795 |  |  | PF.2795 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00115-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00115-LEVEL 11-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 11-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00115-320001TUR | 0
[9 empty] | 2796 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2796 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2796-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2796 |  |  | PF.2796 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00116-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00116-LEVEL 12-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 12-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00116-320001TUR | 0
[9 empty] | 2797 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2797 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2797-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2797 |  |  | PF.2797 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00117-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00117-LEVEL 13-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 13-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00117-320001TUR | 0
[9 empty] | 2798 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2798 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2798-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2798 |  |  | PF.2798 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00118-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00118-LEVEL 14-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 14-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00118-320001TUR | 0
[9 empty] | 2799 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2799 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2799-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2799 |  |  | PF.2799 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00119-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00119-LEVEL 15-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 15-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00119-320001TUR | 0
[9 empty] | 2800 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2800 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2800-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2800 |  |  | PF.2800 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00120-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00120-LEVEL 16-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 16-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00120-320001TUR | 0
[9 empty] | 2801 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2801 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2801-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2801 |  |  | PF.2801 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00121-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00121-LEVEL 17-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 17-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00121-320001TUR | 0
[9 empty] | 2802 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2802 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2802-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2802 |  |  | PF.2802 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00122-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00122-LEVEL 18-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 18-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00122-320001TUR | 0
[9 empty] | 2803 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2803 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2803-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2803 |  |  | PF.2803 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00123-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/4/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00123-LEVEL 19-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 19-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00123-320001TUR | 0
[9 empty] | 2804 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2804 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2804-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2804 |  |  | PF.2804 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00124-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00124-LEVEL 20-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 20-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00124-320001TUR | 0
[9 empty] | 2805 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2805 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2805-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2805 |  |  | PF.2805 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00125-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00125-LEVEL 21-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 21-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00125-320001TUR | 0
[9 empty] | 2806 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2806 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2806-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2806 |  |  | PF.2806 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00126-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00126-LEVEL 22-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 22-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00126-320001TUR | 0
[9 empty] | 2807 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2807 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2807-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2807 |  |  | PF.2807 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00127-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00127-LEVEL 23-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 23-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00127-320001TUR | 0
[9 empty] | 2808 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2808 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2808-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2808 |  |  | PF.2808 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00128-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00128-LEVEL 24-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 24-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00128-320001TUR | 0
[9 empty] | 2809 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2809 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2809-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2809 |  |  | PF.2809 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00129-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00129-LEVEL 25-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 25-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00129-320001TUR | 0
[9 empty] | 2810 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2810 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2810-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2810 |  |  | PF.2810 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00130-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00130-LEVEL 26-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 26-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00130-320001TUR | 0
[9 empty] | 2811 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2811 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2811-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2811 |  |  | PF.2811 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00131-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00131-LEVEL 27-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 27-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00131-320001TUR | 0
[9 empty] | 2812 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2812 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2812-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2812 |  |  | PF.2812 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00132-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/8/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00132-LEVEL 28-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 28-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00132-320001TUR | 0
[9 empty] | 2813 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2813 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2813-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2813 |  |  | PF.2813 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00133-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00133-LEVEL 29-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 29-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00133-320001TUR | 0
[9 empty] | 2814 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2814 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2814-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2814 |  |  | PF.2814 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00134-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00134-LEVEL 30-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 30-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00134-320001TUR | 0
[9 empty] | 2815 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2815 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2815-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2815 |  |  | PF.2815 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00135-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00135-LEVEL 31-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 31-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00135-320001TUR | 0
[9 empty] | 2816 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2816 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2816-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2816 |  |  | PF.2816 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00136-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00136-LEVEL 32-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 32-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00136-320001TUR | 0
[9 empty] | 2817 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2817 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2817-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2817 |  |  | PF.2817 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00137-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00137-LEVEL 33-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 33-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00137-320001TUR | 0
[9 empty] | 2818 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2818 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2818-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2818 |  |  | PF.2818 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00138-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00138-LEVEL 34-CND-TIER 2 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 34-TIER 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00138-320001TUR | 0
[9 empty] | 2819 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2819 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2819-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2819 |  |  | PF.2819 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00139-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00139-LEVEL 35-CND-TIER 3 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 35-TIER 3 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00139-320001TUR | 0
[9 empty] | 2820 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2820 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2820-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2820 |  |  | PF.2820 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00140-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 6/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00140-LEVEL 36-CND-TIER 3 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 36-TIER 3 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00140-320001TUR | 0
[9 empty] | 2821 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2821 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2821-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2821 |  |  | PF.2821 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00141-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 6/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00141-LEVEL 37-CND-AMENITY-MEP PH PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 37-AMENITY-MEP PH PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00141-320001TUR | 0
[9 empty] | 2822 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2822 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2822-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2822 |  |  | PF.2822 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00142-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00142-LEVEL 38-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 38 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00142-320001TUR | 0
[9 empty] | 2823 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2823 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2823-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2823 |  |  | PF.2823 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00143-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00143-LEVEL B1-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL B1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00143-320001TUR | 0
[9 empty] | 2824 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2824 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2824-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2824 |  |  | PF.2824 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00144-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00144-LEVEL 1-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00144-320001TUR | 0
[9 empty] | 2825 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2825 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2825-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2825 |  |  | PF.2825 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00145-320001TUR | MXD_RESI_JAP_ELEC | 0 | 15.60 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00145-LEVEL 2-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00145-320001TUR | 0
[9 empty] | 2826 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2826 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2826-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2826 |  |  | PF.2826 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00146-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 3/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00146-LEVEL 3-LGT-PODIUM LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 3-PODIUM LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00146-320001TUR | 0
[9 empty] | 2827 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2827 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2827-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2827 |  |  | PF.2827 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00147-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 3/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00147-LEVEL 4-LGT-PODIUM LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 4-PODIUM LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00147-320001TUR | 0
[9 empty] | 2828 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2828 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2828-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2828 |  |  | PF.2828 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00148-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 3/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00148-LEVEL 5-LGT-PODIUM LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 5-PODIUM LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00148-320001TUR | 0
[9 empty] | 2829 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2829 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2829-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2829 |  |  | PF.2829 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00149-320001TUR | MXD_RESI_JAP_ELEC | 0 | 15.60 | 0 | 320001TUR | 4/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00149-LEVEL 6-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 6 LEVEL 6 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00149-320001TUR | 0
[9 empty] | 2830 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2830 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2830-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2830 |  |  | PF.2830 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00150-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00150-LEVEL 7-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 7-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00150-320001TUR | 0
[9 empty] | 2831 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2831 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2831-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2831 |  |  | PF.2831 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00151-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/8/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00151-LEVEL 8-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 8-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00151-320001TUR | 0
[9 empty] | 2832 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2832 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2832-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2832 |  |  | PF.2832 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00152-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00152-LEVEL 9-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 9-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00152-320001TUR | 0
[9 empty] | 2833 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2833 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2833-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2833 |  |  | PF.2833 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00153-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00153-LEVEL 10-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 10-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00153-320001TUR | 0
[9 empty] | 2834 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2834 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2834-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2834 |  |  | PF.2834 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00154-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 4/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00154-LEVEL 11-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 11-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00154-320001TUR | 0
[9 empty] | 2835 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2835 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2835-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2835 |  |  | PF.2835 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00155-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 5/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00155-LEVEL 12-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 12-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00155-320001TUR | 0
[9 empty] | 2836 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2836 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2836-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2836 |  |  | PF.2836 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00156-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 5/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00156-LEVEL 13-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 13-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00156-320001TUR | 0
[9 empty] | 2837 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2837 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2837-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2837 |  |  | PF.2837 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00157-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 5/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00157-LEVEL 14-LGT-TIER 1 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 14-TIER 1 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00157-320001TUR | 0
[9 empty] | 2838 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2838 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2838-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2838 |  |  | PF.2838 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00158-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 5/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00158-LEVEL 15-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 15-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00158-320001TUR | 0
[9 empty] | 2839 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2839 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2839-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2839 |  |  | PF.2839 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00159-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00159-LEVEL 16-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 16-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00159-320001TUR | 0
[9 empty] | 2840 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2840 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2840-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2840 |  |  | PF.2840 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00160-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00160-LEVEL 17-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 17-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00160-320001TUR | 0
[9 empty] | 2841 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2841 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2841-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2841 |  |  | PF.2841 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00161-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00161-LEVEL 18-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 18-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00161-320001TUR | 0
[9 empty] | 2842 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2842 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2842-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2842 |  |  | PF.2842 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00162-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/24/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00162-LEVEL 19-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 19-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00162-320001TUR | 0
[9 empty] | 2843 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2843 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2843-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2843 |  |  | PF.2843 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00163-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 6/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00163-LEVEL 20-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 20-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00163-320001TUR | 0
[9 empty] | 2844 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2844 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2844-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2844 |  |  | PF.2844 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00164-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/8/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00164-LEVEL 21-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 21-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00164-320001TUR | 0
[9 empty] | 2845 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2845 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2845-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2845 |  |  | PF.2845 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00165-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00165-LEVEL 22-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 22-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00165-320001TUR | 0
[9 empty] | 2846 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2846 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2846-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2846 |  |  | PF.2846 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00166-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00166-LEVEL 23-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 23-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00166-320001TUR | 0
[9 empty] | 2847 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2847 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2847-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2847 |  |  | PF.2847 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00167-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00167-LEVEL 24-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 24-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00167-320001TUR | 0
[9 empty] | 2848 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2848 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2848-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2848 |  |  | PF.2848 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00168-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 8/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00168-LEVEL 25-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 25-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00168-320001TUR | 0
[9 empty] | 2849 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2849 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2849-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2849 |  |  | PF.2849 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00169-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 8/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00169-LEVEL 26-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 26-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00169-320001TUR | 0
[9 empty] | 2850 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2850 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2850-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2850 |  |  | PF.2850 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00170-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 8/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00170-LEVEL 27-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 27-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00170-320001TUR | 0
[9 empty] | 2851 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2851 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2851-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2851 |  |  | PF.2851 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00171-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 8/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00171-LEVEL 28-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 28-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00171-320001TUR | 0
[9 empty] | 2852 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2852 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2852-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2852 |  |  | PF.2852 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00172-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00172-LEVEL 29-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 29-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00172-320001TUR | 0
[9 empty] | 2853 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2853 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2853-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2853 |  |  | PF.2853 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00173-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00173-LEVEL 30-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 30-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00173-320001TUR | 0
[9 empty] | 2854 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2854 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2854-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2854 |  |  | PF.2854 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00174-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00174-LEVEL 31-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 31-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00174-320001TUR | 0
[9 empty] | 2855 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2855 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2855-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2855 |  |  | PF.2855 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00175-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00175-LEVEL 32-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 32-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00175-320001TUR | 0
[9 empty] | 2856 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2856 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2856-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2856 |  |  | PF.2856 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00176-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 9/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00176-LEVEL 33-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 33-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00176-320001TUR | 0
[9 empty] | 2857 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2857 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2857-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2857 |  |  | PF.2857 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00177-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 10/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00177-LEVEL 34-LGT-TIER 2 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 34-TIER 2 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00177-320001TUR | 0
[9 empty] | 2858 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2858 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2858-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2858 |  |  | PF.2858 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00178-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 10/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00178-LEVEL 35-LGT-TIER 3 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 35-TIER 3 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00178-320001TUR | 0
[9 empty] | 2859 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2859 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2859-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2859 |  |  | PF.2859 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00179-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 10/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00179-LEVEL 36-LGT-TIER 3 LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 36-TIER 3 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00179-320001TUR | 0
[9 empty] | 2860 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2860 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2860-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2860 |  |  | PF.2860 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00180-320001TUR | MXD_RESI_JAP_ELEC | 0 | 15.60 | 0 | 320001TUR | 10/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00180-LEVEL 37-LGT-AMENITY-MEP PH LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 37-AMENITY-MEP PH LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00180-320001TUR | 0
[9 empty] | 2861 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2861 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2861-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2861 |  |  | PF.2861 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00181-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00181-LEVEL 38-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 38 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00181-320001TUR | 0
[9 empty] | 2862 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2862 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2862-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2862 |  |  | PF.2862 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00182-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.90 | 0 | 320001TUR | 7/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00182-LEVEL 39-LGT-LIGHTING CONTROL-2 COMPONENT ASSEMBLY-WIRED | False | LEVEL 39 LIGHTING CONTROL 2 COMPONENT ASSEMBLY WIRED | 0 | FAB-00182-320001TUR | 0
[9 empty] | 2863 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2863 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2863-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2863 |  |  | PF.2863 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00183-320001TUR | MXD_RESI_JAP_ELEC | 0 | 16.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00183-LEVEL B1-LGT-LIGHTING CONTROL PANEL ASSEMBLY WIRED | False | LIGHTING CONTROL PANEL ASSEMBLY WIRED | 0 | FAB-00183-320001TUR | 0
[9 empty] | 2864 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2864 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2864-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2864 |  |  | PF.2864 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00184-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.12 | 0 | 320001TUR | 9/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00184-LEVEL B1-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL B1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00184-320001TUR | 0
[9 empty] | 2865 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2865 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2865-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2865 |  |  | PF.2865 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00185-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.77 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00185-LEVEL 1-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00185-320001TUR | 0
[9 empty] | 2866 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2866 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2866-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2866 |  |  | PF.2866 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00186-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.24 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00186-LEVEL 2-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00186-320001TUR | 0
[9 empty] | 2867 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2867 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2867-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2867 |  |  | PF.2867 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00187-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00187-LEVEL 3-IW-PODIUM JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 3-PODIUM JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00187-320001TUR | 0
[9 empty] | 2868 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2868 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2868-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2868 |  |  | PF.2868 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00188-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00188-LEVEL 4-IW-PODIUM JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 4-PODIUM JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00188-320001TUR | 0
[9 empty] | 2869 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2869 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2869-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2869 |  |  | PF.2869 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00189-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00189-LEVEL 5-IW-PODIUM JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 5-PODIUM JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00189-320001TUR | 0
[9 empty] | 2870 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2870 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2870-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2870 |  |  | PF.2870 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00190-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.24 | 0 | 320001TUR | 9/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00190-LEVEL 6-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 6 LEVEL 6 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00190-320001TUR | 0
[9 empty] | 2871 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2871 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2871-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2871 |  |  | PF.2871 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00191-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00191-LEVEL 7-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 7-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00191-320001TUR | 0
[9 empty] | 2872 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2872 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2872-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2872 |  |  | PF.2872 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00192-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00192-LEVEL 8-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 8-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00192-320001TUR | 0
[9 empty] | 2873 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2873 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2873-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2873 |  |  | PF.2873 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00193-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00193-LEVEL 9-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 9-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00193-320001TUR | 0
[9 empty] | 2874 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2874 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2874-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2874 |  |  | PF.2874 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00194-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00194-LEVEL 10-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 10-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00194-320001TUR | 0
[9 empty] | 2875 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2875 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2875-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2875 |  |  | PF.2875 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00195-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00195-LEVEL 11-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 11-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00195-320001TUR | 0
[9 empty] | 2876 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2876 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2876-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2876 |  |  | PF.2876 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00196-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 12/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00196-LEVEL 12-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 12-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00196-320001TUR | 0
[9 empty] | 2877 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2877 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2877-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2877 |  |  | PF.2877 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00197-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00197-LEVEL 13-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 13-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00197-320001TUR | 0
[9 empty] | 2878 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2878 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2878-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2878 |  |  | PF.2878 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00198-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 1/14/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00198-LEVEL 14-IW-TIER 1 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 14-TIER 1 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00198-320001TUR | 0
[9 empty] | 2879 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2879 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2879-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2879 |  |  | PF.2879 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00199-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 1/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00199-LEVEL 15-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 15-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00199-320001TUR | 0
[9 empty] | 2880 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2880 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2880-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2880 |  |  | PF.2880 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00200-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 1/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00200-LEVEL 16-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 16-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00200-320001TUR | 0
[9 empty] | 2881 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2881 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2881-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2881 |  |  | PF.2881 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00201-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 2/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00201-LEVEL 17-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 17-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00201-320001TUR | 0
[9 empty] | 2882 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2882 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2882-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2882 |  |  | PF.2882 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00202-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 2/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00202-LEVEL 18-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 18-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00202-320001TUR | 0
[9 empty] | 2883 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2883 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2883-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2883 |  |  | PF.2883 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00203-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 2/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00203-LEVEL 19-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 19-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00203-320001TUR | 0
[9 empty] | 2884 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2884 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2884-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2884 |  |  | PF.2884 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00204-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 2/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00204-LEVEL 20-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 20-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00204-320001TUR | 0
[9 empty] | 2885 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2885 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2885-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2885 |  |  | PF.2885 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00205-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 3/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00205-LEVEL 21-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 21-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00205-320001TUR | 0
[9 empty] | 2886 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2886 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2886-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2886 |  |  | PF.2886 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00206-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00206-LEVEL 22-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 22-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00206-320001TUR | 0
[9 empty] | 2887 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2887 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2887-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2887 |  |  | PF.2887 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00207-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 3/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00207-LEVEL 23-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 23-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00207-320001TUR | 0
[9 empty] | 2888 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2888 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2888-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2888 |  |  | PF.2888 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00208-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 3/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00208-LEVEL 24-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 24-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00208-320001TUR | 0
[9 empty] | 2889 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2889 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2889-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2889 |  |  | PF.2889 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00209-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 4/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00209-LEVEL 25-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 25-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00209-320001TUR | 0
[9 empty] | 2890 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2890 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2890-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2890 |  |  | PF.2890 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00210-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 4/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00210-LEVEL 26-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 26-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00210-320001TUR | 0
[9 empty] | 2891 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2891 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2891-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2891 |  |  | PF.2891 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00211-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 4/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00211-LEVEL 27-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 27-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00211-320001TUR | 0
[9 empty] | 2892 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2892 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2892-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2892 |  |  | PF.2892 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00212-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 4/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00212-LEVEL 28-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 28-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00212-320001TUR | 0
[9 empty] | 2893 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2893 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2893-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2893 |  |  | PF.2893 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00213-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 5/4/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00213-LEVEL 29-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 29-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00213-320001TUR | 0
[9 empty] | 2894 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2894 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2894-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2894 |  |  | PF.2894 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00214-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 5/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00214-LEVEL 30-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 30-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00214-320001TUR | 0
[9 empty] | 2895 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2895 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2895-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2895 |  |  | PF.2895 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00215-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 5/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00215-LEVEL 31-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 31-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00215-320001TUR | 0
[9 empty] | 2896 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2896 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2896-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2896 |  |  | PF.2896 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00216-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 5/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00216-LEVEL 32-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 32-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00216-320001TUR | 0
[9 empty] | 2897 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2897 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2897-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2897 |  |  | PF.2897 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00217-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 6/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00217-LEVEL 33-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 33-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00217-320001TUR | 0
[9 empty] | 2898 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2898 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2898-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2898 |  |  | PF.2898 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00218-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 6/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00218-LEVEL 34-IW-TIER 2 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 34-TIER 2 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00218-320001TUR | 0
[9 empty] | 2899 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2899 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2899-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2899 |  |  | PF.2899 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00219-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 6/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00219-LEVEL 35-IW-TIER 3 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 35-TIER 3 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00219-320001TUR | 0
[9 empty] | 2900 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2900 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2900-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2900 |  |  | PF.2900 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00220-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.06 | 0 | 320001TUR | 6/24/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00220-LEVEL 36-IW-TIER 3 JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 36-TIER 3 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00220-320001TUR | 0
[9 empty] | 2901 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2901 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2901-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2901 |  |  | PF.2901 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00221-320001TUR | MXD_RESI_JAP_ELEC | 0 | 7.95 | 0 | 320001TUR | 7/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00221-LEVEL 37-IW-AMENITY-MEP PH JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 37-AMENITY-MEP PH JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00221-320001TUR | 0
[9 empty] | 2902 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2902 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2902-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2902 |  |  | PF.2902 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00222-320001TUR | MXD_RESI_JAP_ELEC | 0 | 4.24 | 0 | 320001TUR | 7/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00222-LEVEL 38-IW-JUNCTION BOX PREP-5-12 K.O.-BRANCH | False | LEVEL 38 JUNCTION BOX PREP 5-12 K.O. BRANCH | 0 | FAB-00222-320001TUR | 0
[9 empty] | 2903 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2903 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2903-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2903 |  |  | PF.2903 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00223-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00223-LEVEL B1-SUP-HANGER STRUT-POWER | False | LEVEL B1 HANGER STRUT POWER | 0 | FAB-00223-320001TUR | 0
[9 empty] | 2904 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2904 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2904-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2904 |  |  | PF.2904 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00224-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00224-LEVEL 1-SUP-HANGER STRUT-POWER | False | LEVEL 1 HANGER STRUT POWER | 0 | FAB-00224-320001TUR | 0
[9 empty] | 2905 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2905 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2905-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2905 |  |  | PF.2905 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00225-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00225-LEVEL 2-SUP-HANGER STRUT-POWER | False | LEVEL 2 HANGER STRUT POWER | 0 | FAB-00225-320001TUR | 0
[9 empty] | 2906 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2906 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2906-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2906 |  |  | PF.2906 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00226-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00226-LEVEL 6-SUP-HANGER STRUT-POWER-WEST SIDE | False | LEVEL 6 HANGER STRUT POWER-WEST SIDE | 0 | FAB-00226-320001TUR | 0
[9 empty] | 2907 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2907 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2907-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2907 |  |  | PF.2907 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00227-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/9/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00227-LEVEL 36-SUP-TIER 3 HANGER STRUT-POWER | False | LEVEL 36-TIER 3 HANGER STRUT POWER | 0 | FAB-00227-320001TUR | 0
[9 empty] | 2908 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2908 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2908-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2908 |  |  | PF.2908 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00228-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00228-LEVEL 37-SUP-AMENITY-MEP PH HANGER STRUT-POWER | False | LEVEL 37-AMENITY-MEP PH HANGER STRUT POWER | 0 | FAB-00228-320001TUR | 0
[9 empty] | 2909 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2909 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2909-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2909 |  |  | PF.2909 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00229-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00229-LEVEL 38-SUP-HANGER STRUT-POWER | False | LEVEL 38 HANGER STRUT POWER | 0 | FAB-00229-320001TUR | 0
[9 empty] | 2910 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2910 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2910-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2910 |  |  | PF.2910 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00230-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00230-LEVEL B1-CND-PIPE BENDS-LARGE POWER | False | LEVEL B1 PIPE BENDS LARGE POWER | 0 | FAB-00230-320001TUR | 0
[9 empty] | 2911 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2911 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2911-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2911 |  |  | PF.2911 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00231-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00231-LEVEL 1-CND-PIPE BENDS-LARGE POWER | False | LEVEL 1 PIPE BENDS LARGE POWER | 0 | FAB-00231-320001TUR | 0
[9 empty] | 2912 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2912 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2912-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2912 |  |  | PF.2912 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00232-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00232-LEVEL 2-CND-PIPE BENDS-LARGE POWER | False | LEVEL 2 PIPE BENDS LARGE POWER | 0 | FAB-00232-320001TUR | 0
[9 empty] | 2913 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2913 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2913-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2913 |  |  | PF.2913 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00233-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 5/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00233-LEVEL 6-CND-PIPE BENDS-LARGE POWER | False | LEVEL 6 LEVEL 6 PIPE BENDS LARGE POWER | 0 | FAB-00233-320001TUR | 0
[9 empty] | 2914 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2914 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2914-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2914 |  |  | PF.2914 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00234-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00234-LEVEL 36-CND-TIER 3 PIPE BENDS-LARGE POWER | False | LEVEL 36-TIER 3 PIPE BENDS LARGE POWER | 0 | FAB-00234-320001TUR | 0
[9 empty] | 2915 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2915 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2915-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2915 |  |  | PF.2915 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00235-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00235-LEVEL 37-CND-AMENITY-MEP PH PIPE BENDS-LARGE POWER | False | LEVEL 37-AMENITY-MEP PH PIPE BENDS LARGE POWER | 0 | FAB-00235-320001TUR | 0
[9 empty] | 2916 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2916 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2916-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2916 |  |  | PF.2916 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00236-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00236-LEVEL 38-CND-PIPE BENDS-LARGE POWER | False | LEVEL 38 PIPE BENDS LARGE POWER | 0 | FAB-00236-320001TUR | 0
[9 empty] | 2917 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2917 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2917-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2917 |  |  | PF.2917 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00237-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00237-LEVEL B1-CND-MODULAR EMT-5 LARGE | False | LEVEL B1 MODULAR EMT 5 LARGE | 0 | FAB-00237-320001TUR | 0
[9 empty] | 2918 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2918 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2918-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2918 |  |  | PF.2918 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00238-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 4/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00238-LEVEL 1-CND-MODULAR EMT-5 LARGE | False | LEVEL 1 MODULAR EMT 5 LARGE | 0 | FAB-00238-320001TUR | 0
[9 empty] | 2919 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2919 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2919-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2919 |  |  | PF.2919 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00239-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00239-LEVEL 35-CND-TIER 3-MODULAR EMT-5 LARGE | False | LEVEL 35-TIER 3-MODULAR EMT 5 LARGE | 0 | FAB-00239-320001TUR | 0
[9 empty] | 2920 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2920 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2920-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2920 |  |  | PF.2920 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00240-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00240-LEVEL 36-CND-TIER 3-MODULAR EMT-5 LARGE | False | LEVEL 36-TIER 3-MODULAR EMT 5 LARGE | 0 | FAB-00240-320001TUR | 0
[9 empty] | 2921 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2921 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2921-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2921 |  |  | PF.2921 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00241-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00241-LEVEL 37-CND-AMENITY-MEP PH-MODULAR EMT-5 LARGE | False | LEVEL 37-AMENITY-MEP PH-MODULAR EMT 5 LARGE | 0 | FAB-00241-320001TUR | 0
[9 empty] | 2922 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2922 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2922-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2922 |  |  | PF.2922 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00242-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00242-LEVEL 38-CND-MODULAR EMT-5 LARGE | False | LEVEL 38 MODULAR EMT 5 LARGE | 0 | FAB-00242-320001TUR | 0
[9 empty] | 2923 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2923 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2923-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2923 |  |  | PF.2923 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00243-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00243-LEVEL 39-CND-MODULAR EMT-5 LARGE | False | LEVEL 39 MODULAR EMT 5 LARGE | 0 | FAB-00243-320001TUR | 0
[9 empty] | 2924 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2924 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2924-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2924 |  |  | PF.2924 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00244-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00244-LEVEL B1-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL B1 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00244-320001TUR | 0
[9 empty] | 2925 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2925 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2925-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2925 |  |  | PF.2925 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00245-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00245-LEVEL 1-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 1 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00245-320001TUR | 0
[9 empty] | 2926 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2926 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2926-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2926 |  |  | PF.2926 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00246-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00246-LEVEL 2-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 2 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00246-320001TUR | 0
[9 empty] | 2927 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2927 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2927-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2927 |  |  | PF.2927 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00247-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00247-LEVEL 3-CND-PODIUM-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 3-PODIUM-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00247-320001TUR | 0
[9 empty] | 2928 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2928 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2928-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2928 |  |  | PF.2928 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00248-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00248-LEVEL 4-CND-PODIUM-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 4-PODIUM-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00248-320001TUR | 0
[9 empty] | 2929 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2929 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2929-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2929 |  |  | PF.2929 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00249-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00249-LEVEL 5-CND-PODIUM-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 5-PODIUM-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00249-320001TUR | 0
[9 empty] | 2930 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2930 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2930-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2930 |  |  | PF.2930 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00250-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00250-LEVEL 6-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 6 LEVEL 6-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00250-320001TUR | 0
[9 empty] | 2931 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2931 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2931-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2931 |  |  | PF.2931 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00251-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00251-LEVEL 7-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 7-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00251-320001TUR | 0
[9 empty] | 2932 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2932 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2932-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2932 |  |  | PF.2932 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00252-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00252-LEVEL 8-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 8-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00252-320001TUR | 0
[9 empty] | 2933 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2933 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2933-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2933 |  |  | PF.2933 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00253-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00253-LEVEL 9-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 9-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00253-320001TUR | 0
[9 empty] | 2934 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2934 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2934-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2934 |  |  | PF.2934 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00254-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00254-LEVEL 10-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 10-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00254-320001TUR | 0
[9 empty] | 2935 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2935 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2935-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2935 |  |  | PF.2935 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00255-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00255-LEVEL 11-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 11-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00255-320001TUR | 0
[9 empty] | 2936 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2936 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2936-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2936 |  |  | PF.2936 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00256-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00256-LEVEL 12-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 12-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00256-320001TUR | 0
[9 empty] | 2937 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2937 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2937-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2937 |  |  | PF.2937 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00257-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00257-LEVEL 13-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 13-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00257-320001TUR | 0
[9 empty] | 2938 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2938 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2938-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2938 |  |  | PF.2938 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00258-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00258-LEVEL 14-CND-TIER 1-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 14-TIER 1-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00258-320001TUR | 0
[9 empty] | 2939 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2939 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2939-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2939 |  |  | PF.2939 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00259-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00259-LEVEL 15-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 15-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00259-320001TUR | 0
[9 empty] | 2940 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2940 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2940-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2940 |  |  | PF.2940 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00260-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00260-LEVEL 16-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 16-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00260-320001TUR | 0
[9 empty] | 2941 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2941 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2941-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2941 |  |  | PF.2941 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00261-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00261-LEVEL 17-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 17-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00261-320001TUR | 0
[9 empty] | 2942 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2942 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2942-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2942 |  |  | PF.2942 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00262-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00262-LEVEL 18-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 18-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00262-320001TUR | 0
[9 empty] | 2943 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2943 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2943-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2943 |  |  | PF.2943 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00263-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00263-LEVEL 19-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 19-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00263-320001TUR | 0
[9 empty] | 2944 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2944 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2944-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2944 |  |  | PF.2944 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00264-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00264-LEVEL 20-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 20-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00264-320001TUR | 0
[9 empty] | 2945 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2945 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2945-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2945 |  |  | PF.2945 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00265-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00265-LEVEL 21-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 21-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00265-320001TUR | 0
[9 empty] | 2946 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2946 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2946-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2946 |  |  | PF.2946 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00266-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/22/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00266-LEVEL 22-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 22-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00266-320001TUR | 0
[9 empty] | 2947 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2947 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2947-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2947 |  |  | PF.2947 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00267-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00267-LEVEL 23-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 23-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00267-320001TUR | 0
[9 empty] | 2948 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2948 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2948-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2948 |  |  | PF.2948 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00268-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00268-LEVEL 24-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 24-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00268-320001TUR | 0
[9 empty] | 2949 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2949 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2949-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2949 |  |  | PF.2949 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00269-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00269-LEVEL 25-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 25-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00269-320001TUR | 0
[9 empty] | 2950 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2950 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2950-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2950 |  |  | PF.2950 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00270-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00270-LEVEL 26-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 26-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00270-320001TUR | 0
[9 empty] | 2951 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2951 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2951-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2951 |  |  | PF.2951 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00271-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00271-LEVEL 27-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 27-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00271-320001TUR | 0
[9 empty] | 2952 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2952 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2952-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2952 |  |  | PF.2952 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00272-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 1/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00272-LEVEL 28-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 28-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00272-320001TUR | 0
[9 empty] | 2953 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2953 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2953-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2953 |  |  | PF.2953 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00273-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00273-LEVEL 29-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 29-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00273-320001TUR | 0
[9 empty] | 2954 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2954 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2954-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2954 |  |  | PF.2954 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00274-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00274-LEVEL 30-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 30-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00274-320001TUR | 0
[9 empty] | 2955 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2955 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2955-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2955 |  |  | PF.2955 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00275-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00275-LEVEL 31-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 31-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00275-320001TUR | 0
[9 empty] | 2956 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2956 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2956-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2956 |  |  | PF.2956 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00276-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 2/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00276-LEVEL 32-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 32-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00276-320001TUR | 0
[9 empty] | 2957 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2957 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2957-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2957 |  |  | PF.2957 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00277-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00277-LEVEL 33-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 33-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00277-320001TUR | 0
[9 empty] | 2958 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2958 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2958-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2958 |  |  | PF.2958 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00278-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00278-LEVEL 34-CND-TIER 2-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 34-TIER 2-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00278-320001TUR | 0
[9 empty] | 2959 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2959 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2959-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2959 |  |  | PF.2959 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00279-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00279-LEVEL 35-CND-TIER 3-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 35-TIER 3-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00279-320001TUR | 0
[9 empty] | 2960 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2960 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2960-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2960 |  |  | PF.2960 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00280-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00280-LEVEL 36-CND-TIER 3-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 36-TIER 3-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00280-320001TUR | 0
[9 empty] | 2961 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2961 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2961-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2961 |  |  | PF.2961 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00281-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/18/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00281-LEVEL 37-CND-AMENITY-MEP PH-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 37-AMENITY-MEP PH-RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00281-320001TUR | 0
[9 empty] | 2962 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2962 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2962-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2962 |  |  | PF.2962 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00282-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00282-LEVEL 38-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 38 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00282-320001TUR | 0
[9 empty] | 2963 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2963 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2963-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2963 |  |  | PF.2963 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00283-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 3/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00283-LEVEL 39-CND-RISER-STICK BUILD-POWER-PLACEHOLDER | False | LEVEL 39 RISER STICK BUILD POWER PLACEHOLDER | 0 | FAB-00283-320001TUR | 0
[9 empty] | 2964 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2964 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2964-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2964 |  |  | PF.2964 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00284-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.50 | 0 | 320001TUR | 7/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00284-LEVEL 1-DE-PANEL ASSEMBLY-STRUT BUILD DH1-EDH1-EL1-LH1-MH1-PL1-SDP1-SP1-LRH1 | False | LEVEL 1 PANEL ASSEMBLY STRUT BUILD DH1 EDH1 EL1 LH1 MH1 PL1 SDP1 SP1 LRH1 | 0 | FAB-00284-320001TUR | 0
[9 empty] | 2965 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2965 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2965-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2965 |  |  | PF.2965 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00285-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.50 | 0 | 320001TUR | 10/20/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00285-LEVEL 2-DE-PANEL ASSEMBLY-STRUT BUILD LH2-MH2-PL2-SP2 | False | LEVEL 2 PANEL ASSEMBLY STRUT BUILD LH2 MH2 PL2 SP2 | 0 | FAB-00285-320001TUR | 0
[9 empty] | 2966 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2966 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2966-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2966 |  |  | PF.2966 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00286-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00286-LEVEL 4-DE-PODIUM-PL4 PANEL ASSEMBLY | False | LEVEL 4-PODIUM-PL4 PANEL ASSEMBLY | 0 | FAB-00286-320001TUR | 0
[9 empty] | 2967 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2967 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2967-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2967 |  |  | PF.2967 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00287-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.50 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00287-LEVEL 5-DE-PODIUM-HPH5-EPH5-EPL5 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 5-PODIUM-HPH5EPH5EPL5 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00287-320001TUR | 0
[9 empty] | 2968 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2968 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2968-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2968 |  |  | PF.2968 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00288-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.00 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00288-LEVEL 6-DE-PANEL ASSEMBLY-STRUT BUILD DH6-LH6-PLM6-PL6 | False | LEVEL 6 LEVEL 6-PANEL ASSEMBLY STRUT BUILD DH6 LH6 PLM6 PL6 | 0 | FAB-00288-320001TUR | 0
[9 empty] | 2969 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2969 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2969-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2969 |  |  | PF.2969 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00289-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00289-LEVEL 6-DE-PODIUM-PL6 PANEL ASSEMBLY | False | LEVEL 6-PODIUM-PL6 PANEL ASSEMBLY | 0 | FAB-00289-320001TUR | 0
[9 empty] | 2970 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2970 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2970-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2970 |  |  | PF.2970 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00290-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 11/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00290-LEVEL 10-DE-EPH10-EPL10 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 10-EPH10EPL10 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00290-320001TUR | 0
[9 empty] | 2971 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2971 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2971-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2971 |  |  | PF.2971 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00291-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00291-LEVEL 11-DE-TIER 1-PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 11-TIER 1-PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00291-320001TUR | 0
[9 empty] | 2972 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2972 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2972-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2972 |  |  | PF.2972 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00292-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00292-LEVEL 14-DE-TIER 1-PL14-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 14-TIER 1-PL14 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00292-320001TUR | 0
[9 empty] | 2973 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2973 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2973-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2973 |  |  | PF.2973 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00293-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 12/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00293-LEVEL 15-DE-TIER 2-EPH15-EPL15 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 15-TIER 2-EPH15EPL15 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00293-320001TUR | 0
[9 empty] | 2974 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2974 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2974-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2974 |  |  | PF.2974 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00294-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00294-LEVEL 17-DE-TIER 2-HPH17 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 17-TIER 2-HPH17 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00294-320001TUR | 0
[9 empty] | 2975 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2975 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2975-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2975 |  |  | PF.2975 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00295-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00295-LEVEL 20-DE-TIER 2-EPH20-EPL20 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 20-TIER 2-EPH20EPL20 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00295-320001TUR | 0
[9 empty] | 2976 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2976 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2976-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2976 |  |  | PF.2976 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00296-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00296-LEVEL 22-DE-TIER 2-PL22 | False | LEVEL 22-TIER 2-PL22 | 0 | FAB-00296-320001TUR | 0
[9 empty] | 2977 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2977 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2977-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2977 |  |  | PF.2977 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00297-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00297-LEVEL 24-DE-TIER 2-PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 24-TIER 2-PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00297-320001TUR | 0
[9 empty] | 2978 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2978 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2978-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2978 |  |  | PF.2978 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00298-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 3/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00298-LEVEL 25-DE-TIER 2-PANEL PL25 | False | LEVEL 25-TIER 2-PANEL PL25 | 0 | FAB-00298-320001TUR | 0
[9 empty] | 2979 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2979 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2979-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2979 |  |  | PF.2979 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00299-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 4/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00299-LEVEL 28-DE-TIER 2-PANEL PL28 | False | LEVEL 28-TIER 2-PANEL PL28 | 0 | FAB-00299-320001TUR | 0
[9 empty] | 2980 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2980 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2980-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2980 |  |  | PF.2980 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00300-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.50 | 0 | 320001TUR | 4/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00300-LEVEL 29-DE-TIER 2-PANEL HPH29-EPH29-EPL29 | False | LEVEL 29-TIER 2-PANEL HPH29EPH29EPL29 | 0 | FAB-00300-320001TUR | 0
[9 empty] | 2981 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2981 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2981-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2981 |  |  | PF.2981 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00301-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 4/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00301-LEVEL 31-DE-TIER 2-PANEL PL31 | False | LEVEL 31-TIER 2-PANEL PL31 | 0 | FAB-00301-320001TUR | 0
[9 empty] | 2982 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2982 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2982-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2982 |  |  | PF.2982 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00302-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 5/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00302-LEVEL 34-DE-TIER 2-PANEL PL34 | False | LEVEL 34-TIER 2-PANEL PL34 | 0 | FAB-00302-320001TUR | 0
[9 empty] | 2983 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2983 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2983-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2983 |  |  | PF.2983 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00303-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.50 | 0 | 320001TUR | 2/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00303-LEVEL 37-DE-AMENITY-MEP PH-PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 37-AMENITY-MEP PH-PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00303-320001TUR | 0
[9 empty] | 2984 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2984 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2984-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2984 |  |  | PF.2984 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00304-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00304-LEVEL 3-DE-PODIUM-HPH3 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 3-PODIUM-HPH3 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00304-320001TUR | 0
[9 empty] | 2985 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2985 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2985-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2985 |  |  | PF.2985 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00305-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00305-LEVEL 4-DE-PODIUM-PANEL EPH4-EPL4 | False | LEVEL 4-PODIUM-PANEL EPH4EPL4 | 0 | FAB-00305-320001TUR | 0
[9 empty] | 2986 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2986 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2986-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2986 |  |  | PF.2986 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00306-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 8/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00306-LEVEL 5-DE-PODIUM-METER STACK | False | LEVEL 5-PODIUM-METER STACK | 0 | FAB-00306-320001TUR | 0
[9 empty] | 2987 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2987 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2987-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2987 |  |  | PF.2987 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00307-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 8/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00307-LEVEL 6-DE-METER STACK | False | LEVEL 6 LEVEL 6-METER STACK | 0 | FAB-00307-320001TUR | 0
[9 empty] | 2988 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2988 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2988-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2988 |  |  | PF.2988 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00308-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 9/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00308-LEVEL 7-DE-TIER 1-METER STACK | False | LEVEL 7-TIER 1-METER STACK | 0 | FAB-00308-320001TUR | 0
[9 empty] | 2989 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2989 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2989-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2989 |  |  | PF.2989 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00309-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00309-LEVEL 8-DE-PL8-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 8-PL8 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00309-320001TUR | 0
[9 empty] | 2990 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2990 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2990-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2990 |  |  | PF.2990 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00310-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 11/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00310-LEVEL 9-DE-HPH9 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 9-HPH9 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00310-320001TUR | 0
[9 empty] | 2991 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2991 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2991-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2991 |  |  | PF.2991 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00311-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00311-LEVEL 10-DE-TIER 1-METER STACK | False | LEVEL 10-TIER 1-METER STACK | 0 | FAB-00311-320001TUR | 0
[9 empty] | 2992 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2992 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2992-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2992 |  |  | PF.2992 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00312-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 11/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00312-LEVEL 11-DE-PL11-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 11-PL11 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00312-320001TUR | 0
[9 empty] | 2993 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2993 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2993-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2993 |  |  | PF.2993 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00313-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00313-LEVEL 12-DE-TIER 1-METER STACK | False | LEVEL 12-TIER 1-METER STACK | 0 | FAB-00313-320001TUR | 0
[9 empty] | 2994 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2994 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2994-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2994 |  |  | PF.2994 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00314-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00314-LEVEL 13-DE-TIER 1-HPH13 PANEL ASSEMBLY-STRUT BUILD | False | LEVEL 13-TIER 1-HPH13 PANEL ASSEMBLY STRUT BUILD | 0 | FAB-00314-320001TUR | 0
[9 empty] | 2995 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2995 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2995-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2995 |  |  | PF.2995 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00315-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 10/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00315-LEVEL 14-DE-TIER 1-METER STACK | False | LEVEL 14-TIER 1-METER STACK | 0 | FAB-00315-320001TUR | 0
[9 empty] | 2996 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2996 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2996-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2996 |  |  | PF.2996 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00316-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00316-LEVEL 15-DE-TIER 2-METER STACK | False | LEVEL 15-TIER 2-METER STACK | 0 | FAB-00316-320001TUR | 0
[9 empty] | 2997 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2997 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2997-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2997 |  |  | PF.2997 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00317-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00317-LEVEL 16-DE-TIER 2-METER STACK | False | LEVEL 16-TIER 2-METER STACK | 0 | FAB-00317-320001TUR | 0
[9 empty] | 2998 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2998 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2998-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2998 |  |  | PF.2998 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00318-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 12/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00318-LEVEL 17-DE-TIER 2-PL17-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 17-TIER 2-PL17 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00318-320001TUR | 0
[9 empty] | 2999 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2999 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2999-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2999 |  |  | PF.2999 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00319-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00319-LEVEL 18-DE-TIER 2-METER STACK | False | LEVEL 18-TIER 2-METER STACK | 0 | FAB-00319-320001TUR | 0
[9 empty] | 3000 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3000 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3000-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3000 |  |  | PF.3000 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00320-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00320-LEVEL 19-DE-TIER 2-METER STACK | False | LEVEL 19-TIER 2-METER STACK | 0 | FAB-00320-320001TUR | 0
[9 empty] | 3001 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3001 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3001-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3001 |  |  | PF.3001 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00321-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.51 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00321-LEVEL 20-DE-TIER 2-PL20-31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS-STICK BUILD | False | LEVEL 20-TIER 2-PL20 31-42 CK PANEL ASSEMBLY JB-WIRED-NO TERM BLOCKS STICK BUILD | 0 | FAB-00321-320001TUR | 0
[9 empty] | 3002 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3002 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3002-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3002 |  |  | PF.3002 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00322-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00322-LEVEL 21-DE-TIER 2-METER STACK | False | LEVEL 21-TIER 2-METER STACK | 0 | FAB-00322-320001TUR | 0
[9 empty] | 3003 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3003 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3003-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3003 |  |  | PF.3003 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00323-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 12/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00323-LEVEL 22-DE-TIER 2-METER STACK | False | LEVEL 22-TIER 2-METER STACK | 0 | FAB-00323-320001TUR | 0
[9 empty] | 3004 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3004 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3004-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3004 |  |  | PF.3004 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00324-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00324-LEVEL 23-DE-TIER 2-METER STACK | False | LEVEL 23-TIER 2-METER STACK | 0 | FAB-00324-320001TUR | 0
[9 empty] | 3005 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3005 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3005-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3005 |  |  | PF.3005 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00325-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00325-LEVEL 24-DE-TIER 2-METER STACK | False | LEVEL 24-TIER 2-METER STACK | 0 | FAB-00325-320001TUR | 0
[9 empty] | 3006 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3006 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3006-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3006 |  |  | PF.3006 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00326-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00326-LEVEL 25-DE-TIER 2-METER STACK | False | LEVEL 25-TIER 2-METER STACK | 0 | FAB-00326-320001TUR | 0
[9 empty] | 3007 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3007 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3007-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3007 |  |  | PF.3007 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00327-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00327-LEVEL 26-DE-TIER 2-METER STACK | False | LEVEL 26-TIER 2-METER STACK | 0 | FAB-00327-320001TUR | 0
[9 empty] | 3008 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3008 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3008-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3008 |  |  | PF.3008 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00328-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00328-LEVEL 27-DE-TIER 2-METER STACK | False | LEVEL 27-TIER 2-METER STACK | 0 | FAB-00328-320001TUR | 0
[9 empty] | 3009 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3009 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3009-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3009 |  |  | PF.3009 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00329-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00329-LEVEL 28-DE-TIER 2-METER STACK | False | LEVEL 28-TIER 2-METER STACK | 0 | FAB-00329-320001TUR | 0
[9 empty] | 3010 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3010 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3010-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3010 |  |  | PF.3010 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00330-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00330-LEVEL 29-DE-TIER 2-METER STACK | False | LEVEL 29-TIER 2-METER STACK | 0 | FAB-00330-320001TUR | 0
[9 empty] | 3011 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3011 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3011-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3011 |  |  | PF.3011 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00331-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00331-LEVEL 30-DE-TIER 2-METER STACK | False | LEVEL 30-TIER 2-METER STACK | 0 | FAB-00331-320001TUR | 0
[9 empty] | 3012 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3012 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3012-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3012 |  |  | PF.3012 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00332-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00332-LEVEL 31-DE-TIER 2-METER STACK | False | LEVEL 31-TIER 2-METER STACK | 0 | FAB-00332-320001TUR | 0
[9 empty] | 3013 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3013 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3013-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3013 |  |  | PF.3013 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00333-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00333-LEVEL 32-DE-TIER 2-METER STACK | False | LEVEL 32-TIER 2-METER STACK | 0 | FAB-00333-320001TUR | 0
[9 empty] | 3014 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3014 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3014-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3014 |  |  | PF.3014 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00334-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00334-LEVEL 33-DE-TIER 2-METER STACK | False | LEVEL 33-TIER 2-METER STACK | 0 | FAB-00334-320001TUR | 0
[9 empty] | 3015 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3015 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3015-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3015 |  |  | PF.3015 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00335-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 3/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00335-LEVEL 34-DE-TIER 2-METER STACK | False | LEVEL 34-TIER 2-METER STACK | 0 | FAB-00335-320001TUR | 0
[9 empty] | 3016 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3016 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3016-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3016 |  |  | PF.3016 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00336-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 4/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00336-LEVEL 35-DE-TIER 3-METER STACK | False | LEVEL 35-TIER 3-METER STACK | 0 | FAB-00336-320001TUR | 0
[9 empty] | 3017 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3017 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3017-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3017 |  |  | PF.3017 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00337-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 4/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00337-LEVEL 36-DE-TIER 3-METER STACK | False | LEVEL 36-TIER 3-METER STACK | 0 | FAB-00337-320001TUR | 0
[9 empty] | 3018 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3018 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3018-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3018 |  |  | PF.3018 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00338-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.33 | 0 | 320001TUR | 8/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00338-LEVEL 1-DE-TRANSFORMER T4 | False | LEVEL 1 TRANSFORMER T4 | 0 | FAB-00338-320001TUR | 0
[9 empty] | 3019 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3019 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3019-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3019 |  |  | PF.3019 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00339-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.33 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00339-LEVEL 6-DE-TRANSFORMER T5 & T4 | False | LEVEL 6-TRANSFORMER T5 & T4 | 0 | FAB-00339-320001TUR | 0
[9 empty] | 3020 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3020 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3020-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3020 |  |  | PF.3020 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00340-320001TUR | MXD_RESI_JAP_ELEC | 0 | 80.00 | 0 | 320001TUR | 2/4/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00340-LEVEL 37-DE-AMENITY-MEP PH-MODULAR ELECT ASSEMBLY-SMALL-PLACEHOLDER | False | LEVEL 37-AMENITY-MEP PH-MODULAR ELECT ASSEMBLY SMALL PLACEHOLDER | 0 | FAB-00340-320001TUR | 0
[9 empty] | 3021 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3021 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3021-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3021 |  |  | PF.3021 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00341-320001TUR | MXD_RESI_JAP_ELEC | 0 | 80.00 | 0 | 320001TUR | 2/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00341-LEVEL 37-DE-AMENITY-MEP PH-MODULAR ELECT ASSEMBLY-SMALL-PLACEHOLDER | False | LEVEL 37-AMENITY-MEP PH-MODULAR ELECT ASSEMBLY SMALL PLACEHOLDER | 0 | FAB-00341-320001TUR | 0
[9 empty] | 3022 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3022 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3022-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3022 |  |  | PF.3022 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00342-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.60 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00342-LEVEL 1-IW-CHIEF BOXES-AV-1 RECEPTACLE | False | LEVEL 1 CHIEF BOXES AV 1 RECEPTACLE | 0 | FAB-00342-320001TUR | 0
[9 empty] | 3023 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3023 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3023-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3023 |  |  | PF.3023 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00343-320001TUR | MXD_RESI_JAP_ELEC | 0 | 13.00 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00343-LEVEL 2-IW-CHIEF BOXES-AV-2 RECEPTACLES | False | LEVEL 2 CHIEF BOXES AV 2 RECEPTACLES | 0 | FAB-00343-320001TUR | 0
[9 empty] | 3024 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3024 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3024-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3024 |  |  | PF.3024 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00344-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.90 | 0 | 320001TUR | 10/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00344-LEVEL 6-IW-CHIEF BOXES-AV-1 RECEPTACLE | False | LEVEL 6 LEVEL 6-CHIEF BOXES AV 1 RECEPTACLE | 0 | FAB-00344-320001TUR | 0
[9 empty] | 3025 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3025 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3025-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3025 |  |  | PF.3025 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00345-320001TUR | MXD_RESI_JAP_ELEC | 0 | 26.00 | 0 | 320001TUR | 6/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00345-LEVEL 37-IW-AMENITY-MEP PH-CHIEF BOXES-AV-2 RECEPTACLES | False | LEVEL 37-AMENITY-MEP PH-CHIEF BOXES AV 2 RECEPTACLES | 0 | FAB-00345-320001TUR | 0
[9 empty] | 3026 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3026 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3026-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3026 |  |  | PF.3026 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00346-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00346-LEVEL 1-TMP-TEMPS-LARGE | False | LEVEL 1 TEMPS LARGE | 0 | FAB-00346-320001TUR | 0
[9 empty] | 3027 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3027 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3027-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3027 |  |  | PF.3027 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00347-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00347-LEVEL 7-TMP-TIER 1-TEMPS-LARGE | False | LEVEL 7-TIER 1-TEMPS LARGE | 0 | FAB-00347-320001TUR | 0
[9 empty] | 3028 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3028 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3028-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3028 |  |  | PF.3028 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00348-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 8/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00348-LEVEL 18-TMP-TIER 2-45KVA PDU | False | LEVEL 18-TIER 2-45KVA PDU | 0 | FAB-00348-320001TUR | 0
[9 empty] | 3029 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3029 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3029-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3029 |  |  | PF.3029 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00349-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00349-LEVEL 24-TMP-TIER 2-45KVA PDU # 082 | False | LEVEL 24-TIER 2-45KVA PDU # 082 | 0 | FAB-00349-320001TUR | 0
[9 empty] | 3030 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3030 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3030-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3030 |  |  | PF.3030 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00350-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 9/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00350-LEVEL 30-TMP-TIER 2-75KVA PDU#068 | False | LEVEL 30-TIER 2-75KVA PDU#068 | 0 | FAB-00350-320001TUR | 0
[9 empty] | 3031 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3031 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3031-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3031 |  |  | PF.3031 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00351-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 12/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00351-LEVEL 37-TMP-TIER 2-75KVA PDU | False | LEVEL 37-TIER 2-75KVA PDU | 0 | FAB-00351-320001TUR | 0
[9 empty] | 3032 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3032 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3032-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3032 |  |  | PF.3032 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00352-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.00 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00352-LEVEL 38-TMP-75KVA PDU | False | LEVEL 38-75KVA PDU | 0 | FAB-00352-320001TUR | 0
[9 empty] | 3033 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3033 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3033-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3033 |  |  | PF.3033 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00353-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00353-LEVEL B1-TMP-TEMPS-SMALL | False | LEVEL B1 TEMPS SMALL | 0 | FAB-00353-320001TUR | 0
[9 empty] | 3034 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3034 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3034-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3034 |  |  | PF.3034 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00354-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00354-LEVEL 1-TMP-TEMPS-SMALL | False | LEVEL 1 TEMPS SMALL | 0 | FAB-00354-320001TUR | 0
[9 empty] | 3035 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3035 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3035-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3035 |  |  | PF.3035 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00355-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00355-LEVEL 2-TMP-TEMPS-SMALL | False | LEVEL 2 TEMPS SMALL | 0 | FAB-00355-320001TUR | 0
[9 empty] | 3036 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3036 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3036-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3036 |  |  | PF.3036 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00356-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00356-LEVEL 3-TMP-PODIUM-TEMPS-SMALL | False | LEVEL 3-PODIUM-TEMPS SMALL | 0 | FAB-00356-320001TUR | 0
[9 empty] | 3037 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3037 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3037-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3037 |  |  | PF.3037 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00357-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00357-LEVEL 4-TMP-PODIUM-TEMPS-SMALL | False | LEVEL 4-PODIUM-TEMPS SMALL | 0 | FAB-00357-320001TUR | 0
[9 empty] | 3038 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3038 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3038-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3038 |  |  | PF.3038 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00358-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00358-LEVEL 5-TMP-PODIUM-TEMPS-SMALL | False | LEVEL 5-PODIUM-TEMPS SMALL | 0 | FAB-00358-320001TUR | 0
[9 empty] | 3039 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3039 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3039-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3039 |  |  | PF.3039 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00359-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00359-LEVEL 6-TMP-TEMPS-SMALL | False | LEVEL 6 LEVEL 6-TEMPS SMALL | 0 | FAB-00359-320001TUR | 0
[9 empty] | 3040 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3040 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3040-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3040 |  |  | PF.3040 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00360-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00360-LEVEL 7-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 7-TIER 1-TEMPS SMALL | 0 | FAB-00360-320001TUR | 0
[9 empty] | 3041 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3041 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3041-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3041 |  |  | PF.3041 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00361-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00361-LEVEL 8-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 8-TIER 1-TEMPS SMALL | 0 | FAB-00361-320001TUR | 0
[9 empty] | 3042 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3042 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3042-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3042 |  |  | PF.3042 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00362-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00362-LEVEL 9-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 9-TIER 1-TEMPS SMALL | 0 | FAB-00362-320001TUR | 0
[9 empty] | 3043 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3043 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3043-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3043 |  |  | PF.3043 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00363-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00363-LEVEL 10-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 10-TIER 1-TEMPS SMALL | 0 | FAB-00363-320001TUR | 0
[9 empty] | 3044 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3044 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3044-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3044 |  |  | PF.3044 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00364-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00364-LEVEL 11-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 11-TIER 1-TEMPS SMALL | 0 | FAB-00364-320001TUR | 0
[9 empty] | 3045 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3045 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3045-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3045 |  |  | PF.3045 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00365-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00365-LEVEL 12-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 12-TIER 1-TEMPS SMALL | 0 | FAB-00365-320001TUR | 0
[9 empty] | 3046 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3046 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3046-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3046 |  |  | PF.3046 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00366-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00366-LEVEL 13-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 13-TIER 1-TEMPS SMALL | 0 | FAB-00366-320001TUR | 0
[9 empty] | 3047 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3047 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3047-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3047 |  |  | PF.3047 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00367-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00367-LEVEL 14-TMP-TIER 1-TEMPS-SMALL | False | LEVEL 14-TIER 1-TEMPS SMALL | 0 | FAB-00367-320001TUR | 0
[9 empty] | 3048 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3048 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3048-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3048 |  |  | PF.3048 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00368-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00368-LEVEL 15-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 15-TIER 2-TEMPS SMALL | 0 | FAB-00368-320001TUR | 0
[9 empty] | 3049 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3049 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3049-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3049 |  |  | PF.3049 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00369-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00369-LEVEL 16-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 16-TIER 2-TEMPS SMALL | 0 | FAB-00369-320001TUR | 0
[9 empty] | 3050 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3050 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3050-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3050 |  |  | PF.3050 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00370-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00370-LEVEL 17-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 17-TIER 2-TEMPS SMALL | 0 | FAB-00370-320001TUR | 0
[9 empty] | 3051 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3051 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3051-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3051 |  |  | PF.3051 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00371-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00371-LEVEL 18-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 18-TIER 2-TEMPS SMALL | 0 | FAB-00371-320001TUR | 0
[9 empty] | 3052 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3052 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3052-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3052 |  |  | PF.3052 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00372-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00372-LEVEL 19-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 19-TIER 2-TEMPS SMALL | 0 | FAB-00372-320001TUR | 0
[9 empty] | 3053 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3053 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3053-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3053 |  |  | PF.3053 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00373-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR |  | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00373-LEVEL 20-TMP-TIER 2-TEMPS-SMALL | False | LEVEL 20-TIER 2-TEMPS SMALL | 0 | FAB-00373-320001TUR | 0
[9 empty] | 3054 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3054 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3054-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3054 |  |  | PF.3054 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00374-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00374-LEVEL 21-TMP-TIER 2-SPIDER BOXES | False | LEVEL 21-TIER 2-SPIDER BOXES | 0 | FAB-00374-320001TUR | 0
[9 empty] | 3055 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3055 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3055-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3055 |  |  | PF.3055 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00375-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00375-LEVEL 22-TMP-TIER 2-SPIDER BOXES | False | LEVEL 22-TIER 2-SPIDER BOXES | 0 | FAB-00375-320001TUR | 0
[9 empty] | 3056 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3056 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3056-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3056 |  |  | PF.3056 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00376-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00376-LEVEL 23-TMP-TIER 2-SPIDER BOXES | False | LEVEL 23-TIER 2-SPIDER BOXES | 0 | FAB-00376-320001TUR | 0
[9 empty] | 3057 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3057 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3057-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3057 |  |  | PF.3057 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00377-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00377-LEVEL 24-TMP-TIER 2-SPIDER BOXES | False | LEVEL 24-TIER 2-SPIDER BOXES | 0 | FAB-00377-320001TUR | 0
[9 empty] | 3058 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3058 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3058-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3058 |  |  | PF.3058 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00378-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00378-LEVEL 25-TMP-TIER 2-SPIDER BOXES | False | LEVEL 25-TIER 2-SPIDER BOXES | 0 | FAB-00378-320001TUR | 0
[9 empty] | 3059 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3059 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3059-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3059 |  |  | PF.3059 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00379-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00379-LEVEL 26-TMP-TIER 2-SPIDER BOXES | False | LEVEL 26-TIER 2-SPIDER BOXES | 0 | FAB-00379-320001TUR | 0
[9 empty] | 3060 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3060 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3060-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3060 |  |  | PF.3060 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00380-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00380-LEVEL 27-TMP-TIER 2-SPIDER BOXES | False | LEVEL 27-TIER 2-SPIDER BOXES | 0 | FAB-00380-320001TUR | 0
[9 empty] | 3061 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3061 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3061-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3061 |  |  | PF.3061 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00381-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 9/30/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00381-LEVEL 28-TMP-TIER 2-SPIDER BOXES | False | LEVEL 28-TIER 2-SPIDER BOXES | 0 | FAB-00381-320001TUR | 0
[9 empty] | 3062 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3062 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3062-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3062 |  |  | PF.3062 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00382-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00382-LEVEL 29-TMP-TIER 2-SPIDER BOXES | False | LEVEL 29-TIER 2-SPIDER BOXES | 0 | FAB-00382-320001TUR | 0
[9 empty] | 3063 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3063 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3063-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3063 |  |  | PF.3063 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00383-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00383-LEVEL 30-TMP-TIER 2-SPIDER BOXES | False | LEVEL 30-TIER 2-SPIDER BOXES | 0 | FAB-00383-320001TUR | 0
[9 empty] | 3064 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3064 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3064-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3064 |  |  | PF.3064 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00384-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 11/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00384-LEVEL 31-TMP-TIER 2-SPIDER BOXES | False | LEVEL 31-TIER 2-SPIDER BOXES | 0 | FAB-00384-320001TUR | 0
[9 empty] | 3065 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3065 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3065-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3065 |  |  | PF.3065 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00385-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00385-LEVEL 32-TMP-TIER 2-SPIDER BOXES | False | LEVEL 32-TIER 2-SPIDER BOXES | 0 | FAB-00385-320001TUR | 0
[9 empty] | 3066 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3066 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3066-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3066 |  |  | PF.3066 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00386-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00386-LEVEL 33-TMP-TIER 2-SPIDER BOXES | False | LEVEL 33-TIER 2-SPIDER BOXES | 0 | FAB-00386-320001TUR | 0
[9 empty] | 3067 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3067 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3067-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3067 |  |  | PF.3067 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00387-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00387-LEVEL 34-TMP-TIER 2-SPIDER BOXES | False | LEVEL 34-TIER 2-SPIDER BOXES | 0 | FAB-00387-320001TUR | 0
[9 empty] | 3068 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3068 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3068-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3068 |  |  | PF.3068 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00388-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00388-LEVEL 35-TMP-TIER 3-SPIDER BOXES | False | LEVEL 35-TIER 3-SPIDER BOXES | 0 | FAB-00388-320001TUR | 0
[9 empty] | 3069 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3069 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3069-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3069 |  |  | PF.3069 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00389-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00389-LEVEL 36-TMP-TIER 3-SPIDER BOXES | False | LEVEL 36-TIER 3-SPIDER BOXES | 0 | FAB-00389-320001TUR | 0
[9 empty] | 3070 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3070 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3070-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3070 |  |  | PF.3070 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00390-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 12/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00390-LEVEL 37-TMP-AMENITY-MEP PH-SPIDER BOXES | False | LEVEL 37-AMENITY-MEP PH-SPIDER BOXES | 0 | FAB-00390-320001TUR | 0
[9 empty] | 3071 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3071 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3071-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3071 |  |  | PF.3071 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00391-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00391-LEVEL 38-TMP-SPIDER BOXES | False | LEVEL 38-SPIDER BOXES | 0 | FAB-00391-320001TUR | 0
[9 empty] | 3072 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3072 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3072-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3072 |  |  | PF.3072 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00392-320001TUR | MXD_RESI_JAP_ELEC | 0 | 3.00 | 0 | 320001TUR | 2/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00392-LEVEL 39-TMP-SPIDER BOXES | False | LEVEL 39-SPIDER BOXES | 0 | FAB-00392-320001TUR | 0
[9 empty] | 3073 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3073 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3073-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3073 |  |  | PF.3073 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00393-320001TUR | MXD_RESI_JAP_ELEC | 0 | 75.00 | 0 | 320001TUR | 5/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00393-LEVEL 39-DE-ROOFTOP DISCONNECTS | False | ROOFTOP DISCONNECTS | 0 | FAB-00393-320001TUR | 0
[9 empty] | 3074 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3074 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3074-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3074 |  |  | PF.3074 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00394-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00394-LEVEL 1-CND-5in and 4in RIGID NIPPLES | False | 5in and 4in RIGID NIPPLES | 0 | FAB-00394-320001TUR | 0
[9 empty] | 3075 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3075 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3075-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3075 |  |  | PF.3075 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00395-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 6/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00395-LEVEL 13-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00395-320001TUR | 0
[9 empty] | 3076 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3076 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3076-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3076 |  |  | PF.3076 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00396-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 6/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00396-LEVEL 14-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00396-320001TUR | 0
[9 empty] | 3077 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3077 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3077-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3077 |  |  | PF.3077 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00397-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00397-LEVEL 15-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00397-320001TUR | 0
[9 empty] | 3078 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3078 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3078-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3078 |  |  | PF.3078 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00398-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00398-LEVEL 16-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00398-320001TUR | 0
[9 empty] | 3079 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3079 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3079-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3079 |  |  | PF.3079 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00399-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00399-LEVEL 17-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00399-320001TUR | 0
[9 empty] | 3080 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3080 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3080-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3080 |  |  | PF.3080 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00400-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00400-LEVEL 18-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00400-320001TUR | 0
[9 empty] | 3081 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3081 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3081-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3081 |  |  | PF.3081 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00401-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00401-LEVEL 19-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00401-320001TUR | 0
[9 empty] | 3082 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3082 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3082-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3082 |  |  | PF.3082 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00402-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00402-LEVEL 20-CND-Deck Sleeves | False | Deck Sleeves | 0 | FAB-00402-320001TUR | 0
[9 empty] | 3083 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3083 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3083-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3083 |  |  | PF.3083 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00403-320001TUR | MXD_RESI_JAP_ELEC | 0 | 31.00 | 0 | 320001TUR | 7/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00403-MULTI LEVEL-TMP-temp power quad outlets | False | temp power quad outlets | 0 | FAB-00403-320001TUR | 0
[9 empty] | 3084 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3084 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3084-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3084 |  |  | PF.3084 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00404-320001TUR | MXD_RESI_JAP_ELEC | 0 | 31.00 | 0 | 320001TUR | 8/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00404-MULTI LEVEL-TMP-temp power quad outlets | False | temp power quad outlets | 0 | FAB-00404-320001TUR | 0
[9 empty] | 3085 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3085 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3085-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3085 |  |  | PF.3085 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00405-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00405-LEVEL 21-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00405-320001TUR | 0
[9 empty] | 3086 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3086 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3086-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3086 |  |  | PF.3086 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00406-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00406-LEVEL 22-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00406-320001TUR | 0
[9 empty] | 3087 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3087 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3087-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3087 |  |  | PF.3087 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00407-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00407-LEVEL 23-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00407-320001TUR | 0
[9 empty] | 3088 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3088 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3088-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3088 |  |  | PF.3088 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00408-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00408-LEVEL 24-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00408-320001TUR | 0
[9 empty] | 3089 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3089 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3089-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3089 |  |  | PF.3089 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00409-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00409-LEVEL 25-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00409-320001TUR | 0
[9 empty] | 3090 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3090 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3090-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3090 |  |  | PF.3090 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00410-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00410-LEVEL 26-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00410-320001TUR | 0
[9 empty] | 3091 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3091 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3091-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3091 |  |  | PF.3091 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00411-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00411-LEVEL 27-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00411-320001TUR | 0
[9 empty] | 3092 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3092 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3092-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3092 |  |  | PF.3092 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00412-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00412-LEVEL 28-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00412-320001TUR | 0
[9 empty] | 3093 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3093 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3093-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3093 |  |  | PF.3093 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00413-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00413-LEVEL 29-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00413-320001TUR | 0
[9 empty] | 3094 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3094 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3094-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3094 |  |  | PF.3094 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00414-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00414-LEVEL 30-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00414-320001TUR | 0
[9 empty] | 3095 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3095 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3095-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3095 |  |  | PF.3095 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00415-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00415-LEVEL 31-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00415-320001TUR | 0
[9 empty] | 3096 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3096 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3096-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3096 |  |  | PF.3096 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00416-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00416-LEVEL 32-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00416-320001TUR | 0
[9 empty] | 3097 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3097 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3097-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3097 |  |  | PF.3097 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00417-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00417-LEVEL 33-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00417-320001TUR | 0
[9 empty] | 3098 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3098 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3098-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3098 |  |  | PF.3098 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00418-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00418-LEVEL 34-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00418-320001TUR | 0
[9 empty] | 3099 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3099 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3099-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3099 |  |  | PF.3099 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00419-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/31/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00419-LEVEL 35-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00419-320001TUR | 0
[9 empty] | 3100 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3100 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3100-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3100 |  |  | PF.3100 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00420-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00420-LEVEL 36-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00420-320001TUR | 0
[9 empty] | 3101 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3101 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3101-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3101 |  |  | PF.3101 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00421-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00421-LEVEL 37-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00421-320001TUR | 0
[9 empty] | 3102 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3102 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3102-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3102 |  |  | PF.3102 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00422-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00422-LEVEL 38-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00422-320001TUR | 0
[9 empty] | 3103 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3103 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3103-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3103 |  |  | PF.3103 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00423-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00423-LEVEL 39-CND-DECK SLEEVES | False | DECK SLEEVES | 0 | FAB-00423-320001TUR | 0
[9 empty] | 3104 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3104 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3104-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3104 |  |  | PF.3104 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00424-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 7/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00424-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00424-320001TUR | 0
[9 empty] | 3105 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3105 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3105-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3105 |  |  | PF.3105 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00425-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00425-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00425-320001TUR | 0
[9 empty] | 3106 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3106 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3106-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3106 |  |  | PF.3106 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00426-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00426-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00426-320001TUR | 0
[9 empty] | 3107 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3107 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3107-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3107 |  |  | PF.3107 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00427-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00427-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00427-320001TUR | 0
[9 empty] | 3108 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3108 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3108-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3108 |  |  | PF.3108 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00428-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00428-MULTI LEVEL-CND-CORE SHEER WALL SLEEVES | False | CORE SHEER WALL SLEEVES | 0 | FAB-00428-320001TUR | 0
[9 empty] | 3109 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3109 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3109-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3109 |  |  | PF.3109 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00429-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00429-LEVEL 21-DE-PANEL HPH21 | False | PANEL HPH21 | 0 | FAB-00429-320001TUR | 0
[9 empty] | 3110 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3110 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3110-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3110 |  |  | PF.3110 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00430-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 2/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00430-LEVEL 24-DE-PANEL EPH24-EPL24 | False | PANEL EPH24EPL24 | 0 | FAB-00430-320001TUR | 0
[9 empty] | 3111 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3111 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3111-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3111 |  |  | PF.3111 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00431-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 2/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00431-LEVEL 25-DE-PANEL HPH25 | False | PANEL HPH25 | 0 | FAB-00431-320001TUR | 0
[9 empty] | 3112 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3112 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3112-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3112 |  |  | PF.3112 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00432-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.50 | 0 | 320001TUR | 5/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00432-LEVEL 33-DE-PANEL HPH33 | False | PANEL HPH33 | 0 | FAB-00432-320001TUR | 0
[9 empty] | 3113 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3113 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3113-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3113 |  |  | PF.3113 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00433-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.00 | 0 | 320001TUR | 5/8/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00433-LEVEL 34-DE-PANELS EPH34-EPL34 | False | PANELS EPH34EPL34 | 0 | FAB-00433-320001TUR | 0
[9 empty] | 3114 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3114 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3114-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3114 |  |  | PF.3114 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00434-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00434-LEVEL 18-CND-6in PVC X 8in LONG CONTROL POINTS | False | 6in PVC X 8in LONG CONTROL POINTS | 0 | FAB-00434-320001TUR | 0
[9 empty] | 3115 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3115 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3115-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3115 |  |  | PF.3115 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00435-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00435-LEVEL 19-CND-6in PVC X 8in LONG CONTROL POINTS | False | 6in PVC X 8in LONG CONTROL POINTS | 0 | FAB-00435-320001TUR | 0
[9 empty] | 3116 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3116 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3116-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3116 |  |  | PF.3116 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00436-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00436-LEVEL 20-CND-6in PVC X 8in LONG CONTROL POINTS | False | 6in PVC X 8in LONG CONTROL POINTS | 0 | FAB-00436-320001TUR | 0
[9 empty] | 3117 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3117 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3117-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3117 |  |  | PF.3117 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00437-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/6/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00437-LEVEL 21-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00437-320001TUR | 0
[9 empty] | 3118 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3118 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3118-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3118 |  |  | PF.3118 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00438-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00438-LEVEL 22-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00438-320001TUR | 0
[9 empty] | 3119 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3119 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3119-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3119 |  |  | PF.3119 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00439-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00439-LEVEL 23-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00439-320001TUR | 0
[9 empty] | 3120 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3120 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3120-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3120 |  |  | PF.3120 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00440-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00440-LEVEL 24-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00440-320001TUR | 0
[9 empty] | 3121 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3121 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3121-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3121 |  |  | PF.3121 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00441-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/11/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00441-LEVEL 25-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00441-320001TUR | 0
[9 empty] | 3122 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3122 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3122-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3122 |  |  | PF.3122 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00442-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00442-LEVEL 26-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00442-320001TUR | 0
[9 empty] | 3123 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3123 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3123-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3123 |  |  | PF.3123 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00443-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00443-LEVEL 27-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00443-320001TUR | 0
[9 empty] | 3124 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3124 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3124-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3124 |  |  | PF.3124 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00444-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00444-LEVEL 28-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00444-320001TUR | 0
[9 empty] | 3125 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3125 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3125-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3125 |  |  | PF.3125 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00445-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00445-LEVEL 29-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00445-320001TUR | 0
[9 empty] | 3126 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3126 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3126-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3126 |  |  | PF.3126 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00446-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00446-LEVEL 30-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00446-320001TUR | 0
[9 empty] | 3127 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3127 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3127-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3127 |  |  | PF.3127 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00447-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00447-LEVEL 31-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00447-320001TUR | 0
[9 empty] | 3128 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3128 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3128-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3128 |  |  | PF.3128 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00448-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00448-LEVEL 32-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00448-320001TUR | 0
[9 empty] | 3129 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3129 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3129-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3129 |  |  | PF.3129 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00449-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00449-LEVEL 33-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00449-320001TUR | 0
[9 empty] | 3130 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3130 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3130-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3130 |  |  | PF.3130 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00450-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00450-LEVEL 34-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00450-320001TUR | 0
[9 empty] | 3131 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3131 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3131-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3131 |  |  | PF.3131 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00451-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00451-LEVEL 35-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00451-320001TUR | 0
[9 empty] | 3132 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3132 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3132-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3132 |  |  | PF.3132 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00452-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00452-LEVEL 36-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00452-320001TUR | 0
[9 empty] | 3133 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3133 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3133-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3133 |  |  | PF.3133 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00453-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00453-LEVEL 37-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00453-320001TUR | 0
[9 empty] | 3134 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3134 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3134-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3134 |  |  | PF.3134 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00454-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00454-LEVEL 38-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00454-320001TUR | 0
[9 empty] | 3135 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3135 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3135-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3135 |  |  | PF.3135 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00455-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00455-LEVEL 39-CND-6in PVC x 8inLONG CONTROL POINTS | False | 6in PVC x 8inLONG CONTROL POINTS | 0 | FAB-00455-320001TUR | 0
[9 empty] | 3136 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3136 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3136-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3136 |  |  | PF.3136 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00456-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.27 | 0 | 320001TUR | 8/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00456-LEVEL 1-IW-shallow box-beam mockup | False | shallow box beam mockup | 0 | FAB-00456-320001TUR | 0
[9 empty] | 3137 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3137 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3137-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3137 |  |  | PF.3137 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00457-320001TUR | MXD_RESI_JAP_ELEC | 0 | 40.00 | 0 | 320001TUR | 8/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00457-MULTI LEVEL-TMP-SPIDER BOXES -15FT-FEMAILE WHIPS | False | SPIDER BOXES -15FT-FEMAILE WHIPS | 0 | FAB-00457-320001TUR | 0
[9 empty] | 3138 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3138 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3138-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3138 |  |  | PF.3138 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00458-320001TUR | MXD_RESI_JAP_ELEC | 0 | 16.00 | 0 | 320001TUR | 8/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00458-SITE-TMP-TEMP PANELS | False | TEMP PANELS | 0 | FAB-00458-320001TUR | 0
[9 empty] | 3139 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3139 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3139-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3139 |  |  | PF.3139 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00459-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00459-LEVEL 3-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00459-320001TUR | 0
[9 empty] | 3140 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3140 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3140-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3140 |  |  | PF.3140 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00460-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00460-LEVEL 4-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00460-320001TUR | 0
[9 empty] | 3141 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3141 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3141-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3141 |  |  | PF.3141 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00461-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00461-LEVEL 5-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00461-320001TUR | 0
[9 empty] | 3142 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3142 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3142-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3142 |  |  | PF.3142 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00462-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00462-LEVEL 6-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00462-320001TUR | 0
[9 empty] | 3143 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3143 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3143-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3143 |  |  | PF.3143 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00463-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00463-LEVEL 7-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00463-320001TUR | 0
[9 empty] | 3144 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3144 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3144-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3144 |  |  | PF.3144 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00464-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00464-LEVEL 8-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00464-320001TUR | 0
[9 empty] | 3145 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3145 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3145-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3145 |  |  | PF.3145 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00465-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00465-LEVEL 9-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00465-320001TUR | 0
[9 empty] | 3146 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3146 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3146-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3146 |  |  | PF.3146 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00466-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00466-LEVEL 10-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00466-320001TUR | 0
[9 empty] | 3147 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3147 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3147-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3147 |  |  | PF.3147 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00467-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00467-LEVEL 11-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00467-320001TUR | 0
[9 empty] | 3148 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3148 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3148-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3148 |  |  | PF.3148 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00468-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00468-LEVEL 12-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00468-320001TUR | 0
[9 empty] | 3149 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3149 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3149-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3149 |  |  | PF.3149 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00469-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00469-LEVEL 13-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00469-320001TUR | 0
[9 empty] | 3150 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3150 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3150-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3150 |  |  | PF.3150 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00470-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00470-LEVEL 14-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00470-320001TUR | 0
[9 empty] | 3151 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3151 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3151-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3151 |  |  | PF.3151 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00471-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00471-LEVEL 15-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00471-320001TUR | 0
[9 empty] | 3152 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3152 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3152-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3152 |  |  | PF.3152 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00472-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00472-LEVEL 16-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00472-320001TUR | 0
[9 empty] | 3153 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3153 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3153-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3153 |  |  | PF.3153 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00473-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00473-LEVEL 17-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00473-320001TUR | 0
[9 empty] | 3154 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3154 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3154-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3154 |  |  | PF.3154 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00474-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00474-LEVEL 18-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00474-320001TUR | 0
[9 empty] | 3155 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3155 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3155-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3155 |  |  | PF.3155 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00475-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00475-LEVEL 19-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00475-320001TUR | 0
[9 empty] | 3156 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3156 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3156-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3156 |  |  | PF.3156 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00476-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00476-LEVEL 20-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00476-320001TUR | 0
[9 empty] | 3157 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3157 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3157-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3157 |  |  | PF.3157 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00477-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00477-LEVEL 21-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00477-320001TUR | 0
[9 empty] | 3158 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3158 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3158-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3158 |  |  | PF.3158 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00478-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00478-LEVEL 22-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00478-320001TUR | 0
[9 empty] | 3159 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3159 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3159-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3159 |  |  | PF.3159 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00479-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00479-LEVEL 23-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00479-320001TUR | 0
[9 empty] | 3160 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3160 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3160-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3160 |  |  | PF.3160 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00480-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00480-LEVEL 24-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00480-320001TUR | 0
[9 empty] | 3161 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3161 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3161-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3161 |  |  | PF.3161 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00481-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00481-LEVEL 25-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00481-320001TUR | 0
[9 empty] | 3162 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3162 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3162-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3162 |  |  | PF.3162 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00482-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00482-LEVEL 26-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00482-320001TUR | 0
[9 empty] | 3163 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3163 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3163-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3163 |  |  | PF.3163 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00483-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00483-LEVEL 27-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00483-320001TUR | 0
[9 empty] | 3164 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3164 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3164-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3164 |  |  | PF.3164 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00484-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00484-LEVEL 28-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00484-320001TUR | 0
[9 empty] | 3165 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3165 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3165-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3165 |  |  | PF.3165 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00485-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00485-LEVEL 29-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00485-320001TUR | 0
[9 empty] | 3166 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3166 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3166-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3166 |  |  | PF.3166 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00486-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00486-LEVEL 30-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00486-320001TUR | 0
[9 empty] | 3167 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3167 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3167-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3167 |  |  | PF.3167 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00487-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00487-LEVEL 31-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00487-320001TUR | 0
[9 empty] | 3168 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3168 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3168-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3168 |  |  | PF.3168 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00488-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00488-LEVEL 32-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00488-320001TUR | 0
[9 empty] | 3169 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3169 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3169-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3169 |  |  | PF.3169 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00489-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00489-LEVEL 33-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00489-320001TUR | 0
[9 empty] | 3170 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3170 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3170-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3170 |  |  | PF.3170 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00490-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00490-LEVEL 34-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00490-320001TUR | 0
[9 empty] | 3171 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3171 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3171-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3171 |  |  | PF.3171 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00491-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00491-LEVEL 35-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00491-320001TUR | 0
[9 empty] | 3172 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3172 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3172-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3172 |  |  | PF.3172 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00492-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00492-LEVEL 36-CND-HILTI WALL SLEEVES | False | HILTI WALL SLEEVES | 0 | FAB-00492-320001TUR | 0
[9 empty] | 3173 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3173 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3173-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3173 |  |  | PF.3173 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00493-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00493-LEVEL 3-CND-CONDUIT RISER SLEEVES | False | CONDUIT RISER SLEEVES | 0 | FAB-00493-320001TUR | 0
[9 empty] | 3174 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3174 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3174-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3174 |  |  | PF.3174 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00494-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00494-LEVEL 4-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00494-320001TUR | 0
[9 empty] | 3175 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3175 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3175-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3175 |  |  | PF.3175 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00495-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 8/25/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00495-LEVEL 5-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00495-320001TUR | 0
[9 empty] | 3176 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3176 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3176-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3176 |  |  | PF.3176 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00496-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00496-LEVEL 6-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00496-320001TUR | 0
[9 empty] | 3177 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3177 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3177-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3177 |  |  | PF.3177 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00497-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00497-LEVEL 7-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00497-320001TUR | 0
[9 empty] | 3178 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3178 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3178-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3178 |  |  | PF.3178 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00498-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00498-LEVEL 8-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00498-320001TUR | 0
[9 empty] | 3179 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3179 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3179-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3179 |  |  | PF.3179 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00499-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00499-LEVEL 9-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00499-320001TUR | 0
[9 empty] | 3180 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3180 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3180-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3180 |  |  | PF.3180 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00500-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00500-LEVEL 10-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00500-320001TUR | 0
[9 empty] | 3181 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3181 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3181-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3181 |  |  | PF.3181 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00501-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00501-LEVEL 11-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00501-320001TUR | 0
[9 empty] | 3182 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3182 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3182-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3182 |  |  | PF.3182 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00502-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00502-LEVEL 12-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00502-320001TUR | 0
[9 empty] | 3183 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3183 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3183-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3183 |  |  | PF.3183 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00503-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00503-LEVEL 13-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00503-320001TUR | 0
[9 empty] | 3184 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3184 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3184-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3184 |  |  | PF.3184 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00504-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00504-LEVEL 14-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00504-320001TUR | 0
[9 empty] | 3185 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3185 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3185-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3185 |  |  | PF.3185 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00505-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 9/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00505-LEVEL 15-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00505-320001TUR | 0
[9 empty] | 3186 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3186 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3186-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3186 |  |  | PF.3186 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00506-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00506-LEVEL 16-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00506-320001TUR | 0
[9 empty] | 3187 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3187 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3187-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3187 |  |  | PF.3187 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00507-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00507-LEVEL 17-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00507-320001TUR | 0
[9 empty] | 3188 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3188 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3188-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3188 |  |  | PF.3188 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00508-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00508-LEVEL 18-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00508-320001TUR | 0
[9 empty] | 3189 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3189 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3189-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3189 |  |  | PF.3189 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00509-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00509-LEVEL 19-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00509-320001TUR | 0
[9 empty] | 3190 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3190 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3190-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3190 |  |  | PF.3190 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00510-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00510-LEVEL 20-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00510-320001TUR | 0
[9 empty] | 3191 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3191 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3191-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3191 |  |  | PF.3191 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00511-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00511-LEVEL 21-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00511-320001TUR | 0
[9 empty] | 3192 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 3192 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 3192-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.3192 |  |  | PF.3192 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00512-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/16/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00512-LEVEL 22-CND-HILTI RISER SLEEVES | False | HILTI RISER SLEEVES | 0 | FAB-00512-320001TUR | 0
[9 empty] | 2393 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2393 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2393-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2393 |  |  | PF.2393 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00146 | SIMMONS_ELEC | 0 | 1.00 | 1 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100 |  | CND---01 | False |  | 42 | 200019SKA-00146 | 0
[9 empty] | 2394 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2394 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2394-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2394 |  |  | PF.2394 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00011 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-04 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 15 | 0 | 200019SKA-00011 | 0
[9 empty] | 2395 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2395 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2395-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2395 |  |  | PF.2395 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00015 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-05 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00015 | 0
[9 empty] | 2396 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2396 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2396-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2396 |  |  | PF.2396 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00024 | SIMMONS_ELEC | 0 | 12.00 | 29 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-06 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 19 | 5698 | 200019SKA-00024 | 0
[9 empty] | 2397 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2397 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2397-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2397 |  |  | PF.2397 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00028 | SIMMONS_ELEC | 0 | 1.00 | 4 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-07 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 18 | 467 | 200019SKA-00028 | 0
[9 empty] | 2398 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2398 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2398-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2398 |  |  | PF.2398 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00032 | SIMMONS_ELEC | 0 | 1.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-08 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 11 | 355 | 200019SKA-00032 | 0
[9 empty] | 2399 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2399 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2399-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2399 |  |  | PF.2399 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00036 | SIMMONS_ELEC | 0 | 2.00 | 15 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-09 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 08 | 1120 | 200019SKA-00036 | 0
[9 empty] | 2400 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2400 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2400-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2400 |  |  | PF.2400 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00037 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-10 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00037 | 0
[9 empty] | 2401 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2401 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2401-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2401 |  |  | PF.2401 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00041 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-11 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 08 | 0 | 200019SKA-00041 | 0
[9 empty] | 2402 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2402 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2402-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2402 |  |  | PF.2402 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00046 | SIMMONS_ELEC | 0 | 4.00 | 16 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-12 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 17 | 3387 | 200019SKA-00046 | 0
[9 empty] | 2403 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2403 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2403-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2403 |  |  | PF.2403 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00050 | SIMMONS_ELEC | 0 | 1.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-13 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 13 | 359 | 200019SKA-00050 | 0
[9 empty] | 2404 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2404 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2404-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2404 |  |  | PF.2404 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00054 | SIMMONS_ELEC | 0 | 1.00 | 7 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-14 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 09 | 377 | 200019SKA-00054 | 0
[9 empty] | 2405 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2405 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2405-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2405 |  |  | PF.2405 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00066 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-15 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\ROOF LEVEL | 0 | 200019SKA-00066 | 0
[9 empty] | 2406 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2406 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2406-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2406 |  |  | PF.2406 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00069 | SIMMONS_ELEC | 0 | 1.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-16 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 730 | 200019SKA-00069 | 0
[9 empty] | 2407 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2407 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2407-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2407 |  |  | PF.2407 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00073 | SIMMONS_ELEC | 0 | 1.00 | 10 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-17 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 457 | 200019SKA-00073 | 0
[9 empty] | 2408 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2408 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2408-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2408 |  |  | PF.2408 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00076 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-18 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00076 | 0
[9 empty] | 2409 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2409 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2409-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2409 |  |  | PF.2409 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00080 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-19 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00080 | 0
[9 empty] | 2410 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2410 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2410-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2410 |  |  | PF.2410 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00082 | SIMMONS_ELEC | 0 | 1.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100 |  | CND--ABOVE PODIUM-20 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 324 | 200019SKA-00082 | 0
[9 empty] | 2411 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2411 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2411-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2411 |  |  | PF.2411 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00084 | SIMMONS_ELEC | 0 | 2.00 | 22 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-21 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 1229 | 200019SKA-00084 | 0
[9 empty] | 2412 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2412 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2412-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2412 |  |  | PF.2412 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00086 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-22 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00086 | 0
[9 empty] | 2413 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2413 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2413-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2413 |  |  | PF.2413 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00088 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-23 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00088 | 0
[9 empty] | 2414 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2414 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2414-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2414 |  |  | PF.2414 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00090 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-24 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00090 | 0
[9 empty] | 2415 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2415 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2415-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2415 |  |  | PF.2415 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00093 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-25 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00093 | 0
[9 empty] | 2416 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2416 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2416-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2416 |  |  | PF.2416 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00094 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-26 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00094 | 0
[9 empty] | 2417 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2417 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2417-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2417 |  |  | PF.2417 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00095 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-27 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00095 | 0
[9 empty] | 2418 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2418 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2418-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2418 |  |  | PF.2418 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00098 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-28 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00098 | 0
[9 empty] | 2419 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2419 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2419-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2419 |  |  | PF.2419 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00099 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-29 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00099 | 0
[9 empty] | 2420 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2420 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2420-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2420 |  |  | PF.2420 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00100 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--ABOVE PODIUM-30 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00100 | 0
[9 empty] | 2421 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2421 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2421-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2421 |  |  | PF.2421 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00106 | SIMMONS_ELEC | 0 | 1.00 | 2 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100 |  | CND--ABOVE PODIUM-31 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 14 | 558 | 200019SKA-00106 | 0
[9 empty] | 2422 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2422 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2422-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2422 |  |  | PF.2422 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00107 | SIMMONS_ELEC | 0 | 1.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND--GRID - ORTHO-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL B01 | 342 | 200019SKA-00107 | 0
[9 empty] | 2423 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2423 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2423-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2423 |  |  | PF.2423 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00010 | SIMMONS_ELEC | 0 | 14.00 | 76 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 01 | 11220 | 200019SKA-00010 | 0
[9 empty] | 2424 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2424 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2424-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2424 |  |  | PF.2424 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00019 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-02 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 01 | 0 | 200019SKA-00019 | 0
[9 empty] | 2425 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2425 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2425-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2425 |  |  | PF.2425 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00059 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-04 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00059 | 0
[9 empty] | 2426 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2426 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2426-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2426 |  |  | PF.2426 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00063 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-05 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00063 | 0
[9 empty] | 2427 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2427 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2427-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2427 |  |  | PF.2427 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00092 | SIMMONS_ELEC | 0 | 6.00 | 48 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-06 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 5223 | 200019SKA-00092 | 0
[9 empty] | 2428 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2428 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2428-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2428 |  |  | PF.2428 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00096 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-07 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00096 | 0
[9 empty] | 2429 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2429 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2429-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2429 |  |  | PF.2429 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00097 | SIMMONS_ELEC | 0 | 6.00 | 38 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-08 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 3868 | 200019SKA-00097 | 0
[9 empty] | 2430 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2430 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2430-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2430 |  |  | PF.2430 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00101 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-09 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00101 | 0
[9 empty] | 2431 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2431 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2431-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2431 |  |  | PF.2431 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00102 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-10 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00102 | 0
[9 empty] | 2432 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2432 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2432-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2432 |  |  | PF.2432 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00103 | SIMMONS_ELEC | 0 | 3.00 | 21 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100 |  | CND-LEVEL 01-ABOVE PODIUM-11 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 02 | 1835 | 200019SKA-00103 | 0
[9 empty] | 2433 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2433 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2433-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2433 |  |  | PF.2433 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00104 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-12 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00104 | 0
[9 empty] | 2434 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2434 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2434-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2434 |  |  | PF.2434 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00105 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | CND-LEVEL 01-ABOVE PODIUM-13 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 02 | 0 | 200019SKA-00105 | 0
[9 empty] | 2435 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2435 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2435-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2435 |  |  | PF.2435 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00148-25 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10 |  | DE----001 | False |  | 0 | 200019SKA-00148-25 | 0
[9 empty] | 2436 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2436 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2436-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2436 |  |  | PF.2436 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00147 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | DE---01 | False | Fa | 0 | 200019SKA-00147 | 0
[9 empty] | 2437 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2437 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2437-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2437 |  |  | PF.2437 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00149-25 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10 |  | DE-LEVEL 02--ABOVE PODIUM-001 | False |  | 0 | 200019SKA-00149-25 | 0
[9 empty] | 2438 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2438 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2438-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2438 |  |  | PF.2438 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00145 | SIMMONS_ELEC | 0 | 0.00 | 1 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10 |  | DE-LEVEL 02-ABOVE PODIUM-01 | False |  | 76 | 200019SKA-00145 | 0
[9 empty] | 2439 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2439 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2439-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2439 |  |  | PF.2439 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00005 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 15 | 0 | 200019SKA-00005 | 0
[9 empty] | 2440 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2440 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2440-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2440 |  |  | PF.2440 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00009 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-02 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00009 | 0
[9 empty] | 2441 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2441 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2441-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2441 |  |  | PF.2441 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00018 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-04 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00018 | 0
[9 empty] | 2442 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2442 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2442-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2442 |  |  | PF.2442 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00031 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-05 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 18 | 0 | 200019SKA-00031 | 0
[9 empty] | 2443 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2443 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2443-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2443 |  |  | PF.2443 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00035 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-06 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00035 | 0
[9 empty] | 2444 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2444 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2444-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2444 |  |  | PF.2444 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00040 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-07 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00040 | 0
[9 empty] | 2445 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2445 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2445-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2445 |  |  | PF.2445 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00045 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-08 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 08 | 0 | 200019SKA-00045 | 0
[9 empty] | 2446 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2446 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2446-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2446 |  |  | PF.2446 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00049 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-09 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 17 | 0 | 200019SKA-00049 | 0
[9 empty] | 2447 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2447 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2447-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2447 |  |  | PF.2447 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00053 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-10 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 13 | 0 | 200019SKA-00053 | 0
[9 empty] | 2448 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2448 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2448-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2448 |  |  | PF.2448 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00057 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-11 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 09 | 0 | 200019SKA-00057 | 0
[9 empty] | 2449 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2449 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2449-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2449 |  |  | PF.2449 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00065 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-12 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00065 | 0
[9 empty] | 2450 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2450 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2450-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2450 |  |  | PF.2450 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00072 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-13 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00072 | 0
[9 empty] | 2451 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2451 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2451-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2451 |  |  | PF.2451 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00075 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-14 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00075 | 0
[9 empty] | 2452 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2452 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2452-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2452 |  |  | PF.2452 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00079 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-15 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00079 | 0
[9 empty] | 2453 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2453 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2453-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2453 |  |  | PF.2453 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00081 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-16 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00081 | 0
[9 empty] | 2454 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2454 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2454-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2454 |  |  | PF.2454 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00083 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-17 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00083 | 0
[9 empty] | 2455 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2455 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2455-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2455 |  |  | PF.2455 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00085 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-18 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00085 | 0
[9 empty] | 2456 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2456 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2456-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2456 |  |  | PF.2456 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00087 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-19 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00087 | 0
[9 empty] | 2457 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2457 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2457-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2457 |  |  | PF.2457 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00089 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-20 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00089 | 0
[9 empty] | 2458 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2458 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2458-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2458 |  |  | PF.2458 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00091 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-21 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00091 | 0
[9 empty] | 2459 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2459 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2459-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2459 |  |  | PF.2459 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00116 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-22 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00116 | 0
[9 empty] | 2460 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2460 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2460-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2460 |  |  | PF.2460 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00117 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-23 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00117 | 0
[9 empty] | 2461 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2461 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2461-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2461 |  |  | PF.2461 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00118 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-24 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00118 | 0
[9 empty] | 2462 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2462 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2462-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2462 |  |  | PF.2462 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00119 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-25 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00119 | 0
[9 empty] | 2463 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2463 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2463-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2463 |  |  | PF.2463 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00121 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-26 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00121 | 0
[9 empty] | 2464 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2464 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2464-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2464 |  |  | PF.2464 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00123 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT--1-ABOVE PODIUM-27 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 14 | 0 | 200019SKA-00123 | 0
[9 empty] | 2465 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2465 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2465-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2465 |  |  | PF.2465 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00023 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT-LEVEL 01-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 01 | 0 | 200019SKA-00023 | 0
[9 empty] | 2466 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2466 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2466-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2466 |  |  | PF.2466 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00122 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT-LEVEL 01-GRID - ORTHO-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 02 | 0 | 200019SKA-00122 | 0
[9 empty] | 2467 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2467 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2467-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2467 |  |  | PF.2467 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00120 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT-LEVEL 03-GRID - ORTHO-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00120 | 0
[9 empty] | 2468 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2468 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2468-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2468 |  |  | PF.2468 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00027 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT-LEVEL 18-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL 19 | 0 | 200019SKA-00027 | 0
[9 empty] | 2469 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2469 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2469-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2469 |  |  | PF.2469 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00124 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT-LEVEL B01-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\LEVEL B01 | 0 | 200019SKA-00124 | 0
[9 empty] | 2470 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2470 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2470-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2470 |  |  | PF.2470 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00068 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | LGT-ROOF LEVEL-ABOVE PODIUM-01 | False | CSG-E-LGT - Lighting for SIMMONS_ELEC\ROOF LEVEL | 0 | 200019SKA-00068 | 0
[9 empty] | 2471 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2471 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2471-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2471 |  |  | PF.2471 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00004 | SIMMONS_ELEC | 0 | 0.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 15 | 359 | 200019SKA-00004 | 0
[9 empty] | 2472 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2472 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2472-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2472 |  |  | PF.2472 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00017 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-04 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00017 | 0
[9 empty] | 2473 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2473 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2473-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2473 |  |  | PF.2473 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00026 | SIMMONS_ELEC | 0 | 0.00 | 30 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-05 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 19 | 6206 | 200019SKA-00026 | 0
[9 empty] | 2474 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2474 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2474-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2474 |  |  | PF.2474 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00030 | SIMMONS_ELEC | 0 | 0.00 | 4 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-06 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 18 | 467 | 200019SKA-00030 | 0
[9 empty] | 2475 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2475 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2475-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2475 |  |  | PF.2475 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00034 | SIMMONS_ELEC | 0 | 0.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-07 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 11 | 355 | 200019SKA-00034 | 0
[9 empty] | 2476 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2476 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2476-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2476 |  |  | PF.2476 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00039 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-08 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00039 | 0
[9 empty] | 2477 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2477 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2477-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2477 |  |  | PF.2477 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00043 | SIMMONS_ELEC | 0 | 0.00 | 15 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-09 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 08 | 1120 | 200019SKA-00043 | 0
[9 empty] | 2478 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2478 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2478-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2478 |  |  | PF.2478 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00044 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-10 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 08 | 0 | 200019SKA-00044 | 0
[9 empty] | 2479 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2479 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2479-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2479 |  |  | PF.2479 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00048 | SIMMONS_ELEC | 0 | 0.00 | 16 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-11 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 17 | 3387 | 200019SKA-00048 | 0
[9 empty] | 2480 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2480 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2480-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2480 |  |  | PF.2480 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00052 | SIMMONS_ELEC | 0 | 0.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-12 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 13 | 359 | 200019SKA-00052 | 0
[9 empty] | 2481 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2481 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2481-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2481 |  |  | PF.2481 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00056 | SIMMONS_ELEC | 0 | 0.00 | 7 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-13 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 09 | 377 | 200019SKA-00056 | 0
[9 empty] | 2482 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2482 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2482-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2482 |  |  | PF.2482 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00067 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-14 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\ROOF LEVEL | 0 | 200019SKA-00067 | 0
[9 empty] | 2483 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2483 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2483-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2483 |  |  | PF.2483 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00071 | SIMMONS_ELEC | 0 | 0.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-15 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 730 | 200019SKA-00071 | 0
[9 empty] | 2484 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2484 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2484-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2484 |  |  | PF.2484 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00074 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-16 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00074 | 0
[9 empty] | 2485 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2485 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2485-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2485 |  |  | PF.2485 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00078 | SIMMONS_ELEC | 0 | 0.00 | 10 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-17 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 457 | 200019SKA-00078 | 0
[9 empty] | 2486 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2486 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2486-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2486 |  |  | PF.2486 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00125 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-18 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00125 | 0
[9 empty] | 2487 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2487 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2487-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2487 |  |  | PF.2487 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00126 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-19 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00126 | 0
[9 empty] | 2488 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2488 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2488-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2488 |  |  | PF.2488 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00127 | SIMMONS_ELEC | 0 | 0.00 | 6 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100 |  | PB--ABOVE PODIUM-20 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 324 | 200019SKA-00127 | 0
[9 empty] | 2489 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2489 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2489-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2489 |  |  | PF.2489 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00128 | SIMMONS_ELEC | 0 | 0.00 | 22 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-21 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 1229 | 200019SKA-00128 | 0
[9 empty] | 2490 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2490 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2490-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2490 |  |  | PF.2490 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00129 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-22 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00129 | 0
[9 empty] | 2491 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2491 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2491-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2491 |  |  | PF.2491 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00130 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-23 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00130 | 0
[9 empty] | 2492 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2492 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2492-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2492 |  |  | PF.2492 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00131 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-24 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00131 | 0
[9 empty] | 2493 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2493 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2493-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2493 |  |  | PF.2493 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00132 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-25 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00132 | 0
[9 empty] | 2494 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2494 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2494-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2494 |  |  | PF.2494 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00136 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--ABOVE PODIUM-26 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00136 | 0
[9 empty] | 2495 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2495 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2495-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2495 |  |  | PF.2495 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00143 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Shipped to Jobsite | 100 |  | PB--ABOVE PODIUM-27 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 14 | 0 | 200019SKA-00143 | 0
[9 empty] | 2496 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2496 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2496-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2496 |  |  | PF.2496 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00144 | SIMMONS_ELEC | 0 | 0.00 | 3 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB--GRID - ORTHO-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL B01 | 342 | 200019SKA-00144 | 0
[9 empty] | 2497 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2497 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2497-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2497 |  |  | PF.2497 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00021 | SIMMONS_ELEC | 0 | 0.00 | 76 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-01 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 01 | 11220 | 200019SKA-00021 | 0
[9 empty] | 2498 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2498 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2498-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2498 |  |  | PF.2498 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00022 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-02 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 01 | 0 | 200019SKA-00022 | 0
[9 empty] | 2499 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2499 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2499-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2499 |  |  | PF.2499 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00061 | SIMMONS_ELEC | 0 | 0.00 | 52 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-03 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 05 | 6680 | 200019SKA-00061 | 0
[9 empty] | 2500 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2500 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2500-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2500 |  |  | PF.2500 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00064 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-04 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00064 | 0
[9 empty] | 2501 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2501 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2501-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2501 |  |  | PF.2501 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00133 | SIMMONS_ELEC | 0 | 0.00 | 48 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-05 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 5223 | 200019SKA-00133 | 0
[9 empty] | 2502 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2502 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2502-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2502 |  |  | PF.2502 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00134 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-06 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00134 | 0
[9 empty] | 2503 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2503 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2503-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2503 |  |  | PF.2503 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00135 | SIMMONS_ELEC | 0 | 0.00 | 38 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-07 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 3868 | 200019SKA-00135 | 0
[9 empty] | 2504 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2504 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2504-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2504 |  |  | PF.2504 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00137 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-08 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00137 | 0
[9 empty] | 2505 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2505 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2505-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2505 |  |  | PF.2505 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00138 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-09 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00138 | 0
[9 empty] | 2506 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2506 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2506-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2506 |  |  | PF.2506 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00139 | SIMMONS_ELEC | 0 | 0.00 | 22 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10 |  | PB-LEVEL 01-ABOVE PODIUM-10 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 02 | 1911 | 200019SKA-00139 | 0
[9 empty] | 2507 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2507 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2507-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2507 |  |  | PF.2507 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00140 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-11 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00140 | 0
[9 empty] | 2508 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2508 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2508-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2508 |  |  | PF.2508 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00141 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-12 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00141 | 0
[9 empty] | 2509 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2509 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2509-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2509 |  |  | PF.2509 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00142 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | PB-LEVEL 01-ABOVE PODIUM-13 | False | CSG-E-CND - Overhead Conduit for SIMMONS_ELEC\LEVEL 02 | 0 | 200019SKA-00142 | 0
[9 empty] | 2510 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2510 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2510-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2510 |  |  | PF.2510 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00115 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 01-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL B01 | 0 | 200019SKA-00115 | 0
[9 empty] | 2511 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2511 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2511-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2511 |  |  | PF.2511 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00020 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 01-GRID - ORTHO-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 01 | 0 | 200019SKA-00020 | 0
[9 empty] | 2512 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2512 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2512-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2512 |  |  | PF.2512 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00060 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 02-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00060 | 0
[9 empty] | 2513 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2513 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2513-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2513 |  |  | PF.2513 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00062 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 02-ABOVE PODIUM-02 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 05 | 0 | 200019SKA-00062 | 0
[9 empty] | 2514 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2514 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2514-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2514 |  |  | PF.2514 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00112 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 02-ABOVE PODIUM-03 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 04 | 0 | 200019SKA-00112 | 0
[9 empty] | 2515 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2515 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2515-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2515 |  |  | PF.2515 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00113 | SIMMONS_ELEC | 0 | 0.00 | 1 | 200019SKA |  | SIMMONS UNV |  | Design Stage | 10 |  | RACK PACKAGE-LEVEL 02-ABOVE PODIUM-04 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 02 | 76 | 200019SKA-00113 | 0
[9 empty] | 2516 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2516 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2516-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2516 |  |  | PF.2516 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00111 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 03-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 03 | 0 | 200019SKA-00111 | 0
[9 empty] | 2517 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2517 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2517-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2517 |  |  | PF.2517 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00007 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-02 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00007 | 0
[9 empty] | 2518 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2518 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2518-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2518 |  |  | PF.2518 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00012 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-03 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 15 | 0 | 200019SKA-00012 | 0
[9 empty] | 2519 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2519 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2519-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2519 |  |  | PF.2519 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00016 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-04 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 12 | 0 | 200019SKA-00016 | 0
[9 empty] | 2520 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2520 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2520-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2520 |  |  | PF.2520 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00029 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-05 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 18 | 0 | 200019SKA-00029 | 0
[9 empty] | 2521 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2521 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2521-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2521 |  |  | PF.2521 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00033 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-06 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00033 | 0
[9 empty] | 2522 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2522 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2522-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2522 |  |  | PF.2522 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00038 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-07 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 11 | 0 | 200019SKA-00038 | 0
[9 empty] | 2523 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2523 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2523-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2523 |  |  | PF.2523 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00042 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-08 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 08 | 0 | 200019SKA-00042 | 0
[9 empty] | 2524 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2524 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2524-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2524 |  |  | PF.2524 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00047 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-09 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 17 | 0 | 200019SKA-00047 | 0
[9 empty] | 2525 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2525 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2525-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2525 |  |  | PF.2525 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00051 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-10 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 13 | 0 | 200019SKA-00051 | 0
[9 empty] | 2526 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2526 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2526-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2526 |  |  | PF.2526 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00070 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-11 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 16 | 0 | 200019SKA-00070 | 0
[9 empty] | 2527 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2527 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2527-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2527 |  |  | PF.2527 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00077 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-12 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00077 | 0
[9 empty] | 2528 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2528 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2528-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2528 |  |  | PF.2528 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00108 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-13 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 10 | 0 | 200019SKA-00108 | 0
[9 empty] | 2529 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2529 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2529-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2529 |  |  | PF.2529 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00109 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-14 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 07 | 0 | 200019SKA-00109 | 0
[9 empty] | 2530 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2530 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2530-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2530 |  |  | PF.2530 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00110 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-15 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 06 | 0 | 200019SKA-00110 | 0
[9 empty] | 2531 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2531 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2531-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2531 |  |  | PF.2531 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00114 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 06-ABOVE PODIUM-16 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 14 | 0 | 200019SKA-00114 | 0
[9 empty] | 2532 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2532 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2532-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2532 |  |  | PF.2532 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00055 | SIMMONS_ELEC | 0 | 0.00 | 0 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 09-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 09 | 0 | 200019SKA-00055 | 0
[9 empty] | 2533 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2533 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2533-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2533 |  |  | PF.2533 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 200019SKA¦200019SKA-00025 | SIMMONS_ELEC | 0 | 0.00 | 1 | 200019SKA |  | SIMMONS UNV |  | Packages (FAB) Confirmed | 50 |  | RACK PACKAGE-LEVEL 19-ABOVE PODIUM-01 | False | CSG-E-DE - Distribution Equipment for SIMMONS_ELEC\LEVEL 19 | 3 | 200019SKA-00025 | 0
[9 empty] | 2534 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2534 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2534-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2534 |  |  | PF.2534 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦FAB-145 | PRINCIPIO - ELEC - SMC - 2023 | 1024 | 9.75 | 0 | 180035PGG | 9/18/2025 | P&G Gillette |  | Design Stage | 10 | VDC | -NORTH MEZZ CABLE TRAY HANGERS-SUP-01 | False |  | 1024 | FAB-145 | 0
[9 empty] | 2535 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2535 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2535-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2535 |  |  | PF.2535 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00001-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 8/30/2024 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00001-CND-RIGID NIPPLES | False |  | 0 | 180035PGG-FAB-00001-25 | 0
[9 empty] | 2536 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2536 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2536-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2536 |  |  | PF.2536 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00002-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 9/16/2024 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00002-SUP-1 5-8- strut cut - 1--6- | False |  | 0 | 180035PGG-FAB-00002-25 | 0
[9 empty] | 2537 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2537 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2537-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2537 |  |  | PF.2537 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00003-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 10/3/2024 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00003-CND-4- grc nipples | False |  | 0 | 180035PGG-FAB-00003-25 | 0
[9 empty] | 2538 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2538 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2538-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2538 |  |  | PF.2538 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00004-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 10/18/2024 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00004-CND-1-4-grc- 4-5- grc nipples | False |  | 0 | 180035PGG-FAB-00004-25 | 0
[9 empty] | 2539 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2539 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2539-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2539 |  |  | PF.2539 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00005-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 2.00 | 0 | 180035PGG | 11/20/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00005-IW-FA IN WALL DEVICES | False |  | 0 | 180035PGG-FAB-00005-25 | 0
[9 empty] | 2540 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2540 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2540-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2540 |  |  | PF.2540 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00006-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 11/3/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00006-IW-FA IN WALL DEVICES | False |  | 0 | 180035PGG-FAB-00006-25 | 0
[9 empty] | 2541 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2541 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2541-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2541 |  |  | PF.2541 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00008-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 11/7/2025 | P&G Gillette |  | Issued for Fabrication | 100 |  | FAB-00008-IW-ELECTRICAL ROUGH-TEL COM DEVICE | False |  | 0 | 180035PGG-FAB-00008-25 | 0
[9 empty] | 2542 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2542 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2542-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2542 |  |  | PF.2542 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00009-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 2.00 | 0 | 180035PGG | 11/20/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00009-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00009-25 | 0
[9 empty] | 2543 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2543 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2543-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2543 |  |  | PF.2543 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00010-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 12/28/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00010-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00010-25 | 0
[9 empty] | 2544 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2544 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2544-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2544 |  |  | PF.2544 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00011-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/3/2025 | P&G Gillette |  | Issued for Fabrication | 100 |  | FAB-00011-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00011-25 | 0
[9 empty] | 2545 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2545 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2545-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2545 |  |  | PF.2545 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00013-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 8/4/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00013-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00013-25 | 0
[9 empty] | 2546 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2546 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2546-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2546 |  |  | PF.2546 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00014-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 8/4/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00014-IW-IN WALL SECURITY DEVICES | False |  | 0 | 180035PGG-FAB-00014-25 | 0
[9 empty] | 2547 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2547 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2547-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2547 |  |  | PF.2547 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00015-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 11/18/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00015-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00015-25 | 0
[9 empty] | 2548 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2548 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2548-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2548 |  |  | PF.2548 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00016-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 12/25/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00016-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00016-25 | 0
[9 empty] | 2549 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2549 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2549-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2549 |  |  | PF.2549 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00017-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 10/7/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00017-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00017-25 | 0
[9 empty] | 2550 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2550 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2550-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2550 |  |  | PF.2550 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00018-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 10/29/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00018-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00018-25 | 0
[9 empty] | 2551 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2551 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2551-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2551 |  |  | PF.2551 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00019-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 11/20/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00019-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00019-25 | 0
[9 empty] | 2552 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2552 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2552-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2552 |  |  | PF.2552 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00020-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 0 | 180035PGG | 11/18/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00020-IW-IN WALL FA DEVICES | False |  | 0 | 180035PGG-FAB-00020-25 | 0
[9 empty] | 2553 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2553 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2553-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2553 |  |  | PF.2553 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00021-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/31/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00021-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00021-25 | 0
[9 empty] | 2554 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2554 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2554-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2554 |  |  | PF.2554 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00022-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.20 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00022-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00022-25 | 0
[9 empty] | 2555 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2555 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2555-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2555 |  |  | PF.2555 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00023-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 36.44 | 0 | 180035PGG | 9/1/2025 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00023-IW-MAIN LEVEL IN WALL ROUGH PLAN SECTION B | False |  | 0 | 180035PGG-FAB-00023-25 | 0
[9 empty] | 2556 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2556 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2556-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2556 |  |  | PF.2556 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00024-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 2/6/2026 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00024-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00024-25 | 0
[9 empty] | 2557 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2557 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2557-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2557 |  |  | PF.2557 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00025-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 11/17/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00025-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00025-25 | 0
[9 empty] | 2558 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2558 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2558-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2558 |  |  | PF.2558 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00026-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00026-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00026-25 | 0
[9 empty] | 2559 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2559 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2559-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2559 |  |  | PF.2559 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00027-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 1/9/2026 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00027-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00027-25 | 0
[9 empty] | 2560 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2560 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2560-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2560 |  |  | PF.2560 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00028-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.20 | 0 | 180035PGG | 2/2/2026 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00028-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00028-25 | 0
[9 empty] | 2561 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2561 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2561-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2561 |  |  | PF.2561 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00030-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.20 | 0 | 180035PGG | 1/14/2026 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00030-LGT-INSTALL WHIPS ON FIXTURES | False |  | 0 | 180035PGG-FAB-00030-25 | 0
[9 empty] | 2562 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2562 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2562-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2562 |  |  | PF.2562 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00031-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 9/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00031-CND-INSTALL OH ELECT PIPING | False |  | 0 | 180035PGG-FAB-00031-25 | 0
[9 empty] | 2563 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2563 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2563-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2563 |  |  | PF.2563 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00032-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 27.33 | 0 | 180035PGG | 11/14/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00032-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00032-25 | 0
[9 empty] | 2564 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2564 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2564-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2564 |  |  | PF.2564 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00033-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 12/8/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00033-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00033-25 | 0
[9 empty] | 2565 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2565 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2565-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2565 |  |  | PF.2565 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00034-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 10/3/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00034-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00034-25 | 0
[9 empty] | 2566 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2566 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2566-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2566 |  |  | PF.2566 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00035-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 27.33 | 0 | 180035PGG | 10/27/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00035-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00035-25 | 0
[9 empty] | 2567 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2567 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2567-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2567 |  |  | PF.2567 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00036-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 11/18/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00036-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00036-25 | 0
[9 empty] | 2568 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2568 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2568-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2568 |  |  | PF.2568 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00037-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 8/4/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00037-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00037-25 | 0
[9 empty] | 2569 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2569 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2569-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2569 |  |  | PF.2569 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00038-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.47 | 0 | 180035PGG | 8/4/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00038-IW-INSTALL IN WALL ROUGH | False |  | 0 | 180035PGG-FAB-00038-25 | 0
[9 empty] | 2570 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2570 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2570-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2570 |  |  | PF.2570 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00039-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 60.00 | 0 | 180035PGG | 11/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00039-DE-VFD ASSEMBLIES | False |  | 0 | 180035PGG-FAB-00039-25 | 0
[9 empty] | 2571 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2571 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2571-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2571 |  |  | PF.2571 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00040-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 9/11/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00040-SUP-STAIR 1- STAIR 3 | False |  | 0 | 180035PGG-FAB-00040-25 | 0
[9 empty] | 2572 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2572 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2572-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2572 |  |  | PF.2572 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00041-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 60.00 | 0 | 180035PGG | 6/26/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00041-DE-ROOF DISCONNECTS | False |  | 0 | 180035PGG-FAB-00041-25 | 0
[9 empty] | 2573 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2573 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2573-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2573 |  |  | PF.2573 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00042-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.00 | 31 | 180035PGG | 8/1/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00042-CND-SPOOL - A - SECTION 6 | False |  | 2564 | 180035PGG-FAB-00042-25 | 0
[9 empty] | 2574 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2574 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2574-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2574 |  |  | PF.2574 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00043-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 6 | 180035PGG | 8/1/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00043-CND-SPOOL - B - SECTION 6 | False |  | 277 | 180035PGG-FAB-00043-25 | 0
[9 empty] | 2575 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2575 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2575-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2575 |  |  | PF.2575 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00044-25 | PRINCIPIO - ELEC - SMC - 2023 | 1 | 1.00 | 23 | 180035PGG | 7/7/2025 | P&G Gillette |  | Received on Jobsite | 15.7 |  | FAB-00044-CND-SPOOL - C - SECTION 1 | False |  | 1238 | 180035PGG-FAB-00044-25 | 51
[9 empty] | 2576 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2576 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2576-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2576 |  |  | PF.2576 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00045-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 7 | 180035PGG | 7/25/2025 | P&G Gillette |  | Issued for Fabrication | 14.5 | Shop Labor-Station 9 | FAB-00045-CND-SPOOL - F - SECTION 1 | False |  | 417 | 180035PGG-FAB-00045-25 | 55
[9 empty] | 2577 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2577 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2577-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2577 |  |  | PF.2577 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00046-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 8 | 180035PGG | 6/30/2025 | P&G Gillette |  | Issued for Fabrication | 17.9 | Shop Labor-Station 9 | FAB-00046-CND-SPOOL - G - SECTION 1 | False |  | 290 | 180035PGG-FAB-00046-25 | 67
[9 empty] | 2578 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2578 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2578-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2578 |  |  | PF.2578 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00047-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 10 | 180035PGG | 6/30/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00047-CND-SPOOL - H - SECTION 1 | False |  | 456 | 180035PGG-FAB-00047-25 | 0
[9 empty] | 2579 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2579 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2579-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2579 |  |  | PF.2579 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00048-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 2.00 | 27 | 180035PGG | 7/11/2025 | P&G Gillette |  | Received on Jobsite | 0 |  | FAB-00048-CND-SPOOL - I - SECTION 1 | False |  | 1254 | 180035PGG-FAB-00048-25 | 47
[9 empty] | 2580 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2580 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2580-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2580 |  |  | PF.2580 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00049-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/1/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00049-CND-SPARE LINE ITEM | False |  | 0 | 180035PGG-FAB-00049-25 | 0
[9 empty] | 2581 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2581 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2581-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2581 |  |  | PF.2581 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00050-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 8 | 180035PGG | 8/18/2025 | P&G Gillette |  | Issued for Fabrication | 0 | Shop Labor-Station 9 | FAB-00050-CND-SPOOL - H - SECTION 2 | False |  | 360 | 180035PGG-FAB-00050-25 | 11
[9 empty] | 2582 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2582 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2582-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2582 |  |  | PF.2582 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00051-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 56 | 180035PGG | 7/25/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00051-CND-PIPE BENDS -LARGE- POWER | False |  | 157 | 180035PGG-FAB-00051-25 | 0
[9 empty] | 2583 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2583 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2583-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2583 |  |  | PF.2583 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00052-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 41.00 | 12 | 180035PGG | 6/24/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00052-SUP-SECTION 1 MEZZ HANGERS -59-65-5 - A-5-A-9- | False |  | 4834 | 180035PGG-FAB-00052-25 | 0
[9 empty] | 2584 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2584 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2584-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2584 |  |  | PF.2584 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00053-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 22.75 | 7 | 180035PGG | 7/7/2025 | P&G Gillette |  | Issued for Fabrication | 0 |  | FAB-00053-SUP-MAIN LEVEL HANGERS-SECTION 6- | False |  | 2384 | 180035PGG-FAB-00053-25 | 280
[9 empty] | 2585 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2585 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2585-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2585 |  |  | PF.2585 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00054-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 8 | 180035PGG | 8/18/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00054-CND-SPOOL - I - SECTION 2 | False |  | 412 | 180035PGG-FAB-00054-25 | 0
[9 empty] | 2586 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2586 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2586-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2586 |  |  | PF.2586 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00055-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.00 | 0 | 180035PGG | 9/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00055-IW-IDF WIREMOLD | False |  | 0 | 180035PGG-FAB-00055-25 | 0
[9 empty] | 2587 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2587 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2587-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2587 |  |  | PF.2587 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00056-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.00 | 0 | 180035PGG | 9/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00056-IW-IDF WIREMOLD | False |  | 0 | 180035PGG-FAB-00056-25 | 0
[9 empty] | 2588 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2588 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2588-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2588 |  |  | PF.2588 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00057-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 24.00 | 0 | 180035PGG | 7/31/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00057-DE-75 KVA PDU- | False |  | 0 | 180035PGG-FAB-00057-25 | 0
[9 empty] | 2589 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2589 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2589-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2589 |  |  | PF.2589 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00059-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 5 | 180035PGG | 8/11/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00059-CND-SPOOL - J - SECTION 5 | False |  | 203 | 180035PGG-FAB-00059-25 | 0
[9 empty] | 2590 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2590 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2590-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2590 |  |  | PF.2590 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00060-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 10 | 180035PGG | 7/14/2025 | P&G Gillette |  | Received on Jobsite | 0 |  | FAB-00060-CND-SPOOL - D - SECTION 3 | False |  | 389 | 180035PGG-FAB-00060-25 | 1
[9 empty] | 2591 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2591 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2591-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2591 |  |  | PF.2591 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00061-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 13 | 180035PGG | 7/18/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00061-CND-SPOOL - E - SECTION 3 | False |  | 567 | 180035PGG-FAB-00061-25 | 0
[9 empty] | 2592 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2592 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2592-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2592 |  |  | PF.2592 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00062-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 6 | 180035PGG | 8/25/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00062-CND-SPOOL - H - SECTION 4 -DELIVERY 1- j | False |  | 231 | 180035PGG-FAB-00062-25 | 0
[9 empty] | 2593 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2593 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2593-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2593 |  |  | PF.2593 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00063-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 5 | 180035PGG | 8/25/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00063-CND-SPOOL - I - SECTION 4 -DELIVERY 1- | False |  | 204 | 180035PGG-FAB-00063-25 | 0
[9 empty] | 2594 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2594 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2594-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2594 |  |  | PF.2594 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00064-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.50 | 23 | 180035PGG | 8/18/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00064-CND-SPOOL - C - SECTION 5 | False |  | 1453 | 180035PGG-FAB-00064-25 | 0
[9 empty] | 2595 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2595 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2595-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2595 |  |  | PF.2595 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00065-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 4 | 180035PGG | 8/11/2025 | P&G Gillette |  | Received on Jobsite | 0 |  | FAB-00065-CND-SPOOL - E - SECTION 5 | False |  | 111 | 180035PGG-FAB-00065-25 | 6
[9 empty] | 2596 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2596 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2596-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2596 |  |  | PF.2596 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00066-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00066-CND-SPOOL - A - SECTION 6 | False |  | 0 | 180035PGG-FAB-00066-25 | 0
[9 empty] | 2597 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2597 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2597-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2597 |  |  | PF.2597 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00067-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00067-CND-SPOOL - B - SECTION 6 | False |  | 0 | 180035PGG-FAB-00067-25 | 0
[9 empty] | 2598 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2598 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2598-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2598 |  |  | PF.2598 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00068-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00068-DE-TEMP PDU 75KVA | False |  | 0 | 180035PGG-FAB-00068-25 | 0
[9 empty] | 2599 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2599 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2599-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2599 |  |  | PF.2599 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00069-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG | 9/8/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00069-DE-TEMP PDU 75KVA | False |  | 0 | 180035PGG-FAB-00069-25 | 0
[9 empty] | 2600 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2600 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2600-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2600 |  |  | PF.2600 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00070-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG | 9/8/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00070-DE-TEMP PDU 75KVA | False |  | 0 | 180035PGG-FAB-00070-25 | 0
[9 empty] | 2601 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2601 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2601-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2601 |  |  | PF.2601 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00071-25 | PRINCIPIO - ELEC - SMC - 2023 | 5 | 9.00 | 0 | 180035PGG | 10/14/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00071-DE-VFD BUILD EF 8-9-14A-14B-15 | False | NOT SHOWN | 5 | 180035PGG-FAB-00071-25 | 0
[9 empty] | 2602 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2602 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2602-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2602 |  |  | PF.2602 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00072-25 | PRINCIPIO - ELEC - SMC - 2023 | 2 | 4.50 | 0 | 180035PGG | 10/14/2025 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00072-DE-VFD BUILD EF 3A-3B | False | NOT SHOWN | 2 | 180035PGG-FAB-00072-25 | 0
[9 empty] | 2603 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2603 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2603-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2603 |  |  | PF.2603 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00073-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/14/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 |  | FAB-00073-DE-VFD BUILD EF 5-6-18 | False | NOT SHOWN | 0 | 180035PGG-FAB-00073-25 | 0
[9 empty] | 2604 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2604 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2604-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2604 |  |  | PF.2604 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00074-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.50 | 0 | 180035PGG | 10/14/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 |  | FAB-00074-DE-VFD BUILD EF 12-17 | False |  | 0 | 180035PGG-FAB-00074-25 | 0
[9 empty] | 2605 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2605 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2605-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2605 |  |  | PF.2605 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00075-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 3/24/2025 | P&G Gillette |  | Received on Jobsite | 10 | Field Labor | FAB-00075-CND-4- RIGID NIPPLES | False | NOT SHOWN | 0 | 180035PGG-FAB-00075-25 | 0
[9 empty] | 2606 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2606 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2606-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2606 |  |  | PF.2606 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00076-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 4/9/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00076-CND-POLE BASE PIPE BENDS | False |  | 0 | 180035PGG-FAB-00076-25 | 0
[9 empty] | 2607 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2607 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2607-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2607 |  |  | PF.2607 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦FAB-00077_180035PGG | PRINCIPIO - ELEC - SMC - 2023 | 3 | 0.00 | 0 | 180035PGG |  | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00077--DE-VFD-CHP-8 | False | VFD-CHP-8 | 3 | FAB-00077_180035PGG | 0
[9 empty] | 2608 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2608 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2608-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2608 |  |  | PF.2608 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00077-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 9.00 | 0 | 180035PGG | 11/24/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 |  | FAB-00077-DE-VFD BUILD CHP-7-8 | False |  | 0 | 180035PGG-FAB-00077-25 | 0
[9 empty] | 2609 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2609 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2609-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2609 |  |  | PF.2609 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00078-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 9.00 | 0 | 180035PGG | 11/24/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00078-DE-VFD BUILD CHP-1-2-4-5 | False |  | 0 | 180035PGG-FAB-00078-25 | 0
[9 empty] | 2610 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2610 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2610-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2610 |  |  | PF.2610 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00079-25 | PRINCIPIO - ELEC - SMC - 2023 | 9 | 15.00 | 1 | 180035PGG | 12/10/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00079-DE-BDA PANEL ASSEMBLY - MEZZANINE | False |  | 11 | 180035PGG-FAB-00079-25 | 0
[9 empty] | 2611 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2611 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2611-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2611 |  |  | PF.2611 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00080-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00080-CND-WIREMOLD ASSEMBLIES - AHU SHUT DOWN | False |  | 0 | 180035PGG-FAB-00080-25 | 0
[9 empty] | 2612 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2612 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2612-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2612 |  |  | PF.2612 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00081-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 72.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00081-IW-WIREMOLD ASSEMBLIES - RELAYS | False |  | 0 | 180035PGG-FAB-00081-25 | 0
[9 empty] | 2613 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2613 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2613-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2613 |  |  | PF.2613 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00082-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 12.00 | 0 | 180035PGG | 9/1/2025 | P&G Gillette |  | Hold | 0 |  | FAB-00082-DE-LEVEL 1 PUMP HOUSE ASSEMBLY | False |  | 0 | 180035PGG-FAB-00082-25 | 0
[9 empty] | 2614 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2614 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2614-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2614 |  |  | PF.2614 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00083-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 30.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 |  | FAB-00083-DE-PANEL ASSEMBLIES - LEVEL 1 MAIN MANUFACTURING | False | NOT SHOWN | 0 | 180035PGG-FAB-00083-25 | 0
[9 empty] | 2615 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2615 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2615-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2615 |  |  | PF.2615 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00084-25 | PRINCIPIO - ELEC - SMC - 2023 | 27 | 10.00 | 1 | 180035PGG | 12/29/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00084-DE-PANEL ASSEMBLIES - LEVEL MEZZANINE | False |  | 29 | 180035PGG-FAB-00084-25 | 0
[9 empty] | 2616 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2616 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2616-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2616 |  |  | PF.2616 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00086-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 15.00 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00086-DE-POWER SUPPLY ASSEMBLY - LEVEL MEZZANINE MANUFACTURING | False |  | 0 | 180035PGG-FAB-00086-25 | 0
[9 empty] | 2617 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2617 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2617-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2617 |  |  | PF.2617 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00087-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 15.00 | 0 | 180035PGG | 5/14/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00087-DE-POWER SUPPLY ASSEMBLY - LEVEL 1 MAIN WAREHOUSE MV SWITCHGEAR ENCLOSURE | False |  | 0 | 180035PGG-FAB-00087-25 | 0
[9 empty] | 2618 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2618 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2618-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2618 |  |  | PF.2618 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00088-25 | PRINCIPIO - ELEC - SMC - 2023 | 11 | 15.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 |  | FAB-00088-DE-POWER SUPPLY ASSEMBLY - LEVEL 1 MAIN MANUFACTURING | False |  | 11 | 180035PGG-FAB-00088-25 | 0
[9 empty] | 2619 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2619 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2619-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2619 |  |  | PF.2619 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00089-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Issued for Fabrication | 100 |  | FAB-00089-DE-ELEVATOR RECALL ASSEMBLY - LEVEL 1 | False | NOT SHOWN | 0 | 180035PGG-FAB-00089-25 | 0
[9 empty] | 2620 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2620 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2620-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2620 |  |  | PF.2620 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00090-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 9.00 | 0 | 180035PGG | 5/27/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00090-DE-SPIDER BOXES | False |  | 0 | 180035PGG-FAB-00090-25 | 0
[9 empty] | 2621 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2621 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2621-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2621 |  |  | PF.2621 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00091-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00091-DE-Power Supply MAIN WAREHOUSE Janitor Closet PS2 | False |  | 0 | 180035PGG-FAB-00091-25 | 0
[9 empty] | 2622 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2622 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2622-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2622 |  |  | PF.2622 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00092-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 100.00 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00092-IW-DUCT SMOKE BUILDS | False |  | 0 | 180035PGG-FAB-00092-25 | 0
[9 empty] | 2623 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2623 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2623-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2623 |  |  | PF.2623 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00093-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 30.00 | 0 | 180035PGG | 5/30/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00093-DE-FIRE ALARM FIRE COMMAND CENTER | False | NOT SHOWN | 0 | 180035PGG-FAB-00093-25 | 0
[9 empty] | 2624 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2624 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2624-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2624 |  |  | PF.2624 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00094-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 19.83 | 0 | 180035PGG | 7/7/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00094-IW-JB WITH TERM BLOCK | False |  | 0 | 180035PGG-FAB-00094-25 | 0
[9 empty] | 2625 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2625 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2625-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2625 |  |  | PF.2625 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00095-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.61 | 0 | 180035PGG |  | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00095-PB-JB WITH TERM BLOCK | False |  | 0 | 180035PGG-FAB-00095-25 | 0
[9 empty] | 2626 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2626 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2626-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2626 |  |  | PF.2626 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00096-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.83 | 0 | 180035PGG | 6/6/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00096-PB-CUTOUT BOTTOM OF STAINLESS NEXWCOM CAN | False |  | 0 | 180035PGG-FAB-00096-25 | 0
[9 empty] | 2627 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2627 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2627-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2627 |  |  | PF.2627 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00097-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.50 | 0 | 180035PGG | 12/29/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00097-LGT-FA SWIVELS | False |  | 0 | 180035PGG-FAB-00097-25 | 0
[9 empty] | 2628 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2628 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2628-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2628 |  |  | PF.2628 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00098-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 2.70 | 0 | 180035PGG | 6/17/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00098-IW-exterior wall in wall rough | False |  | 0 | 180035PGG-FAB-00098-25 | 0
[9 empty] | 2629 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2629 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2629-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2629 |  |  | PF.2629 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00099-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 0 | 180035PGG | 7/28/2025 | P&G Gillette |  | FAB CANCELLED | 0 |  | FAB-00099-DE-STICK BUILT PANELS | False |  | 0 | 180035PGG-FAB-00099-25 | 0
[9 empty] | 2630 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2630 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2630-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2630 |  |  | PF.2630 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00100-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 0 | 180035PGG | 7/4/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00100-DE-OPEN CLEAN-KO SEAL 1200AMP 120-208V TEMPS GEAR | False |  | 0 | 180035PGG-FAB-00100-25 | 0
[9 empty] | 2631 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2631 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2631-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2631 |  |  | PF.2631 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00101-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 4.75 | 2 | 180035PGG | 8/11/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00101-SUP-SLAB ON GRADE SECTION 2 HANGERS | False |  | 570 | 180035PGG-FAB-00101-25 | 0
[9 empty] | 2632 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2632 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2632-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2632 |  |  | PF.2632 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00102-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 15.00 | 6 | 180035PGG | 8/4/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00102-SUP-MEZZANINE HANGERS SECTION 5 HANGERS | False |  | 1653 | 180035PGG-FAB-00102-25 | 0
[9 empty] | 2633 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2633 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2633-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2633 |  |  | PF.2633 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00103-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 10.00 | 3 | 180035PGG | 8/11/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 100 |  | FAB-00103-SUP-SLAB ON GRADE SECTION 4 HANGERS | False |  | 1196 | 180035PGG-FAB-00103-25 | 243
[9 empty] | 2634 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2634 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2634-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2634 |  |  | PF.2634 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00104-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.00 | 1 | 180035PGG | 9/18/2025 | P&G Gillette |  | Shipped to Jobsite | 100 | Shop Labor-Station 9 | FAB-00104-SUP-SLAB ON GRADE SECTION 8 HANGERS | False |  | 600 | 180035PGG-FAB-00104-25 | 0
[9 empty] | 2635 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2635 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2635-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2635 |  |  | PF.2635 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00105-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 1 | 180035PGG | 9/18/2025 | P&G Gillette |  | Shipped to Jobsite | 0 | Shop Labor-Station 9 | FAB-00105-SUP-SLAB ON GRADE SECTION 7 HANGERS | False |  | 844 | 180035PGG-FAB-00105-25 | 96
[9 empty] | 2636 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2636 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2636-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2636 |  |  | PF.2636 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00106-25 | PRINCIPIO - ELEC - SMC - 2023 | 2 | 1.50 | 4 | 180035PGG | 7/28/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00106-DE-SINGLE TUB BUILDS BATCH 1 | False |  | 142 | 180035PGG-FAB-00106-25 | 0
[9 empty] | 2637 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2637 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2637-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2637 |  |  | PF.2637 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00107-25 | PRINCIPIO - ELEC - SMC - 2023 | 68 | 25.95 | 10 | 180035PGG | 7/28/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00107-DE-DOUBLE TUB BUILDS BATCH 1 | False |  | 418 | 180035PGG-FAB-00107-25 | 0
[9 empty] | 2638 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2638 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2638-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2638 |  |  | PF.2638 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00108-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 8.00 | 3 | 180035PGG | 8/18/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00108-DE-SINGLE TUB BUILDS BATCH 2 | False |  | 105 | 180035PGG-FAB-00108-25 | 0
[9 empty] | 2639 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2639 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2639-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2639 |  |  | PF.2639 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00109-25 | PRINCIPIO - ELEC - SMC - 2023 | 1 | 21.62 | 10 | 180035PGG | 8/18/2025 | P&G Gillette |  | Design Stage | 10 |  | FAB-00109-DE-DOUBLE TUB BUILDS BATCH 2 | False |  | 351 | 180035PGG-FAB-00109-25 | 0
[9 empty] | 2640 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2640 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2640-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2640 |  |  | PF.2640 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00110-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 0 | 180035PGG | 9/11/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 |  | FAB-00110-DE-SINGLE TUB BUILDS BATCH 3 | False |  | 0 | 180035PGG-FAB-00110-25 | 0
[9 empty] | 2641 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2641 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2641-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2641 |  |  | PF.2641 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00111-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 14.55 | 10 | 180035PGG | 9/11/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 |  | FAB-00111-DE-DOUBLE TUB BUILDS BATCH 3 | False |  | 350 | 180035PGG-FAB-00111-25 | 0
[9 empty] | 2642 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2642 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2642-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2642 |  |  | PF.2642 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00112-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 3.60 | 0 | 180035PGG | 8/5/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00112-PB-12 x 12 x 48- HR TROUGHS | False |  | 0 | 180035PGG-FAB-00112-25 | 0
[9 empty] | 2643 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2643 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2643-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2643 |  |  | PF.2643 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00113-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 23.84 | 0 | 180035PGG | 8/5/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00113-PB-MC SATELLITE JUNCTION BOXES | False |  | 0 | 180035PGG-FAB-00113-25 | 0
[9 empty] | 2644 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2644 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2644-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2644 |  |  | PF.2644 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00114-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 12.00 | 0 | 180035PGG | 8/11/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00114-DE-TEMP POWER RACKS | False |  | 0 | 180035PGG-FAB-00114-25 | 0
[9 empty] | 2645 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2645 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2645-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2645 |  |  | PF.2645 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00115-25 | PRINCIPIO - ELEC - SMC - 2023 | 31 | 1.50 | 0 | 180035PGG | 8/8/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00115-DE-BDA MAST | False |  | 31 | 180035PGG-FAB-00115-25 | 0
[9 empty] | 2646 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2646 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2646-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2646 |  |  | PF.2646 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00116-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 6 | 180035PGG | 7/31/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00116-CND-SPOOL - C - SECTION 6 | False |  | 252 | 180035PGG-FAB-00116-25 | 0
[9 empty] | 2647 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2647 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2647-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2647 |  |  | PF.2647 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00117-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 13 | 180035PGG | 7/30/2025 | P&G Gillette |  | Received on Jobsite | 10 | Field Management | FAB-00117-CND-SECTION 6 PIPE BENDS | False |  | 50 | 180035PGG-FAB-00117-25 | 0
[9 empty] | 2648 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2648 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2648-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2648 |  |  | PF.2648 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00118-25 | PRINCIPIO - ELEC - SMC - 2023 | 10 | 6.00 | 0 | 180035PGG | 10/1/2025 | P&G Gillette |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 |  | FAB-00118-DE-VFD STICK BUILD HWP 1- HWP 2 | False |  | 10 | 180035PGG-FAB-00118-25 | 0
[9 empty] | 2649 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2649 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2649-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2649 |  |  | PF.2649 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00119-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/1/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00119-DE-VFD STICK BUILD HWP 4- HWP 5 | False | NOT SHOWN | 0 | 180035PGG-FAB-00119-25 | 0
[9 empty] | 2650 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2650 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2650-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2650 |  |  | PF.2650 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00120-25 | PRINCIPIO - ELEC - SMC - 2023 | 10 | 6.00 | 0 | 180035PGG | 10/3/2025 | P&G Gillette |  | Issued for Fabrication | 100 |  | FAB-00120-DE-VFD STICK BUILD PHCP -1- PHCP -2 | False | NOT SHOWN | 10 | 180035PGG-FAB-00120-25 | 0
[9 empty] | 2651 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2651 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2651-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2651 |  |  | PF.2651 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00121-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/3/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00121-DE-VFD STICK BUILD PHCP -3A- PHCP -3B | False |  | 0 | 180035PGG-FAB-00121-25 | 0
[9 empty] | 2652 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2652 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2652-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2652 |  |  | PF.2652 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00122-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/6/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00122-DE-VFD STICK BUILD PHCP -4A- PHCP -4B | False |  | 0 | 180035PGG-FAB-00122-25 | 0
[9 empty] | 2653 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2653 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2653-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2653 |  |  | PF.2653 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00123-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 6.00 | 0 | 180035PGG | 10/6/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00123-DE-VFD STICK BUILD PHCP -5A- PHCP -5B | False |  | 0 | 180035PGG-FAB-00123-25 | 0
[9 empty] | 2654 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2654 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2654-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2654 |  |  | PF.2654 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00124-25 | PRINCIPIO - ELEC - SMC - 2023 | 14 | 6.00 | 0 | 180035PGG | 10/7/2025 | P&G Gillette |  | Issued for Fabrication | 100 | VDC | FAB-00124-DE-VFD STICK BUILD PHCP -6A- PHCP -6B | False |  | 14 | 180035PGG-FAB-00124-25 | 0
[9 empty] | 2655 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2655 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2655-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2655 |  |  | PF.2655 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00125-25 | PRINCIPIO - ELEC - SMC - 2023 | 1 | 1.00 | 7 | 180035PGG | 9/3/2025 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00125-CND-SPOOL - I -SECTION 4 -DELIVERY 2- | False |  | 346 | 180035PGG-FAB-00125-25 | 0
[9 empty] | 2656 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2656 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2656-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2656 |  |  | PF.2656 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00126-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 14 | 180035PGG | 9/3/2025 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00126-CND-SPOOL - HI -SECTION 4 -DELIVERY 2- | False |  | 734 | 180035PGG-FAB-00126-25 | 0
[9 empty] | 2657 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2657 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2657-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2657 |  |  | PF.2657 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00127-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.00 | 4 | 180035PGG | 8/4/2025 | P&G Gillette |  | Received on Jobsite | 10 |  | FAB-00127-SUP-FA MINI HANGERS -SECTION 5- | False |  | 758 | 180035PGG-FAB-00127-25 | 0
[9 empty] | 2658 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2658 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2658-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2658 |  |  | PF.2658 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00128-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.28 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00128-IW-IDF IN WALL ROOM 211 | False |  | 0 | 180035PGG-FAB-00128-25 | 0
[9 empty] | 2659 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2659 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2659-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2659 |  |  | PF.2659 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00129-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.28 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00129-IW-IDF IN WALL ROOM 224 | False |  | 0 | 180035PGG-FAB-00129-25 | 0
[9 empty] | 2660 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2660 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2660-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2660 |  |  | PF.2660 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00130-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.32 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00130-PB-IDF SECURITY JBS ROOM 224 | False |  | 0 | 180035PGG-FAB-00130-25 | 0
[9 empty] | 2661 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2661 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2661-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2661 |  |  | PF.2661 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00131-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.66 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00131-PB-IDF SECURITY JBS ROOM 134 | False |  | 0 | 180035PGG-FAB-00131-25 | 0
[9 empty] | 2662 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2662 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2662-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2662 |  |  | PF.2662 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00132-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.28 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00132-IW-IDF IN WALL ROOM 134 | False |  | 0 | 180035PGG-FAB-00132-25 | 0
[9 empty] | 2663 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2663 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2663-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2663 |  |  | PF.2663 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00133-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 0.66 | 0 | 180035PGG | 9/15/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00133-PB-IDF SECURITY JBS ROOM 221 | False |  | 0 | 180035PGG-FAB-00133-25 | 0
[9 empty] | 2664 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2664 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2664-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2664 |  |  | PF.2664 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00134-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 5.00 | 0 | 180035PGG | 9/25/2025 | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-00134-IW-IDF WIREMOLD | False |  | 0 | 180035PGG-FAB-00134-25 | 0
[9 empty] | 2665 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2665 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2665-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2665 |  |  | PF.2665 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00135-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 47.20 | 0 | 180035PGG | 9/25/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00135-LGT-MEZZANINE LIGHTING CONTROL | False |  | 0 | 180035PGG-FAB-00135-25 | 0
[9 empty] | 2666 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2666 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2666-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2666 |  |  | PF.2666 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00136-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 47.20 | 0 | 180035PGG | 9/25/2025 | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00136-LGT-MAIN LEVEL LIGHTING CONTROL | False |  | 0 | 180035PGG-FAB-00136-25 | 0
[9 empty] | 2667 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2667 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2667-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2667 |  |  | PF.2667 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦180035PGG-FAB-00137-25 | PRINCIPIO - ELEC - SMC - 2023 | 0 | 1.00 | 16 | 180035PGG | 9/22/2025 | P&G Gillette |  | Shipped to Jobsite | 100 | Shipping & Receiving | FAB-00137-CND-SPOOL - HI -SECTION 8 | False | MODULAR EMT | 792 | 180035PGG-FAB-00137-25 | 130
[9 empty] | 2668 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2668 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2668-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2668 |  |  | PF.2668 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦6232025SMC-FAB-00141-25 | PRINCIPIO - ELEC - SMC - 2023 | 48 | 0.00 | 2 | 180035PGG |  | P&G Gillette |  | Packages (FAB) Confirmed | 50 |  | FAB-00142-DE-PERIMETER FOOTING-B2 | False |  | 52 | 6232025SMC-FAB-00141-25 | 0
[9 empty] | 2669 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2669 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2669-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2669 |  |  | PF.2669 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 180035PGG¦FAB-077.1_180035PGG | PRINCIPIO - ELEC - SMC - 2023 | 3 | 0.00 | 0 | 180035PGG |  | P&G Gillette |  | Shipped to Jobsite | 100 |  | FAB-077.1-MAIN LEVEL-DE-VFD-CHP-7 | False | VFD-CHP-7 | 3 | FAB-077.1_180035PGG | 0
[9 empty] | 2670 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2670 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2670-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2670 |  |  | PF.2670 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 150273WAL¦FAB-00152 | MXD_RESI_JAP_ELEC | 8 | 0.00 | 19 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Design Stage | 10 |  | -LEVEL 11-40-DE-01 | False |  | 136 | FAB-00152 | 0
[9 empty] | 2671 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2671 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2671-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2671 |  |  | PF.2671 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 150273WAL¦FAB-00151 | MXD_RESI_JAP_ELEC | 1710 | 0.00 | 2 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Packages (FAB) Confirmed | 50 |  | 002-LEVEL B1-10-DE-01 | False |  | 1716 | FAB-00151 | 0
[9 empty] | 2672 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2672 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2672-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2672 |  |  | PF.2672 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 150273WAL¦320001TUR-FAB-00003-25 | MXD_RESI_JAP_ELEC | 761 | 0.00 | 0 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Packages (FAB) Confirmed | 50 |  | FAB-00025-IW-Level 3-36-Units | False |  | 761 | 320001TUR-FAB-00003-25 | 0
[9 empty] | 2673 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2673 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2673-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2673 |  |  | PF.2673 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 150273WAL¦320001TUR-FAB-00004-25 | MXD_RESI_JAP_ELEC | 33 | 0.00 | 3 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Design Stage | 10 |  | FAB-00026-CND-LEVEL 37-LEVEL 15 | False | Riser | 48 | 320001TUR-FAB-00004-25 | 0
[9 empty] | 2674 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2674 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2674-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2674 |  |  | PF.2674 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 150273WAL¦150273WAL-00001-25 | MGH GBJ_ELEC_SMC_Stratus | 203 | 0.00 | 0 | 150273WAL |  | 1570273WAL - MGH 789 GBJ GEN (R23) |  | Packages (FAB) Confirmed | 50 |  | CND---ROOF LINE (TOP OF INSULATION)-001 | False |  | 203 | 150273WAL-00001-25 | 0
[9 empty] | 2675 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2675 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2675-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2675 |  |  | PF.2675 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 00001SMC¦FAB-00150 | SMC PILOT PROJECT_R23 | 8 | 0.25 | 0 | 00001SMC |  | PILOT TEST(R23) |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 | VDC | -LEVEL 1-SUP-01 | False |  | 8 | FAB-00150 | 0
[9 empty] | 2676 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2676 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2676-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2676 |  |  | PF.2676 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 00001SMC¦FAB-00146 | SMC PILOT PROJECT_R23 | 33 | 0.00 | 1 | 00001SMC | 9/24/2025 | PILOT TEST(R23) |  | Packages (FAB) Confirmed | 50 | VDC | 01-LEVEL 1-DE- XFMER01 | False |  | 41 | FAB-00146 | 0
[9 empty] | 2677 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2677 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2677-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2677 |  |  | PF.2677 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 00001SMC¦FAB-00147 | SMC PILOT PROJECT_R23 | 8 | 0.00 | 0 | 00001SMC | 9/24/2025 | PILOT TEST(R23) |  | Packages (FAB) Confirmed | 50 | VDC | 02-LEVEL 1-DE-ENCLOSURES01 | False |  | 8 | FAB-00147 | 0
[9 empty] | 2678 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2678 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2678-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2678 |  |  | PF.2678 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 00001SMC¦FAB-00148 | SMC PILOT PROJECT_R23 | 13 | 0.00 | 0 | 00001SMC | 9/24/2025 | PILOT TEST(R23) |  | Design Stage | 10 | VDC | 03-LEVEL 1-PB-01 | False |  | 13 | FAB-00148 | 0
[9 empty] | 2679 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2679 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2679-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2679 |  |  | PF.2679 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 00001SMC¦FAB-00149 | SMC PILOT PROJECT_R23 | 22 | 0.75 | 0 | 00001SMC | 9/24/2025 | PILOT TEST(R23) |  | BIM VDC Coordination Complete (Approved Signed Off) | 35 | VDC | 04-LEVEL 1-SUP-01 | False |  | 22 | FAB-00149 | 0
[9 empty] | 2680 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2680 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2680-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2680 |  |  | PF.2680 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 00001SMC¦FAB-00153_00001SMC | SMC PILOT PROJECT_R23 | 0 | 0.00 | 0 | 00001SMC |  | PILOT TEST(R23) |  | New Item | 35 |  | FAB-00001--CND | False |  | 0 | FAB-00153_00001SMC | 0
[9 empty] | 2681 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2681 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2681-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2681 |  |  | PF.2681 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00001-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00001-LEVEL 3-DE-Level 3-Load Centers 125A | False | Level 3-Load Centers 125A | 0 | FAB-00001-320001TUR | 0
[9 empty] | 2682 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2682 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2682-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2682 |  |  | PF.2682 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00002-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 10/20/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00002-LEVEL 3-DE-Level 3-Load Centers 150A | False | Level 3-Load Centers 150A | 0 | FAB-00002-320001TUR | 0
[9 empty] | 2683 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2683 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2683-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2683 |  |  | PF.2683 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00003-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00003-LEVEL 4-DE-Level 4-Load Centers 125A | False | Level 4-Load Centers 125A | 0 | FAB-00003-320001TUR | 0
[9 empty] | 2684 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2684 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2684-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2684 |  |  | PF.2684 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00004-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00004-LEVEL 4-DE-Level 4-Load Centers 150A | False | Level 4-Load Centers 150A | 0 | FAB-00004-320001TUR | 0
[9 empty] | 2685 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2685 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2685-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2685 |  |  | PF.2685 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00005-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 11/17/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00005-LEVEL 5-DE-Level 5-Load Centers 125A | False | Level 5-Load Centers 125A | 0 | FAB-00005-320001TUR | 0
[9 empty] | 2686 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2686 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2686-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2686 |  |  | PF.2686 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00006-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 11/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00006-LEVEL 5-DE-Level 5-Load Centers 150A | False | Level 5-Load Centers 150A | 0 | FAB-00006-320001TUR | 0
[9 empty] | 2687 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2687 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2687-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2687 |  |  | PF.2687 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00007-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 12/1/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00007-LEVEL 7-DE-Level 7-Load Centers 125A | False | Level 7-Load Centers 125A | 0 | FAB-00007-320001TUR | 0
[9 empty] | 2688 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2688 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2688-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2688 |  |  | PF.2688 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00008-320001TUR | MXD_RESI_JAP_ELEC | 0 | 31.68 | 0 | 320001TUR | 12/8/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00008-LEVEL 7-DE-Level 7-Load Centers 150A | False | Level 7-Load Centers 150A | 0 | FAB-00008-320001TUR | 0
[9 empty] | 2689 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2689 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2689-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2689 |  |  | PF.2689 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00009-320001TUR | MXD_RESI_JAP_ELEC | 0 | 48.37 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00009-LEVEL 8-DE-Level 8-Load Centers 125A | False | Level 8-Load Centers 125A | 0 | FAB-00009-320001TUR | 0
[9 empty] | 2690 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2690 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2690-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2690 |  |  | PF.2690 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00010-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 12/22/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00010-LEVEL 8-DE-Level 8-Load Centers 150A | False | Level 8-Load Centers 150A | 0 | FAB-00010-320001TUR | 0
[9 empty] | 2691 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2691 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2691-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2691 |  |  | PF.2691 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00011-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.28 | 0 | 320001TUR | 12/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00011-LEVEL 9-DE-Level 9-Load Centers 125A | False | Level 9-Load Centers 125A | 0 | FAB-00011-320001TUR | 0
[9 empty] | 2692 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2692 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2692-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2692 |  |  | PF.2692 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00012-320001TUR | MXD_RESI_JAP_ELEC | 0 | 31.68 | 0 | 320001TUR | 1/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00012-LEVEL 9-DE-Level 9-Load Centers 150A | False | Level 9-Load Centers 150A | 0 | FAB-00012-320001TUR | 0
[9 empty] | 2693 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2693 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2693-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2693 |  |  | PF.2693 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00013-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00013-LEVEL 10-DE-Level 10-Load Centers 125A | False | Level 10-Load Centers 125A | 0 | FAB-00013-320001TUR | 0
[9 empty] | 2694 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2694 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2694-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2694 |  |  | PF.2694 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00014-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00014-LEVEL 10-DE-Level 10-Load Centers 150A | False | Level 10-Load Centers 150A | 0 | FAB-00014-320001TUR | 0
[9 empty] | 2695 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2695 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2695-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2695 |  |  | PF.2695 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00015-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00015-LEVEL 11-DE-Level 11-Load Centers 125A | False | Level 11-Load Centers 125A | 0 | FAB-00015-320001TUR | 0
[9 empty] | 2696 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2696 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2696-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2696 |  |  | PF.2696 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00016-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00016-LEVEL 11-DE-Level 11-Load Centers 150A | False | Level 11-Load Centers 150A | 0 | FAB-00016-320001TUR | 0
[9 empty] | 2697 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2697 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2697-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2697 |  |  | PF.2697 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00017-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00017-LEVEL 12-DE-Level 12-Load Centers 125A | False | Level 12-Load Centers 125A | 0 | FAB-00017-320001TUR | 0
[9 empty] | 2698 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2698 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2698-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2698 |  |  | PF.2698 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00018-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00018-LEVEL 12-DE-Level 12-Load Centers 150A | False | Level 12-Load Centers 150A | 0 | FAB-00018-320001TUR | 0
[9 empty] | 2699 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2699 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2699-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2699 |  |  | PF.2699 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00019-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00019-LEVEL 13-DE-Level 13-Load Centers 125A | False | Level 13-Load Centers 125A | 0 | FAB-00019-320001TUR | 0
[9 empty] | 2700 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2700 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2700-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2700 |  |  | PF.2700 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00020-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00020-LEVEL 13-DE-Level 13-Load Centers 150A | False | Level 13-Load Centers 150A | 0 | FAB-00020-320001TUR | 0
[9 empty] | 2701 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2701 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2701-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2701 |  |  | PF.2701 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00021-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 3/9/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00021-LEVEL 14-DE-Level 14-Load Centers 125A | False | Level 14-Load Centers 125A | 0 | FAB-00021-320001TUR | 0
[9 empty] | 2702 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2702 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2702-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2702 |  |  | PF.2702 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00022-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/16/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00022-LEVEL 14-DE-Level 14-Load Centers 150A | False | Level 14-Load Centers 150A | 0 | FAB-00022-320001TUR | 0
[9 empty] | 2703 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2703 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2703-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2703 |  |  | PF.2703 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00023-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 3/23/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00023-LEVEL 15-DE-Level 15-Load Centers 125A | False | Level 15-Load Centers 125A | 0 | FAB-00023-320001TUR | 0
[9 empty] | 2704 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2704 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2704-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2704 |  |  | PF.2704 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00024-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/30/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00024-LEVEL 15-DE-Level 15-Load Centers 150A | False | Level 15-Load Centers 150A | 0 | FAB-00024-320001TUR | 0
[9 empty] | 2705 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2705 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2705-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2705 |  |  | PF.2705 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00025-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 4/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00025-LEVEL 16-DE-Level 16-Load Centers 125A | False | Level 16-Load Centers 125A | 0 | FAB-00025-320001TUR | 0
[9 empty] | 2706 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2706 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2706-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2706 |  |  | PF.2706 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00026-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 4/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00026-LEVEL 16-DE-Level 16-Load Centers 150A | False | Level 16-Load Centers 150A | 0 | FAB-00026-320001TUR | 0
[9 empty] | 2707 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2707 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2707-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2707 |  |  | PF.2707 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00027-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 4/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00027-LEVEL 17-DE-Level 17-Load Centers 125A | False | Level 17-Load Centers 125A | 0 | FAB-00027-320001TUR | 0
[9 empty] | 2708 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2708 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2708-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2708 |  |  | PF.2708 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00028-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 4/28/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00028-LEVEL 17-DE-Level 17-Load Centers 150A | False | Level 17-Load Centers 150A | 0 | FAB-00028-320001TUR | 0
[9 empty] | 2709 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2709 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2709-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2709 |  |  | PF.2709 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00029-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 5/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00029-LEVEL 18-DE-Level 18-Load Centers 125A | False | Level 18-Load Centers 125A | 0 | FAB-00029-320001TUR | 0
[9 empty] | 2710 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2710 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2710-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2710 |  |  | PF.2710 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00030-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 5/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00030-LEVEL 18-DE-Level 18-Load Centers 150A | False | Level 18-Load Centers 150A | 0 | FAB-00030-320001TUR | 0
[9 empty] | 2711 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2711 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2711-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2711 |  |  | PF.2711 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00031-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 5/19/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00031-LEVEL 19-DE-Level 19-Load Centers 125A | False | Level 19-Load Centers 125A | 0 | FAB-00031-320001TUR | 0
[9 empty] | 2712 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2712 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2712-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2712 |  |  | PF.2712 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00032-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 5/27/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00032-LEVEL 19-DE-Level 19-Load Centers 150A | False | Level 19-Load Centers 150A | 0 | FAB-00032-320001TUR | 0
[9 empty] | 2713 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2713 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2713-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2713 |  |  | PF.2713 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00033-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 6/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00033-LEVEL 20-DE-Level 20-Load Centers 125A | False | Level 20-Load Centers 125A | 0 | FAB-00033-320001TUR | 0
[9 empty] | 2714 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2714 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2714-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2714 |  |  | PF.2714 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00034-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00034-LEVEL 20-DE-Level 20-Load Centers 150A | False | Level 20-Load Centers 150A | 0 | FAB-00034-320001TUR | 0
[9 empty] | 2715 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2715 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2715-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2715 |  |  | PF.2715 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00035-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00035-LEVEL 21-DE-Level 21-Load Centers 125A | False | Level 21-Load Centers 125A | 0 | FAB-00035-320001TUR | 0
[9 empty] | 2716 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2716 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2716-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2716 |  |  | PF.2716 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00036-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00036-LEVEL 21-DE-Level 21-Load Centers 150A | False | Level 21-Load Centers 150A | 0 | FAB-00036-320001TUR | 0
[9 empty] | 2717 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2717 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2717-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2717 |  |  | PF.2717 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00037-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00037-LEVEL 22-DE-Level 22-Load Centers 125A | False | Level 22-Load Centers 125A | 0 | FAB-00037-320001TUR | 0
[9 empty] | 2718 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2718 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2718-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2718 |  |  | PF.2718 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00038-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00038-LEVEL 22-DE-Level 22-Load Centers 150A | False | Level 22-Load Centers 150A | 0 | FAB-00038-320001TUR | 0
[9 empty] | 2719 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2719 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2719-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2719 |  |  | PF.2719 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00039-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00039-LEVEL 23-DE-Level 23-Load Centers 125A | False | Level 23-Load Centers 125A | 0 | FAB-00039-320001TUR | 0
[9 empty] | 2720 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2720 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2720-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2720 |  |  | PF.2720 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00040-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00040-LEVEL 23-DE-Level 23-Load Centers 150A | False | Level 23-Load Centers 150A | 0 | FAB-00040-320001TUR | 0
[9 empty] | 2721 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2721 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2721-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2721 |  |  | PF.2721 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00041-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00041-LEVEL 24-DE-Level 24-Load Centers 125A | False | Level 24-Load Centers 125A | 0 | FAB-00041-320001TUR | 0
[9 empty] | 2722 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2722 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2722-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2722 |  |  | PF.2722 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00042-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00042-LEVEL 24-DE-Level 24-Load Centers 150A | False | Level 24-Load Centers 150A | 0 | FAB-00042-320001TUR | 0
[9 empty] | 2723 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2723 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2723-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2723 |  |  | PF.2723 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00043-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00043-LEVEL 25-DE-Level 25-Load Centers 125A | False | Level 25-Load Centers 125A | 0 | FAB-00043-320001TUR | 0
[9 empty] | 2724 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2724 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2724-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2724 |  |  | PF.2724 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00044-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00044-LEVEL 25-DE-Level 25-Load Centers 150A | False | Level 25-Load Centers 150A | 0 | FAB-00044-320001TUR | 0
[9 empty] | 2725 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2725 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2725-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2725 |  |  | PF.2725 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00045-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 1/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00045-LEVEL 26-DE-Level 26-Load Centers 125A | False | Level 26-Load Centers 125A | 0 | FAB-00045-320001TUR | 0
[9 empty] | 2726 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2726 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2726-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2726 |  |  | PF.2726 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00046-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 1/29/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00046-LEVEL 26-DE-Level 26-Load Centers 150A | False | Level 26-Load Centers 150A | 0 | FAB-00046-320001TUR | 0
[9 empty] | 2727 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2727 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2727-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2727 |  |  | PF.2727 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00047-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00047-LEVEL 27-DE-Level 27-Load Centers 125A | False | Level 27-Load Centers 125A | 0 | FAB-00047-320001TUR | 0
[9 empty] | 2728 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2728 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2728-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2728 |  |  | PF.2728 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00048-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/3/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00048-LEVEL 27-DE-Level 27-Load Centers 150A | False | Level 27-Load Centers 150A | 0 | FAB-00048-320001TUR | 0
[9 empty] | 2729 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2729 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2729-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2729 |  |  | PF.2729 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00049-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00049-LEVEL 28-DE-Level 28-Load Centers 125A | False | Level 28-Load Centers 125A | 0 | FAB-00049-320001TUR | 0
[9 empty] | 2730 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2730 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2730-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2730 |  |  | PF.2730 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00050-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00050-LEVEL 28-DE-Level 28-Load Centers 150A | False | Level 28-Load Centers 150A | 0 | FAB-00050-320001TUR | 0
[9 empty] | 2731 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2731 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2731-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2731 |  |  | PF.2731 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00051-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00051-LEVEL 29-DE-Level 29-Load Centers 125A | False | Level 29-Load Centers 125A | 0 | FAB-00051-320001TUR | 0
[9 empty] | 2732 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2732 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2732-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2732 |  |  | PF.2732 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00052-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/11/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00052-LEVEL 29-DE-Level 29-Load Centers 150A | False | Level 29-Load Centers 150A | 0 | FAB-00052-320001TUR | 0
[9 empty] | 2733 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2733 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2733-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2733 |  |  | PF.2733 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00053-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00053-LEVEL 30-DE-Level 30-Load Centers 125A | False | Level 30-Load Centers 125A | 0 | FAB-00053-320001TUR | 0
[9 empty] | 2734 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2734 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2734-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2734 |  |  | PF.2734 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00054-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/17/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00054-LEVEL 30-DE-Level 30-Load Centers 150A | False | Level 30-Load Centers 150A | 0 | FAB-00054-320001TUR | 0
[9 empty] | 2735 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2735 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2735-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2735 |  |  | PF.2735 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00055-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00055-LEVEL 31-DE-Level 31-Load Centers 125A | False | Level 31-Load Centers 125A | 0 | FAB-00055-320001TUR | 0
[9 empty] | 2736 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2736 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2736-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2736 |  |  | PF.2736 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00056-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/20/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00056-LEVEL 31-DE-Level 31-Load Centers 150A | False | Level 31-Load Centers 150A | 0 | FAB-00056-320001TUR | 0
[9 empty] | 2737 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2737 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2737-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2737 |  |  | PF.2737 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00057-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 2/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00057-LEVEL 32-DE-Level 32-Load Centers 125A | False | Level 32-Load Centers 125A | 0 | FAB-00057-320001TUR | 0
[9 empty] | 2738 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2738 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2738-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2738 |  |  | PF.2738 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00058-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 2/25/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00058-LEVEL 32-DE-Level 32-Load Centers 150A | False | Level 32-Load Centers 150A | 0 | FAB-00058-320001TUR | 0
[9 empty] | 2739 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2739 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2739-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2739 |  |  | PF.2739 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00059-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00059-LEVEL 33-DE-Level 33-Load Centers 125A | False | Level 33-Load Centers 125A | 0 | FAB-00059-320001TUR | 0
[9 empty] | 2740 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2740 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2740-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2740 |  |  | PF.2740 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00060-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00060-LEVEL 33-DE-Level 33-Load Centers 150A | False | Level 33-Load Centers 150A | 0 | FAB-00060-320001TUR | 0
[9 empty] | 2741 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2741 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2741-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2741 |  |  | PF.2741 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00061-320001TUR | MXD_RESI_JAP_ELEC | 0 | 62.19 | 0 | 320001TUR | 3/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00061-LEVEL 34-DE-Level 34-Load Centers 125A | False | Level 34-Load Centers 125A | 0 | FAB-00061-320001TUR | 0
[9 empty] | 2742 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2742 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2742-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2742 |  |  | PF.2742 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00062-320001TUR | MXD_RESI_JAP_ELEC | 0 | 39.60 | 0 | 320001TUR | 3/5/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00062-LEVEL 34-DE-Level 34-Load Centers 150A | False | Level 34-Load Centers 150A | 0 | FAB-00062-320001TUR | 0
[9 empty] | 2743 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2743 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2743-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2743 |  |  | PF.2743 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00063-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.44 | 0 | 320001TUR | 3/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00063-LEVEL 35-DE-Level 35-Load Centers 150A | False | Level 35-Load Centers 150A | 0 | FAB-00063-320001TUR | 0
[9 empty] | 2744 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2744 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2744-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2744 |  |  | PF.2744 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00064-320001TUR | MXD_RESI_JAP_ELEC | 0 | 55.44 | 0 | 320001TUR | 3/13/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00064-LEVEL 36-DE-Level 36-Load Centers 150A | False | Level 36-Load Centers 150A | 0 | FAB-00064-320001TUR | 0
[9 empty] | 2745 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2745 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2745-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2745 |  |  | PF.2745 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00065-320001TUR | MXD_RESI_JAP_ELEC | 0 | 2.73 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00065-LEVEL B1-IW-LAUNDRY-BATHROOM IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL B1 LAUNDRY-BATHROOM IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00065-320001TUR | 0
[9 empty] | 2746 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2746 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2746-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2746 |  |  | PF.2746 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00066-320001TUR | MXD_RESI_JAP_ELEC | 0 | 8.56 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00066-LEVEL 1-IW-IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00066-320001TUR | 0
[9 empty] | 2747 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2747 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2747-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2747 |  |  | PF.2747 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00067-320001TUR | MXD_RESI_JAP_ELEC | 0 | 9.11 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00067-LEVEL 2-IW-IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00067-320001TUR | 0
[9 empty] | 2748 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2748 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2748-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2748 |  |  | PF.2748 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00068-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 10/27/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00068-LEVEL 3-IW-PODIUM IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 3-PODIUM IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00068-320001TUR | 0
[9 empty] | 2749 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2749 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2749-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2749 |  |  | PF.2749 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00069-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/3/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00069-LEVEL 4-IW-PODIUM IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 4-PODIUM IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00069-320001TUR | 0
[9 empty] | 2750 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2750 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2750-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2750 |  |  | PF.2750 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00070-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00070-LEVEL 5-IW-PODIUM IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 5-PODIUM IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00070-320001TUR | 0
[9 empty] | 2751 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2751 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2751-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2751 |  |  | PF.2751 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00071-320001TUR | MXD_RESI_JAP_ELEC | 0 | 17.86 | 0 | 320001TUR | 10/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00071-LEVEL 6-IW-IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 6 LEVEL 6 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00071-320001TUR | 0
[9 empty] | 2752 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2752 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2752-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2752 |  |  | PF.2752 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00072-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/7/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00072-LEVEL 7-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 7-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00072-320001TUR | 0
[9 empty] | 2753 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2753 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2753-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2753 |  |  | PF.2753 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00073-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00073-LEVEL 8-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 8-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00073-320001TUR | 0
[9 empty] | 2754 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2754 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2754-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2754 |  |  | PF.2754 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00074-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/18/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00074-LEVEL 9-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 9-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00074-320001TUR | 0
[9 empty] | 2755 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2755 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2755-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2755 |  |  | PF.2755 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00075-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/21/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00075-LEVEL 10-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 10-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00075-320001TUR | 0
[9 empty] | 2756 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2756 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2756-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2756 |  |  | PF.2756 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00076-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 11/26/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00076-LEVEL 11-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 11-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00076-320001TUR | 0
[9 empty] | 2757 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2757 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2757-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2757 |  |  | PF.2757 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00077-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/2/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00077-LEVEL 12-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 12-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00077-320001TUR | 0
[9 empty] | 2758 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2758 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2758-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2758 |  |  | PF.2758 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00078-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/5/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00078-LEVEL 13-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 13-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00078-320001TUR | 0
[9 empty] | 2759 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2759 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2759-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2759 |  |  | PF.2759 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00079-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/10/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00079-LEVEL 14-IW-TIER 1 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 14-TIER 1 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00079-320001TUR | 0
[9 empty] | 2760 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2760 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2760-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2760 |  |  | PF.2760 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00080-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00080-LEVEL 15-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 15-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00080-320001TUR | 0
[9 empty] | 2761 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2761 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2761-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2761 |  |  | PF.2761 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00081-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/23/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00081-LEVEL 16-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 16-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00081-320001TUR | 0
[9 empty] | 2762 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2762 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2762-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2762 |  |  | PF.2762 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00082-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 12/29/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00082-LEVEL 17-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 17-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00082-320001TUR | 0
[9 empty] | 2763 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2763 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2763-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2763 |  |  | PF.2763 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00083-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/2/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00083-LEVEL 18-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 18-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00083-320001TUR | 0
[9 empty] | 2764 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2764 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2764-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2764 |  |  | PF.2764 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00084-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/7/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00084-LEVEL 19-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 19-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00084-320001TUR | 0
[9 empty] | 2765 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2765 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2765-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2765 |  |  | PF.2765 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00085-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/12/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00085-LEVEL 20-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 20-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00085-320001TUR | 0
[9 empty] | 2766 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2766 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2766-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2766 |  |  | PF.2766 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00086-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00086-LEVEL 21-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 21-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00086-320001TUR | 0
[9 empty] | 2767 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2767 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2767-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2767 |  |  | PF.2767 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00087-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/15/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00087-LEVEL 22-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 22-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00087-320001TUR | 0
[9 empty] | 2768 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2768 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2768-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2768 |  |  | PF.2768 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00088-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/21/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00088-LEVEL 23-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 23-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00088-320001TUR | 0
[9 empty] | 2769 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2769 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2769-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2769 |  |  | PF.2769 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00089-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 1/26/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00089-LEVEL 24-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 24-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00089-320001TUR | 0
[9 empty] | 2770 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2770 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2770-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2770 |  |  | PF.2770 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00090-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00090-LEVEL 25-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 25-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00090-320001TUR | 0
[9 empty] | 2771 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2771 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2771-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2771 |  |  | PF.2771 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00091-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00091-LEVEL 26-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 26-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00091-320001TUR | 0
[9 empty] | 2772 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2772 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2772-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2772 |  |  | PF.2772 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00092-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00092-LEVEL 27-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 27-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00092-320001TUR | 0
[9 empty] | 2773 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2773 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2773-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2773 |  |  | PF.2773 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00093-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00093-LEVEL 28-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 28-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00093-320001TUR | 0
[9 empty] | 2774 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2774 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2774-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2774 |  |  | PF.2774 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00094-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00094-LEVEL 29-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 29-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00094-320001TUR | 0
[9 empty] | 2775 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2775 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2775-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2775 |  |  | PF.2775 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00095-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00095-LEVEL 30-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 30-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00095-320001TUR | 0
[9 empty] | 2776 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2776 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2776-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2776 |  |  | PF.2776 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00096-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00096-LEVEL 31-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 31-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00096-320001TUR | 0
[9 empty] | 2777 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2777 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2777-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2777 |  |  | PF.2777 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00097-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00097-LEVEL 32-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 32-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00097-320001TUR | 0
[9 empty] | 2778 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2778 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2778-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2778 |  |  | PF.2778 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00098-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 2/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00098-LEVEL 33-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 33-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00098-320001TUR | 0
[9 empty] | 2779 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2779 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2779-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2779 |  |  | PF.2779 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00099-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 3/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00099-LEVEL 34-IW-TIER 2 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 34-TIER 2 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00099-320001TUR | 0
[9 empty] | 2780 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2780 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2780-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2780 |  |  | PF.2780 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00100-320001TUR | MXD_RESI_JAP_ELEC | 0 | 1.82 | 0 | 320001TUR | 3/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00100-LEVEL 35-IW-TIER 3 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 35-TIER 3 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00100-320001TUR | 0
[9 empty] | 2781 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2781 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2781-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2781 |  |  | PF.2781 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00101-320001TUR | MXD_RESI_JAP_ELEC | 0 | 18.22 | 0 | 320001TUR | 3/10/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00101-LEVEL 36-IW-TIER 3 IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 36-TIER 3 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00101-320001TUR | 0
[9 empty] | 2782 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2782 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2782-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2782 |  |  | PF.2782 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00102-320001TUR | MXD_RESI_JAP_ELEC | 0 | 18.22 | 0 | 320001TUR | 3/6/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00102-LEVEL 37-IW-AMENITY-MEP PH IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 37-AMENITY-MEP PH IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00102-320001TUR | 0
[9 empty] | 2783 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2783 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2783-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2783 |  |  | PF.2783 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00103-320001TUR | MXD_RESI_JAP_ELEC | 0 | 9.11 | 0 | 320001TUR | 7/1/2026 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00103-LEVEL 38-IW-IN-WALL ASSEMBLIES-MIXED SYSTEMS | False | LEVEL 38 IN-WALL ASSEMBLIES MIXED SYSTEMS | 0 | FAB-00103-320001TUR | 0
[9 empty] | 2784 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2784 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2784-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2784 |  |  | PF.2784 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00104-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00104-LEVEL B1-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL B1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00104-320001TUR | 0
[9 empty] | 2785 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2785 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2785-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2785 |  |  | PF.2785 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00105-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/14/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00105-LEVEL 1-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00105-320001TUR | 0
[9 empty] | 2786 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2786 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2786-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2786 |  |  | PF.2786 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00106-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 12/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00106-LEVEL 2-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 2 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00106-320001TUR | 0
[9 empty] | 2787 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2787 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2787-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2787 |  |  | PF.2787 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00107-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/15/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00107-LEVEL 3-CND-PODIUM PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 3-PODIUM PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00107-320001TUR | 0
[9 empty] | 2788 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2788 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2788-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2788 |  |  | PF.2788 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00108-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/24/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00108-LEVEL 4-CND-PODIUM PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 4-PODIUM PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00108-320001TUR | 0
[9 empty] | 2789 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2789 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2789-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2789 |  |  | PF.2789 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00109-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/4/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00109-LEVEL 5-CND-PODIUM PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 5-PODIUM PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00109-320001TUR | 0
[9 empty] | 2790 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2790 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2790-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2790 |  |  | PF.2790 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00110-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 10/28/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00110-LEVEL 6-CND-PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 6 LEVEL 6 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00110-320001TUR | 0
[9 empty] | 2791 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2791 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2791-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2791 |  |  | PF.2791 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00111-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/12/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00111-LEVEL 7-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 7-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00111-320001TUR | 0
[9 empty] | 2792 | 320001TUR | [6 empty] | 121 BROADWAY MXD TOWER |  | #INVALID DATA TYPE | [7 empty] | 0 |  | #INVALID DATA TYPE |  | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 2792 |  |  | #DIVIDE BY ZERO | 0 |  | 0 |  | 0 | 0 | 0 | #DIVIDE BY ZERO | #DIVIDE BY ZERO |  | 2792-320001TUR | PRE-FAB - - | #NO MATCH | #NO MATCH | PF.2792 |  |  | PF.2792 | NOT ON PROJECT SCHEDULE | #DIVIDE BY ZERO |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE |  | 2025-10-05 22:38:50 | 4 | 320001TUR¦FAB-00112-320001TUR | MXD_RESI_JAP_ELEC | 0 | 0.00 | 0 | 320001TUR | 11/19/2025 | 320001TUR - 121 BROADWAY STREET (R22) |  | New Item | 0 |  | FAB-00112-LEVEL 8-CND-TIER 1 PIPE BENDS-0.75in-1.25in PIPE TD | False | LEVEL 8-TIER 1 PIPE BENDS 0.75in-1.25in PIPE TD | 0 | FAB-00112-320001TUR | 0