## STRATUS PACKAGES -ALL PROJECTS
STRATUS_PackageId | Package Name | Tracking Status | Qty Planned | Qty Complete | COST CODE | FAB # | JOB# (HIDDEN) | FOREMAN CONTACT | LOCATION | CATEGORY | PRE-FAB ITEM | QUANTITY PER BUILD | STATUS (HIDDEN) | PROJECT NAME (HIDDEN) | DETAILER | DETAIL DUE BY | DETAIL COMPLETE | DETAIL APPROVAL | MATERIAL RECEIVED | MATERIAL RECEIVED HELPER (HIDDEN) | EQUIPMENT RECEIVED | EQUIPMENT RECEIVED HELPER (HIDDEN) | APPROVAL TO BEGIN FAB | ESTIMATED MAN HOURS PER BUILD (HIDDEN) | WORK DAYS (HIDDEN) | WORK DAYS | CREW | PRE-FAB BUILD START | PRE-FAB BUILD END | PROJECTED COMPLETE DATE | PROJECTED LATER THAN DUE HELPER (HIDDEN) | DUE ON SITE | DUE ONSITE-PROJECT SCHEDULE DUE ONSITE (HIDDEN) | PROJECT SCHEDULE DUE ON SITE DATE (REFERENCE) | SHIPPED TO SITE | CREW MEMBERS (HIDDEN) | PRE-FAB COMPLETE | MATERIAL TRANSFER | STATION (HIDDEN) | PROJECT MANAGER (HIDDEN) | FAB HELPER (HIDDEN) | BUILD YEAR (HIDDEN) | MATERIAL LOCATION (HIDDEN) | PRE-FAB ACTUAL BUILD TIME (PER UNIT) (HIDDEN) | PRE-FAB ACTUAL BUILD TIME (TOTAL) | PRE-FAB ESTIMATED BUILD TIME (PER UNIT) (HIDDEN) | PRE-FAB ESTIMATED BUILD TIME (TOTAL) | CONEST ESTIMATED HOURS (PER UNIT) (HIDDEN) | CONEST ESTIMATED BUILD TIME (TOTAL) (HIDDEN) | CONEST VS ACTUAL LOWEST - HELPER (HIDDEN) | CONEST LESS THAN ACTUAL - HELPER (HIDDEN) | ESTIMATED VS ACTUAL LOWEST - HELPER (HIDDEN) | ESTIMATED LOWER - HELPER (HIDDEN) | BUILD YEAR HELPER (HIDDEN) | FAB#-JOB# | ACTIVITY DESCRIPTION (HIDDEN) | PROJECT SCHEDULE ROW # (HIDDEN) | ITEM LINK TO IN PROJECT SCHEDULE | ACTIVITY ID | COST CODE HELPER (HIDDEN) | STAR (HIDDEN) | Activity ID PREFAB Helper (HIDDEN) | Activity ID Project Schedule Sheet | % Complete | QA/QC COMPLETE | BIM/CAD COORDINATOR | COORDINATION COMPLETE DUE DATE | COORDINATION COMPLETED | TODAY (HIDDEN) | DAYS FROM TODAY TO PREFAB START (HIDDEN) | STATION CONFIRMED
[5 empty] | 9000030 | 100 | 320001TUR | Stephen Yee | LEVEL 35 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 35 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-24 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-03-03 | 2026-03-04 | 2026-03-06 |  | 2026-03-10 | DATES MISALIGNED | 2026-06-09 | [5 empty] | Kerri Pandolfi | 100 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 100-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1618 | LEVEL 35 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.100 | 9000030 |  | PF.100 | PF.100 | 0% |  |  | 2026-02-17 |  | 2025-10-05 | 108
[5 empty] | 9000030 | 101 | 320001TUR | Stephen Yee | LEVEL 36 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 36 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 100 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-26 | [7 empty] | 18.22 | 1.1388 | 2 | 2 | 2026-03-05 | 2026-03-08 | 2026-03-10 |  | 2026-03-10 | DATES MISALIGNED | 2026-06-16 | [5 empty] | Kerri Pandolfi | 101 | 26 |  | 0 | 0 | 0.1822 | 18.22 | 1.15 | 115 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 101-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1651 | LEVEL 36 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.101 | 9000030 |  | PF.101 | PF.101 | 0% |  |  | 2026-02-19 |  | 2025-10-05 | 110
[5 empty] | 9000030 | 102 | 320001TUR | Stephen Yee | LEVEL 37 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 37 - AMENITY/MEP PH IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 100 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-23 | [7 empty] | 18.22 | 1.1388 | 2 | 2 | 2026-03-02 | 2026-03-04 | 2026-03-06 |  | 2026-03-06 | DATES MISALIGNED | 2026-06-16 | [5 empty] | Kerri Pandolfi | 102 | 26 |  | 0 | 0 | 0.1822 | 18.22 | 1.15 | 115 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 102-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1624 | LEVEL 36 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.102 | 9000030 |  | PF.102 | PF.102 | 0% |  |  | 2026-02-16 |  | 2025-10-05 | 107
[5 empty] | 9000030 | 103 | 320001TUR | Stephen Yee | LEVEL 38 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 38 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 50 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-06-19 | [7 empty] | 9.11 | 0.56938 | 1 | 2 | 2026-06-26 | 2026-06-29 | 2026-07-01 |  | 2026-07-01 |  | 2026-07-01 | [5 empty] | Kerri Pandolfi | 103 | 26 |  | 0 | 0 | 0.1822 | 9.11 | 1.15 | 57.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 103-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1708 | LEVEL 38 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.103 | 9000030 |  | PF.103 | PF.103 | 0% |  |  | 2026-06-12 |  | 2025-10-05 | 191
[5 empty] | 9000103 | 104 | 320001TUR | Stephen Yee | LEVEL B1 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL B1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 2 | Gray | 121 BROADWAY MXD TOWER | Eddie Velez | 2025-09-19 | 2025-09-19 | JOHN CORSO | TRUE | true | TRUE | True | APPROVED | 0.5 | 0.03125 | 1 | 2 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-14 |  |  |  |  | Image 2025-09-30 10-33-54.jpeg |  | 3 | Kerri Pandolfi | 104 | 25 |  | 0.25 | 0.5 | 0.25 | 0.5 | 1.74 | 3.48 | 0.25 | 1.49 | 0.25 | 0 | 25 | 104-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1977 |  | PF.104 | 9000103 |  | PF.104 | PF.104 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000103 | 105 | 320001TUR | Stephen Yee | LEVEL 1 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 17 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-15 | 2025-08-21 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4.25 | 0.26562 | 1 | 2 | 2025-08-22 | 2025-08-23 | 2025-08-25 |  | 2025-10-14 | DATES MISALIGNED | 2025-08-25 |  |  | Image 2025-09-30 10-34-16.jpeg |  | 3 | Kerri Pandolfi | 105 | 25 |  | 0.14706 | 2.5 | 0.25 | 4.25 | 1.74 | 29.58 | 0.25 | 1.49 | 0.14706 | -0.10294 | 25 | 105-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 113 | INSTALL - LEVEL 1 - TELCOM BNDS | PF.105 | 9000103 |  | PF.105 | PF.105 | 99% | TRUE |  | 2025-08-08 |  | 2025-10-05 | -31 | TRUE
[5 empty] | 9000103 | 106 | 320001TUR | Stephen Yee | LEVEL 2 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 25 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 6.25 | 0.39062 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | DATES MISALIGNED | 2025-09-08 | [5 empty] | Kerri Pandolfi | 106 | 25 |  | 0 | 0 | 0.25 | 6.25 | 1.74 | 43.5 | 0.25 | 1.49 | 0 | -0.25 | 25 | 106-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 152 | LEVEL 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.106 | 9000103 |  | PF.106 | PF.106 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000103 | 107 | 320001TUR | Stephen Yee | LEVEL 3 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 3 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-03 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-10-10 | 2025-10-13 | 2025-10-15 |  | 2025-10-15 |  | 2025-10-24 | TRUE |  | X |  |  | Kerri Pandolfi | 107 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 107-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 333 | INSTALL - LEVEL 3 - TELCOM BNDS | PF.107 | 9000103 |  | PF.107 | DELETED | 100% |  |  | 2025-09-26 |  | 2025-10-05 | 6
[5 empty] | 9000103 | 108 | 320001TUR | Stephen Yee | LEVEL 4 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 4 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-10 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-10-17 | 2025-10-20 | 2025-10-22 |  | 2025-10-24 |  | 2025-10-31 | TRUE |  | X |  |  | Kerri Pandolfi | 108 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 108-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 374 | INSTALL - LEVEL 4 - TELCOM BNDS | PF.108 | 9000103 |  | PF.108 | DELETED | 100% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[5 empty] | 9000103 | 109 | 320001TUR | Stephen Yee | LEVEL 5 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 5 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-10-31 | 2025-11-02 | 2025-11-04 |  | 2025-11-04 |  | 2025-11-07 | TRUE |  | X |  |  | Kerri Pandolfi | 109 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 109-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 403 | INSTALL - LEVEL 5 - TELCOM BNDS | PF.109 | 9000103 |  | PF.109 | DELETED | 100% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[5 empty] | 9000103 | 110 | 320001TUR | Stephen Yee | LEVEL 6 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 6 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 13 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3.25 | 0.20312 | 1 | 2 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-28 | DATES MISALIGNED | 2025-09-16 |  |  |  |  | 2 | Kerri Pandolfi | 110 | 25 |  | 0.076923 | 1 | 0.25 | 3.25 | 1.74 | 22.62 | 0.25 | 1.49 | 0.076923 | -0.17308 | 25 | 110-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 198 | INSTALL - LEVEL 6 - TELCOM BNDS | PF.110 | 9000103 |  | PF.110 | PF.110 | 30.77% |  |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000103 | 111 | 320001TUR | Stephen Yee | LEVEL 7 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 7 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 | DATES MISALIGNED | 2025-11-21 | [5 empty] | Kerri Pandolfi | 111 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 111-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 483 | INSTALL - LEVEL 7 - TELCOM BNDS | PF.111 | 9000103 |  | PF.111 | PF.111 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[5 empty] | 9000103 | 112 | 320001TUR | Stephen Yee | LEVEL 8 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 8 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-07 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-11-14 | 2025-11-17 | 2025-11-19 |  | 2025-11-19 | DATES MISALIGNED | 2025-12-01 | [5 empty] | Kerri Pandolfi | 112 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 112-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 516 | INSTALL - LEVEL 8 - TELCOM BNDS | PF.112 | 9000103 |  | PF.112 | PF.112 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[5 empty] | 9000103 | 113 | 320001TUR | Stephen Yee | LEVEL 9 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 9 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-14 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-11-21 | 2025-11-23 | 2025-11-25 |  | 2025-11-25 | DATES MISALIGNED | 2025-12-08 | [5 empty] | Kerri Pandolfi | 113 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 113-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 558 | INSTALL - LEVEL 9 - TELCOM BNDS | PF.113 | 9000103 |  | PF.113 | PF.113 | 0% |  |  | 2025-11-07 |  | 2025-10-05 | 36
[5 empty] | 9000103 | 114 | 320001TUR | Stephen Yee | LEVEL 10 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 10 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-21 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-11-28 | 2025-12-01 | 2025-12-03 |  | 2025-12-03 | DATES MISALIGNED | 2025-12-12 | [5 empty] | Kerri Pandolfi | 114 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 114-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 589 | INSTALL - LEVEL 10 - TELCOM BNDS | PF.114 | 9000103 |  | PF.114 | PF.114 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[5 empty] | 9000103 | 115 | 320001TUR | Stephen Yee | LEVEL 11 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 11 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-28 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-12-05 | 2025-12-08 | 2025-12-10 |  | 2025-12-10 | DATES MISALIGNED | 2025-12-19 | [5 empty] | Kerri Pandolfi | 115 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 115-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 630 | INSTALL - LEVEL 11 - TELCOM BNDS | PF.115 | 9000103 |  | PF.115 | PF.115 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[5 empty] | 9000103 | 116 | 320001TUR | Stephen Yee | LEVEL 12 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 12 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-12-12 | 2025-12-15 | 2025-12-17 |  | 2025-12-17 | DATES MISALIGNED | 2025-12-29 | [5 empty] | Kerri Pandolfi | 116 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 116-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 674 | INSTALL - LEVEL 12 - TELCOM BNDS | PF.116 | 9000103 |  | PF.116 | PF.116 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000103 | 117 | 320001TUR | Stephen Yee | LEVEL 13 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 13 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-12 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-12-19 | 2025-12-21 | 2025-12-23 |  | 2025-12-23 | DATES MISALIGNED | 2026-01-06 | [5 empty] | Kerri Pandolfi | 117 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 117-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 715 | INSTALL - LEVEL 13 - TELCOM BNDS | PF.117 | 9000103 |  | PF.117 | PF.117 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[5 empty] | 9000103 | 118 | 320001TUR | Stephen Yee | LEVEL 14 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 14 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-19 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2025-12-26 | 2025-12-28 | 2025-12-30 |  | 2025-12-30 | DATES MISALIGNED | 2026-01-12 | [5 empty] | Kerri Pandolfi | 118 | 25 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 25 | 118-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 763 | INSTALL - LEVEL 14 - TELCOM BNDS | PF.118 | 9000103 |  | PF.118 | PF.118 | 0% |  |  | 2025-12-12 |  | 2025-10-05 | 61
[5 empty] | 9000103 | 119 | 320001TUR | Stephen Yee | LEVEL 15 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 15 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-26 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-02 | 2026-01-05 | 2026-01-07 |  | 2026-01-07 | DATES MISALIGNED | 2026-01-16 | [5 empty] | Kerri Pandolfi | 119 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 119-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 788 | INSTALL - LEVEL 15 - TELCOM BNDS | PF.119 | 9000103 |  | PF.119 | PF.119 | 0% |  |  | 2025-12-19 |  | 2025-10-05 | 66
[5 empty] | 9000103 | 120 | 320001TUR | Stephen Yee | LEVEL 16 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 16 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-09 | 2026-01-12 | 2026-01-14 |  | 2026-01-14 | DATES MISALIGNED | 2026-01-26 | [5 empty] | Kerri Pandolfi | 120 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 120-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 839 | INSTALL - LEVEL 16 - TELCOM BNDS | PF.120 | 9000103 |  | PF.120 | PF.120 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[5 empty] | 9000103 | 121 | 320001TUR | Stephen Yee | LEVEL 17 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 17 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-09 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-16 | 2026-01-19 | 2026-01-21 |  | 2026-01-21 | DATES MISALIGNED | 2026-02-02 | [5 empty] | Kerri Pandolfi | 121 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 121-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 887 | INSTALL - LEVEL 17 - TELCOM BNDS | PF.121 | 9000103 |  | PF.121 | PF.121 | 0% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[5 empty] | 9000103 | 122 | 320001TUR | Stephen Yee | LEVEL 18 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 18 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-16 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-23 | 2026-01-26 | 2026-01-28 |  | 2026-01-28 | DATES MISALIGNED | 2026-02-06 | [5 empty] | Kerri Pandolfi | 122 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 122-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 926 | INSTALL - LEVEL 18 - TELCOM BNDS | PF.122 | 9000103 |  | PF.122 | PF.122 | 0% |  |  | 2026-01-09 |  | 2025-10-05 | 81
[5 empty] | 9000103 | 123 | 320001TUR | Stephen Yee | LEVEL 19 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 19 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-23 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-01-30 | 2026-02-02 | 2026-02-04 |  | 2026-02-04 | DATES MISALIGNED | 2026-02-13 | [5 empty] | Kerri Pandolfi | 123 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 123-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 964 | INSTALL - LEVEL 19 - TELCOM BNDS | PF.123 | 9000103 |  | PF.123 | PF.123 | 0% |  |  | 2026-01-16 |  | 2025-10-05 | 86
[5 empty] | 9000103 | 124 | 320001TUR | Stephen Yee | LEVEL 20 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 20 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-30 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-02-06 | 2026-02-09 | 2026-02-11 |  | 2026-02-11 | DATES MISALIGNED | 2026-02-23 | [5 empty] | Kerri Pandolfi | 124 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 124-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1009 | INSTALL - LEVEL 20 - TELCOM BNDS | PF.124 | 9000103 |  | PF.124 | PF.124 | 0% |  |  | 2026-01-23 |  | 2025-10-05 | 91
[5 empty] | 9000103 | 125 | 320001TUR | Stephen Yee | LEVEL 21 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 21 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-06 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-02-13 | 2026-02-16 | 2026-02-18 |  | 2026-02-18 | DATES MISALIGNED | 2026-03-02 | [5 empty] | Kerri Pandolfi | 125 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 125-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1053 | INSTALL - LEVEL 21 - TELCOM BNDS | PF.125 | 9000103 |  | PF.125 | PF.125 | 0% |  |  | 2026-01-30 |  | 2025-10-05 | 96
[5 empty] | 9000103 | 126 | 320001TUR | Stephen Yee | LEVEL 22 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 22 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-13 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-02-20 | 2026-02-23 | 2026-02-25 |  | 2026-02-25 | DATES MISALIGNED | 2026-03-06 | [5 empty] | Kerri Pandolfi | 126 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 126-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1093 | INSTALL - LEVEL 22 - TELCOM BNDS | PF.126 | 9000103 |  | PF.126 | PF.126 | 0% |  |  | 2026-02-06 |  | 2025-10-05 | 101
[5 empty] | 9000103 | 127 | 320001TUR | Stephen Yee | LEVEL 23 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 23 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-20 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-02-27 | 2026-03-02 | 2026-03-04 |  | 2026-03-04 | DATES MISALIGNED | 2026-03-13 | [5 empty] | Kerri Pandolfi | 127 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 127-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1139 | INSTALL - LEVEL 23 - TELCOM BNDS | PF.127 | 9000103 |  | PF.127 | PF.127 | 0% |  |  | 2026-02-13 |  | 2025-10-05 | 106
[5 empty] | 9000103 | 128 | 320001TUR | Stephen Yee | LEVEL 24 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 24 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-27 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-03-06 | 2026-03-09 | 2026-03-11 |  | 2026-03-11 | DATES MISALIGNED | 2026-03-20 | [5 empty] | Kerri Pandolfi | 128 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 128-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1181 | INSTALL - LEVEL 24 - TELCOM BNDS | PF.128 | 9000103 |  | PF.128 | PF.128 | 0% |  |  | 2026-02-20 |  | 2025-10-05 | 111
[5 empty] | 9000103 | 129 | 320001TUR | Stephen Yee | LEVEL 25 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 25 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-06 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-03-13 | 2026-03-16 | 2026-03-18 |  | 2026-03-18 | DATES MISALIGNED | 2026-03-27 | [5 empty] | Kerri Pandolfi | 129 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 129-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1226 | INSTALL - LEVEL 25 - TELCOM BNDS | PF.129 | 9000103 |  | PF.129 | PF.129 | 0% |  |  | 2026-02-27 |  | 2025-10-05 | 116
[5 empty] | 9000103 | 130 | 320001TUR | Stephen Yee | LEVEL 26 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 26 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-16 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-03-23 | 2026-03-24 | 2026-03-26 |  | 2026-03-26 | DATES MISALIGNED | 2026-04-06 | [5 empty] | Kerri Pandolfi | 130 | 26 |  | 0.4 | 2 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0.25 | 0 | 26 | 130-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1269 | INSTALL - LEVEL 26 - TELCOM BNDS | PF.130 | 9000103 |  | PF.130 | PF.130 | 75% |  |  | 2026-03-09 |  | 2025-10-05 | 122
[5 empty] | 9000103 | 131 | 320001TUR | Stephen Yee | LEVEL 27 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 27 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-20 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-03-27 | 2026-03-30 | 2026-04-01 |  | 2026-04-01 | DATES MISALIGNED | 2026-04-10 | [5 empty] | Kerri Pandolfi | 131 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 131-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1307 | INSTALL - LEVEL 27 - TELCOM BNDS | PF.131 | 9000103 |  | PF.131 | PF.131 | 0% |  |  | 2026-03-13 |  | 2025-10-05 | 126
[5 empty] | 9000103 | 132 | 320001TUR | Stephen Yee | LEVEL 28 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 28 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-27 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-04-03 | 2026-04-06 | 2026-04-08 |  | 2026-04-08 | DATES MISALIGNED | 2026-04-17 | [5 empty] | Kerri Pandolfi | 132 | 26 |  | 0.2 | 1 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0.2 | -0.05 | 26 | 132-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1350 | INSTALL - LEVEL 28 - TELCOM BNDS | PF.132 | 9000103 |  | PF.132 | PF.132 | 75% |  |  | 2026-03-20 |  | 2025-10-05 | 131
[5 empty] | 9000103 | 133 | 320001TUR | Stephen Yee | LEVEL 29 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 29 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-03 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-04-10 | 2026-04-13 | 2026-04-15 |  | 2026-04-15 | DATES MISALIGNED | 2026-04-27 | [5 empty] | Kerri Pandolfi | 133 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 133-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1391 | INSTALL - LEVEL 29 - TELCOM BNDS | PF.133 | 9000103 |  | PF.133 | PF.133 | 0% |  |  | 2026-03-27 |  | 2025-10-05 | 136
[5 empty] | 9000103 | 134 | 320001TUR | Stephen Yee | LEVEL 30 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 30 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-13 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-04-20 | 2026-04-21 | 2026-04-23 |  | 2026-04-23 | DATES MISALIGNED | 2026-05-04 | [5 empty] | Kerri Pandolfi | 134 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 134-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1431 | INSTALL - LEVEL 30 - TELCOM BNDS | PF.134 | 9000103 |  | PF.134 | PF.134 | 0% |  |  | 2026-04-06 |  | 2025-10-05 | 142
[5 empty] | 9000103 | 135 | 320001TUR | Stephen Yee | LEVEL 31 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 31 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-20 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-04-27 | 2026-04-28 | 2026-04-30 |  | 2026-04-30 | DATES MISALIGNED | 2026-05-11 | [5 empty] | Kerri Pandolfi | 135 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 135-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1470 | INSTALL - LEVEL 31 - TELCOM BNDS | PF.135 | 9000103 |  | PF.135 | PF.135 | 0% |  |  | 2026-04-13 |  | 2025-10-05 | 147
[5 empty] | 9000103 | 136 | 320001TUR | Stephen Yee | LEVEL 32 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 32 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-27 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-05-04 | 2026-05-05 | 2026-05-07 |  | 2026-05-07 | DATES MISALIGNED | 2026-05-18 | [5 empty] | Kerri Pandolfi | 136 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 136-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1512 | INSTALL - LEVEL 32 - TELCOM BNDS | PF.136 | 9000103 |  | PF.136 | PF.136 | 0% |  |  | 2026-04-20 |  | 2025-10-05 | 152
[5 empty] | 9000103 | 137 | 320001TUR | Stephen Yee | LEVEL 33 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 33 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-04 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-05-11 | 2026-05-12 | 2026-05-14 |  | 2026-05-14 | DATES MISALIGNED | 2026-05-26 | [5 empty] | Kerri Pandolfi | 137 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 137-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1550 | INSTALL - LEVEL 33 - TELCOM BNDS | PF.137 | 9000103 |  | PF.137 | PF.137 | 0% |  |  | 2026-04-27 |  | 2025-10-05 | 157
[5 empty] | 9000103 | 138 | 320001TUR | Stephen Yee | LEVEL 34 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 34 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-11 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-05-18 | 2026-05-19 | 2026-05-21 |  | 2026-05-21 | DATES MISALIGNED | 2026-06-02 | [5 empty] | Kerri Pandolfi | 138 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 138-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1582 | INSTALL - LEVEL 34 - TELCOM BNDS | PF.138 | 9000103 |  | PF.138 | PF.138 | 0% |  |  | 2026-05-04 |  | 2025-10-05 | 162
[5 empty] | 9000103 | 139 | 320001TUR | Stephen Yee | LEVEL 35 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 35 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-19 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-05-26 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | DATES MISALIGNED | 2026-06-09 | [5 empty] | Kerri Pandolfi | 139 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 139-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1620 | INSTALL - LEVEL 35 - TELCOM BNDS | PF.139 | 9000103 |  | PF.139 | PF.139 | 0% |  |  | 2026-05-12 |  | 2025-10-05 | 168
[5 empty] | 9000103 | 140 | 320001TUR | Stephen Yee | LEVEL 36 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 36 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-26 | [7 empty] | 1.25 | 0.078125 | 1 | 2 | 2026-06-02 | 2026-06-03 | 2026-06-05 |  | 2026-06-05 | DATES MISALIGNED | 2026-06-16 | [5 empty] | Kerri Pandolfi | 140 | 26 |  | 0 | 0 | 0.25 | 1.25 | 1.74 | 8.7 | 0.25 | 1.49 | 0 | -0.25 | 26 | 140-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1653 | INSTALL - LEVEL 36 - TELCOM BNDS | PF.140 | 9000103 |  | PF.140 | PF.140 | 0% |  |  | 2026-05-19 |  | 2025-10-05 | 173
[5 empty] | 9000103 | 141 | 320001TUR | Stephen Yee | LEVEL 37 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 37 - AMENITY/MEP PH PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 50 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-06-19 | [7 empty] | 12.5 | 0.78125 | 1 | 2 | 2026-06-26 | 2026-06-28 | 2026-06-30 |  | 2026-06-30 |  | 2026-06-30 | [5 empty] | Kerri Pandolfi | 141 | 26 |  | 0 | 0 | 0.25 | 12.5 | 1.74 | 87 | 0.25 | 1.49 | 0 | -0.25 | 26 | 141-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1688 | INSTALL - LEVEL 37 - TELCOM BNDS | PF.141 | 9000103 |  | PF.141 | PF.141 | 0% |  |  | 2026-06-12 |  | 2025-10-05 | 191
[5 empty] | 9000103 | 142 | 320001TUR | Stephen Yee | LEVEL 38 | PIPE BENDS (3/4" -1 1/4" PIPE) T/D | LEVEL 38 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 25 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-06-26 | [7 empty] | 6.25 | 0.39062 | 1 | 2 | 2026-07-03 | 2026-07-04 | 2026-07-06 |  | 2026-07-06 |  | 2026-07-06 | [5 empty] | Kerri Pandolfi | 142 | 26 |  | 0 | 0 | 0.25 | 6.25 | 1.74 | 43.5 | 0.25 | 1.49 | 0 | -0.25 | 26 | 142-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | 1714 | INSTALL - LEVEL 38 - TELCOM BNDS | PF.142 | 9000103 |  | PF.142 | PF.142 | 0% |  |  | 2026-06-19 |  | 2025-10-05 | 196
[5 empty] | 9000020 | 143 | 320001TUR | Stephen Yee | LEVEL B1 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL B1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID OPERATION | [7 empty] | 3.9 | 0.24375 | 1 | 2 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 143 | #INVALID VALUE |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | LE | 143-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | #NO MATCH | #NO MATCH | PF.143 | 9000020 |  | PF.143 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[5 empty] | 9000020 | 144 | 320001TUR | Stephen Yee | LEVEL 1 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-21 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-28 | 2026-08-30 | 2026-09-01 |  | 2026-09-01 |  | 2026-09-01 | [5 empty] | Kerri Pandolfi | 144 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 144-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1851 | INSTALL - LEVEL 1 - LIGHTING CNTRL | PF.144 | 9000020 |  | PF.144 | PF.144 | 0% |  |  | 2026-08-14 |  | 2025-10-05 | 236
[5 empty] | 9000020 | 145 | 320001TUR | Stephen Yee | LEVEL 2 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 20 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2025-11-07 | [7 empty] | 15.6 | 0.975 | 1 | 2 | 2025-11-14 | 2025-11-15 | 2025-11-17 |  | 2025-11-17 |  | 2025-11-17 | [5 empty] | Kerri Pandolfi | 145 | 25 |  | 0 | 0 | 0.78 | 15.6 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 25 | 145-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 428 | INSTALL - LEVEL 2 - LIGHTING CNTRL | PF.145 | 9000020 |  | PF.145 | PF.145 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[5 empty] | 9000020 | 146 | 320001TUR | Stephen Yee | LEVEL 3 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 3 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2025-11-07 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2025-11-14 | 2025-11-15 | 2025-11-17 |  | 2026-03-11 |  | 2026-03-12 | [5 empty] | Kerri Pandolfi | 146 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 146-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1104 | INSTALL - LEVEL 3 - LIGHTING CNTRL | PF.146 | 9000020 |  | PF.146 | PF.146 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[5 empty] | 9000020 | 147 | 320001TUR | Stephen Yee | LEVEL 4 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 4 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-02 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-03-09 | 2026-03-10 | 2026-03-12 |  | 2026-03-18 |  | 2026-03-19 | [5 empty] | Kerri Pandolfi | 147 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 147-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1145 | INSTALL - LEVEL 4 - LIGHTING CNTRL | PF.147 | 9000020 |  | PF.147 | PF.147 | 0% |  |  | 2026-02-23 |  | 2025-10-05 | 112
[5 empty] | 9000020 | 148 | 320001TUR | Stephen Yee | LEVEL 5 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 5 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-09 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-03-16 | 2026-03-17 | 2026-03-19 |  | 2026-03-25 |  | 2026-03-25 | [5 empty] | Kerri Pandolfi | 148 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 148-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1186 | INSTALL - LEVEL 5 - LIGHTING CNTRL | PF.148 | 9000020 |  | PF.148 | PF.148 | 0% |  |  | 2026-03-02 |  | 2025-10-05 | 117
[5 empty] | 9000020 | 149 | 320001TUR | Stephen Yee | LEVEL 6 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 6 LEVEL 6 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 20 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-13 | [7 empty] | 15.6 | 0.975 | 1 | 2 | 2026-03-20 | 2026-03-23 | 2026-03-25 |  | 2026-04-01 |  | 2026-04-01 | [5 empty] | Kerri Pandolfi | 149 | 26 |  | 0 | 0 | 0.78 | 15.6 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 149-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1225 | INSTALL - LEVEL 6 - LIGHTING CNTRL | PF.149 | 9000020 |  | PF.149 | PF.149 | 0% |  |  | 2026-03-06 |  | 2025-10-05 | 121
[5 empty] | 9000020 | 150 | 320001TUR | Stephen Yee | LEVEL 7 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 7 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-20 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-03-27 | 2026-03-30 | 2026-04-01 |  | 2026-04-01 |  | 2026-04-01 | [5 empty] | Kerri Pandolfi | 150 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 150-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1231 | INSTALL - LEVEL 7 - LIGHTING CNTRL | PF.150 | 9000020 |  | PF.150 | PF.150 | 0% |  |  | 2026-03-13 |  | 2025-10-05 | 126
[5 empty] | 9000020 | 151 | 320001TUR | Stephen Yee | LEVEL 8 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 8 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-20 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-03-27 | 2026-03-30 | 2026-04-01 |  | 2026-04-08 |  | 2026-04-08 | [5 empty] | Kerri Pandolfi | 151 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 151-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1268 | INSTALL - LEVEL 8 - LIGHTING CNTRL | PF.151 | 9000020 |  | PF.151 | PF.151 | 0% |  |  | 2026-03-13 |  | 2025-10-05 | 126
[5 empty] | 9000020 | 152 | 320001TUR | Stephen Yee | LEVEL 9 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 9 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-03-27 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-04-03 | 2026-04-06 | 2026-04-08 |  | 2026-04-14 |  | 2026-04-15 | [5 empty] | Kerri Pandolfi | 152 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 152-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1316 | INSTALL - LEVEL 9 - LIGHTING CNTRL | PF.152 | 9000020 |  | PF.152 | PF.152 | 0% |  |  | 2026-03-20 |  | 2025-10-05 | 131
[5 empty] | 9000020 | 153 | 320001TUR | Stephen Yee | LEVEL 10 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 10 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-04-03 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-04-10 | 2026-04-13 | 2026-04-15 |  | 2026-04-22 |  | 2026-04-23 | [5 empty] | Kerri Pandolfi | 153 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 153-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1356 | INSTALL - LEVEL 10 - LIGHTING CNTRL | PF.153 | 9000020 |  | PF.153 | PF.153 | 0% |  |  | 2026-03-27 |  | 2025-10-05 | 136
[5 empty] | 9000020 | 154 | 320001TUR | Stephen Yee | LEVEL 11 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 11 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-04-13 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-04-20 | 2026-04-21 | 2026-04-23 |  | 2026-04-29 |  | 2026-04-30 | [5 empty] | Kerri Pandolfi | 154 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 154-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1395 | INSTALL - LEVEL 11 - LIGHTING CNTRL | PF.154 | 9000020 |  | PF.154 | PF.154 | 0% |  |  | 2026-04-06 |  | 2025-10-05 | 142
[5 empty] | 9000020 | 155 | 320001TUR | Stephen Yee | LEVEL 12 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 12 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-04-20 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-04-27 | 2026-04-28 | 2026-04-30 |  | 2026-05-06 |  | 2026-05-07 | [5 empty] | Kerri Pandolfi | 155 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 155-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1436 | INSTALL - LEVEL 12 - LIGHTING CNTRL | PF.155 | 9000020 |  | PF.155 | PF.155 | 0% |  |  | 2026-04-13 |  | 2025-10-05 | 147
[5 empty] | 9000020 | 156 | 320001TUR | Stephen Yee | LEVEL 13 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 13 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-04-27 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-05-04 | 2026-05-05 | 2026-05-07 |  | 2026-05-13 |  | 2026-05-14 | [5 empty] | Kerri Pandolfi | 156 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 156-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1474 | INSTALL - LEVEL 13 - LIGHTING CNTRL | PF.156 | 9000020 |  | PF.156 | PF.156 | 0% |  |  | 2026-04-20 |  | 2025-10-05 | 152
[5 empty] | 9000020 | 157 | 320001TUR | Stephen Yee | LEVEL 14 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 14 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-05-04 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-05-11 | 2026-05-12 | 2026-05-14 |  | 2026-05-19 |  | 2026-05-21 | [5 empty] | Kerri Pandolfi | 157 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 157-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1519 | INSTALL - LEVEL 14 - LIGHTING CNTRL | PF.157 | 9000020 |  | PF.157 | PF.157 | 0% |  |  | 2026-04-27 |  | 2025-10-05 | 157
[5 empty] | 9000020 | 158 | 320001TUR | Stephen Yee | LEVEL 15 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 15 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-05-11 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-05-18 | 2026-05-19 | 2026-05-21 |  | 2026-05-27 |  | 2026-05-28 | [5 empty] | Kerri Pandolfi | 158 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 158-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1549 | INSTALL - LEVEL 15 - LIGHTING CNTRL | PF.158 | 9000020 |  | PF.158 | PF.158 | 0% |  |  | 2026-05-04 |  | 2025-10-05 | 162
[5 empty] | 9000020 | 159 | 320001TUR | Stephen Yee | LEVEL 16 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 16 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-05-18 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-05-25 | 2026-05-26 | 2026-05-28 |  | 2026-06-03 |  | 2026-06-04 | [5 empty] | Kerri Pandolfi | 159 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 159-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1581 | INSTALL - LEVEL 16 - LIGHTING CNTRL | PF.159 | 9000020 |  | PF.159 | PF.159 | 0% |  |  | 2026-05-11 |  | 2025-10-05 | 167
[5 empty] | 9000020 | 160 | 320001TUR | Stephen Yee | LEVEL 17 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 17 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-05-25 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-01 | 2026-06-02 | 2026-06-04 |  | 2026-06-10 |  | 2026-06-11 | [5 empty] | Kerri Pandolfi | 160 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 160-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1619 | INSTALL - LEVEL 17 - LIGHTING CNTRL | PF.160 | 9000020 |  | PF.160 | PF.160 | 0% |  |  | 2026-05-18 |  | 2025-10-05 | 172
[5 empty] | 9000020 | 161 | 320001TUR | Stephen Yee | LEVEL 18 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 18 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-01 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-08 | 2026-06-09 | 2026-06-11 |  | 2026-06-17 |  | 2026-06-18 | [5 empty] | Kerri Pandolfi | 161 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 161-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1652 | INSTALL - LEVEL 18 - LIGHTING CNTRL | PF.161 | 9000020 |  | PF.161 | PF.161 | 0% |  |  | 2026-05-25 |  | 2025-10-05 | 177
[5 empty] | 9000020 | 162 | 320001TUR | Stephen Yee | LEVEL 19 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 19 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-08 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-15 | 2026-06-16 | 2026-06-18 |  | 2026-06-24 |  | 2026-06-25 | [5 empty] | Kerri Pandolfi | 162 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 162-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1683 | INSTALL - LEVEL 19 - LIGHTING CNTRL | PF.162 | 9000020 |  | PF.162 | PF.162 | 0% |  |  | 2026-06-01 |  | 2025-10-05 | 182
[5 empty] | 9000020 | 163 | 320001TUR | Stephen Yee | LEVEL 20 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 20 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-15 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-22 | 2026-06-23 | 2026-06-25 |  | 2026-06-30 |  | 2026-07-01 | [5 empty] | Kerri Pandolfi | 163 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 163-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1712 | INSTALL - LEVEL 20 - LIGHTING CNTRL | PF.163 | 9000020 |  | PF.163 | PF.163 | 0% |  |  | 2026-06-08 |  | 2025-10-05 | 187
[5 empty] | 9000020 | 164 | 320001TUR | Stephen Yee | LEVEL 21 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 21 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-19 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-06-26 | 2026-06-29 | 2026-07-01 |  | 2026-07-08 |  | 2026-07-09 | [5 empty] | Kerri Pandolfi | 164 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 164-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1739 | INSTALL - LEVEL 21 - LIGHTING CNTRL | PF.164 | 9000020 |  | PF.164 | PF.164 | 0% |  |  | 2026-06-12 |  | 2025-10-05 | 191
[5 empty] | 9000020 | 165 | 320001TUR | Stephen Yee | LEVEL 22 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 22 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-29 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-06 | 2026-07-07 | 2026-07-09 |  | 2026-07-15 |  | 2026-07-16 | [5 empty] | Kerri Pandolfi | 165 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 165-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1760 | INSTALL - LEVEL 22 - LIGHTING CNTRL | PF.165 | 9000020 |  | PF.165 | PF.165 | 0% |  |  | 2026-06-22 |  | 2025-10-05 | 197
[5 empty] | 9000020 | 166 | 320001TUR | Stephen Yee | LEVEL 23 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 23 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-06 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-13 | 2026-07-14 | 2026-07-16 |  | 2026-07-22 |  | 2026-07-23 | [5 empty] | Kerri Pandolfi | 166 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 166-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1778 | INSTALL - LEVEL 23 - LIGHTING CNTRL | PF.166 | 9000020 |  | PF.166 | PF.166 | 0% |  |  | 2026-06-29 |  | 2025-10-05 | 202
[5 empty] | 9000020 | 167 | 320001TUR | Stephen Yee | LEVEL 24 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 24 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-13 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-20 | 2026-07-21 | 2026-07-23 |  | 2026-07-29 |  | 2026-07-30 | [5 empty] | Kerri Pandolfi | 167 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 167-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1795 | INSTALL - LEVEL 24 - LIGHTING CNTRL | PF.167 | 9000020 |  | PF.167 | PF.167 | 0% |  |  | 2026-07-06 |  | 2025-10-05 | 207
[5 empty] | 9000020 | 168 | 320001TUR | Stephen Yee | LEVEL 25 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 25 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-20 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-27 | 2026-07-28 | 2026-07-30 |  | 2026-08-05 |  | 2026-08-06 | [5 empty] | Kerri Pandolfi | 168 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 168-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1811 | INSTALL - LEVEL 25 - LIGHTING CNTRL | PF.168 | 9000020 |  | PF.168 | PF.168 | 0% |  |  | 2026-07-13 |  | 2025-10-05 | 212
[5 empty] | 9000020 | 169 | 320001TUR | Stephen Yee | LEVEL 26 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 26 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-27 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-03 | 2026-08-04 | 2026-08-06 |  | 2026-08-12 |  | 2026-08-12 | [5 empty] | Kerri Pandolfi | 169 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 169-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1819 | INSTALL - LEVEL 26 - LIGHTING CNTRL | PF.169 | 9000020 |  | PF.169 | PF.169 | 0% |  |  | 2026-07-20 |  | 2025-10-05 | 217
[5 empty] | 9000020 | 170 | 320001TUR | Stephen Yee | LEVEL 27 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 27 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-07-31 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-07 | 2026-08-10 | 2026-08-12 |  | 2026-08-19 |  | 2026-08-19 | [5 empty] | Kerri Pandolfi | 170 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 170-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1832 | INSTALL - LEVEL 27 - LIGHTING CNTRL | PF.170 | 9000020 |  | PF.170 | PF.170 | 0% |  |  | 2026-07-24 |  | 2025-10-05 | 221
[5 empty] | 9000020 | 171 | 320001TUR | Stephen Yee | LEVEL 28 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 28 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-07 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-14 | 2026-08-17 | 2026-08-19 |  | 2026-08-26 |  | 2026-08-26 | [5 empty] | Kerri Pandolfi | 171 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 171-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1845 | INSTALL - LEVEL 28 - LIGHTING CNTRL | PF.171 | 9000020 |  | PF.171 | PF.171 | 0% |  |  | 2026-07-31 |  | 2025-10-05 | 226
[5 empty] | 9000020 | 172 | 320001TUR | Stephen Yee | LEVEL 29 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 29 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-14 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-21 | 2026-08-24 | 2026-08-26 |  | 2026-09-01 |  | 2026-09-02 | [5 empty] | Kerri Pandolfi | 172 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 172-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1858 | INSTALL - LEVEL 29 - LIGHTING CNTRL | PF.172 | 9000020 |  | PF.172 | PF.172 | 0% |  |  | 2026-08-07 |  | 2025-10-05 | 231
[5 empty] | 9000020 | 173 | 320001TUR | Stephen Yee | LEVEL 30 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 30 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-21 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-08-28 | 2026-08-31 | 2026-09-02 |  | 2026-09-09 |  | 2026-09-10 | [5 empty] | Kerri Pandolfi | 173 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 173-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1870 | INSTALL - LEVEL 30 - LIGHTING CNTRL | PF.173 | 9000020 |  | PF.173 | PF.173 | 0% |  |  | 2026-08-14 |  | 2025-10-05 | 236
[5 empty] | 9000020 | 174 | 320001TUR | Stephen Yee | LEVEL 31 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 31 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-08-31 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-09-07 | 2026-09-08 | 2026-09-10 |  | 2026-09-16 |  | 2026-09-17 | [5 empty] | Kerri Pandolfi | 174 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 174-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1880 | INSTALL - LEVEL 31 - LIGHTING CNTRL | PF.174 | 9000020 |  | PF.174 | PF.174 | 0% |  |  | 2026-08-24 |  | 2025-10-05 | 242
[5 empty] | 9000020 | 175 | 320001TUR | Stephen Yee | LEVEL 32 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 32 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-09-07 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-09-14 | 2026-09-15 | 2026-09-17 |  | 2026-09-23 |  | 2026-09-24 | [5 empty] | Kerri Pandolfi | 175 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 175-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1888 | INSTALL - LEVEL 32 - LIGHTING CNTRL | PF.175 | 9000020 |  | PF.175 | PF.175 | 0% |  |  | 2026-08-31 |  | 2025-10-05 | 247
[5 empty] | 9000020 | 176 | 320001TUR | Stephen Yee | LEVEL 33 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 33 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-09-14 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-09-21 | 2026-09-22 | 2026-09-24 |  | 2026-09-30 |  | 2026-10-01 | [5 empty] | Kerri Pandolfi | 176 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 176-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1895 | INSTALL - LEVEL 33 - LIGHTING CNTRL | PF.176 | 9000020 |  | PF.176 | PF.176 | 0% |  |  | 2026-09-07 |  | 2025-10-05 | 252
[5 empty] | 9000020 | 177 | 320001TUR | Stephen Yee | LEVEL 34 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 34 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-09-21 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-09-28 | 2026-09-29 | 2026-10-01 |  | 2026-10-06 |  | 2026-10-08 | [5 empty] | Kerri Pandolfi | 177 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 177-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1901 | INSTALL - LEVEL 34 - LIGHTING CNTRL | PF.177 | 9000020 |  | PF.177 | PF.177 | 0% |  |  | 2026-09-14 |  | 2025-10-05 | 257
[5 empty] | 9000020 | 178 | 320001TUR | Stephen Yee | LEVEL 35 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 35 - TIER 3 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-09-28 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-10-05 | 2026-10-06 | 2026-10-08 |  | 2026-10-14 |  | 2026-10-15 | [5 empty] | Kerri Pandolfi | 178 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 178-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1906 | INSTALL - LEVEL 35 - LIGHTING CNTRL | PF.178 | 9000020 |  | PF.178 | PF.178 | 0% |  |  | 2026-09-21 |  | 2025-10-05 | 262
[5 empty] | 9000020 | 179 | 320001TUR | Stephen Yee | LEVEL 36 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 36 - TIER 3 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-10-05 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-10-12 | 2026-10-13 | 2026-10-15 |  | 2026-10-21 |  | 2026-10-22 | [5 empty] | Kerri Pandolfi | 179 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 179-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1910 | INSTALL - LEVEL 36 - LIGHTING CNTRL | PF.179 | 9000020 |  | PF.179 | PF.179 | 0% |  |  | 2026-09-28 |  | 2025-10-05 | 267
[5 empty] | 9000020 | 180 | 320001TUR | Stephen Yee | LEVEL 37 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 37 - AMENITY/MEP PH LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 20 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-10-12 | [7 empty] | 15.6 | 0.975 | 1 | 2 | 2026-10-19 | 2026-10-20 | 2026-10-22 |  | 2026-10-22 | [7 empty] | Kerri Pandolfi | 180 | 26 |  | 0 | 0 | 0.78 | 15.6 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 180-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1967 | INSTALL - LEVEL 37 - LIGHTING CNTRL | PF.180 | 9000020 |  | PF.180 | PF.180 | 0% |  |  | 2026-10-05 |  | 2025-10-05 | 272
[5 empty] | 9000020 | 181 | 320001TUR | Stephen Yee | LEVEL 38 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 38 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-26 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-03 | 2026-07-04 | 2026-07-06 |  | 2026-07-06 | [7 empty] | Kerri Pandolfi | 181 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 181-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1970 | INSTALL - LEVEL 38 - LIGHTING CNTRL | PF.181 | 9000020 |  | PF.181 | PF.181 | 0% |  |  | 2026-06-19 |  | 2025-10-05 | 196
[5 empty] | 9000020 | 182 | 320001TUR | Stephen Yee | LEVEL 39 | LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | LEVEL 39 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez, Paul Simcoe | 2026-06-26 | [7 empty] | 3.9 | 0.24375 | 1 | 2 | 2026-07-03 | 2026-07-04 | 2026-07-06 |  | 2026-07-06 | [7 empty] | Kerri Pandolfi | 182 | 26 |  | 0 | 0 | 0.78 | 3.9 |  | 0 | 0.78 | -0.78 | 0 | -0.78 | 26 | 182-320001TUR | PRE-FAB - LEVEL 39 - LEVEL 39 LIGHTING CONTROL (2) COMPONENT ASSEMBLY (WIRED) | 1973 | INSTALL - LEVEL 39 - LIGHTING CNTRL | PF.182 | 9000020 |  | PF.182 | PF.182 | 0% |  |  | 2026-06-19 |  | 2025-10-05 | 196
[5 empty] | 9000021 | 183 | 320001TUR | Stephen Yee | LEVEL B1 | LIGHTING CONTROL PANEL ASSEMBLY WIRED | LIGHTING CONTROL PANEL ASSEMBLY WIRED | 2 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID OPERATION | [7 empty] | 16 | 1 | 1 | 2 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 183 | #INVALID VALUE |  | 0 | 0 | 8 | 16 | 11.25 | 22.5 | 8 | 3.25 | 0 | -8 | LE | 183-320001TUR | PRE-FAB - LEVEL B1 - LIGHTING CONTROL PANEL ASSEMBLY WIRED | #NO MATCH | #NO MATCH | PF.183 | 9000021 |  | PF.183 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[5 empty] | 9000031 | 184 | 320001TUR | Stephen Yee | LEVEL B1 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL B1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 4 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo, Eddie Velez | 2025-08-22 | [7 empty] | 2.1193 | 0.13246 | 1 | 2 | 2025-08-29 | 2025-08-30 | 2025-09-01 |  | 2025-09-01 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 184 | 25 |  | 0 | 0 | 0.52983 | 2.1193 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 184-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | #NO MATCH | #NO MATCH | PF.184 | 9000031 |  | PF.184 | DELETED | 100% |  |  | 2025-08-15 |  | 2025-10-05 | -26
[5 empty] | 9000031 | 185 | 320001TUR | Stephen Yee | LEVEL 1 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 9 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-05 | 2025-08-28 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4.7684 | 0.29803 | 1 | 2 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-14 | DATES MISALIGNED | 2025-08-25 |  |  | Image 2025-09-22 08-57-43.jpeg |  | 8 | Kerri Pandolfi | 185 | 25 |  | 0.44444 | 4 | 0.52983 | 4.7684 |  | 0 | 0.52983 | -0.52983 | 0.44444 | -0.085383 | 25 | 185-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 114 | INSTALL - LEVEL 1 - D&B HR JB | PF.185 | 9000031 |  | PF.185 | PF.185 | 99% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000031 | 186 | 320001TUR | Stephen Yee | LEVEL 2 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 8 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 4.2386 | 0.26491 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | DATES MISALIGNED | 2025-09-10 | [5 empty] | Kerri Pandolfi | 186 | 25 |  | 0 | 0 | 0.52983 | 4.2386 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 186-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 163 | LEVEL 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.186 | 9000031 |  | PF.186 | PF.186 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000031 | 187 | 320001TUR | Stephen Yee | LEVEL 3 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 3 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-14 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-10-21 | 2025-10-22 | 2025-10-24 |  | 2025-10-24 |  | 2025-10-24 | TRUE |  | X |  |  | Kerri Pandolfi | 187 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 187-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 321 | INSTALL - LEVEL 3 - D&B HR JB | PF.187 | 9000031 |  | PF.187 | DELETED | 100% |  |  | 2025-10-07 |  | 2025-10-05 | 13
[5 empty] | 9000031 | 188 | 320001TUR | Stephen Yee | LEVEL 4 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 4 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-21 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-10-28 | 2025-10-29 | 2025-10-31 |  | 2025-10-31 |  | 2025-10-31 | TRUE |  | X |  |  | Kerri Pandolfi | 188 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 188-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 365 | INSTALL - LEVEL 4 - D&B HR JB | PF.188 | 9000031 |  | PF.188 | DELETED | 100% |  |  | 2025-10-14 |  | 2025-10-05 | 18
[5 empty] | 9000031 | 189 | 320001TUR | Stephen Yee | LEVEL 5 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 5 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-28 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-11-04 | 2025-11-05 | 2025-11-07 |  | 2025-11-07 |  | 2025-11-07 | TRUE |  | X |  |  | Kerri Pandolfi | 189 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 189-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 398 | INSTALL - LEVEL 5 - D&B HR JB | PF.189 | 9000031 |  | PF.189 | DELETED | 100% |  |  | 2025-10-21 |  | 2025-10-05 | 23
[5 empty] | 9000031 | 190 | 320001TUR | Stephen Yee | LEVEL 6 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 6 LEVEL 6 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 8 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-12 | [7 empty] | 4.2386 | 0.26491 | 1 | 2 | 2025-09-19 | 2025-09-22 | 2025-09-24 |  | 2025-09-24 |  | 2025-11-14 | TRUE |  | x |  |  | Kerri Pandolfi | 190 | 25 |  | 0 | 0 | 0.52983 | 4.2386 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 190-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 425 | INSTALL - LEVEL 6 - D&B HR JB | PF.190 | 9000031 |  | PF.190 | DELETED | 100% |  |  | 2025-09-05 |  | 2025-10-05 | -11
[5 empty] | 9000031 | 191 | 320001TUR | Stephen Yee | LEVEL 7 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 7 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-11 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-11-18 | 2025-11-19 | 2025-11-21 |  | 2025-11-21 |  | 2025-11-21 | [5 empty] | Kerri Pandolfi | 191 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 191-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 473 | INSTALL - LEVEL 7 - D&B HR JB | PF.191 | 9000031 |  | PF.191 | PF.191 | 0% |  |  | 2025-11-04 |  | 2025-10-05 | 33
[5 empty] | 9000031 | 192 | 320001TUR | Stephen Yee | LEVEL 8 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 8 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-21 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-11-28 | 2025-11-29 | 2025-12-01 |  | 2025-12-01 |  | 2025-12-01 | [5 empty] | Kerri Pandolfi | 192 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 192-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 510 | INSTALL - LEVEL 8 - D&B HR JB | PF.192 | 9000031 |  | PF.192 | PF.192 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[5 empty] | 9000031 | 193 | 320001TUR | Stephen Yee | LEVEL 9 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 9 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-28 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-12-05 | 2025-12-06 | 2025-12-08 |  | 2025-12-08 |  | 2025-12-08 | [5 empty] | Kerri Pandolfi | 193 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 193-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 550 | INSTALL - LEVEL 9 - D&B HR JB | PF.193 | 9000031 |  | PF.193 | PF.193 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[5 empty] | 9000031 | 194 | 320001TUR | Stephen Yee | LEVEL 10 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 10 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 |  | 2025-12-15 | [5 empty] | Kerri Pandolfi | 194 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 194-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 584 | INSTALL - LEVEL 10 - D&B HR JB | PF.194 | 9000031 |  | PF.194 | PF.194 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000031 | 195 | 320001TUR | Stephen Yee | LEVEL 11 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 11 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-12 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-12-19 | 2025-12-20 | 2025-12-22 |  | 2025-12-22 |  | 2025-12-22 | [5 empty] | Kerri Pandolfi | 195 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 195-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 624 | INSTALL - LEVEL 11 - D&B HR JB | PF.195 | 9000031 |  | PF.195 | PF.195 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[5 empty] | 9000031 | 196 | 320001TUR | Stephen Yee | LEVEL 12 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 12 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-19 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2025-12-26 | 2025-12-28 | 2025-12-30 |  | 2025-12-30 |  | 2025-12-30 | [5 empty] | Kerri Pandolfi | 196 | 25 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 25 | 196-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 667 | INSTALL - LEVEL 12 - D&B HR JB | PF.196 | 9000031 |  | PF.196 | PF.196 | 0% |  |  | 2025-12-12 |  | 2025-10-05 | 61
[5 empty] | 9000031 | 197 | 320001TUR | Stephen Yee | LEVEL 13 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 13 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-26 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-01-02 | 2026-01-05 | 2026-01-07 |  | 2026-01-07 |  | 2026-01-07 | [5 empty] | Kerri Pandolfi | 197 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 197-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 709 | INSTALL - LEVEL 13 - D&B HR JB | PF.197 | 9000031 |  | PF.197 | PF.197 | 0% |  |  | 2025-12-19 |  | 2025-10-05 | 66
[5 empty] | 9000031 | 198 | 320001TUR | Stephen Yee | LEVEL 14 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 14 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-01-09 | 2026-01-12 | 2026-01-14 |  | 2026-01-14 |  | 2026-01-14 | [5 empty] | Kerri Pandolfi | 198 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 198-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 764 | INSTALL - LEVEL 14 - D&B HR JB | PF.198 | 9000031 |  | PF.198 | PF.198 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[5 empty] | 9000031 | 199 | 320001TUR | Stephen Yee | LEVEL 15 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 15 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-12 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-01-19 | 2026-01-20 | 2026-01-22 |  | 2026-01-22 |  | 2026-01-22 | [5 empty] | Kerri Pandolfi | 199 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 199-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 814 | INSTALL - LEVEL 15 - D&B HR JB | PF.199 | 9000031 |  | PF.199 | PF.199 | 0% |  |  | 2026-01-05 |  | 2025-10-05 | 77
[5 empty] | 9000031 | 200 | 320001TUR | Stephen Yee | LEVEL 16 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 16 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-19 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-01-26 | 2026-01-27 | 2026-01-29 |  | 2026-01-29 |  | 2026-01-29 | [5 empty] | Kerri Pandolfi | 200 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 200-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 866 | INSTALL - LEVEL 16 - D&B HR JB | PF.200 | 9000031 |  | PF.200 | PF.200 | 0% |  |  | 2026-01-12 |  | 2025-10-05 | 82
[5 empty] | 9000031 | 201 | 320001TUR | Stephen Yee | LEVEL 17 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 17 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-26 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-02-02 | 2026-02-03 | 2026-02-05 |  | 2026-02-05 |  | 2026-02-05 | [5 empty] | Kerri Pandolfi | 201 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 201-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 913 | INSTALL - LEVEL 17 - D&B HR JB | PF.201 | 9000031 |  | PF.201 | PF.201 | 0% |  |  | 2026-01-19 |  | 2025-10-05 | 87
[5 empty] | 9000031 | 202 | 320001TUR | Stephen Yee | LEVEL 18 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 18 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-02 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-02-09 | 2026-02-10 | 2026-02-12 |  | 2026-02-12 |  | 2026-02-12 | [5 empty] | Kerri Pandolfi | 202 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 202-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 955 | INSTALL - LEVEL 18 - D&B HR JB | PF.202 | 9000031 |  | PF.202 | PF.202 | 0% |  |  | 2026-01-26 |  | 2025-10-05 | 92
[5 empty] | 9000031 | 203 | 320001TUR | Stephen Yee | LEVEL 19 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 19 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-10 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-02-17 | 2026-02-18 | 2026-02-20 |  | 2026-02-20 |  | 2026-02-20 | [5 empty] | Kerri Pandolfi | 203 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 203-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1000 | INSTALL - LEVEL 19 - D&B HR JB | PF.203 | 9000031 |  | PF.203 | PF.203 | 0% |  |  | 2026-02-03 |  | 2025-10-05 | 98
[5 empty] | 9000031 | 204 | 320001TUR | Stephen Yee | LEVEL 20 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 20 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-17 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-02-24 | 2026-02-25 | 2026-02-27 |  | 2026-02-27 |  | 2026-02-27 | [5 empty] | Kerri Pandolfi | 204 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 204-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1040 | INSTALL - LEVEL 20 - D&B HR JB | PF.204 | 9000031 |  | PF.204 | PF.204 | 0% |  |  | 2026-02-10 |  | 2025-10-05 | 103
[5 empty] | 9000031 | 205 | 320001TUR | Stephen Yee | LEVEL 21 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 21 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-24 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-03 | 2026-03-04 | 2026-03-06 |  | 2026-03-06 |  | 2026-03-06 | [5 empty] | Kerri Pandolfi | 205 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 205-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1085 | INSTALL - LEVEL 21 - D&B HR JB | PF.205 | 9000031 |  | PF.205 | PF.205 | 0% |  |  | 2026-02-17 |  | 2025-10-05 | 108
[5 empty] | 9000031 | 206 | 320001TUR | Stephen Yee | LEVEL 22 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 22 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-03 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-10 | 2026-03-11 | 2026-03-13 |  | 2026-03-13 |  | 2026-03-13 | [5 empty] | Kerri Pandolfi | 206 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 206-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1133 | INSTALL - LEVEL 22 - D&B HR JB | PF.206 | 9000031 |  | PF.206 | PF.206 | 0% |  |  | 2026-02-24 |  | 2025-10-05 | 113
[5 empty] | 9000031 | 207 | 320001TUR | Stephen Yee | LEVEL 23 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 23 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-10 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-17 | 2026-03-18 | 2026-03-20 |  | 2026-03-20 |  | 2026-03-20 | [5 empty] | Kerri Pandolfi | 207 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 207-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1174 | INSTALL - LEVEL 23 - D&B HR JB | PF.207 | 9000031 |  | PF.207 | PF.207 | 0% |  |  | 2026-03-03 |  | 2025-10-05 | 118
[5 empty] | 9000031 | 208 | 320001TUR | Stephen Yee | LEVEL 24 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 24 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-17 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-24 | 2026-03-25 | 2026-03-27 |  | 2026-03-27 |  | 2026-03-27 | [5 empty] | Kerri Pandolfi | 208 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 208-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1221 | INSTALL - LEVEL 24 - D&B HR JB | PF.208 | 9000031 |  | PF.208 | PF.208 | 0% |  |  | 2026-03-10 |  | 2025-10-05 | 123
[5 empty] | 9000031 | 209 | 320001TUR | Stephen Yee | LEVEL 25 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 25 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-03-24 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-03-31 | 2026-04-01 | 2026-04-03 |  | 2026-04-03 |  | 2026-04-03 | [5 empty] | Kerri Pandolfi | 209 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 209-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1261 | INSTALL - LEVEL 25 - D&B HR JB | PF.209 | 9000031 |  | PF.209 | PF.209 | 0% |  |  | 2026-03-17 |  | 2025-10-05 | 128
[5 empty] | 9000031 | 210 | 320001TUR | Stephen Yee | LEVEL 26 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 26 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-03-31 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-04-07 | 2026-04-08 | 2026-04-10 |  | 2026-04-10 |  | 2026-04-10 | [5 empty] | Kerri Pandolfi | 210 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 210-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1302 | INSTALL - LEVEL 26 - D&B HR JB | PF.210 | 9000031 |  | PF.210 | PF.210 | 0% |  |  | 2026-03-24 |  | 2025-10-05 | 133
[5 empty] | 9000031 | 211 | 320001TUR | Stephen Yee | LEVEL 27 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 27 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-04-07 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-04-14 | 2026-04-15 | 2026-04-17 |  | 2026-04-17 |  | 2026-04-17 | [5 empty] | Kerri Pandolfi | 211 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 211-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1346 | INSTALL - LEVEL 27 - D&B HR JB | PF.211 | 9000031 |  | PF.211 | PF.211 | 0% |  |  | 2026-03-31 |  | 2025-10-05 | 138
[5 empty] | 9000031 | 212 | 320001TUR | Stephen Yee | LEVEL 28 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 28 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-04-17 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-04-24 | 2026-04-25 | 2026-04-27 |  | 2026-04-27 |  | 2026-04-27 | [5 empty] | Kerri Pandolfi | 212 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 212-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1383 | INSTALL - LEVEL 28 - D&B HR JB | PF.212 | 9000031 |  | PF.212 | PF.212 | 0% |  |  | 2026-04-10 |  | 2025-10-05 | 146
[5 empty] | 9000031 | 213 | 320001TUR | Stephen Yee | LEVEL 29 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 29 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-04-24 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-01 | 2026-05-02 | 2026-05-04 |  | 2026-05-04 |  | 2026-05-04 | [5 empty] | Kerri Pandolfi | 213 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 213-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1425 | INSTALL - LEVEL 29 - D&B HR JB | PF.213 | 9000031 |  | PF.213 | PF.213 | 0% |  |  | 2026-04-17 |  | 2025-10-05 | 151
[5 empty] | 9000031 | 214 | 320001TUR | Stephen Yee | LEVEL 30 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 30 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-01 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-08 | 2026-05-09 | 2026-05-11 |  | 2026-05-11 |  | 2026-05-11 | [5 empty] | Kerri Pandolfi | 214 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 214-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1463 | INSTALL - LEVEL 30 - D&B HR JB | PF.214 | 9000031 |  | PF.214 | PF.214 | 0% |  |  | 2026-04-24 |  | 2025-10-05 | 156
[5 empty] | 9000031 | 215 | 320001TUR | Stephen Yee | LEVEL 31 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 31 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-08 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-15 | 2026-05-16 | 2026-05-18 |  | 2026-05-18 |  | 2026-05-18 | [5 empty] | Kerri Pandolfi | 215 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 215-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1505 | INSTALL - LEVEL 31 - D&B HR JB | PF.215 | 9000031 |  | PF.215 | PF.215 | 0% |  |  | 2026-05-01 |  | 2025-10-05 | 161
[5 empty] | 9000031 | 216 | 320001TUR | Stephen Yee | LEVEL 32 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 32 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-15 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-22 | 2026-05-24 | 2026-05-26 |  | 2026-05-26 |  | 2026-05-26 | [5 empty] | Kerri Pandolfi | 216 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 216-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1546 | INSTALL - LEVEL 32 - D&B HR JB | PF.216 | 9000031 |  | PF.216 | PF.216 | 0% |  |  | 2026-05-08 |  | 2025-10-05 | 166
[5 empty] | 9000031 | 217 | 320001TUR | Stephen Yee | LEVEL 33 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 33 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-22 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-05-29 | 2026-05-31 | 2026-06-02 |  | 2026-06-02 |  | 2026-06-02 | [5 empty] | Kerri Pandolfi | 217 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 217-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1572 | INSTALL - LEVEL 33 - D&B HR JB | PF.217 | 9000031 |  | PF.217 | PF.217 | 0% |  |  | 2026-05-15 |  | 2025-10-05 | 171
[5 empty] | 9000031 | 218 | 320001TUR | Stephen Yee | LEVEL 34 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 34 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-29 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-06-05 | 2026-06-07 | 2026-06-09 |  | 2026-06-09 |  | 2026-06-09 | [5 empty] | Kerri Pandolfi | 218 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 218-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1609 | INSTALL - LEVEL 34 - D&B HR JB | PF.218 | 9000031 |  | PF.218 | PF.218 | 0% |  |  | 2026-05-22 |  | 2025-10-05 | 176
[5 empty] | 9000031 | 219 | 320001TUR | Stephen Yee | LEVEL 35 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 35 - TIER 3 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-06-05 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-06-12 | 2026-06-14 | 2026-06-16 |  | 2026-06-16 |  | 2026-06-16 | [5 empty] | Kerri Pandolfi | 219 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 219-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1642 | INSTALL - LEVEL 35 - D&B HR JB | PF.219 | 9000031 |  | PF.219 | PF.219 | 0% |  |  | 2026-05-29 |  | 2025-10-05 | 181
[5 empty] | 9000031 | 220 | 320001TUR | Stephen Yee | LEVEL 36 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 36 - TIER 3 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-06-12 | [7 empty] | 1.0597 | 0.066228 | 1 | 2 | 2026-06-19 | 2026-06-22 | 2026-06-24 |  | 2026-06-24 |  | 2026-06-24 | [5 empty] | Kerri Pandolfi | 220 | 26 |  | 0 | 0 | 0.52983 | 1.0597 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 220-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1682 | INSTALL - LEVEL 36 - D&B HR JB | PF.220 | 9000031 |  | PF.220 | PF.220 | 0% |  |  | 2026-06-05 |  | 2025-10-05 | 186
[5 empty] | 9000031 | 221 | 320001TUR | Stephen Yee | LEVEL 37 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 37 - AMENITY/MEP PH JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 15 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-15 | [7 empty] | 7.9474 | 0.49671 | 1 | 2 | 2026-05-22 | 2026-05-24 | 2026-05-26 |  | 2026-07-07 |  | 2026-07-01 | [5 empty] | Kerri Pandolfi | 221 | 26 |  | 0 | 0 | 0.52983 | 7.9474 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 221-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1710 | INSTALL - LEVEL 37 - D&B HR JB | PF.221 | 9000031 |  | PF.221 | PF.221 | 0% |  |  | 2026-05-08 |  | 2025-10-05 | 166
[5 empty] | 9000031 | 222 | 320001TUR | Stephen Yee | LEVEL 38 | JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | LEVEL 38 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 8 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-22 | [7 empty] | 4.2386 | 0.26491 | 1 | 2 | 2026-05-29 | 2026-05-31 | 2026-06-02 |  | 2026-07-07 |  | 2026-07-01 | [5 empty] | Kerri Pandolfi | 222 | 26 |  | 0 | 0 | 0.52983 | 4.2386 |  | 0 | 0.52983 | -0.52983 | 0 | -0.52983 | 26 | 222-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | 1711 | INSTALL - LEVEL 38 - D&B HR JB | PF.222 | 9000031 |  | PF.222 | PF.222 | 0% |  |  | 2026-05-15 |  | 2025-10-05 | 171
[5 empty] | 9000051 | 223 | 320001TUR | Stephen Yee | LEVEL B1 | HANGER STRUT (POWER) | LEVEL B1 HANGER STRUT (POWER) | 50 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | #INVALID OPERATION | [7 empty] | 13.701 | 1.7126 | 2 | 1 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 223 | #INVALID VALUE |  | 0 | 0 | 0.27402 | 13.701 | 1.08 | 54 | 0.27402 | 0.80598 | 0 | -0.27402 | LE | 223-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 HANGER STRUT (POWER) | #NO MATCH | #NO MATCH | PF.223 | 9000051 |  | PF.223 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[5 empty] | 9000051 | 224 | 320001TUR | Stephen Yee | LEVEL 1 | HANGER STRUT (POWER) | LEVEL 1 HANGER STRUT (POWER) | 50 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-03-21 | [7 empty] | 13.701 | 1.7126 | 2 | 1 | 2025-03-28 | 2025-04-01 | 2025-04-03 |  | 2025-04-03 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 224 | 25 |  | 0 | 0 | 0.27402 | 13.701 | 1.08 | 54 | 0.27402 | 0.80598 | 0 | -0.27402 | 25 | 224-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 HANGER STRUT (POWER) | #NO MATCH | #NO MATCH | PF.224 | 9000051 |  | PF.224 | DELETED | 100% |  |  | 2025-03-14 |  | 2025-10-05 | -136
[5 empty] | 9000051 | 225 | 320001TUR | Stephen Yee | LEVEL 2 | HANGER STRUT (POWER) | LEVEL 2 HANGER STRUT (POWER) | 88 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez, Steve D'Entremont | 2025-09-02 | 2025-09-09 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 24.1137 | 3.0142 | 4 | 1 | 2025-09-09 | 2025-09-13 | 2025-09-15 |  | 2025-09-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-09-16 12-35-27.jpeg | YES | 3 | Kerri Pandolfi | 225 | 25 |  | 0.80682 | 71 | 0.27402 | 24.1137 | 1.08 | 95.04 | 0.27402 | 0.80598 | 0.27402 | 0 | 25 | 225-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 HANGER STRUT (POWER) | #NO MATCH | #NO MATCH | PF.225 | 9000051 |  | PF.225 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-08-26 |  | 2025-10-05 | -19 | TRUE
[5 empty] | 9000051 | 226 | 320001TUR | Stephen Yee | LEVEL 6 | HANGER STRUT (POWER) | LEVEL 6 HANGER STRUT (POWER) - WEST SIDE | 50 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-07-17 | 2025-07-30 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 13.701 | 1.7126 | 2 | 1 | 2025-07-24 | 2025-07-28 | 2025-07-30 |  | 2025-08-04 |  | 2025-05-19 | TRUE |  | Image 2025-08-01 08-26-35.jpeg |  | 9 | Kerri Pandolfi | 226 | 25 |  | 0.3 | 15 | 0.27402 | 13.701 | 1.08 | 54 | 0.27402 | 0.80598 | 0.27402 | 0 | 25 | 226-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 HANGER STRUT (POWER) - WEST SIDE | 8 | INSTALL - LEVEL 6 - CONDUIT HANGERS | PF.226 | 9000051 |  | PF.226 | PF.226 | 100% | TRUE |  | 2025-07-10 |  | 2025-10-05 | -52 | TRUE
[5 empty] | 9000051 | 227 | 320001TUR | Stephen Yee | LEVEL 36 | HANGER STRUT (POWER) | LEVEL 36 - TIER 3 HANGER STRUT (POWER) | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-11-28 | [7 empty] | 2.7402 | 0.34252 | 1 | 1 | 2025-12-05 | 2025-12-07 | 2025-12-09 |  | 2025-12-09 | DATES MISALIGNED | 2026-01-09 | [5 empty] | Kerri Pandolfi | 227 | 25 |  | 0 | 0 | 0.27402 | 2.7402 | 1.08 | 10.8 | 0.27402 | 0.80598 | 0 | -0.27402 | 25 | 227-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 HANGER STRUT (POWER) | 718 | INSTALL - LEVEL 36 - CONDUIT HANGERS | PF.227 | 9000051 |  | PF.227 | PF.227 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[5 empty] | 9000051 | 228 | 320001TUR | Stephen Yee | LEVEL 37 | HANGER STRUT (POWER) | LEVEL 37 - AMENITY/MEP PH HANGER STRUT (POWER) | 150 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-09 | [7 empty] | 41.1029 | 5.1379 | 6 | 1 | 2025-12-16 | 2025-12-24 | 2025-12-26 |  | 2025-12-26 | DATES MISALIGNED | 2026-01-15 | [5 empty] | Kerri Pandolfi | 228 | 25 |  | 0 | 0 | 0.27402 | 41.1029 | 1.08 | 162 | 0.27402 | 0.80598 | 0 | -0.27402 | 25 | 228-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH HANGER STRUT (POWER) | 713 | INSTALL - LEVEL 37 - CONDUIT HANGERS | PF.228 | 9000051 |  | PF.228 | PF.228 | 0% |  |  | 2025-12-02 |  | 2025-10-05 | 53
[5 empty] | 9000051 | 229 | 320001TUR | Stephen Yee | LEVEL 38 | HANGER STRUT (POWER) | LEVEL 38 HANGER STRUT (POWER) | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-30 | [7 empty] | 2.7402 | 0.34252 | 1 | 1 | 2026-01-06 | 2026-01-07 | 2026-01-09 |  | 2026-01-09 | DATES MISALIGNED | 2026-01-22 | [5 empty] | Kerri Pandolfi | 229 | 26 |  | 0 | 0 | 0.27402 | 2.7402 | 1.08 | 10.8 | 0.27402 | 0.80598 | 0 | -0.27402 | 26 | 229-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 HANGER STRUT (POWER) | 813 | INSTALL - LEVEL 38 - CONDUIT HANGERS | PF.229 | 9000051 |  | PF.229 | PF.229 | 0% |  |  | 2025-12-23 |  | 2025-10-05 | 68
[5 empty] | 9000050 | 230 | 320001TUR | Stephen Yee | LEVEL B1 | PIPE BENDS (LARGE) POWER | LEVEL B1 PIPE BENDS (LARGE) POWER | 15 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | #INVALID OPERATION | [7 empty] | 12.3549 | 1.5444 | 2 | 1 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 230 | #INVALID VALUE |  | 0 | 0 | 0.82366 | 12.3549 | 0.72 | 10.8 | 0.72 | 0 | 0 | -0.82366 | LE | 230-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 PIPE BENDS (LARGE) POWER | #NO MATCH | #NO MATCH | PF.230 | 9000050 |  | PF.230 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[5 empty] | 9000050 | 231 | 320001TUR | Stephen Yee | LEVEL 1 | PIPE BENDS (LARGE) POWER | LEVEL 1 PIPE BENDS (LARGE) POWER | 15 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-03-28 | [7 empty] | 12.3549 | 1.5444 | 2 | 1 | 2025-04-04 | 2025-04-08 | 2025-04-10 |  | 2025-04-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 231 | 25 |  | 0 | 0 | 0.82366 | 12.3549 | 0.72 | 10.8 | 0.72 | 0 | 0 | -0.82366 | 25 | 231-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 PIPE BENDS (LARGE) POWER | #NO MATCH | #NO MATCH | PF.231 | 9000050 |  | PF.231 | DELETED | 100% |  |  | 2025-03-21 |  | 2025-10-05 | -131
[5 empty] | 9000050 | 232 | 320001TUR | Stephen Yee | LEVEL 2 | PIPE BENDS (LARGE) POWER | LEVEL 2 PIPE BENDS (LARGE) POWER | 30 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-04-08 | [7 empty] | 24.7098 | 3.0887 | 4 | 1 | 2025-04-15 | 2025-04-20 | 2025-04-22 |  | 2025-04-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 232 | 25 |  | 0 | 0 | 0.82366 | 24.7098 | 0.72 | 21.6 | 0.72 | 0 | 0 | -0.82366 | 25 | 232-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 PIPE BENDS (LARGE) POWER | #NO MATCH | #NO MATCH | PF.232 | 9000050 |  | PF.232 | DELETED | 100% |  |  | 2025-04-01 |  | 2025-10-05 | -124
[5 empty] | 9000050 | 233 | 320001TUR | Stephen Yee | LEVEL 6 | PIPE BENDS (LARGE) POWER | LEVEL 6 LEVEL 6 PIPE BENDS (LARGE) POWER | 30 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-05-13 |  |  |  |  | TRUE | True |  | 24.7098 | 3.0887 | 4 | 1 | 2025-05-20 | 2025-05-26 | 2025-05-28 |  | 2025-05-28 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 233 | 25 |  | 0 | 0 | 0.82366 | 24.7098 | 0.72 | 21.6 | 0.72 | 0 | 0 | -0.82366 | 25 | 233-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 PIPE BENDS (LARGE) POWER | #NO MATCH | #NO MATCH | PF.233 | 9000050 |  | PF.233 | DELETED | 100% |  |  | 2025-05-06 |  | 2025-10-05 | -99
[5 empty] | 9000050 | 234 | 320001TUR | Stephen Yee | LEVEL 36 | PIPE BENDS (LARGE) POWER | LEVEL 36 - TIER 3 PIPE BENDS (LARGE) POWER | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-05 | [7 empty] | 2.471 | 0.30887 | 1 | 1 | 2025-12-12 | 2025-12-15 | 2025-12-17 |  | 2025-12-17 | DATES MISALIGNED | 2026-01-13 | [5 empty] | Kerri Pandolfi | 234 | 25 |  | 0 | 0 | 0.82366 | 2.471 | 0.72 | 2.16 | 0.72 | 0 | 0 | -0.82366 | 25 | 234-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 PIPE BENDS (LARGE) POWER | 732 | INSTALL - LEVEL 36 - CONDUIT BENDS | PF.234 | 9000050 |  | PF.234 | PF.234 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000050 | 235 | 320001TUR | Stephen Yee | LEVEL 37 | PIPE BENDS (LARGE) POWER | LEVEL 37 - AMENITY/MEP PH PIPE BENDS (LARGE) POWER | 45 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-22 | [7 empty] | 37.0647 | 4.6331 | 5 | 1 | 2025-12-29 | 2026-01-04 | 2026-01-06 |  | 2026-01-06 | DATES MISALIGNED | 2026-01-20 | [5 empty] | Kerri Pandolfi | 235 | 26 |  | 0 | 0 | 0.82366 | 37.0647 | 0.72 | 32.4 | 0.72 | 0 | 0 | -0.82366 | 26 | 235-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH PIPE BENDS (LARGE) POWER | 728 | INSTALL - LEVEL 37 - CONDUIT BENDS | PF.235 | 9000050 |  | PF.235 | PF.235 | 0% |  |  | 2025-12-15 |  | 2025-10-05 | 62
[5 empty] | 9000050 | 236 | 320001TUR | Stephen Yee | LEVEL 38 | PIPE BENDS (LARGE) POWER | LEVEL 38 PIPE BENDS (LARGE) POWER | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2026-01-09 | [7 empty] | 2.471 | 0.30887 | 1 | 1 | 2026-01-16 | 2026-01-18 | 2026-01-20 |  | 2026-01-20 |  | 2026-01-26 | [5 empty] | Kerri Pandolfi | 236 | 26 |  | 0 | 0 | 0.82366 | 2.471 | 0.72 | 2.16 | 0.72 | 0 | 0 | -0.82366 | 26 | 236-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 PIPE BENDS (LARGE) POWER | 827 | INSTALL - LEVEL 38 - CONDUIT BENDS | PF.236 | 9000050 |  | PF.236 | PF.236 | 0% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[5 empty] | 9000052 | 237 | 320001TUR | Stephen Yee | LEVEL B1 | MODULAR EMT (5) LARGE | LEVEL B1 MODULAR EMT (5) LARGE | 2 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | #INVALID OPERATION | [7 empty] | 5.34 | 0.6675 | 1 | 1 | #INVALID OPERATION | #INVALID OPERATION | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 237 | #INVALID VALUE |  | 0 | 0 | 2.67 | 5.34 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | LE | 237-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 MODULAR EMT (5) LARGE | #NO MATCH | #NO MATCH | PF.237 | 9000052 |  | PF.237 | DELETED | 100% |  |  | #INVALID OPERATION |  | 2025-10-05 | #INVALID OPERATION
[5 empty] | 9000052 | 238 | 320001TUR | Stephen Yee | LEVEL 1 | MODULAR EMT (5) LARGE | LEVEL 1 MODULAR EMT (5) LARGE | 10 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-03-26 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2025-04-02 | 2025-04-08 | 2025-04-10 |  | 2025-04-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 238 | 25 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 25 | 238-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 MODULAR EMT (5) LARGE | #NO MATCH | #NO MATCH | PF.238 | 9000052 |  | PF.238 | DELETED | 100% |  |  | 2025-03-19 |  | 2025-10-05 | -133
[5 empty] | 9000052 | 239 | 320001TUR | Stephen Yee | LEVEL 35 | MODULAR EMT (5) LARGE | LEVEL 35 - TIER 3 - MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-11-19 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2025-11-26 | 2025-12-02 | 2025-12-04 |  | 2025-12-04 | DATES MISALIGNED | 2026-01-02 | [5 empty] | Kerri Pandolfi | 239 | 25 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 25 | 239-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 - MODULAR EMT (5) LARGE | 639 | INSTALL - LEVEL 35 - CONDUIT MODULES | PF.239 | 9000052 |  | PF.239 | PF.239 | 0% |  |  | 2025-11-12 |  | 2025-10-05 | 39
[5 empty] | 9000052 | 240 | 320001TUR | Stephen Yee | LEVEL 36 | MODULAR EMT (5) LARGE | LEVEL 36 - TIER 3 - MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-02 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2025-12-09 | 2025-12-15 | 2025-12-17 |  | 2025-12-17 | DATES MISALIGNED | 2026-01-15 | [5 empty] | Kerri Pandolfi | 240 | 25 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 25 | 240-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 - MODULAR EMT (5) LARGE | 726 | INSTALL - LEVEL 36 - CONDUIT MODULES | PF.240 | 9000052 |  | PF.240 | PF.240 | 0% |  |  | 2025-11-25 |  | 2025-10-05 | 48
[5 empty] | 9000052 | 241 | 320001TUR | Stephen Yee | LEVEL 37 | MODULAR EMT (5) LARGE | LEVEL 37 - AMENITY/MEP PH - MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-23 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2025-12-30 | 2026-01-04 | 2026-01-06 |  | 2026-01-06 | DATES MISALIGNED | 2026-01-22 | [5 empty] | Kerri Pandolfi | 241 | 26 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 26 | 241-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - MODULAR EMT (5) LARGE | 773 | INSTALL - LEVEL 37 - CONDUIT MODULES | PF.241 | 9000052 |  | PF.241 | PF.241 | 0% |  |  | 2025-12-16 |  | 2025-10-05 | 63
[5 empty] | 9000052 | 242 | 320001TUR | Stephen Yee | LEVEL 38 | MODULAR EMT (5) LARGE | LEVEL 38 MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-25 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2026-01-01 | 2026-01-07 | 2026-01-09 |  | 2026-01-20 | DATES MISALIGNED | 2026-01-28 | [5 empty] | Kerri Pandolfi | 242 | 26 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 26 | 242-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 MODULAR EMT (5) LARGE | 821 | INSTALL - LEVEL 38 - CONDUIT MODULES | PF.242 | 9000052 |  | PF.242 | PF.242 | 0% |  |  | 2025-12-18 |  | 2025-10-05 | 65
[5 empty] | 9000052 | 243 | 320001TUR | Stephen Yee | LEVEL 39 | MODULAR EMT (5) LARGE | LEVEL 39 MODULAR EMT (5) LARGE | 10 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2025-12-31 | [7 empty] | 26.7 | 3.3375 | 4 | 1 | 2026-01-07 | 2026-01-13 | 2026-01-15 |  | 2026-01-21 |  | 2026-01-27 | [5 empty] | Kerri Pandolfi | 243 | 26 |  | 0 | 0 | 2.67 | 26.7 |  | 0 | 2.67 | -2.67 | 0 | -2.67 | 26 | 243-320001TUR | PRE-FAB - LEVEL 39 - LEVEL 39 MODULAR EMT (5) LARGE | 811 | INSTALL - LEVEL 39 - CONDUIT MODULES | PF.243 | 9000052 |  | PF.243 | PF.243 | 0% |  |  | 2025-12-24 |  | 2025-10-05 | 69
[5 empty] | 9000054 | 244 | 320001TUR | Stephen Yee | LEVEL B1 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL B1 RISER (STICK BUILD) (POWER) (PLACEHOLDER) |  | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-14 | [7 empty] | 0 | 0 | 0 | 1 | 2026-03-21 | 2026-03-21 | 2026-03-23 |  | 2026-03-23 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 244 | 26 |  | #DIVIDE BY ZERO | 0 | 2.225 | 0 |  | 0 | 2.225 | -2.225 | #DIVIDE BY ZERO | #DIVIDE BY ZERO | 26 | 244-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.244 | 9000054 |  | PF.244 | DELETED | 100% |  |  | 2026-03-07 |  | 2025-10-05 | 121
[5 empty] | 9000054 | 245 | 320001TUR | Stephen Yee | LEVEL 1 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 1 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-04 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 245 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 245-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.245 | 9000054 |  | PF.245 | DELETED | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[5 empty] | 9000054 | 246 | 320001TUR | Stephen Yee | LEVEL 2 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 2 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-12 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 246 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 246-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.246 | 9000054 |  | PF.246 | DELETED | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[5 empty] | 9000054 | 247 | 320001TUR | Stephen Yee | LEVEL 3 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 3 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-22 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-29 | 2025-08-31 | 2025-09-02 |  | 2025-09-02 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 247 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 247-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.247 | 9000054 |  | PF.247 | DELETED | 100% |  |  | 2025-08-15 |  | 2025-10-05 | -26
[5 empty] | 9000054 | 248 | 320001TUR | Stephen Yee | LEVEL 4 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 4 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-29 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-05 | 2025-09-08 | 2025-09-10 |  | 2025-09-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 248 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 248-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.248 | 9000054 |  | PF.248 | DELETED | 100% |  |  | 2025-08-22 |  | 2025-10-05 | -21
[5 empty] | 9000054 | 249 | 320001TUR | Stephen Yee | LEVEL 5 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 5 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-12 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 249 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 249-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.249 | 9000054 |  | PF.249 | DELETED | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[5 empty] | 9000054 | 250 | 320001TUR | Stephen Yee | LEVEL 6 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 6 LEVEL 6 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-22 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-08-29 | 2025-08-31 | 2025-09-02 |  | 2025-09-02 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 250 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 250-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.250 | 9000054 |  | PF.250 | DELETED | 100% |  |  | 2025-08-15 |  | 2025-10-05 | -26
[5 empty] | 9000054 | 251 | 320001TUR | Stephen Yee | LEVEL 7 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 7 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-29 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-05 | 2025-09-08 | 2025-09-10 |  | 2025-09-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 251 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 251-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.251 | 9000054 |  | PF.251 | DELETED | 100% |  |  | 2025-08-22 |  | 2025-10-05 | -21
[5 empty] | 9000054 | 252 | 320001TUR | Stephen Yee | LEVEL 8 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 8 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-08 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 252 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 252-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.252 | 9000054 |  | PF.252 | DELETED | 100% |  |  | 2025-09-01 |  | 2025-10-05 | -15
[5 empty] | 9000054 | 253 | 320001TUR | Stephen Yee | LEVEL 9 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 9 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-09 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-16 | 2025-09-17 | 2025-09-19 |  | 2025-09-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 253 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 253-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.253 | 9000054 |  | PF.253 | DELETED | 100% |  |  | 2025-09-02 |  | 2025-10-05 | -14
[5 empty] | 9000054 | 254 | 320001TUR | Stephen Yee | LEVEL 10 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 10 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-16 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-09-26 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 254 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 254-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.254 | 9000054 |  | PF.254 | DELETED | 100% |  |  | 2025-09-09 |  | 2025-10-05 | -9
[5 empty] | 9000054 | 255 | 320001TUR | Stephen Yee | LEVEL 11 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 11 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-23 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-09-30 | 2025-10-01 | 2025-10-03 |  | 2025-10-03 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 255 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 255-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.255 | 9000054 |  | PF.255 | DELETED | 100% |  |  | 2025-09-16 |  | 2025-10-05 | -4
[5 empty] | 9000054 | 256 | 320001TUR | Stephen Yee | LEVEL 12 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 12 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-30 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-10-07 | 2025-10-08 | 2025-10-10 |  | 2025-10-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 256 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 256-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.256 | 9000054 |  | PF.256 | DELETED | 100% |  |  | 2025-09-23 |  | 2025-10-05 | 3
[5 empty] | 9000054 | 257 | 320001TUR | Stephen Yee | LEVEL 13 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 13 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-07 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-10-14 | 2025-10-15 | 2025-10-17 |  | 2025-10-17 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 257 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 257-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.257 | 9000054 |  | PF.257 | DELETED | 100% |  |  | 2025-09-30 |  | 2025-10-05 | 8
[5 empty] | 9000054 | 258 | 320001TUR | Stephen Yee | LEVEL 14 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 14 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-14 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-10-21 | 2025-10-22 | 2025-10-24 |  | 2025-10-24 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 258 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 258-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.258 | 9000054 |  | PF.258 | DELETED | 100% |  |  | 2025-10-07 |  | 2025-10-05 | 13
[5 empty] | 9000054 | 259 | 320001TUR | Stephen Yee | LEVEL 15 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 15 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-10-31 | 2025-11-01 | 2025-11-03 |  | 2025-11-03 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 259 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 259-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.259 | 9000054 |  | PF.259 | DELETED | 100% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[5 empty] | 9000054 | 260 | 320001TUR | Stephen Yee | LEVEL 16 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 16 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 260 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 260-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.260 | 9000054 |  | PF.260 | DELETED | 100% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[5 empty] | 9000054 | 261 | 320001TUR | Stephen Yee | LEVEL 17 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 17 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-04 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-11-11 | 2025-11-12 | 2025-11-14 |  | 2025-11-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 261 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 261-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.261 | 9000054 |  | PF.261 | DELETED | 100% |  |  | 2025-10-28 |  | 2025-10-05 | 28
[5 empty] | 9000054 | 262 | 320001TUR | Stephen Yee | LEVEL 18 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 18 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-11 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-11-18 | 2025-11-19 | 2025-11-21 |  | 2025-11-21 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 262 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 262-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.262 | 9000054 |  | PF.262 | DELETED | 100% |  |  | 2025-11-04 |  | 2025-10-05 | 33
[5 empty] | 9000054 | 263 | 320001TUR | Stephen Yee | LEVEL 19 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 19 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-18 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-11-25 | 2025-11-26 | 2025-11-28 |  | 2025-11-28 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 263 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 263-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.263 | 9000054 |  | PF.263 | DELETED | 100% |  |  | 2025-11-11 |  | 2025-10-05 | 38
[5 empty] | 9000054 | 264 | 320001TUR | Stephen Yee | LEVEL 20 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 20 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-25 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-12-02 | 2025-12-03 | 2025-12-05 |  | 2025-12-05 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 264 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 264-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.264 | 9000054 |  | PF.264 | DELETED | 100% |  |  | 2025-11-18 |  | 2025-10-05 | 43
[5 empty] | 9000054 | 265 | 320001TUR | Stephen Yee | LEVEL 21 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 21 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-02 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-12-09 | 2025-12-10 | 2025-12-12 |  | 2025-12-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 265 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 265-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.265 | 9000054 |  | PF.265 | DELETED | 100% |  |  | 2025-11-25 |  | 2025-10-05 | 48
[5 empty] | 9000054 | 266 | 320001TUR | Stephen Yee | LEVEL 22 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 22 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-12 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-19 | 2026-01-20 | 2026-01-22 |  | 2026-01-22 |  | 2026-01-21 | TRUE |  | X |  |  | Kerri Pandolfi | 266 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 266-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 785 | INSTALL - LEVEL 22 - FEEDER RISERS | PF.266 | 9000054 |  | PF.266 | DELETED | 100% |  |  | 2026-01-05 |  | 2025-10-05 | 77
[5 empty] | 9000054 | 267 | 320001TUR | Stephen Yee | LEVEL 23 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 23 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-16 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-12-23 | 2025-12-24 | 2025-12-26 |  | 2025-12-26 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 267 | 25 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 25 | 267-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.267 | 9000054 |  | PF.267 | DELETED | 100% |  |  | 2025-12-09 |  | 2025-10-05 | 58
[5 empty] | 9000054 | 268 | 320001TUR | Stephen Yee | LEVEL 24 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 24 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-23 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2025-12-30 | 2025-12-31 | 2026-01-02 |  | 2026-01-02 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 268 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 268-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.268 | 9000054 |  | PF.268 | DELETED | 100% |  |  | 2025-12-16 |  | 2025-10-05 | 63
[5 empty] | 9000054 | 269 | 320001TUR | Stephen Yee | LEVEL 25 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 25 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-30 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-06 | 2026-01-07 | 2026-01-09 |  | 2026-01-09 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 269 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 269-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.269 | 9000054 |  | PF.269 | DELETED | 100% |  |  | 2025-12-23 |  | 2025-10-05 | 68
[5 empty] | 9000054 | 270 | 320001TUR | Stephen Yee | LEVEL 26 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 26 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-09 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-16 | 2026-01-18 | 2026-01-20 |  | 2026-01-20 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 270 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 270-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.270 | 9000054 |  | PF.270 | DELETED | 100% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[5 empty] | 9000054 | 271 | 320001TUR | Stephen Yee | LEVEL 27 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 27 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-16 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-23 | 2026-01-26 | 2026-01-28 |  | 2026-01-28 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 271 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 271-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.271 | 9000054 |  | PF.271 | DELETED | 100% |  |  | 2026-01-09 |  | 2025-10-05 | 81
[5 empty] | 9000054 | 272 | 320001TUR | Stephen Yee | LEVEL 28 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 28 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-20 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-01-27 | 2026-01-28 | 2026-01-30 |  | 2026-01-30 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 272 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 272-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.272 | 9000054 |  | PF.272 | DELETED | 100% |  |  | 2026-01-13 |  | 2025-10-05 | 83
[5 empty] | 9000054 | 273 | 320001TUR | Stephen Yee | LEVEL 29 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 29 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 273 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 273-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.273 | 9000054 |  | PF.273 | DELETED | 100% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[5 empty] | 9000054 | 274 | 320001TUR | Stephen Yee | LEVEL 30 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 30 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-03 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-02-10 | 2026-02-11 | 2026-02-13 |  | 2026-02-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 274 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 274-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.274 | 9000054 |  | PF.274 | DELETED | 100% |  |  | 2026-01-27 |  | 2025-10-05 | 93
[5 empty] | 9000054 | 275 | 320001TUR | Stephen Yee | LEVEL 31 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 31 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-10 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-02-17 | 2026-02-18 | 2026-02-20 |  | 2026-02-20 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 275 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 275-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.275 | 9000054 |  | PF.275 | DELETED | 100% |  |  | 2026-02-03 |  | 2025-10-05 | 98
[5 empty] | 9000054 | 276 | 320001TUR | Stephen Yee | LEVEL 32 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 32 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-17 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-02-24 | 2026-02-25 | 2026-02-27 |  | 2026-02-27 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 276 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 276-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.276 | 9000054 |  | PF.276 | DELETED | 100% |  |  | 2026-02-10 |  | 2025-10-05 | 103
[5 empty] | 9000054 | 277 | 320001TUR | Stephen Yee | LEVEL 33 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 33 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-24 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-03 | 2026-03-04 | 2026-03-06 |  | 2026-03-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 277 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 277-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.277 | 9000054 |  | PF.277 | DELETED | 100% |  |  | 2026-02-17 |  | 2025-10-05 | 108
[5 empty] | 9000054 | 278 | 320001TUR | Stephen Yee | LEVEL 34 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 34 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-03 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-10 | 2026-03-11 | 2026-03-13 |  | 2026-03-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 278 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 278-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.278 | 9000054 |  | PF.278 | DELETED | 100% |  |  | 2026-02-24 |  | 2025-10-05 | 113
[5 empty] | 9000054 | 279 | 320001TUR | Stephen Yee | LEVEL 35 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 35 - TIER 3 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-06 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-13 | 2026-03-14 | 2026-03-16 |  | 2026-03-16 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 279 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 279-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.279 | 9000054 |  | PF.279 | DELETED | 100% |  |  | 2026-02-27 |  | 2025-10-05 | 116
[5 empty] | 9000054 | 280 | 320001TUR | Stephen Yee | LEVEL 36 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 36 - TIER 3 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-06 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-13 | 2026-03-15 | 2026-03-17 |  | 2026-03-17 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 280 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 280-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.280 | 9000054 |  | PF.280 | DELETED | 100% |  |  | 2026-02-27 |  | 2025-10-05 | 116
[5 empty] | 9000054 | 281 | 320001TUR | Stephen Yee | LEVEL 37 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 37 - AMENITY/MEP PH - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-06 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-13 | 2026-03-16 | 2026-03-18 |  | 2026-03-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 281 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 281-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.281 | 9000054 |  | PF.281 | DELETED | 100% |  |  | 2026-02-27 |  | 2025-10-05 | 116
[5 empty] | 9000054 | 282 | 320001TUR | Stephen Yee | LEVEL 38 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 38 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-09 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-16 | 2026-03-17 | 2026-03-19 |  | 2026-03-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 282 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 282-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | #NO MATCH | #NO MATCH | PF.282 | 9000054 |  | PF.282 | DELETED | 100% |  |  | 2026-03-02 |  | 2025-10-05 | 117
[5 empty] | 9000054 | 283 | 320001TUR | Stephen Yee | LEVEL 39 | RISER (STICK BUILD) (POWER) (PLACEHOLDER) | LEVEL 39 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-10 | [7 empty] | 2.225 | 0.27813 | 1 | 1 | 2026-03-17 | 2026-03-18 | 2026-03-20 |  | 2026-03-20 |  |  | TRUE |  | X |  |  | Kerri Pandolfi | 283 | 26 |  | 0 | 0 | 2.225 | 2.225 |  | 0 | 2.225 | -2.225 | 0 | -2.225 | 26 | 283-320001TUR | PRE-FAB - LEVEL 39 - LEVEL 39 RISER (STICK BUILD) (POWER) (PLACEHOLDER) | 1974 | INSTALL - LEVEL 39 - FEEDER RISERS | PF.283 | 9000054 |  | PF.283 | DELETED | 100% |  |  | 2026-03-03 |  | 2025-10-05 | 118
[5 empty] | 9000060 | 284 | 320001TUR | Stephen Yee | LEVEL 1 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 1 PANEL ASSEMBLY (STRUT BUILD) DH1, EDH1, EL1, LH1, MH1, PL1, SDP1, SP1, LRH1 | 5 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-12 | [7 empty] | 2.5 | 0.3125 | 1 | 1 | 2026-01-19 | 2026-01-20 | 2026-01-22 |  | 2026-07-30 |  | 2026-07-30 | [5 empty] | Kerri Pandolfi | 284 | 26 |  | 0 | 0 | 0.5 | 2.5 | 0.7 | 3.5 | 0.5 | 0.2 | 0 | -0.5 | 26 | 284-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 PANEL ASSEMBLY (STRUT BUILD) DH1, EDH1, EL1, LH1, MH1, PL1, SDP1, SP1, LRH1 | 1794 | LEVEL 1 TRANSFORMER PREP LUG ONLY | PF.284 | 9000060 |  | PF.284 | PF.284 | 0% |  |  | 2026-01-05 |  | 2025-10-05 | 77
[5 empty] | 9000060 | 285 | 320001TUR | Stephen Yee | LEVEL 2 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 2 PANEL ASSEMBLY (STRUT BUILD) LH2, MH2, PL2, SP2 | 5 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-10 | [7 empty] | 2.5 | 0.3125 | 1 | 1 | 2025-10-17 | 2025-10-18 | 2025-10-20 |  | 2025-10-20 | DATES MISALIGNED | 2025-10-07 | [5 empty] | Kerri Pandolfi | 285 | 25 |  | 0 | 0 | 0.5 | 2.5 | 0.7 | 3.5 | 0.5 | 0.2 | 0 | -0.5 | 25 | 285-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 PANEL ASSEMBLY (STRUT BUILD) LH2, MH2, PL2, SP2 | 252 | LEVEL 3 - PODIUM - HPH3 PANEL ASSEMBLY (STRUT BUILD) | PF.285 | 9000060 |  | PF.285 | PF.285 | 0% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[5 empty] | 9000060 | 286 | 320001TUR | Stephen Yee | LEVEL 4 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 4 - PODIUM - PL4 PANEL ASSEMBLY | 1 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-25 | 2025-08-28 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8.51 | 1.0637 | 2 | 1 | 2025-10-02 | 2025-10-05 | 2025-10-07 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-07 |  |  |  |  | 8 | Kerri Pandolfi | 286 | 25 |  | 20 | 20 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 8.51 | 0 | 25 | 286-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM - PL4 PANEL ASSEMBLY | 250 | LEVEL 4 - PODIUM - PANEL EPH4,EPL4 | PF.286 | 9000060 |  | PF.286 | PF.286 | 75% |  |  | 2025-09-18 |  | 2025-10-05 | -2 | TRUE
[5 empty] | 9000060 | 287 | 320001TUR | Stephen Yee | LEVEL 5 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 5 - PODIUM -HPH5,EPH5,EPL5 PANEL ASSEMBLY (STRUT BUILD) | 3 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-29 | 2025-09-25 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 1.5 | 0.1875 | 1 | 1 | 2025-10-06 | 2025-10-07 | 2025-10-09 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 8 | Kerri Pandolfi | 287 | 25 |  | 1.3333 | 4 | 0.5 | 1.5 | 0.7 | 2.1 | 0.5 | 0.2 | 0.5 | 0 | 25 | 287-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM -HPH5,EPH5,EPL5 PANEL ASSEMBLY (STRUT BUILD) | 274 | INSTALL - LEVEL 5 - DISTRIBUTION EQUIP | PF.287 | 9000060 |  | PF.287 | PF.287 | 75% |  |  | 2025-09-22 |  | 2025-10-05 | 2 | TRUE
[5 empty] | 9000060 | 288 | 320001TUR | Stephen Yee | LEVEL 6 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 6 - PANEL ASSEMBLY (STRUT BUILD) DH6, LH6, PLM6, PL6 | 4 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-29 | 2025-10-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.25 | 1 | 1 | 2025-10-06 | 2025-10-07 | 2025-10-09 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 8 | Kerri Pandolfi | 288 | 25 |  | 2 | 8 | 0.5 | 2 | 0.7 | 2.8 | 0.5 | 0.2 | 0.5 | 0 | 25 | 288-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 - PANEL ASSEMBLY (STRUT BUILD) DH6, LH6, PLM6, PL6 | 268 | INSTALL - LEVEL 6 - DISTRIBUTION EQUIP | PF.288 | 9000060 |  | PF.288 | PF.288 | 75% |  |  | 2025-09-22 |  | 2025-10-05 | 2 | TRUE
[5 empty] | 9000060 | 289 | 320001TUR | Stephen Yee | LEVEL 6 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 6 - PODIUM - PL6 PANEL ASSEMBLY | 1 | Gray | 121 BROADWAY MXD TOWER | Eddie Velez | 2025-09-26 | 2025-10-01 |  | TRUE | true | TRUE | True |  | 8.51 | 1.0637 | 2 | 1 | 2025-10-03 | 2025-10-07 | 2025-10-09 |  | 2025-11-03 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  | 14 | Kerri Pandolfi | 289 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 289-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 - PODIUM - PL6 PANEL ASSEMBLY | #NO MATCH | #NO MATCH | PF.289 | 9000060 |  | PF.289 | DELETED | 100% |  |  | 2025-09-19 |  | 2025-10-05 | -1
[5 empty] | 9000060 | 290 | 320001TUR | Stephen Yee | LEVEL 10 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 10 - EPH10,EPL10 PANEL ASSEMBLY (STRUT BUILD) | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-04 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2025-11-11 | 2025-11-12 | 2025-11-14 |  | 2025-11-14 |  | 2025-11-14 | [5 empty] | Kerri Pandolfi | 290 | 25 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 25 | 290-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - EPH10,EPL10 PANEL ASSEMBLY (STRUT BUILD) | 427 | INSTALL - LEVEL 10 - DISTRIBUTION EQUIP | PF.290 | 9000060 |  | PF.290 | PF.290 | 0% |  |  | 2025-10-28 |  | 2025-10-05 | 28
[5 empty] | 9000060 | 291 | 320001TUR | Stephen Yee | LEVEL 11 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 11 - TIER 1 - PANEL ASSEMBLY (STRUT BUILD) | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-10-14 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-21 | 2025-10-22 | 2025-10-24 |  | 2025-10-24 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 291 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 291-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 - PANEL ASSEMBLY (STRUT BUILD) | #NO MATCH | #NO MATCH | PF.291 | 9000060 |  | PF.291 | DELETED | 100% |  |  | 2025-10-07 |  | 2025-10-05 | 13
[5 empty] | 9000060 | 292 | 320001TUR | Stephen Yee | LEVEL 14 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 14 - TIER 1 - PL14 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-11 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-12-18 | 2025-12-20 | 2025-12-22 |  | 2025-12-22 |  | 2025-12-22 | [5 empty] | Kerri Pandolfi | 292 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 292-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 - PL14 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 604 | INSTALL - LEVEL 14 - DISTRIBUTION EQUIP | PF.292 | 9000060 |  | PF.292 | PF.292 | 0% |  |  | 2025-12-04 |  | 2025-10-05 | 55
[5 empty] | 9000060 | 293 | 320001TUR | Stephen Yee | LEVEL 15 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 15 - TIER 2 -EPH15,EPL15 PANEL ASSEMBLY (STRUT BUILD) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-12 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2025-12-19 | 2025-12-21 | 2025-12-23 |  | 2025-12-23 |  | 2025-12-23 | [5 empty] | Kerri Pandolfi | 293 | 25 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 25 | 293-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 -EPH15,EPL15 PANEL ASSEMBLY (STRUT BUILD) | 629 | INSTALL - LEVEL 15 - DISTRIBUTION EQUIP | PF.293 | 9000060 |  | PF.293 | PF.293 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[5 empty] | 9000060 | 294 | 320001TUR | Stephen Yee | LEVEL 17 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 17 - TIER 2 -HPH17 PANEL ASSEMBLY (STRUT BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-21 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-11-28 | 2025-11-29 | 2025-12-01 |  | 2025-12-12 |  | 2025-12-18 | [5 empty] | Kerri Pandolfi | 294 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 294-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 -HPH17 PANEL ASSEMBLY (STRUT BUILD) | 599 | LEVEL 17 - TIER 2 - PL17 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | PF.294 | 9000060 |  | PF.294 | PF.294 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[5 empty] | 9000060 | 295 | 320001TUR | Stephen Yee | LEVEL 20 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 20 - TIER 2 -EPH20,EPL20 PANEL ASSEMBLY (STRUT BUILD) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-19 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2025-12-26 | 2025-12-27 | 2025-12-29 |  | 2026-01-21 |  | 2026-01-26 | [5 empty] | Kerri Pandolfi | 295 | 26 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 26 | 295-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 -EPH20,EPL20 PANEL ASSEMBLY (STRUT BUILD) | 826 | LEVEL 20 - TIER 2 - PL20 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | PF.295 | 9000060 |  | PF.295 | PF.295 | 0% |  |  | 2025-12-12 |  | 2025-10-05 | 61
[5 empty] | 9000060 | 296 | 320001TUR | Stephen Yee | LEVEL 22 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 22 - TIER 2 - PL22 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-22 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-12-29 | 2025-12-31 | 2026-01-02 |  | 2026-01-26 |  | 2026-01-29 | [5 empty] | Kerri Pandolfi | 296 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 296-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 - PL22 | 837 | INSTALL - LEVEL 22 - DISTRIBUTION EQUIP | PF.296 | 9000060 |  | PF.296 | PF.296 | 0% |  |  | 2025-12-15 |  | 2025-10-05 | 62
[5 empty] | 9000060 | 297 | 320001TUR | Stephen Yee | LEVEL 24 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 24 - TIER 2 - PANEL ASSEMBLY (STRUT BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-05 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-12 | 2026-01-13 | 2026-01-15 |  | 2026-03-03 |  | 2026-03-06 | [5 empty] | Kerri Pandolfi | 297 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 297-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - PANEL ASSEMBLY (STRUT BUILD) | 1086 | INSTALL - LEVEL 24 - DISTRIBUTION EQUIP | PF.297 | 9000060 |  | PF.297 | PF.297 | 0% |  |  | 2025-12-29 |  | 2025-10-05 | 72
[5 empty] | 9000060 | 298 | 320001TUR | Stephen Yee | LEVEL 25 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 25 - TIER 2 - PANEL PL25 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-09 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2026-01-16 | 2026-01-20 | 2026-01-22 |  | 2026-03-03 |  | 2026-03-06 | [5 empty] | Kerri Pandolfi | 298 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 298-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 - PANEL PL25 | 1057 | INSTALL - LEVEL 25 - DISTRIBUTION EQUIP | PF.298 | 9000060 |  | PF.298 | PF.298 | 0% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[5 empty] | 9000060 | 299 | 320001TUR | Stephen Yee | LEVEL 28 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 28 - TIER 2 - PANEL PL28 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-15 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2026-01-22 | 2026-01-26 | 2026-01-28 |  | 2026-04-07 |  | 2026-04-10 | [5 empty] | Kerri Pandolfi | 299 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 299-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 - PANEL PL28 | 1271 | INSTALL - LEVEL 28 - DISTRIBUTION EQUIP | PF.299 | 9000060 |  | PF.299 | PF.299 | 0% |  |  | 2026-01-08 |  | 2025-10-05 | 80
[5 empty] | 9000060 | 300 | 320001TUR | Stephen Yee | LEVEL 29 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 29 - TIER 2 - PANEL HPH29,EPH29,EPL29 | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-16 | 2025-09-16 | [6 empty] | 1.5 | 0.1875 | 1 | 1 | 2026-01-23 | 2026-01-25 | 2026-01-27 |  | 2026-04-07 |  | 2026-04-10 | [5 empty] | Kerri Pandolfi | 300 | 26 |  | 0 | 0 | 0.5 | 1.5 | 0.7 | 2.1 | 0.5 | 0.2 | 0 | -0.5 | 26 | 300-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 - PANEL HPH29,EPH29,EPL29 | 1301 | INSTALL - LEVEL 29 - DISTRIBUTION EQUIP | PF.300 | 9000060 |  | PF.300 | PF.300 | 0% |  |  | 2026-01-09 |  | 2025-10-05 | 81
[5 empty] | 9000060 | 301 | 320001TUR | Stephen Yee | LEVEL 31 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 31 - TIER 2 - PANEL PL31 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-03-12 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2026-03-19 | 2026-03-21 | 2026-03-23 |  | 2026-04-07 |  | 2026-04-10 | [5 empty] | Kerri Pandolfi | 301 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 301-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 - PANEL PL31 | 1272 | INSTALL - LEVEL 31 - DISTRIBUTION EQUIP | PF.301 | 9000060 |  | PF.301 | PF.301 | 0% |  |  | 2026-03-05 |  | 2025-10-05 | 120
[5 empty] | 9000060 | 302 | 320001TUR | Stephen Yee | LEVEL 34 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 34 - TIER 2 - PANEL PL34 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-03-12 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2026-03-19 | 2026-03-21 | 2026-03-23 |  | 2026-05-13 |  | 2026-05-18 | [5 empty] | Kerri Pandolfi | 302 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 302-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 - PANEL PL34 | 1475 | INSTALL - LEVEL 34 - DISTRIBUTION EQUIP | PF.302 | 9000060 |  | PF.302 | PF.302 | 0% |  |  | 2026-03-05 |  | 2025-10-05 | 120
[5 empty] | 9000060 | 303 | 320001TUR | Stephen Yee | LEVEL 37 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 37 - AMENITY/MEP PH - PANEL ASSEMBLY (STRUT BUILD) | 5 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-02-17 | [7 empty] | 2.5 | 0.3125 | 1 | 1 | 2026-02-24 | 2026-02-25 | 2026-02-27 |  | 2026-02-27 | DATES MISALIGNED | 2026-05-18 | [5 empty] | Kerri Pandolfi | 303 | 26 |  | 0 | 0 | 0.5 | 2.5 | 0.7 | 3.5 | 0.5 | 0.2 | 0 | -0.5 | 26 | 303-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - PANEL ASSEMBLY (STRUT BUILD) | 1504 | INSTALL - LEVEL 37 - DISTRIBUTION EQUIP | PF.303 | 9000060 |  | PF.303 | PF.303 | 0% |  |  | 2026-02-10 |  | 2025-10-05 | 103
[5 empty] | 9000060 | 304 | 320001TUR | Stephen Yee | LEVEL 3 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 3 - PODIUM - HPH3 PANEL ASSEMBLY (STRUT BUILD) | 1 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-29 | 2025-08-28 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 0.5 | 0.0625 | 1 | 1 | 2025-10-06 | 2025-10-07 | 2025-10-09 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 8 | Kerri Pandolfi | 304 | 25 |  | 8 | 8 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0.5 | 0 | 25 | 304-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM - HPH3 PANEL ASSEMBLY (STRUT BUILD) | 269 | INSTALL - LEVEL 3 - DISTRIBUTION EQUIP | PF.304 | 9000060 |  | PF.304 | PF.304 | 75% |  |  | 2025-09-22 |  | 2025-10-05 | 2 | TRUE
[5 empty] | 9000060 | 305 | 320001TUR | Stephen Yee | LEVEL 4 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 4 - PODIUM - PANEL EPH4,EPL4 | 2 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-26 | 2025-09-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 1 | 0.125 | 1 | 1 | 2025-10-03 | 2025-10-05 | 2025-10-07 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 8 | Kerri Pandolfi | 305 | 25 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 25 | 305-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM - PANEL EPH4,EPL4 | 270 | INSTALL - LEVEL 4 - DISTRIBUTION EQUIP | PF.305 | 9000060 |  | PF.305 | PF.305 | 0% |  |  | 2025-09-19 |  | 2025-10-05 | -1 | TRUE
[5 empty] | 9000060 | 306 | 320001TUR | Stephen Yee | LEVEL 5 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 5 - PODIUM - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-19 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-08-26 | 2025-08-27 | 2025-08-29 |  | 2025-08-29 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 306 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 306-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM - METER STACK | #NO MATCH | #NO MATCH | PF.306 | 9000060 |  | PF.306 | DELETED | 100% |  |  | 2025-08-12 |  | 2025-10-05 | -29
[5 empty] | 9000060 | 307 | 320001TUR | Stephen Yee | LEVEL 6 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 6 LEVEL 6 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-19 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-08-26 | 2025-08-27 | 2025-08-29 |  | 2025-08-29 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 307 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 307-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 - METER STACK | #NO MATCH | #NO MATCH | PF.307 | 9000060 |  | PF.307 | DELETED | 100% |  |  | 2025-08-12 |  | 2025-10-05 | -29
[5 empty] | 9000060 | 308 | 320001TUR | Stephen Yee | LEVEL 7 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 7 - TIER 1 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-16 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-09-26 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 308 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 308-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 - METER STACK | #NO MATCH | #NO MATCH | PF.308 | 9000060 |  | PF.308 | DELETED | 100% |  |  | 2025-09-09 |  | 2025-10-05 | -9
[5 empty] | 9000060 | 309 | 320001TUR | Stephen Yee | LEVEL 8 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 8 - PL8 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-30 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-11-06 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 |  | 2025-11-14 | [5 empty] | Kerri Pandolfi | 309 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 309-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - PL8 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 438 | INSTALL - LEVEL 8 - DISTRIBUTION EQUIP | PF.309 | 9000060 |  | PF.309 | PF.309 | 0% |  |  | 2025-10-23 |  | 2025-10-05 | 25
[5 empty] | 9000060 | 310 | 320001TUR | Stephen Yee | LEVEL 9 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 9 -HPH9 PANEL ASSEMBLY (STRUT BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-14 |  | 2025-11-14 | [5 empty] | Kerri Pandolfi | 310 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 310-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 -HPH9 PANEL ASSEMBLY (STRUT BUILD) | 429 | INSTALL - LEVEL 9 - DISTRIBUTION EQUIP | PF.310 | 9000060 |  | PF.310 | PF.310 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[5 empty] | 9000060 | 311 | 320001TUR | Stephen Yee | LEVEL 10 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 10 - TIER 1 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-15 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-09-25 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 311 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 311-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 - METER STACK | #NO MATCH | #NO MATCH | PF.311 | 9000060 |  | PF.311 | DELETED | 100% |  |  | 2025-09-08 |  | 2025-10-05 | -10
[5 empty] | 9000060 | 312 | 320001TUR | Stephen Yee | LEVEL 11 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 11 - PL11 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-30 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-11-06 | 2025-11-10 | 2025-11-12 |  | 2025-11-18 |  | 2025-11-14 | [5 empty] | Kerri Pandolfi | 312 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 312-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - PL11 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 439 | INSTALL - LEVEL 11 - DISTRIBUTION EQUIP | PF.312 | 9000060 |  | PF.312 | PF.312 | 0% |  |  | 2025-10-23 |  | 2025-10-05 | 25
[5 empty] | 9000060 | 313 | 320001TUR | Stephen Yee | LEVEL 12 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 12 - TIER 1 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-10-14 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-21 | 2025-10-22 | 2025-10-24 |  | 2025-10-24 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 313 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 313-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 - METER STACK | #NO MATCH | #NO MATCH | PF.313 | 9000060 |  | PF.313 | DELETED | 100% |  |  | 2025-10-07 |  | 2025-10-05 | 13
[5 empty] | 9000060 | 314 | 320001TUR | Stephen Yee | LEVEL 13 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 13 - TIER 1 - HPH13 PANEL ASSEMBLY (STRUT BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-24 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-31 | 2025-11-01 | 2025-11-03 |  | 2025-12-17 |  | 2025-12-22 | [5 empty] | Kerri Pandolfi | 314 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 314-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 - HPH13 PANEL ASSEMBLY (STRUT BUILD) | 625 | INSTALL - LEVEL 13 - DISTRIBUTION EQUIP | PF.314 | 9000060 |  | PF.314 | PF.314 | 0% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[5 empty] | 9000060 | 315 | 320001TUR | Stephen Yee | LEVEL 14 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 14 - TIER 1 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-10-13 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-20 | 2025-10-21 | 2025-10-23 |  | 2025-10-23 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 315 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 315-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 - METER STACK | #NO MATCH | #NO MATCH | PF.315 | 9000060 |  | PF.315 | DELETED | 100% |  |  | 2025-10-06 |  | 2025-10-05 | 12
[5 empty] | 9000060 | 316 | 320001TUR | Stephen Yee | LEVEL 15 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 15 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-10-10 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-10-17 | 2025-10-20 | 2025-10-22 |  | 2025-10-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 316 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 316-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.316 | 9000060 |  | PF.316 | DELETED | 100% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[5 empty] | 9000060 | 317 | 320001TUR | Stephen Yee | LEVEL 16 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 16 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-11-11 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-11-18 | 2025-11-19 | 2025-11-21 |  | 2025-11-21 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 317 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 317-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.317 | 9000060 |  | PF.317 | DELETED | 100% |  |  | 2025-11-04 |  | 2025-10-05 | 33
[5 empty] | 9000060 | 318 | 320001TUR | Stephen Yee | LEVEL 17 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 17 - TIER 2 - PL17 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-20 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-11-27 | 2025-11-29 | 2025-12-01 |  | 2025-12-17 |  | 2025-12-23 | [5 empty] | Kerri Pandolfi | 318 | 25 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 25 | 318-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 - PL17 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 623 | INSTALL - LEVEL 17 - DISTRIBUTION EQUIP | PF.318 | 9000060 |  | PF.318 | PF.318 | 0% |  |  | 2025-11-13 |  | 2025-10-05 | 40
[5 empty] | 9000060 | 319 | 320001TUR | Stephen Yee | LEVEL 18 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 18 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-11-11 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-11-18 | 2025-11-19 | 2025-11-21 |  | 2025-11-21 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 319 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 319-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.319 | 9000060 |  | PF.319 | DELETED | 100% |  |  | 2025-11-04 |  | 2025-10-05 | 33
[5 empty] | 9000060 | 320 | 320001TUR | Stephen Yee | LEVEL 19 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 19 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-12-09 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-12-16 | 2025-12-17 | 2025-12-19 |  | 2025-12-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 320 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 320-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.320 | 9000060 |  | PF.320 | DELETED | 100% |  |  | 2025-12-02 |  | 2025-10-05 | 53
[5 empty] | 9000060 | 321 | 320001TUR | Stephen Yee | LEVEL 20 | (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | LEVEL 20 - TIER 2 - PL20 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-18 | 2025-09-16 | [6 empty] | 8.51 | 1.0637 | 2 | 1 | 2025-12-25 | 2025-12-27 | 2025-12-29 |  | 2026-01-26 |  | 2026-01-29 | [5 empty] | Kerri Pandolfi | 321 | 26 |  | 0 | 0 | 8.51 | 8.51 |  | 0 | 8.51 | -8.51 | 0 | -8.51 | 26 | 321-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 - PL20 (31-42 CK) PANEL ASSEMBLY W/ JB - (WIRED/ NO TERM BLOCKS) (STICK BUILD) | 836 | INSTALL - LEVEL 20 - DISTRIBUTION EQUIP | PF.321 | 9000060 |  | PF.321 | PF.321 | 0% |  |  | 2025-12-11 |  | 2025-10-05 | 60
[5 empty] | 9000060 | 322 | 320001TUR | Stephen Yee | LEVEL 21 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 21 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-12-09 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-12-16 | 2025-12-17 | 2025-12-19 |  | 2025-12-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 322 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 322-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.322 | 9000060 |  | PF.322 | DELETED | 100% |  |  | 2025-12-02 |  | 2025-10-05 | 53
[5 empty] | 9000060 | 323 | 320001TUR | Stephen Yee | LEVEL 22 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 22 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-12-08 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2025-12-15 | 2025-12-16 | 2025-12-18 |  | 2025-12-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 323 | 25 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 25 | 323-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.323 | 9000060 |  | PF.323 | DELETED | 100% |  |  | 2025-12-01 |  | 2025-10-05 | 52
[5 empty] | 9000060 | 324 | 320001TUR | Stephen Yee | LEVEL 23 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 23 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-01-06 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-13 | 2026-01-14 | 2026-01-16 |  | 2026-01-16 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 324 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 324-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.324 | 9000060 |  | PF.324 | DELETED | 100% |  |  | 2025-12-30 |  | 2025-10-05 | 73
[5 empty] | 9000060 | 325 | 320001TUR | Stephen Yee | LEVEL 24 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 24 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-01-05 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-12 | 2026-01-13 | 2026-01-15 |  | 2026-01-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 325 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 325-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.325 | 9000060 |  | PF.325 | DELETED | 100% |  |  | 2025-12-29 |  | 2025-10-05 | 72
[5 empty] | 9000060 | 326 | 320001TUR | Stephen Yee | LEVEL 25 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 25 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-01-05 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-12 | 2026-01-13 | 2026-01-15 |  | 2026-01-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 326 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 326-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.326 | 9000060 |  | PF.326 | DELETED | 100% |  |  | 2025-12-29 |  | 2025-10-05 | 72
[5 empty] | 9000060 | 327 | 320001TUR | Stephen Yee | LEVEL 26 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 26 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-01-06 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-13 | 2026-01-14 | 2026-01-16 |  | 2026-01-16 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 327 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 327-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.327 | 9000060 |  | PF.327 | DELETED | 100% |  |  | 2025-12-30 |  | 2025-10-05 | 73
[5 empty] | 9000060 | 328 | 320001TUR | Stephen Yee | LEVEL 27 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 27 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-02-03 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-10 | 2026-02-11 | 2026-02-13 |  | 2026-02-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 328 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 328-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.328 | 9000060 |  | PF.328 | DELETED | 100% |  |  | 2026-01-27 |  | 2025-10-05 | 93
[5 empty] | 9000060 | 329 | 320001TUR | Stephen Yee | LEVEL 28 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 28 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-02-02 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-09 | 2026-02-10 | 2026-02-12 |  | 2026-02-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 329 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 329-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.329 | 9000060 |  | PF.329 | DELETED | 100% |  |  | 2026-01-26 |  | 2025-10-05 | 92
[5 empty] | 9000060 | 330 | 320001TUR | Stephen Yee | LEVEL 29 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 29 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-02-02 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-09 | 2026-02-10 | 2026-02-12 |  | 2026-02-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 330 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 330-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.330 | 9000060 |  | PF.330 | DELETED | 100% |  |  | 2026-01-26 |  | 2025-10-05 | 92
[5 empty] | 9000060 | 331 | 320001TUR | Stephen Yee | LEVEL 30 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 30 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-02-03 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-10 | 2026-02-11 | 2026-02-13 |  | 2026-02-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 331 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 331-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.331 | 9000060 |  | PF.331 | DELETED | 100% |  |  | 2026-01-27 |  | 2025-10-05 | 93
[5 empty] | 9000060 | 332 | 320001TUR | Stephen Yee | LEVEL 31 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 31 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-02 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-03-09 | 2026-03-10 | 2026-03-12 |  | 2026-03-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 332 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 332-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.332 | 9000060 |  | PF.332 | DELETED | 100% |  |  | 2026-02-23 |  | 2025-10-05 | 112
[5 empty] | 9000060 | 333 | 320001TUR | Stephen Yee | LEVEL 32 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 32 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-03 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-03-10 | 2026-03-11 | 2026-03-13 |  | 2026-03-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 333 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 333-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.333 | 9000060 |  | PF.333 | DELETED | 100% |  |  | 2026-02-24 |  | 2025-10-05 | 113
[5 empty] | 9000060 | 334 | 320001TUR | Stephen Yee | LEVEL 33 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 33 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-03 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-03-10 | 2026-03-11 | 2026-03-13 |  | 2026-03-13 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 334 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 334-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.334 | 9000060 |  | PF.334 | DELETED | 100% |  |  | 2026-02-24 |  | 2025-10-05 | 113
[5 empty] | 9000060 | 335 | 320001TUR | Stephen Yee | LEVEL 34 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 34 - TIER 2 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-02 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-03-09 | 2026-03-10 | 2026-03-12 |  | 2026-03-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 335 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 335-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 - METER STACK | #NO MATCH | #NO MATCH | PF.335 | 9000060 |  | PF.335 | DELETED | 100% |  |  | 2026-02-23 |  | 2025-10-05 | 112
[5 empty] | 9000060 | 336 | 320001TUR | Stephen Yee | LEVEL 35 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 35 - TIER 3 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-31 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-04-07 | 2026-04-08 | 2026-04-10 |  | 2026-04-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 336 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 336-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 - METER STACK | #NO MATCH | #NO MATCH | PF.336 | 9000060 |  | PF.336 | DELETED | 100% |  |  | 2026-03-24 |  | 2025-10-05 | 133
[5 empty] | 9000060 | 337 | 320001TUR | Stephen Yee | LEVEL 36 | PANEL ASSEMBLY (STRUT BUILD) | LEVEL 36 - TIER 3 - METER STACK | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2026-03-31 | [7 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-04-07 | 2026-04-08 | 2026-04-10 |  | 2026-04-10 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 337 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 337-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 - METER STACK | #NO MATCH | #NO MATCH | PF.337 | 9000060 |  | PF.337 | DELETED | 100% |  |  | 2026-03-24 |  | 2025-10-05 | 133
[5 empty] | 9000060 | 338 | 320001TUR | Stephen Yee | LEVEL 1 | TRANSFORMER PREP LUGGING / PUNCHING PER (1) TRANSFORMER | LEVEL 1 TRANSFORMER T4 | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-07-24 | [7 empty] | 3.3333 | 0.41667 | 1 | 1 | 2026-07-31 | 2026-08-01 | 2026-08-03 |  | 2026-08-03 |  | 2026-08-03 | [5 empty] | Kerri Pandolfi | 338 | 26 |  | 0 | 0 | 1.6667 | 3.3333 | 1.67 | 3.34 | 1.6667 | 0.0033333 | 0 | -1.6667 | 26 | 338-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 TRANSFORMER T4 | 1796 | INSTALL - LEVEL 1 - DISTRIBUTION EQUIP | PF.338 | 9000060 |  | PF.338 | PF.338 | 0% |  |  | 2026-07-17 |  | 2025-10-05 | 216
[5 empty] | 9000060 | 339 | 320001TUR | Stephen Yee | LEVEL 6 | TRANSFORMER PREP LUGGING / PUNCHING PER (1) TRANSFORMER | LEVEL 6 - TRANSFORMER T5 & T4 | 2 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | [7 empty] | 3.3333 | 0.41667 | 1 | 1 | 2025-10-31 | 2025-11-01 | 2025-11-03 |  | 2025-11-03 | DATES MISALIGNED | 2025-10-07 | [5 empty] | Kerri Pandolfi | 339 | 25 |  | 0 | 0 | 1.6667 | 3.3333 | 1.67 | 3.34 | 1.6667 | 0.0033333 | 0 | -1.6667 | 25 | 339-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 - TRANSFORMER T5 & T4 | 257 | LEVEL 6 LEVEL 6 - PANEL ASSEMBLY (STRUT BUILD) | PF.339 | 9000060 |  | PF.339 | PF.339 | 0% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[5 empty] | 9000061 | 340 | 320001TUR | Stephen Yee | LEVEL 37 | MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2026-01-19 | [7 empty] | 80 | 5 | 5 | 2 | 2026-01-26 | 2026-02-02 | 2026-02-04 |  | 2026-02-04 | DATES MISALIGNED | 2026-02-26 | [5 empty] | Kerri Pandolfi | 340 | 26 |  | 0 | 0 | 40 | 80 | 53.8 | 107.6 | 40 | 13.8 | 0 | -40 | 26 | 340-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | 920 | LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | PF.340 | 9000061 |  | PF.340 | PF.340 | 0% |  |  | 2026-01-12 |  | 2025-10-05 | 82
[5 empty] | 9000061 | 341 | 320001TUR | Stephen Yee | LEVEL 37 | MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe, Steve D'Entremont | 2026-02-09 | [7 empty] | 80 | 5 | 5 | 2 | 2026-02-16 | 2026-02-23 | 2026-02-25 |  | 2026-02-25 | DATES MISALIGNED | 2026-03-18 | [5 empty] | Kerri Pandolfi | 341 | 26 |  | 0 | 0 | 40 | 80 | 53.8 | 107.6 | 40 | 13.8 | 0 | -40 | 26 | 341-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - MODULAR ELECT ASSEMBLY (SMALL) (PLACEHOLDER) | 1044 | INSTALL - LEVEL 37 - MODULAR DIST EQUIP | PF.341 | 9000061 |  | PF.341 | PF.341 | 0% |  |  | 2026-02-02 |  | 2025-10-05 | 97
[5 empty] | 9000150 | 342 | 320001TUR | Stephen Yee | LEVEL 1 | CHIEF BOXES (A/V) (2 RECEPTACLES) | LEVEL 1 CHIEF BOXES (A/V) (1 RECEPTACLE) | 1 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-12 | 2025-09-15 | Chris Gauvin | TRUE | true | TRUE | True | APPROVED | 2.6 | 0.1625 | 1 | 2 | 2025-09-19 | 2025-09-20 | 2025-09-22 |  | 2025-10-14 | DATES MISALIGNED | 2025-08-18 |  |  | Image 2025-09-22 08-57-15.jpeg |  | 8 | Kerri Pandolfi | 342 | 25 |  | 2 | 2 | 2.6 | 2.6 |  | 0 | 2.6 | -2.6 | 2 | -0.6 | 25 | 342-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 CHIEF BOXES (A/V) (1 RECEPTACLE) | 90 | LEVEL 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.342 | 9000150 |  | PF.342 | PF.342 | 99% | TRUE |  | 2025-09-05 |  | 2025-10-05 | -11 | TRUE
[5 empty] | 9000150 | 343 | 320001TUR | Stephen Yee | LEVEL 2 | CHIEF BOXES (A/V) (2 RECEPTACLES) | LEVEL 2 CHIEF BOXES (A/V) (2 RECEPTACLES) | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 13 | 0.8125 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | DATES MISALIGNED | 2025-08-28 | [5 empty] | Kerri Pandolfi | 343 | 25 |  | 0 | 0 | 2.6 | 13 |  | 0 | 2.6 | -2.6 | 0 | -2.6 | 25 | 343-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 CHIEF BOXES (A/V) (2 RECEPTACLES) | 126 | LEVEL 1 JUNCTION BOX PREP (5-12 K.O.) (BRANCH) | PF.343 | 9000150 |  | PF.343 | PF.343 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000150 | 344 | 320001TUR | Stephen Yee | LEVEL 6 | CHIEF BOXES (A/V) (1 RECEPTACLE) | LEVEL 6 - CHIEF BOXES (A/V) (1 RECEPTACLE) | 11 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-18 | Chris Gauvin | TRUE | true | TRUE | True | APPROVED | 8.9007 | 0.55629 | 1 | 2 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-28 | DATES MISALIGNED | 2025-09-16 |  |  | Image 2025-10-03 07-27-23.jpeg |  | 2 | Kerri Pandolfi | 344 | 25 |  | 1.4091 | 15.5 | 0.80915 | 8.9007 | 2.8 | 30.8 | 0.80915 | 1.9909 | 0.80915 | 0 | 25 | 344-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 - CHIEF BOXES (A/V) (1 RECEPTACLE) | 176 | LEVEL 6 LEVEL 6 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.344 | 9000150 |  | PF.344 | PF.344 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000150 | 345 | 320001TUR | Stephen Yee | LEVEL 37 | CHIEF BOXES (A/V) (2 RECEPTACLES) | LEVEL 37 - AMENITY/MEP PH - CHIEF BOXES (A/V) (2 RECEPTACLES) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-06-15 | [7 empty] | 26 | 1.625 | 2 | 2 | 2026-06-22 | 2026-06-24 | 2026-06-26 |  | 2026-06-26 |  | 2026-06-26 | [5 empty] | Kerri Pandolfi | 345 | 26 |  | 0 | 0 | 2.6 | 26 |  | 0 | 2.6 | -2.6 | 0 | -2.6 | 26 | 345-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - CHIEF BOXES (A/V) (2 RECEPTACLES) | 1680 | LEVEL 37 - AMENITY/MEP PH PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.345 | 9000150 |  | PF.345 | PF.345 | 0% |  |  | 2026-06-08 |  | 2025-10-05 | 187
[5 empty] | 9000220 | 346 | 320001TUR | Stephen Yee | LEVEL 1 | TEMPS (LARGE) | LEVEL 1 TEMPS (LARGE) | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 8 | 1 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 346 |  |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 |  | 346-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 TEMPS (LARGE) | #NO MATCH | #NO MATCH | PF.346 | 9000220 |  | PF.346 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 347 | 320001TUR | Stephen Yee | LEVEL 7 | TEMPS (LARGE) | LEVEL 7 - TIER 1 - TEMPS (LARGE) | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 8 | 1 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 347 |  |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 |  | 347-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 - TEMPS (LARGE) | #NO MATCH | #NO MATCH | PF.347 | 9000220 |  | PF.347 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 348 | 320001TUR | Stephen Yee | LEVEL 18 | TEMPS (LARGE) | LEVEL 18 - TIER 2 - 45KVA PDU | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-18 | 2025-07-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-07-25 | 2025-07-28 | 2025-07-30 |  | 2025-08-04 |  |  | TRUE |  | Image 2025-08-01 08-34-04.jpeg |  | 4 | Kerri Pandolfi | 348 | 25 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 25 | 348-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 - 45KVA PDU | 1934 |  | PF.348 | 9000220 |  | PF.348 | PF.348 | 100% |  |  | 2025-07-11 |  | 2025-10-05 | -51 | TRUE
[5 empty] | 9000220 | 349 | 320001TUR | Stephen Yee | LEVEL 24 | TEMPS (LARGE) | LEVEL 24 - TIER 2 - 45KVA PDU # 082 | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-07-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-22 |  |  | TRUE |  | Image 2025-09-19 10-37-51.jpeg |  |  | Kerri Pandolfi | 349 | 25 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 25 | 349-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - 45KVA PDU # 082 | 1941 | INSTALL - LEVEL 22 - TEMP WIRING | PF.349 | 9000220 |  | PF.349 | PF.349 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15
[5 empty] | 9000220 | 350 | 320001TUR | Stephen Yee | LEVEL 30 | TEMPS (LARGE) | LEVEL 30 - TIER 2 - 75KVA PDU#068 | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | [7 empty] | 8 | 1 | 1 | 1 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-09-30 |  |  | TRUE |  | Image 2025-09-19 10-39-05.jpeg |  |  | Kerri Pandolfi | 350 | 25 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 25 | 350-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 - 75KVA PDU#068 | 1952 | INSTALL - LEVEL 28 - TEMP WIRING | PF.350 | 9000220 |  | PF.350 | PF.350 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6
[5 empty] | 9000220 | 351 | 320001TUR | Stephen Yee | LEVEL 37 | TEMPS (LARGE) | LEVEL 37 - TIER 2 - 75KVA PDU | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-12 | [7 empty] | 8 | 1 | 1 | 1 | 2025-12-19 | 2025-12-22 | 2025-12-24 |  | 2025-12-24 | [7 empty] | Kerri Pandolfi | 351 | 25 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 25 | 351-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - TIER 2 - 75KVA PDU | 1968 | INSTALL - LEVEL 33 - TEMP WIRING | PF.351 | 9000220 |  | PF.351 | PF.351 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[5 empty] | 9000220 | 352 | 320001TUR | Stephen Yee | LEVEL 38 | TEMPS (LARGE) | LEVEL 38 - 75KVA PDU | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-02 | [7 empty] | 8 | 1 | 1 | 1 | 2026-01-09 | 2026-01-10 | 2026-01-12 |  | 2026-01-12 | [7 empty] | Kerri Pandolfi | 352 | 26 |  | 0 | 0 | 8 | 8 |  | 0 | 8 | -8 | 0 | -8 | 26 | 352-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 - 75KVA PDU | 1971 | INSTALL - LEVEL 38 - TEMP WIRING | PF.352 | 9000220 |  | PF.352 | PF.352 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[5 empty] | 9000220 | 353 | 320001TUR | Stephen Yee | LEVEL B1 | TEMPS (SMALL) | LEVEL B1 TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 353 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 353-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.353 | 9000220 |  | PF.353 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 354 | 320001TUR | Stephen Yee | LEVEL 1 | TEMPS (SMALL) | LEVEL 1 TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 354 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 354-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.354 | 9000220 |  | PF.354 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 355 | 320001TUR | Stephen Yee | LEVEL 2 | TEMPS (SMALL) | LEVEL 2 TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 355 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 355-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.355 | 9000220 |  | PF.355 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 356 | 320001TUR | Stephen Yee | LEVEL 3 | TEMPS (SMALL) | LEVEL 3 - PODIUM - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 356 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 356-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.356 | 9000220 |  | PF.356 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 357 | 320001TUR | Stephen Yee | LEVEL 4 | TEMPS (SMALL) | LEVEL 4 - PODIUM - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 357 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 357-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.357 | 9000220 |  | PF.357 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 358 | 320001TUR | Stephen Yee | LEVEL 5 | TEMPS (SMALL) | LEVEL 5 - PODIUM - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 358 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 358-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.358 | 9000220 |  | PF.358 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 359 | 320001TUR | Stephen Yee | LEVEL 6 | TEMPS (SMALL) | LEVEL 6 LEVEL 6 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 359 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 359-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 LEVEL 6 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.359 | 9000220 |  | PF.359 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 360 | 320001TUR | Stephen Yee | LEVEL 7 | TEMPS (SMALL) | LEVEL 7 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 360 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 360-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.360 | 9000220 |  | PF.360 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 361 | 320001TUR | Stephen Yee | LEVEL 8 | TEMPS (SMALL) | LEVEL 8 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 361 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 361-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.361 | 9000220 |  | PF.361 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 362 | 320001TUR | Stephen Yee | LEVEL 9 | TEMPS (SMALL) | LEVEL 9 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 362 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 362-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.362 | 9000220 |  | PF.362 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 363 | 320001TUR | Stephen Yee | LEVEL 10 | TEMPS (SMALL) | LEVEL 10 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 363 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 363-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.363 | 9000220 |  | PF.363 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 364 | 320001TUR | Stephen Yee | LEVEL 11 | TEMPS (SMALL) | LEVEL 11 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 364 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 364-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.364 | 9000220 |  | PF.364 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 365 | 320001TUR | Stephen Yee | LEVEL 12 | TEMPS (SMALL) | LEVEL 12 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 365 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 365-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.365 | 9000220 |  | PF.365 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 366 | 320001TUR | Stephen Yee | LEVEL 13 | TEMPS (SMALL) | LEVEL 13 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 366 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 366-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.366 | 9000220 |  | PF.366 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 367 | 320001TUR | Stephen Yee | LEVEL 14 | TEMPS (SMALL) | LEVEL 14 - TIER 1 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 367 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 367-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.367 | 9000220 |  | PF.367 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 368 | 320001TUR | Stephen Yee | LEVEL 15 | TEMPS (SMALL) | LEVEL 15 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 368 |  |  | 0.66667 | 2 | 1 | 3 | 2 | 6 | 1 | 1 | 0.66667 | -0.33333 |  | 368-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.368 | 9000220 |  | PF.368 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 369 | 320001TUR | Stephen Yee | LEVEL 16 | TEMPS (SMALL) | LEVEL 16 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 369 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 369-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.369 | 9000220 |  | PF.369 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 370 | 320001TUR | Stephen Yee | LEVEL 17 | TEMPS (SMALL) | LEVEL 17 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 370 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 370-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.370 | 9000220 |  | PF.370 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 371 | 320001TUR | Stephen Yee | LEVEL 18 | TEMPS (SMALL) | LEVEL 18 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 371 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 371-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.371 | 9000220 |  | PF.371 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 372 | 320001TUR | Stephen Yee | LEVEL 19 | TEMPS (SMALL) | LEVEL 19 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 372 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 372-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.372 | 9000220 |  | PF.372 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 373 | 320001TUR | Stephen Yee | LEVEL 20 | TEMPS (SMALL) | LEVEL 20 - TIER 2 - TEMPS (SMALL) | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | #INVALID DATA TYPE | [7 empty] | 3 | 0.375 | 1 | 1 | #INVALID DATA TYPE | [5 empty] | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | x |  |  | Kerri Pandolfi | 373 |  |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 |  | 373-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 - TEMPS (SMALL) | #NO MATCH | #NO MATCH | PF.373 | 9000220 |  | PF.373 | DELETED | 100% |  |  | #INVALID DATA TYPE |  | 2025-10-05 | #INVALID DATA TYPE
[5 empty] | 9000220 | 374 | 320001TUR | Stephen Yee | LEVEL 21 | TEMPS (SMALL) | LEVEL 21 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-22 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-08-29 | 2025-08-30 | 2025-09-01 |  | 2025-09-01 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 374 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 374-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.374 | 9000220 |  | PF.374 | DELETED | 100% |  |  | 2025-08-15 |  | 2025-10-05 | -26
[5 empty] | 9000220 | 375 | 320001TUR | Stephen Yee | LEVEL 22 | TEMPS (SMALL) | LEVEL 22 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-29 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-09-05 | 2025-09-06 | 2025-09-08 |  | 2025-09-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 375 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 375-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.375 | 9000220 |  | PF.375 | DELETED | 100% |  |  | 2025-08-22 |  | 2025-10-05 | -21
[5 empty] | 9000220 | 376 | 320001TUR | Stephen Yee | LEVEL 23 | TEMPS (SMALL) | LEVEL 23 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-05 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-09-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 376 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 376-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.376 | 9000220 |  | PF.376 | DELETED | 100% |  |  | 2025-08-29 |  | 2025-10-05 | -16
[5 empty] | 9000220 | 377 | 320001TUR | Stephen Yee | LEVEL 24 | TEMPS (SMALL) | LEVEL 24 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-12 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-09-19 | 2025-09-20 | 2025-09-22 |  | 2025-09-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 377 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 377-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.377 | 9000220 |  | PF.377 | DELETED | 100% |  |  | 2025-09-05 |  | 2025-10-05 | -11
[5 empty] | 9000220 | 378 | 320001TUR | Stephen Yee | LEVEL 25 | TEMPS (SMALL) | LEVEL 25 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-19 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-09-26 | 2025-09-27 | 2025-09-29 |  | 2025-09-29 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 378 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 378-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.378 | 9000220 |  | PF.378 | DELETED | 100% |  |  | 2025-09-12 |  | 2025-10-05 | -6
[5 empty] | 9000220 | 379 | 320001TUR | Stephen Yee | LEVEL 26 | TEMPS (SMALL) | LEVEL 26 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-23 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3 | 0.375 | 1 | 1 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-09-30 |  |  |  |  | Image 2025-09-26 10-11-15.jpeg |  | 14 | Kerri Pandolfi | 379 | 25 |  | 0.66667 | 2 | 1 | 3 | 2 | 6 | 1 | 1 | 0.66667 | -0.33333 | 25 | 379-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 - SPIDER BOXES | 1944 | INSTALL - LEVEL 26 - TEMP WIRING | PF.379 | 9000220 |  | PF.379 | PF.379 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000220 | 380 | 320001TUR | Stephen Yee | LEVEL 27 | TEMPS (SMALL) | LEVEL 27 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-23 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3 | 0.375 | 1 | 1 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-09-30 |  |  |  |  | Image 2025-09-26 10-11-51.jpeg |  | 14 | Kerri Pandolfi | 380 | 25 |  | 0.66667 | 2 | 1 | 3 | 2 | 6 | 1 | 1 | 0.66667 | -0.33333 | 25 | 380-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 - SPIDER BOXES | 1946 | INSTALL - LEVEL 27 - TEMP WIRING | PF.380 | 9000220 |  | PF.380 | PF.380 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000220 | 381 | 320001TUR | Stephen Yee | LEVEL 28 | TEMPS (SMALL) | LEVEL 28 - TIER 2 - SPIDER BOXES | 3 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-26 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3 | 0.375 | 1 | 1 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-09-30 |  |  |  |  | Image 2025-09-26 10-12-29.jpeg |  |  | Kerri Pandolfi | 381 | 25 |  | 0.66667 | 2 | 1 | 3 | 2 | 6 | 1 | 1 | 0.66667 | -0.33333 | 25 | 381-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 - SPIDER BOXES | 1948 | LEVEL 30 - TIER 2 - 75KVA PDU | PF.381 | 9000220 |  | PF.381 | PF.381 | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6
[5 empty] | 9000220 | 382 | 320001TUR | Stephen Yee | LEVEL 29 | TEMPS (SMALL) | LEVEL 29 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-17 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-10-24 | 2025-10-25 | 2025-10-27 |  | 2025-10-27 | [7 empty] | Kerri Pandolfi | 382 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 382-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 - SPIDER BOXES | 1950 |  | PF.382 | 9000220 |  | PF.382 | PF.382 | 0% |  |  | 2025-10-10 |  | 2025-10-05 | 16
[5 empty] | 9000220 | 383 | 320001TUR | Stephen Yee | LEVEL 30 | TEMPS (SMALL) | LEVEL 30 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-09 | [7 empty] | 3 | 0.375 | 1 | 1 | 2026-01-16 | 2026-01-19 | 2026-01-21 | OVER DUE | 2025-10-27 | [7 empty] | Kerri Pandolfi | 383 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 383-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 - SPIDER BOXES | 1953 |  | PF.383 | 9000220 |  | PF.383 | PF.383 | 0% |  |  | 2026-01-02 |  | 2025-10-05 | 76
[5 empty] | 9000220 | 384 | 320001TUR | Stephen Yee | LEVEL 31 | TEMPS (SMALL) | LEVEL 31 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-31 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-11-07 | 2025-11-08 | 2025-11-10 |  | 2025-11-10 | [7 empty] | Kerri Pandolfi | 384 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 384-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 - SPIDER BOXES | 1955 |  | PF.384 | 9000220 |  | PF.384 | PF.384 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[5 empty] | 9000220 | 385 | 320001TUR | Stephen Yee | LEVEL 32 | TEMPS (SMALL) | LEVEL 32 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-07 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-11-14 | 2025-11-15 | 2025-11-17 |  | 2025-11-17 | [7 empty] | Kerri Pandolfi | 385 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 385-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 - SPIDER BOXES | 1957 | INSTALL - LEVEL 32 - TEMP WIRING | PF.385 | 9000220 |  | PF.385 | PF.385 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[5 empty] | 9000220 | 386 | 320001TUR | Stephen Yee | LEVEL 33 | TEMPS (SMALL) | LEVEL 33 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-14 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-11-21 | 2025-11-22 | 2025-11-24 |  | 2025-11-24 | [7 empty] | Kerri Pandolfi | 386 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 386-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 - SPIDER BOXES | 1959 | LEVEL 37 - TIER 2 - 75KVA PDU | PF.386 | 9000220 |  | PF.386 | PF.386 | 0% |  |  | 2025-11-07 |  | 2025-10-05 | 36
[5 empty] | 9000220 | 387 | 320001TUR | Stephen Yee | LEVEL 34 | TEMPS (SMALL) | LEVEL 34 - TIER 2 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-21 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-11-28 | 2025-11-29 | 2025-12-01 |  | 2025-12-01 | [7 empty] | Kerri Pandolfi | 387 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 387-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 - SPIDER BOXES | 1961 | INSTALL - LEVEL 34 - TEMP WIRING | PF.387 | 9000220 |  | PF.387 | PF.387 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[5 empty] | 9000220 | 388 | 320001TUR | Stephen Yee | LEVEL 35 | TEMPS (SMALL) | LEVEL 35 - TIER 3 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-11-28 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-12-05 | 2025-12-06 | 2025-12-08 |  | 2025-12-08 | [7 empty] | Kerri Pandolfi | 388 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 388-320001TUR | PRE-FAB - LEVEL 35 - LEVEL 35 - TIER 3 - SPIDER BOXES | 1963 | INSTALL - LEVEL 35 - TEMP WIRING | PF.388 | 9000220 |  | PF.388 | PF.388 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[5 empty] | 9000220 | 389 | 320001TUR | Stephen Yee | LEVEL 36 | TEMPS (SMALL) | LEVEL 36 - TIER 3 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-05 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | [7 empty] | Kerri Pandolfi | 389 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 389-320001TUR | PRE-FAB - LEVEL 36 - LEVEL 36 - TIER 3 - SPIDER BOXES | 1965 | INSTALL - LEVEL 36 - TEMP WIRING | PF.389 | 9000220 |  | PF.389 | PF.389 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000220 | 390 | 320001TUR | Stephen Yee | LEVEL 37 | TEMPS (SMALL) | LEVEL 37 - AMENITY/MEP PH - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-12-12 | [7 empty] | 3 | 0.375 | 1 | 1 | 2025-12-19 | 2025-12-22 | 2025-12-24 |  | 2025-12-24 | [7 empty] | Kerri Pandolfi | 390 | 25 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 25 | 390-320001TUR | PRE-FAB - LEVEL 37 - LEVEL 37 - AMENITY/MEP PH - SPIDER BOXES | 1969 |  | PF.390 | 9000220 |  | PF.390 | PF.390 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[5 empty] | 9000220 | 391 | 320001TUR | Stephen Yee | LEVEL 38 | TEMPS (SMALL) | LEVEL 38 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 3 | 0.375 | 1 | 1 | 2026-01-09 | 2026-01-10 | 2026-01-12 |  | 2026-01-12 | [7 empty] | Kerri Pandolfi | 391 | 26 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 26 | 391-320001TUR | PRE-FAB - LEVEL 38 - LEVEL 38 - SPIDER BOXES | 1972 | LEVEL 38 - 75KVA PDU | PF.391 | 9000220 |  | PF.391 | PF.391 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[5 empty] | 9000220 | 392 | 320001TUR | Stephen Yee | LEVEL 39 | TEMPS (SMALL) | LEVEL 39 - SPIDER BOXES | 3 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-02-02 | [7 empty] | 3 | 0.375 | 1 | 1 | 2026-02-09 | 2026-02-10 | 2026-02-12 |  | 2026-02-12 | [7 empty] | Kerri Pandolfi | 392 | 26 |  | 0 | 0 | 1 | 3 | 2 | 6 | 1 | 1 | 0 | -1 | 26 | 392-320001TUR | PRE-FAB - LEVEL 39 - LEVEL 39 - SPIDER BOXES | 1975 | INSTALL - LEVEL 39 - TEMP WIRING | PF.392 | 9000220 |  | PF.392 | PF.392 | 0% |  |  | 2026-01-26 |  | 2025-10-05 | 92
[5 empty] | 9000063 | 001 | 320001TUR | Stephen Yee | LEVEL 3 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 3 - Load Centers 125A | 8 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-02 | 2025-08-13 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 55.28 | 3.455 | 4 | 2 | 2025-09-09 | 2025-09-15 | 2025-09-17 |  | 2025-10-14 |  | 2025-09-17 | TRUE |  | Image 2025-09-10 13-03-36.jpeg |  | 1 | Kerri Pandolfi | 1 | 25 |  | 7.625 | 61 | 6.91 | 55.28 |  | 0 | 6.91 | -6.91 | 6.91 | 0 | 25 | 001-320001TUR | PRE-FAB - LEVEL 3 - Level 3 - Load Centers 125A | 189 | Level 3 - Load Centers 150A | PF.001 | 9000063 |  | PF.001 | PF.001 | 100% | TRUE |  | 2025-08-26 |  | 2025-10-05 | -19 | TRUE
[5 empty] | 9000063 | 002 | 320001TUR | Stephen Yee | LEVEL 3 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 3 - Load Centers 150A | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-05 | 2025-08-13 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-09-12 | 2025-09-17 | 2025-09-19 |  | 2025-10-20 |  | 2025-09-19 | TRUE |  | Image 2025-09-10 13-04-02.jpeg |  | 1 | Kerri Pandolfi | 2 | 25 |  | 9.8 | 49 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 7.92 | 0 | 25 | 002-320001TUR | PRE-FAB - LEVEL 3 - Level 3 - Load Centers 150A | 205 | Level 4 - Load Centers 125A | PF.002 | 9000063 |  | PF.002 | PF.002 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000063 | 003 | 320001TUR | Stephen Yee | LEVEL 4 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 4 - Load Centers 125A | 8 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-09 | 2025-08-27 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 55.28 | 3.455 | 4 | 2 | 2025-09-16 | 2025-09-21 | 2025-09-23 |  | 2025-10-27 |  | 2025-09-23 | TRUE |  | Image 2025-09-10 13-05-07.jpeg |  | 1 | Kerri Pandolfi | 3 | 25 |  | 5.125 | 41 | 6.91 | 55.28 |  | 0 | 6.91 | -6.91 | 5.125 | -1.785 | 25 | 003-320001TUR | PRE-FAB - LEVEL 4 - Level 4 - Load Centers 125A | 212 | Level 4 - Load Centers 150A | PF.003 | 9000063 |  | PF.003 | PF.003 | 100% | TRUE |  | 2025-09-02 |  | 2025-10-05 | -14 | TRUE
[5 empty] | 9000063 | 004 | 320001TUR | Stephen Yee | LEVEL 4 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 4 - Load Centers 150A | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-11 | 2025-08-27 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-09-18 | 2025-09-23 | 2025-09-25 |  | 2025-11-07 |  | 2025-09-25 | TRUE |  | Image 2025-09-10 13-05-43.jpeg |  | 1 | Kerri Pandolfi | 4 | 25 |  | 6.2 | 31 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 6.2 | -1.72 | 25 | 004-320001TUR | PRE-FAB - LEVEL 4 - Level 4 - Load Centers 150A | 222 | Level 5 - Load Centers 125A | PF.004 | 9000063 |  | PF.004 | PF.004 | 100% | TRUE |  | 2025-09-04 |  | 2025-10-05 | -12 | TRUE
[5 empty] | 9000063 | 005 | 320001TUR | Stephen Yee | LEVEL 5 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 5 - Load Centers 125A | 8 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-16 | 2025-09-09 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 55.28 | 3.455 | 4 | 2 | 2025-09-23 | 2025-09-28 | 2025-09-30 |  | 2025-11-17 |  | 2025-09-30 | TRUE |  | Image 2025-09-29 13-51-21.jpeg |  | 1 | Kerri Pandolfi | 5 | 25 |  | 3.9375 | 31.5 | 6.91 | 55.28 |  | 0 | 6.91 | -6.91 | 3.9375 | -2.9725 | 25 | 005-320001TUR | PRE-FAB - LEVEL 5 - Level 5 - Load Centers 125A | 229 | Level 5 - Load Centers 150A | PF.005 | 9000063 |  | PF.005 | PF.005 | 100% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000063 | 006 | 320001TUR | Stephen Yee | LEVEL 5 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 5 - Load Centers 150A | 5 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-17 | 2025-09-09 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-09-24 | 2025-09-29 | 2025-10-01 |  | 2025-11-24 |  | 2025-10-01 | TRUE |  | Image 2025-09-29 13-52-00.jpeg |  | 1 | Kerri Pandolfi | 6 | 25 |  | 6.8 | 34 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 6.8 | -1.12 | 25 | 006-320001TUR | PRE-FAB - LEVEL 5 - Level 5 - Load Centers 150A | 241 | Level 7 - Load Centers 125A | PF.006 | 9000063 |  | PF.006 | PF.006 | 100% | TRUE |  | 2025-09-10 |  | 2025-10-05 | -8 | TRUE
[5 empty] | 9000063 | 007 | 320001TUR | Stephen Yee | LEVEL 7 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 7 - Load Centers 125A | 8 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-23 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 55.28 | 3.455 | 4 | 2 | 2025-09-30 | 2025-10-04 | 2025-10-06 |  | 2025-12-01 | DATES MISALIGNED | 2025-10-06 |  |  | 2025-10-01 |  | 1 | Kerri Pandolfi | 7 | 25 |  | 4.625 | 37 | 6.91 | 55.28 |  | 0 | 6.91 | -6.91 | 4.625 | -2.285 | 25 | 007-320001TUR | PRE-FAB - LEVEL 7 - Level 7 - Load Centers 125A | 247 | Level 7 - Load Centers 150A | PF.007 | 9000063 |  | PF.007 | PF.007 | 99% |  |  | 2025-09-16 |  | 2025-10-05 | -4 | TRUE
[5 empty] | 9000063 | 008 | 320001TUR | Stephen Yee | LEVEL 7 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 7 - Load Centers 150A | 4 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-25 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 31.68 | 1.98 | 2 | 2 | 2025-10-02 | 2025-10-05 | 2025-10-07 |  | 2025-12-08 | DATES MISALIGNED | 2025-10-07 |  |  | 2025-10-01 |  | 1 | Kerri Pandolfi | 8 | 25 |  | 6.625 | 26.5 | 7.92 | 31.68 |  | 0 | 7.92 | -7.92 | 6.625 | -1.295 | 25 | 008-320001TUR | PRE-FAB - LEVEL 7 - Level 7 - Load Centers 150A | 256 | Level 8 - Load Centers 125A | PF.008 | 9000063 |  | PF.008 | PF.008 | 99% |  |  | 2025-09-18 |  | 2025-10-05 | -2 | TRUE
[5 empty] | 9000063 | 009 | 320001TUR | Stephen Yee | LEVEL 8 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 8 - Load Centers 125A | 7 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-24 | 2025-09-30 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 48.37 | 3.0231 | 4 | 2 | 2025-10-01 | 2025-10-07 | 2025-10-09 |  | 2025-12-15 | DATES MISALIGNED | 2025-10-09 |  |  |  |  | 1 | Kerri Pandolfi | 9 | 25 |  | 4.5714 | 32 | 6.91 | 48.37 |  | 0 | 6.91 | -6.91 | 4.5714 | -2.3386 | 25 | 009-320001TUR | PRE-FAB - LEVEL 8 - Level 8 - Load Centers 125A | 267 | Level 8 - Load Centers 150A | PF.009 | 9000063 |  | PF.009 | PF.009 | 75% |  |  | 2025-09-17 |  | 2025-10-05 | -3 | TRUE
[5 empty] | 9000063 | 010 | 320001TUR | Stephen Yee | LEVEL 8 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 8 - Load Centers 150A | 5 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-01 | 2025-10-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-08 | 2025-10-12 | 2025-10-14 |  | 2025-12-22 | DATES MISALIGNED | 2025-10-14 |  |  |  |  | 1 | Kerri Pandolfi | 10 | 25 |  | 2.8 | 14 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 2.8 | -5.12 | 25 | 010-320001TUR | PRE-FAB - LEVEL 8 - Level 8 - Load Centers 150A | 276 | Level 9 - Load Centers 125A | PF.010 | 9000063 |  | PF.010 | PF.010 | 35.35% |  |  | 2025-09-24 |  | 2025-10-05 | 4 | TRUE
[5 empty] | 9000063 | 011 | 320001TUR | Stephen Yee | LEVEL 9 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 9 - Load Centers 125A | 7 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-01 | 2025-10-02 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 48.37 | 3.0231 | 4 | 2 | 2025-10-08 | 2025-10-14 | 2025-10-16 |  | 2025-12-29 | DATES MISALIGNED | 2025-10-16 |  |  |  |  | 1 | Kerri Pandolfi | 11 | 25 |  | 0.57143 | 4 | 6.91 | 48.37 |  | 0 | 6.91 | -6.91 | 0.57143 | -6.3386 | 25 | 011-320001TUR | PRE-FAB - LEVEL 9 - Level 9 - Load Centers 125A | 287 | Level 9 - Load Centers 150A | PF.011 | 9000063 |  | PF.011 | PF.011 | 8.27% |  |  | 2025-09-24 |  | 2025-10-05 | 4 | TRUE
[5 empty] | 9000063 | 012 | 320001TUR | Stephen Yee | LEVEL 9 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 9 - Load Centers 150A | 5 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-03 | 2025-10-02 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-10 | 2025-10-15 | 2025-10-17 |  | 2026-01-05 | DATES MISALIGNED | 2025-10-17 |  |  |  |  | 1 | Kerri Pandolfi | 12 | 26 |  | 0.2 | 1 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.2 | -7.72 | 26 | 012-320001TUR | PRE-FAB - LEVEL 9 - Level 9 - Load Centers 150A | 298 | Level 10 - Load Centers 125A | PF.012 | 9000063 |  | PF.012 | PF.012 | 2.525% |  |  | 2025-09-26 |  | 2025-10-05 | 6 | TRUE
[5 empty] | 9000063 | 013 | 320001TUR | Stephen Yee | LEVEL 10 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 10 - Load Centers 125A | 9 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-07 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 62.19 | 3.8869 | 4 | 2 | 2025-10-14 | 2025-10-20 | 2025-10-22 |  | 2026-01-12 | DATES MISALIGNED | 2025-10-22 |  |  |  |  | 1 | Kerri Pandolfi | 13 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 013-320001TUR | PRE-FAB - LEVEL 10 - Level 10 - Load Centers 125A | 303 | Level 10 - Load Centers 150A | PF.013 | 9000063 |  | PF.013 | PF.013 | 4.824% |  |  | 2025-09-30 |  | 2025-10-05 | 8 | TRUE
[5 empty] | 9000063 | 014 | 320001TUR | Stephen Yee | LEVEL 10 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 10 - Load Centers 150A | 5 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-10 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-17 | 2025-10-22 | 2025-10-24 |  | 2026-01-20 | DATES MISALIGNED | 2025-10-24 |  |  |  |  | 1 | Kerri Pandolfi | 14 | 26 |  | 0.7 | 3.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.7 | -7.22 | 26 | 014-320001TUR | PRE-FAB - LEVEL 10 - Level 10 - Load Centers 150A | 320 | Level 11 - Load Centers 125A | PF.014 | 9000063 |  | PF.014 | PF.014 | 8.838% |  |  | 2025-10-03 |  | 2025-10-05 | 11 | TRUE
[5 empty] | 9000063 | 015 | 320001TUR | Stephen Yee | LEVEL 11 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 11 - Load Centers 125A | 9 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-14 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 62.19 | 3.8869 | 4 | 2 | 2025-10-21 | 2025-10-26 | 2025-10-28 |  | 2026-01-26 | DATES MISALIGNED | 2025-10-28 |  |  |  |  | 1 | Kerri Pandolfi | 15 | 26 |  | 0.44444 | 4 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.44444 | -6.4656 | 26 | 015-320001TUR | PRE-FAB - LEVEL 11 - Level 11 - Load Centers 125A | 330 | Level 11 - Load Centers 150A | PF.015 | 9000063 |  | PF.015 | PF.015 | 6.432% |  |  | 2025-10-07 |  | 2025-10-05 | 13 | TRUE
[5 empty] | 9000063 | 016 | 320001TUR | Stephen Yee | LEVEL 11 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 11 - Load Centers 150A | 5 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-16 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-23 | 2025-10-28 | 2025-10-30 |  | 2026-02-02 | DATES MISALIGNED | 2025-10-30 |  |  |  |  | 1 | Kerri Pandolfi | 16 | 26 |  | 0.7 | 3.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.7 | -7.22 | 26 | 016-320001TUR | PRE-FAB - LEVEL 11 - Level 11 - Load Centers 150A | 345 | Level 12 - Load Centers 125A | PF.016 | 9000063 |  | PF.016 | PF.016 | 8.838% |  |  | 2025-10-09 |  | 2025-10-05 | 15 | TRUE
[5 empty] | 9000063 | 017 | 320001TUR | Stephen Yee | LEVEL 12 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 12 - Load Centers 125A | 9 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-21 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 62.19 | 3.8869 | 4 | 2 | 2025-10-28 | 2025-11-02 | 2025-11-04 |  | 2026-02-09 | DATES MISALIGNED | 2025-11-04 |  |  |  |  | 1 | Kerri Pandolfi | 17 | 26 |  | 0.44444 | 4 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.44444 | -6.4656 | 26 | 017-320001TUR | PRE-FAB - LEVEL 12 - Level 12 - Load Centers 125A | 370 | Level 12 - Load Centers 150A | PF.017 | 9000063 |  | PF.017 | PF.017 | 6.432% |  |  | 2025-10-14 |  | 2025-10-05 | 18 | TRUE
[5 empty] | 9000063 | 018 | 320001TUR | Stephen Yee | LEVEL 12 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 12 - Load Centers 150A | 5 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-22 | 2025-10-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 39.6 | 2.475 | 3 | 2 | 2025-10-29 | 2025-11-03 | 2025-11-05 |  | 2026-02-17 | DATES MISALIGNED | 2025-11-05 |  |  |  |  | 1 | Kerri Pandolfi | 18 | 26 |  | 0.7 | 3.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.7 | -7.22 | 26 | 018-320001TUR | PRE-FAB - LEVEL 12 - Level 12 - Load Centers 150A | 382 | Level 13 - Load Centers 125A | PF.018 | 9000063 |  | PF.018 | PF.018 | 8.838% |  |  | 2025-10-15 |  | 2025-10-05 | 19 | TRUE
[5 empty] | 9000063 | 019 | 320001TUR | Stephen Yee | LEVEL 13 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 13 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-28 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-04 | 2025-11-08 | 2025-11-10 |  | 2026-02-23 | DATES MISALIGNED | 2025-11-10 |  |  |  |  | 1 | Kerri Pandolfi | 19 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 019-320001TUR | PRE-FAB - LEVEL 13 - Level 13 - Load Centers 125A | 399 | Level 13 - Load Centers 150A | PF.019 | 9000063 |  | PF.019 | PF.019 | 4.02% |  |  | 2025-10-21 |  | 2025-10-05 | 23 | TRUE
[5 empty] | 9000063 | 020 | 320001TUR | Stephen Yee | LEVEL 13 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 13 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-30 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-11-06 | 2025-11-11 | 2025-11-13 |  | 2026-03-02 | DATES MISALIGNED | 2025-11-13 |  |  |  |  | 1 | Kerri Pandolfi | 20 | 26 |  | 1 | 5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 1 | -6.92 | 26 | 020-320001TUR | PRE-FAB - LEVEL 13 - Level 13 - Load Centers 150A | 409 | Level 14 - Load Centers 125A | PF.020 | 9000063 |  | PF.020 | PF.020 | 12.63% |  |  | 2025-10-23 |  | 2025-10-05 | 25 | TRUE
[5 empty] | 9000063 | 021 | 320001TUR | Stephen Yee | LEVEL 14 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 14 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-04 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-11 | 2025-11-15 | 2025-11-17 |  | 2026-03-09 | DATES MISALIGNED | 2025-11-17 |  |  |  |  | 1 | Kerri Pandolfi | 21 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 021-320001TUR | PRE-FAB - LEVEL 14 - Level 14 - Load Centers 125A | 433 | Level 14 - Load Centers 150A | PF.021 | 9000063 |  | PF.021 | PF.021 | 4.02% |  |  | 2025-10-28 |  | 2025-10-05 | 28 | TRUE
[5 empty] | 9000063 | 022 | 320001TUR | Stephen Yee | LEVEL 14 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 14 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-05 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-11-12 | 2025-11-17 | 2025-11-19 |  | 2026-03-16 | DATES MISALIGNED | 2025-11-19 |  |  |  |  | 1 | Kerri Pandolfi | 22 | 26 |  | 0.5 | 2.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.5 | -7.42 | 26 | 022-320001TUR | PRE-FAB - LEVEL 14 - Level 14 - Load Centers 150A | 451 | Level 15 - Load Centers 125A | PF.022 | 9000063 |  | PF.022 | PF.022 | 6.313% |  |  | 2025-10-29 |  | 2025-10-05 | 29 | TRUE
[5 empty] | 9000063 | 023 | 320001TUR | Stephen Yee | LEVEL 15 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 15 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-11 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-18 | 2025-11-22 | 2025-11-24 |  | 2026-03-23 | DATES MISALIGNED | 2025-11-24 |  |  |  |  | 1 | Kerri Pandolfi | 23 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 023-320001TUR | PRE-FAB - LEVEL 15 - Level 15 - Load Centers 125A | 471 | Level 15 - Load Centers 150A | PF.023 | 9000063 |  | PF.023 | PF.023 | 4.02% |  |  | 2025-11-04 |  | 2025-10-05 | 33 | TRUE
[5 empty] | 9000063 | 024 | 320001TUR | Stephen Yee | LEVEL 15 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 15 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-12 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-11-19 | 2025-11-23 | 2025-11-25 |  | 2026-03-30 | DATES MISALIGNED | 2025-11-25 |  |  |  |  | 1 | Kerri Pandolfi | 24 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 024-320001TUR | PRE-FAB - LEVEL 15 - Level 15 - Load Centers 150A | 489 | Level 16 - Load Centers 125A | PF.024 | 9000063 |  | PF.024 | PF.024 | 5.051% |  |  | 2025-11-05 |  | 2025-10-05 | 34 | TRUE
[5 empty] | 9000063 | 025 | 320001TUR | Stephen Yee | LEVEL 16 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 16 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-18 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-25 | 2025-11-29 | 2025-12-01 |  | 2026-04-06 | DATES MISALIGNED | 2025-12-01 |  |  |  |  | 1 | Kerri Pandolfi | 25 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 025-320001TUR | PRE-FAB - LEVEL 16 - Level 16 - Load Centers 125A | 491 | Level 16 - Load Centers 150A | PF.025 | 9000063 |  | PF.025 | PF.025 | 4.02% |  |  | 2025-11-11 |  | 2025-10-05 | 38 | TRUE
[5 empty] | 9000063 | 026 | 320001TUR | Stephen Yee | LEVEL 16 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 16 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-19 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-11-26 | 2025-12-01 | 2025-12-03 |  | 2026-04-13 | DATES MISALIGNED | 2025-12-03 |  |  |  |  | 1 | Kerri Pandolfi | 26 | 26 |  | 0.6 | 3 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.6 | -7.32 | 26 | 026-320001TUR | PRE-FAB - LEVEL 16 - Level 16 - Load Centers 150A | 513 | Level 17 - Load Centers 125A | PF.026 | 9000063 |  | PF.026 | PF.026 | 7.576% |  |  | 2025-11-12 |  | 2025-10-05 | 39 | TRUE
[5 empty] | 9000063 | 027 | 320001TUR | Stephen Yee | LEVEL 17 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 17 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-20 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-11-27 | 2025-12-03 | 2025-12-05 |  | 2026-04-21 | DATES MISALIGNED | 2025-12-05 |  |  |  |  | 1 | Kerri Pandolfi | 27 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 027-320001TUR | PRE-FAB - LEVEL 17 - Level 17 - Load Centers 125A | 526 | Level 17 - Load Centers 150A | PF.027 | 9000063 |  | PF.027 | PF.027 | 4.02% |  |  | 2025-11-13 |  | 2025-10-05 | 40 | TRUE
[5 empty] | 9000063 | 028 | 320001TUR | Stephen Yee | LEVEL 17 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 17 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-26 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-03 | 2025-12-07 | 2025-12-09 |  | 2026-04-28 | DATES MISALIGNED | 2025-12-09 |  |  |  |  | 1 | Kerri Pandolfi | 28 | 26 |  | 0.7 | 3.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.7 | -7.22 | 26 | 028-320001TUR | PRE-FAB - LEVEL 17 - Level 17 - Load Centers 150A | 555 | Level 18 - Load Centers 125A | PF.028 | 9000063 |  | PF.028 | PF.028 | 8.838% |  |  | 2025-11-19 |  | 2025-10-05 | 44 | TRUE
[5 empty] | 9000063 | 029 | 320001TUR | Stephen Yee | LEVEL 18 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 18 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-27 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-04 | 2025-12-10 | 2025-12-12 |  | 2026-05-05 | DATES MISALIGNED | 2025-12-12 |  |  |  |  | 1 | Kerri Pandolfi | 29 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 029-320001TUR | PRE-FAB - LEVEL 18 - Level 18 - Load Centers 125A | 563 | Level 18 - Load Centers 150A | PF.029 | 9000063 |  | PF.029 | PF.029 | 4.02% |  |  | 2025-11-20 |  | 2025-10-05 | 45 | TRUE
[5 empty] | 9000063 | 030 | 320001TUR | Stephen Yee | LEVEL 18 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 18 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-03 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-10 | 2025-12-13 | 2025-12-15 |  | 2026-05-12 | DATES MISALIGNED | 2025-12-15 |  |  |  |  | 1 | Kerri Pandolfi | 30 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 030-320001TUR | PRE-FAB - LEVEL 18 - Level 18 - Load Centers 150A | 585 | Level 19 - Load Centers 125A | PF.030 | 9000063 |  | PF.030 | PF.030 | 5.051% |  |  | 2025-11-26 |  | 2025-10-05 | 49 | TRUE
[5 empty] | 9000063 | 031 | 320001TUR | Stephen Yee | LEVEL 19 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 19 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-03 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-10 | 2025-12-16 | 2025-12-18 |  | 2026-05-19 | DATES MISALIGNED | 2025-12-18 |  |  |  |  | 1 | Kerri Pandolfi | 31 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 031-320001TUR | PRE-FAB - LEVEL 19 - Level 19 - Load Centers 125A | 595 | Level 19 - Load Centers 150A | PF.031 | 9000063 |  | PF.031 | PF.031 | 4.824% |  |  | 2025-11-26 |  | 2025-10-05 | 49 | TRUE
[5 empty] | 9000063 | 032 | 320001TUR | Stephen Yee | LEVEL 19 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 19 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-10 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-17 | 2025-12-20 | 2025-12-22 |  | 2026-05-27 | DATES MISALIGNED | 2025-12-22 |  |  |  |  | 1 | Kerri Pandolfi | 32 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 032-320001TUR | PRE-FAB - LEVEL 19 - Level 19 - Load Centers 150A | 622 | Level 20 - Load Centers 125A | PF.032 | 9000063 |  | PF.032 | PF.032 | 5.051% |  |  | 2025-12-03 |  | 2025-10-05 | 54 | TRUE
[5 empty] | 9000063 | 033 | 320001TUR | Stephen Yee | LEVEL 20 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 20 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-09 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-16 | 2025-12-22 | 2025-12-24 |  | 2026-06-03 | DATES MISALIGNED | 2025-12-24 |  |  |  |  | 1 | Kerri Pandolfi | 33 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 033-320001TUR | PRE-FAB - LEVEL 20 - Level 20 - Load Centers 125A | 633 | Level 20 - Load Centers 150A | PF.033 | 9000063 |  | PF.033 | PF.033 | 4.824% |  |  | 2025-12-02 |  | 2025-10-05 | 53 | TRUE
[5 empty] | 9000063 | 034 | 320001TUR | Stephen Yee | LEVEL 20 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 20 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-17 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-24 | 2025-12-27 | 2025-12-29 |  | 2026-01-02 |  | 2025-12-29 |  |  |  |  | 1 | Kerri Pandolfi | 34 | 26 |  | 0.25 | 1.25 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.25 | -7.67 | 26 | 034-320001TUR | PRE-FAB - LEVEL 20 - Level 20 - Load Centers 150A | 648 | Level 21 - Load Centers 125A | PF.034 | 9000063 |  | PF.034 | PF.034 | 3.157% |  |  | 2025-12-10 |  | 2025-10-05 | 59 | TRUE
[5 empty] | 9000063 | 035 | 320001TUR | Stephen Yee | LEVEL 21 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 21 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-18 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-25 | 2025-12-31 | 2026-01-02 |  | 2026-01-07 |  | 2026-01-02 |  |  |  |  | 1 | Kerri Pandolfi | 35 | 26 |  | 0.36111 | 3.25 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.36111 | -6.5489 | 26 | 035-320001TUR | PRE-FAB - LEVEL 21 - Level 21 - Load Centers 125A | 672 | Level 21 - Load Centers 150A | PF.035 | 9000063 |  | PF.035 | PF.035 | 5.226% |  |  | 2025-12-11 |  | 2025-10-05 | 60 | TRUE
[5 empty] | 9000063 | 036 | 320001TUR | Stephen Yee | LEVEL 21 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 21 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-24 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2025-12-31 | 2026-01-04 | 2026-01-06 |  | 2026-01-07 |  | 2026-01-06 |  |  |  |  | 1 | Kerri Pandolfi | 36 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 036-320001TUR | PRE-FAB - LEVEL 21 - Level 21 - Load Centers 150A | 687 | Level 22 - Load Centers 125A | PF.036 | 9000063 |  | PF.036 | PF.036 | 5.051% |  |  | 2025-12-17 |  | 2025-10-05 | 64 | TRUE
[5 empty] | 9000063 | 037 | 320001TUR | Stephen Yee | LEVEL 22 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 22 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-24 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2025-12-31 | 2026-01-06 | 2026-01-08 |  | 2026-01-12 |  | 2026-01-08 |  |  |  |  | 1 | Kerri Pandolfi | 37 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 037-320001TUR | PRE-FAB - LEVEL 22 - Level 22 - Load Centers 125A | 712 | Level 22 - Load Centers 150A | PF.037 | 9000063 |  | PF.037 | PF.037 | 4.02% |  |  | 2025-12-17 |  | 2025-10-05 | 64 | TRUE
[5 empty] | 9000063 | 038 | 320001TUR | Stephen Yee | LEVEL 22 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 22 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-31 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-07 | 2026-01-10 | 2026-01-12 |  | 2026-01-12 |  | 2026-01-12 |  |  |  |  | 1 | Kerri Pandolfi | 38 | 26 |  | 0.3 | 1.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.3 | -7.62 | 26 | 038-320001TUR | PRE-FAB - LEVEL 22 - Level 22 - Load Centers 150A | 727 | Level 23 - Load Centers 125A | PF.038 | 9000063 |  | PF.038 | PF.038 | 3.788% |  |  | 2025-12-24 |  | 2025-10-05 | 69 | TRUE
[5 empty] | 9000063 | 039 | 320001TUR | Stephen Yee | LEVEL 23 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 23 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-30 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-01-06 | 2026-01-12 | 2026-01-14 |  | 2026-01-15 |  | 2026-01-14 |  |  |  |  | 1 | Kerri Pandolfi | 39 | 26 |  | 0.27778 | 2.5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.27778 | -6.6322 | 26 | 039-320001TUR | PRE-FAB - LEVEL 23 - Level 23 - Load Centers 125A | 760 | Level 23 - Load Centers 150A | PF.039 | 9000063 |  | PF.039 | PF.039 | 4.02% |  |  | 2025-12-23 |  | 2025-10-05 | 68 | TRUE
[5 empty] | 9000063 | 040 | 320001TUR | Stephen Yee | LEVEL 23 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 23 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-09 | 2026-01-14 | 2026-01-16 | OVER DUE | 2026-01-15 |  | 2026-01-16 |  |  |  |  | 1 | Kerri Pandolfi | 40 | 26 |  | 0.3 | 1.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.3 | -7.62 | 26 | 040-320001TUR | PRE-FAB - LEVEL 23 - Level 23 - Load Centers 150A | 774 | Level 24 - Load Centers 125A | PF.040 | 9000063 |  | PF.040 | PF.040 | 3.788% |  |  | 2025-12-26 |  | 2025-10-05 | 71 | TRUE
[5 empty] | 9000063 | 041 | 320001TUR | Stephen Yee | LEVEL 24 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 24 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-07 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-01-14 | 2026-01-20 | 2026-01-22 | OVER DUE | 2026-01-21 |  | 2026-01-22 |  |  |  |  | 1 | Kerri Pandolfi | 41 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 041-320001TUR | PRE-FAB - LEVEL 24 - Level 24 - Load Centers 125A | 787 | Level 24 - Load Centers 150A | PF.041 | 9000063 |  | PF.041 | PF.041 | 4.824% |  |  | 2025-12-31 |  | 2025-10-05 | 74 | TRUE
[5 empty] | 9000063 | 042 | 320001TUR | Stephen Yee | LEVEL 24 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 24 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-14 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-21 | 2026-01-24 | 2026-01-26 | OVER DUE | 2026-01-21 |  | 2026-01-26 |  |  |  |  | 1 | Kerri Pandolfi | 42 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 042-320001TUR | PRE-FAB - LEVEL 24 - Level 24 - Load Centers 150A | 825 | Level 25 - Load Centers 125A | PF.042 | 9000063 |  | PF.042 | PF.042 | 5.051% |  |  | 2026-01-07 |  | 2025-10-05 | 79 | TRUE
[5 empty] | 9000063 | 043 | 320001TUR | Stephen Yee | LEVEL 25 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 25 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-13 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-01-20 | 2026-01-26 | 2026-01-28 | OVER DUE | 2026-01-26 |  | 2026-01-28 |  |  |  |  | 1 | Kerri Pandolfi | 43 | 26 |  | 0.44444 | 4 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.44444 | -6.4656 | 26 | 043-320001TUR | PRE-FAB - LEVEL 25 - Level 25 - Load Centers 125A | 833 | Level 25 - Load Centers 150A | PF.043 | 9000063 |  | PF.043 | PF.043 | 6.432% |  |  | 2026-01-06 |  | 2025-10-05 | 78 | TRUE
[5 empty] | 9000063 | 044 | 320001TUR | Stephen Yee | LEVEL 25 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 25 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-16 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-23 | 2026-01-28 | 2026-01-30 | OVER DUE | 2026-01-26 |  | 2026-01-30 |  |  |  |  | 1 | Kerri Pandolfi | 44 | 26 |  | 0.4 | 2 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.4 | -7.52 | 26 | 044-320001TUR | PRE-FAB - LEVEL 25 - Level 25 - Load Centers 150A | 871 | Level 26 - Load Centers 125A | PF.044 | 9000063 |  | PF.044 | PF.044 | 5.051% |  |  | 2026-01-09 |  | 2025-10-05 | 81 | TRUE
[5 empty] | 9000063 | 045 | 320001TUR | Stephen Yee | LEVEL 26 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 26 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-20 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-01-27 | 2026-02-01 | 2026-02-03 | OVER DUE | 2026-01-29 |  | 2026-02-03 |  |  |  |  | 1 | Kerri Pandolfi | 45 | 26 |  | 0.55556 | 5 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.55556 | -6.3544 | 26 | 045-320001TUR | PRE-FAB - LEVEL 26 - Level 26 - Load Centers 125A | 883 | Level 26 - Load Centers 150A | PF.045 | 9000063 |  | PF.045 | PF.045 | 8.04% |  |  | 2026-01-13 |  | 2025-10-05 | 83 | TRUE
[5 empty] | 9000063 | 046 | 320001TUR | Stephen Yee | LEVEL 26 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 26 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-22 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-01-29 | 2026-02-03 | 2026-02-05 | OVER DUE | 2026-01-29 | DATES MISALIGNED | 2026-02-05 |  |  |  |  | 1 | Kerri Pandolfi | 46 | 26 |  | 0.1 | 0.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.1 | -7.82 | 26 | 046-320001TUR | PRE-FAB - LEVEL 26 - Level 26 - Load Centers 150A | 914 | Level 27 - Load Centers 125A | PF.046 | 9000063 |  | PF.046 | PF.046 | 1.263% |  |  | 2026-01-15 |  | 2025-10-05 | 85 | TRUE
[5 empty] | 9000063 | 047 | 320001TUR | Stephen Yee | LEVEL 27 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 27 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-03 | 2026-02-08 | 2026-02-10 | OVER DUE | 2026-02-03 | DATES MISALIGNED | 2026-02-10 |  |  |  |  | 1 | Kerri Pandolfi | 47 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 047-320001TUR | PRE-FAB - LEVEL 27 - Level 27 - Load Centers 125A | 919 | Level 27 - Load Centers 150A | PF.047 | 9000063 |  | PF.047 | PF.047 | 4.824% |  |  | 2026-01-20 |  | 2025-10-05 | 88 | TRUE
[5 empty] | 9000063 | 048 | 320001TUR | Stephen Yee | LEVEL 27 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 27 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-29 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-02-05 | 2026-02-10 | 2026-02-12 | OVER DUE | 2026-02-03 | DATES MISALIGNED | 2026-02-12 |  |  |  |  | 1 | Kerri Pandolfi | 48 | 26 |  | 0.15 | 0.75 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.15 | -7.77 | 26 | 048-320001TUR | PRE-FAB - LEVEL 27 - Level 27 - Load Centers 150A | 953 | Level 28 - Load Centers 125A | PF.048 | 9000063 |  | PF.048 | PF.048 | 1.894% |  |  | 2026-01-22 |  | 2025-10-05 | 90 | TRUE
[5 empty] | 9000063 | 049 | 320001TUR | Stephen Yee | LEVEL 28 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 28 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-03 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-10 | 2026-02-15 | 2026-02-17 | OVER DUE | 2026-02-06 | DATES MISALIGNED | 2026-02-17 |  |  |  |  | 1 | Kerri Pandolfi | 49 | 26 |  | 0.22222 | 2 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.22222 | -6.6878 | 26 | 049-320001TUR | PRE-FAB - LEVEL 28 - Level 28 - Load Centers 125A | 959 | Level 28 - Load Centers 150A | PF.049 | 9000063 |  | PF.049 | PF.049 | 3.216% |  |  | 2026-01-27 |  | 2025-10-05 | 93 | TRUE
[5 empty] | 9000063 | 050 | 320001TUR | Stephen Yee | LEVEL 28 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 28 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-05 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-02-12 | 2026-02-17 | 2026-02-19 | OVER DUE | 2026-02-06 | DATES MISALIGNED | 2026-02-19 |  |  |  |  | 1 | Kerri Pandolfi | 50 | 26 |  | 0.3 | 1.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.3 | -7.62 | 26 | 050-320001TUR | PRE-FAB - LEVEL 28 - Level 28 - Load Centers 150A | 967 | Level 29 - Load Centers 125A | PF.050 | 9000063 |  | PF.050 | PF.050 | 3.788% |  |  | 2026-01-29 |  | 2025-10-05 | 95 | TRUE
[5 empty] | 9000063 | 051 | 320001TUR | Stephen Yee | LEVEL 29 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 29 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-10 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-17 | 2026-02-21 | 2026-02-23 | OVER DUE | 2026-02-11 | DATES MISALIGNED | 2026-02-23 |  |  |  |  | 1 | Kerri Pandolfi | 51 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 051-320001TUR | PRE-FAB - LEVEL 29 - Level 29 - Load Centers 125A | 1003 | Level 29 - Load Centers 150A | PF.051 | 9000063 |  | PF.051 | PF.051 | 4.824% |  |  | 2026-02-03 |  | 2025-10-05 | 98 | TRUE
[5 empty] | 9000063 | 052 | 320001TUR | Stephen Yee | LEVEL 29 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 29 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-11 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-02-18 | 2026-02-23 | 2026-02-25 | OVER DUE | 2026-02-11 | DATES MISALIGNED | 2026-02-25 |  |  |  |  | 1 | Kerri Pandolfi | 52 | 26 |  | 0.3 | 1.5 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.3 | -7.62 | 26 | 052-320001TUR | PRE-FAB - LEVEL 29 - Level 29 - Load Centers 150A | 1010 | Level 30 - Load Centers 125A | PF.052 | 9000063 |  | PF.052 | PF.052 | 3.788% |  |  | 2026-02-04 |  | 2025-10-05 | 99 | TRUE
[5 empty] | 9000063 | 053 | 320001TUR | Stephen Yee | LEVEL 30 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 30 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-17 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-24 | 2026-02-28 | 2026-03-02 | OVER DUE | 2026-02-17 | DATES MISALIGNED | 2026-03-02 |  |  |  |  | 1 | Kerri Pandolfi | 53 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 053-320001TUR | PRE-FAB - LEVEL 30 - Level 30 - Load Centers 125A | 1039 | Level 30 - Load Centers 150A | PF.053 | 9000063 |  | PF.053 | PF.053 | 4.824% |  |  | 2026-02-10 |  | 2025-10-05 | 103 | TRUE
[5 empty] | 9000063 | 054 | 320001TUR | Stephen Yee | LEVEL 30 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 30 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-18 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-02-25 | 2026-03-02 | 2026-03-04 | OVER DUE | 2026-02-17 | DATES MISALIGNED | 2026-03-04 |  |  |  |  | 1 | Kerri Pandolfi | 54 | 26 |  | 0.35 | 1.75 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.35 | -7.57 | 26 | 054-320001TUR | PRE-FAB - LEVEL 30 - Level 30 - Load Centers 150A | 1050 | Level 31 - Load Centers 125A | PF.054 | 9000063 |  | PF.054 | PF.054 | 4.419% |  |  | 2026-02-11 |  | 2025-10-05 | 104 | TRUE
[5 empty] | 9000063 | 055 | 320001TUR | Stephen Yee | LEVEL 31 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 31 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-19 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-02-26 | 2026-03-04 | 2026-03-06 | OVER DUE | 2026-02-20 | DATES MISALIGNED | 2026-03-06 |  |  |  |  | 1 | Kerri Pandolfi | 55 | 26 |  | 0.33333 | 3 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0.33333 | -6.5767 | 26 | 055-320001TUR | PRE-FAB - LEVEL 31 - Level 31 - Load Centers 125A | 1083 | Level 31 - Load Centers 150A | PF.055 | 9000063 |  | PF.055 | PF.055 | 4.824% |  |  | 2026-02-12 |  | 2025-10-05 | 105 | TRUE
[5 empty] | 9000063 | 056 | 320001TUR | Stephen Yee | LEVEL 31 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 31 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-25 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-03-04 | 2026-03-08 | 2026-03-10 | OVER DUE | 2026-02-20 | DATES MISALIGNED | 2026-03-10 |  |  |  |  | 1 | Kerri Pandolfi | 56 | 26 |  | 0.15 | 0.75 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0.15 | -7.77 | 26 | 056-320001TUR | PRE-FAB - LEVEL 31 - Level 31 - Load Centers 150A | 1091 | Level 32 - Load Centers 125A | PF.056 | 9000063 |  | PF.056 | PF.056 | 1.894% |  |  | 2026-02-18 |  | 2025-10-05 | 109 | TRUE
[5 empty] | 9000063 | 057 | 320001TUR | Stephen Yee | LEVEL 32 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 32 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-25 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-03-04 | 2026-03-10 | 2026-03-12 | OVER DUE | 2026-02-25 | DATES MISALIGNED | 2026-03-12 |  |  |  |  | 1 | Kerri Pandolfi | 57 | 26 |  | 0 | 0 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0 | -6.91 | 26 | 057-320001TUR | PRE-FAB - LEVEL 32 - Level 32 - Load Centers 125A | 1103 | Level 32 - Load Centers 150A | PF.057 | 9000063 |  | PF.057 | PF.057 | 0% |  |  | 2026-02-18 |  | 2025-10-05 | 109 | TRUE
[5 empty] | 9000063 | 058 | 320001TUR | Stephen Yee | LEVEL 32 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 32 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-04 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-03-11 | 2026-03-14 | 2026-03-16 | OVER DUE | 2026-02-25 | DATES MISALIGNED | 2026-03-16 |  |  |  |  | 1 | Kerri Pandolfi | 58 | 26 |  | 0 | 0 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 058-320001TUR | PRE-FAB - LEVEL 32 - Level 32 - Load Centers 150A | 1134 | Level 33 - Load Centers 125A | PF.058 | 9000063 |  | PF.058 | PF.058 | 0% |  |  | 2026-02-25 |  | 2025-10-05 | 114 | TRUE
[5 empty] | 9000063 | 059 | 320001TUR | Stephen Yee | LEVEL 33 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 33 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-04 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-03-11 | 2026-03-17 | 2026-03-19 | OVER DUE | 2026-03-02 | DATES MISALIGNED | 2026-03-19 |  |  |  |  | 1 | Kerri Pandolfi | 59 | 26 |  | 0 | 0 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0 | -6.91 | 26 | 059-320001TUR | PRE-FAB - LEVEL 33 - Level 33 - Load Centers 125A | 1143 | Level 33 - Load Centers 150A | PF.059 | 9000063 |  | PF.059 | PF.059 | 0% |  |  | 2026-02-25 |  | 2025-10-05 | 114 | TRUE
[5 empty] | 9000063 | 060 | 320001TUR | Stephen Yee | LEVEL 33 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 33 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-11 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-03-18 | 2026-03-21 | 2026-03-23 | OVER DUE | 2026-03-02 | DATES MISALIGNED | 2026-03-23 |  |  |  |  | 1 | Kerri Pandolfi | 60 | 26 |  | 0 | 0 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 060-320001TUR | PRE-FAB - LEVEL 33 - Level 33 - Load Centers 150A | 1176 | Level 34 - Load Centers 125A | PF.060 | 9000063 |  | PF.060 | PF.060 | 0% |  |  | 2026-03-04 |  | 2025-10-05 | 119 | TRUE
[5 empty] | 9000063 | 061 | 320001TUR | Stephen Yee | LEVEL 34 | LOAD CENTER - 125A - 20ck TERMINATIONS | Level 34 - Load Centers 125A | 9 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-10 | [7 empty] | 62.19 | 3.8869 | 4 | 2 | 2026-03-17 | 2026-03-23 | 2026-03-25 | OVER DUE | 2026-03-05 | DATES MISALIGNED | 2026-03-25 |  |  |  |  | 1 | Kerri Pandolfi | 61 | 26 |  | 0 | 0 | 6.91 | 62.19 |  | 0 | 6.91 | -6.91 | 0 | -6.91 | 26 | 061-320001TUR | PRE-FAB - LEVEL 34 - Level 34 - Load Centers 125A | 1185 | Level 34 - Load Centers 150A | PF.061 | 9000063 |  | PF.061 | PF.061 | 0% |  |  | 2026-03-03 |  | 2025-10-05 | 118 | TRUE
[5 empty] | 9000063 | 062 | 320001TUR | Stephen Yee | LEVEL 34 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 34 - Load Centers 150A | 5 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-13 | [7 empty] | 39.6 | 2.475 | 3 | 2 | 2026-03-20 | 2026-03-25 | 2026-03-27 | OVER DUE | 2026-03-05 | DATES MISALIGNED | 2026-03-27 |  |  |  |  | 1 | Kerri Pandolfi | 62 | 26 |  | 0 | 0 | 7.92 | 39.6 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 062-320001TUR | PRE-FAB - LEVEL 34 - Level 34 - Load Centers 150A | 1220 | Level 35 - Load Centers 150A | PF.062 | 9000063 |  | PF.062 | PF.062 | 0% |  |  | 2026-03-06 |  | 2025-10-05 | 121 | TRUE
[5 empty] | 9000063 | 063 | 320001TUR | Stephen Yee | LEVEL 35 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 35 - Load Centers 150A | 7 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-17 | [7 empty] | 55.44 | 3.465 | 4 | 2 | 2026-03-24 | 2026-03-29 | 2026-03-31 | OVER DUE | 2026-03-10 | DATES MISALIGNED | 2026-03-31 |  |  |  |  | 1 | Kerri Pandolfi | 63 | 26 |  | 0 | 0 | 7.92 | 55.44 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 063-320001TUR | PRE-FAB - LEVEL 35 - Level 35 - Load Centers 150A | 1223 | Level 36 - Load Centers 150A | PF.063 | 9000063 |  | PF.063 | PF.063 | 0% |  |  | 2026-03-10 |  | 2025-10-05 | 123 | TRUE
[5 empty] | 9000063 | 064 | 320001TUR | Stephen Yee | LEVEL 36 | LOAD CENTER - 150A - 30ck TERMINATIONS | Level 36 - Load Centers 150A | 7 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-19 | [7 empty] | 55.44 | 3.465 | 4 | 2 | 2026-03-26 | 2026-04-01 | 2026-04-03 | OVER DUE | 2026-03-13 | DATES MISALIGNED | 2026-04-03 |  |  |  |  | 1 | Kerri Pandolfi | 64 | 26 |  | 0 | 0 | 7.92 | 55.44 |  | 0 | 7.92 | -7.92 | 0 | -7.92 | 26 | 064-320001TUR | PRE-FAB - LEVEL 36 - Level 36 - Load Centers 150A | 1257 |  | PF.064 | 9000063 |  | PF.064 | PF.064 | 0% |  |  | 2026-03-12 |  | 2025-10-05 | 125 | TRUE
[5 empty] | 9000030 | 065 | 320001TUR | Stephen Yee | LEVEL B1 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL B1 LAUNDRY/BATHROOM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 15 | Gray | 121 BROADWAY MXD TOWER | Eddie Velez | 2025-09-19 | 2025-09-19 | JOHN CORSO | TRUE | true | TRUE | True | APPROVED | 2.733 | 0.17081 | 1 | 2 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET |  |  | Image 2025-09-30 09-46-35.jpeg |  | 3 | Kerri Pandolfi | 65 | 25 |  | 0.33333 | 5 | 0.1822 | 2.733 | 1.15 | 17.25 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 065-320001TUR | PRE-FAB - LEVEL B1 - LEVEL B1 LAUNDRY/BATHROOM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | #NO MATCH | #NO MATCH | PF.065 | 9000030 |  | PF.065 | NOT ON PROJECT SCHEDULE | 99% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000030 | 066 | 320001TUR | Stephen Yee | LEVEL 1 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 47 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-08-26 | 2025-08-21 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8.5634 | 0.53521 | 1 | 2 | 2025-09-02 | 2025-09-03 | 2025-09-05 |  | 2025-10-14 | DATES MISALIGNED | 2025-08-21 |  |  |  |  | 2 | Kerri Pandolfi | 66 | 25 |  | 0.2234 | 10.5 | 0.1822 | 8.5634 | 1.15 | 54.05 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 066-320001TUR | PRE-FAB - LEVEL 1 - LEVEL 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 99 | LEVEL 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.066 | 9000030 |  | PF.066 | PF.066 | 75% | TRUE |  | 2025-08-19 |  | 2025-10-05 | -24 | TRUE
[5 empty] | 9000030 | 067 | 320001TUR | Stephen Yee | LEVEL 2 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 50 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 9.11 | 0.56938 | 1 | 2 | 2025-12-12 | 2025-12-13 | 2025-12-15 |  | 2025-12-15 | DATES MISALIGNED | 2025-09-03 | [5 empty] | Kerri Pandolfi | 67 | 25 |  | 0 | 0 | 0.1822 | 9.11 | 1.15 | 57.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 067-320001TUR | PRE-FAB - LEVEL 2 - LEVEL 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 139 | LEVEL 2 CHIEF BOXES (A/V) (2 RECEPTACLES) | PF.067 | 9000030 |  | PF.067 | PF.067 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000030 | 068 | 320001TUR | Stephen Yee | LEVEL 3 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 3 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-10 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-17 | 2025-10-19 | 2025-10-21 |  | 2025-10-27 |  | 2025-10-24 | TRUE |  | X |  |  | Kerri Pandolfi | 68 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 068-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 332 | LEVEL 3 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.068 | 9000030 |  | PF.068 | DELETED | 100% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[5 empty] | 9000030 | 069 | 320001TUR | Stephen Yee | LEVEL 4 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 4 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-07 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-14 | 2025-10-15 | 2025-10-17 |  | 2025-11-03 |  | 2025-10-31 | [5 empty] | Kerri Pandolfi | 69 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 069-320001TUR | PRE-FAB - LEVEL 4 - LEVEL 4 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 373 | LEVEL 4 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.069 | 9000030 |  | PF.069 | PF.069 | 0% |  |  | 2025-09-30 |  | 2025-10-05 | 8
[5 empty] | 9000030 | 070 | 320001TUR | Stephen Yee | LEVEL 5 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 5 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-17 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-24 | 2025-10-26 | 2025-10-28 |  | 2025-11-04 |  | 2025-11-07 | [5 empty] | Kerri Pandolfi | 70 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 070-320001TUR | PRE-FAB - LEVEL 5 - LEVEL 5 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 401 | LEVEL 5 - PODIUM PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.070 | 9000030 |  | PF.070 | PF.070 | 0% |  |  | 2025-10-10 |  | 2025-10-05 | 16
[5 empty] | 9000030 | 071 | 320001TUR | Stephen Yee | LEVEL 6 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 6 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 98 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-26 | 2025-09-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 17.8556 | 1.116 | 2 | 2 | 2025-10-03 | 2025-10-07 | 2025-10-09 |  | 2025-10-28 | DATES MISALIGNED | 2025-09-10 |  |  |  |  | 2 | Kerri Pandolfi | 71 | 25 |  | 0.14796 | 14.5 | 0.1822 | 17.8556 | 1.15 | 112.7 | 0.1822 | 0.9678 | 0.14796 | -0.034241 | 25 | 071-320001TUR | PRE-FAB - LEVEL 6 - LEVEL 6 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 175 | LEVEL 6 LEVEL 6 - CHIEF BOXES (A/V) (2 RECEPTACLES) | PF.071 | 9000030 |  | PF.071 | PF.071 | 75% | TRUE |  | 2025-09-19 |  | 2025-10-05 | -1 | TRUE
[5 empty] | 9000030 | 072 | 320001TUR | Stephen Yee | LEVEL 7 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 7 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-21 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-28 | 2025-10-29 | 2025-10-31 |  | 2025-11-07 | DATES MISALIGNED | 2025-11-21 | [5 empty] | Kerri Pandolfi | 72 | 25 |  | 0.5 | 5 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 072-320001TUR | PRE-FAB - LEVEL 7 - LEVEL 7 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 482 | LEVEL 7 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.072 | 9000030 |  | PF.072 | PF.072 | 75% |  |  | 2025-10-14 |  | 2025-10-05 | 18
[5 empty] | 9000030 | 073 | 320001TUR | Stephen Yee | LEVEL 8 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 8 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-10-31 | 2025-11-03 | 2025-11-05 |  | 2025-11-18 | DATES MISALIGNED | 2025-12-01 | [5 empty] | Kerri Pandolfi | 73 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 073-320001TUR | PRE-FAB - LEVEL 8 - LEVEL 8 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 515 | LEVEL 8 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.073 | 9000030 |  | PF.073 | PF.073 | 0% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[5 empty] | 9000030 | 074 | 320001TUR | Stephen Yee | LEVEL 9 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 9 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-07 | 2025-11-08 | 2025-11-10 |  | 2025-11-18 | DATES MISALIGNED | 2025-12-08 | [5 empty] | Kerri Pandolfi | 74 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 074-320001TUR | PRE-FAB - LEVEL 9 - LEVEL 9 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 557 | LEVEL 9 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.074 | 9000030 |  | PF.074 | PF.074 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[5 empty] | 9000030 | 075 | 320001TUR | Stephen Yee | LEVEL 10 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 10 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-04 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-11 | 2025-11-12 | 2025-11-14 |  | 2025-11-21 | DATES MISALIGNED | 2025-12-12 | [5 empty] | Kerri Pandolfi | 75 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 075-320001TUR | PRE-FAB - LEVEL 10 - LEVEL 10 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 587 | LEVEL 10 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.075 | 9000030 |  | PF.075 | PF.075 | 0% |  |  | 2025-10-28 |  | 2025-10-05 | 28
[5 empty] | 9000030 | 076 | 320001TUR | Stephen Yee | LEVEL 11 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 11 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-07 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-14 | 2025-11-17 | 2025-11-19 |  | 2025-11-26 | DATES MISALIGNED | 2025-12-19 | [5 empty] | Kerri Pandolfi | 76 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 076-320001TUR | PRE-FAB - LEVEL 11 - LEVEL 11 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 628 | LEVEL 11 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.076 | 9000030 |  | PF.076 | PF.076 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[5 empty] | 9000030 | 077 | 320001TUR | Stephen Yee | LEVEL 12 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 12 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-14 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-21 | 2025-11-22 | 2025-11-24 |  | 2025-12-02 | DATES MISALIGNED | 2025-12-29 | [5 empty] | Kerri Pandolfi | 77 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 077-320001TUR | PRE-FAB - LEVEL 12 - LEVEL 12 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 673 | LEVEL 12 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.077 | 9000030 |  | PF.077 | PF.077 | 0% |  |  | 2025-11-07 |  | 2025-10-05 | 36
[5 empty] | 9000030 | 078 | 320001TUR | Stephen Yee | LEVEL 13 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 13 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-18 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-25 | 2025-11-26 | 2025-11-28 |  | 2025-12-05 | DATES MISALIGNED | 2026-01-06 | [5 empty] | Kerri Pandolfi | 78 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 078-320001TUR | PRE-FAB - LEVEL 13 - LEVEL 13 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 714 | LEVEL 13 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.078 | 9000030 |  | PF.078 | PF.078 | 0% |  |  | 2025-11-11 |  | 2025-10-05 | 38
[5 empty] | 9000030 | 079 | 320001TUR | Stephen Yee | LEVEL 14 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 14 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-21 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-11-28 | 2025-12-01 | 2025-12-03 |  | 2025-12-10 | DATES MISALIGNED | 2026-01-12 | [5 empty] | Kerri Pandolfi | 79 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 079-320001TUR | PRE-FAB - LEVEL 14 - LEVEL 14 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 762 | LEVEL 14 - TIER 1 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.079 | 9000030 |  | PF.079 | PF.079 | 0% |  |  | 2025-11-14 |  | 2025-10-05 | 41
[5 empty] | 9000030 | 080 | 320001TUR | Stephen Yee | LEVEL 15 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 15 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-28 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-05 | 2025-12-06 | 2025-12-08 |  | 2025-12-15 | DATES MISALIGNED | 2026-01-16 | [5 empty] | Kerri Pandolfi | 80 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 080-320001TUR | PRE-FAB - LEVEL 15 - LEVEL 15 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 786 | LEVEL 15 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.080 | 9000030 |  | PF.080 | PF.080 | 0% |  |  | 2025-11-21 |  | 2025-10-05 | 46
[5 empty] | 9000030 | 081 | 320001TUR | Stephen Yee | LEVEL 16 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 16 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-01 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-08 | 2025-12-09 | 2025-12-11 |  | 2025-12-23 | DATES MISALIGNED | 2026-01-26 | [5 empty] | Kerri Pandolfi | 81 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 081-320001TUR | PRE-FAB - LEVEL 16 - LEVEL 16 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 835 | LEVEL 16 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.081 | 9000030 |  | PF.081 | PF.081 | 0% |  |  | 2025-11-24 |  | 2025-10-05 | 47
[5 empty] | 9000030 | 082 | 320001TUR | Stephen Yee | LEVEL 17 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 17 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-05 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-12 | 2025-12-14 | 2025-12-16 |  | 2025-12-29 | DATES MISALIGNED | 2026-02-02 | [5 empty] | Kerri Pandolfi | 82 | 25 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 082-320001TUR | PRE-FAB - LEVEL 17 - LEVEL 17 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 886 | LEVEL 17 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.082 | 9000030 |  | PF.082 | PF.082 | 0% |  |  | 2025-11-28 |  | 2025-10-05 | 51
[5 empty] | 9000030 | 083 | 320001TUR | Stephen Yee | LEVEL 18 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 18 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-09 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-16 | 2025-12-17 | 2025-12-19 |  | 2026-01-02 | DATES MISALIGNED | 2026-02-06 | [5 empty] | Kerri Pandolfi | 83 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 083-320001TUR | PRE-FAB - LEVEL 18 - LEVEL 18 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 925 | LEVEL 18 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.083 | 9000030 |  | PF.083 | PF.083 | 0% |  |  | 2025-12-02 |  | 2025-10-05 | 53
[5 empty] | 9000030 | 084 | 320001TUR | Stephen Yee | LEVEL 19 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 19 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-12 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-19 | 2025-12-22 | 2025-12-24 |  | 2026-01-07 | DATES MISALIGNED | 2026-02-13 | [5 empty] | Kerri Pandolfi | 84 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 084-320001TUR | PRE-FAB - LEVEL 19 - LEVEL 19 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 963 | LEVEL 19 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.084 | 9000030 |  | PF.084 | PF.084 | 0% |  |  | 2025-12-05 |  | 2025-10-05 | 56
[5 empty] | 9000030 | 085 | 320001TUR | Stephen Yee | LEVEL 20 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 20 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-19 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2025-12-26 | 2025-12-28 | 2025-12-30 |  | 2026-01-12 | DATES MISALIGNED | 2026-02-23 | [5 empty] | Kerri Pandolfi | 85 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 085-320001TUR | PRE-FAB - LEVEL 20 - LEVEL 20 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1008 | LEVEL 20 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.085 | 9000030 |  | PF.085 | PF.085 | 0% |  |  | 2025-12-12 |  | 2025-10-05 | 61
[5 empty] | 9000030 | 086 | 320001TUR | Stephen Yee | LEVEL 21 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 21 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-26 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-02 | 2026-01-03 | 2026-01-05 |  | 2026-01-15 | DATES MISALIGNED | 2026-03-02 | [5 empty] | Kerri Pandolfi | 86 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 086-320001TUR | PRE-FAB - LEVEL 21 - LEVEL 21 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1051 | LEVEL 21 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.086 | 9000030 |  | PF.086 | PF.086 | 0% |  |  | 2025-12-19 |  | 2025-10-05 | 66
[5 empty] | 9000030 | 087 | 320001TUR | Stephen Yee | LEVEL 22 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 22 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-29 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-05 | 2026-01-06 | 2026-01-08 |  | 2026-01-15 | DATES MISALIGNED | 2026-03-06 | [5 empty] | Kerri Pandolfi | 87 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 087-320001TUR | PRE-FAB - LEVEL 22 - LEVEL 22 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1092 | LEVEL 22 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.087 | 9000030 |  | PF.087 | PF.087 | 0% |  |  | 2025-12-22 |  | 2025-10-05 | 67
[5 empty] | 9000030 | 088 | 320001TUR | Stephen Yee | LEVEL 23 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 23 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-02 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-09 | 2026-01-11 | 2026-01-13 |  | 2026-01-21 | DATES MISALIGNED | 2026-03-13 | [5 empty] | Kerri Pandolfi | 88 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 088-320001TUR | PRE-FAB - LEVEL 23 - LEVEL 23 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1138 | LEVEL 23 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.088 | 9000030 |  | PF.088 | PF.088 | 0% |  |  | 2025-12-26 |  | 2025-10-05 | 71
[5 empty] | 9000030 | 089 | 320001TUR | Stephen Yee | LEVEL 24 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 24 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-06 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-13 | 2026-01-14 | 2026-01-16 |  | 2026-01-26 | DATES MISALIGNED | 2026-03-20 | [5 empty] | Kerri Pandolfi | 89 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 089-320001TUR | PRE-FAB - LEVEL 24 - LEVEL 24 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1180 | LEVEL 24 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.089 | 9000030 |  | PF.089 | PF.089 | 0% |  |  | 2025-12-30 |  | 2025-10-05 | 73
[5 empty] | 9000030 | 090 | 320001TUR | Stephen Yee | LEVEL 25 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 25 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-12 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-19 | 2026-01-20 | 2026-01-22 |  | 2026-02-06 | DATES MISALIGNED | 2026-03-27 | [5 empty] | Kerri Pandolfi | 90 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 090-320001TUR | PRE-FAB - LEVEL 25 - LEVEL 25 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1224 | LEVEL 25 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.090 | 9000030 |  | PF.090 | PF.090 | 0% |  |  | 2026-01-05 |  | 2025-10-05 | 77
[5 empty] | 9000030 | 091 | 320001TUR | Stephen Yee | LEVEL 26 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 26 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-04-06 | [5 empty] | Kerri Pandolfi | 91 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 091-320001TUR | PRE-FAB - LEVEL 26 - LEVEL 26 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1267 | LEVEL 26 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.091 | 9000030 |  | PF.091 | PF.091 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[5 empty] | 9000030 | 092 | 320001TUR | Stephen Yee | LEVEL 27 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 27 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-20 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-27 | 2026-01-28 | 2026-01-30 |  | 2026-02-06 | DATES MISALIGNED | 2026-04-10 | [5 empty] | Kerri Pandolfi | 92 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 092-320001TUR | PRE-FAB - LEVEL 27 - LEVEL 27 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1306 | LEVEL 27 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.092 | 9000030 |  | PF.092 | PF.092 | 0% |  |  | 2026-01-13 |  | 2025-10-05 | 83
[5 empty] | 9000030 | 093 | 320001TUR | Stephen Yee | LEVEL 28 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 28 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-23 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-01-30 | 2026-02-02 | 2026-02-04 |  | 2026-02-06 | DATES MISALIGNED | 2026-04-17 | [5 empty] | Kerri Pandolfi | 93 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 093-320001TUR | PRE-FAB - LEVEL 28 - LEVEL 28 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1349 | LEVEL 28 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.093 | 9000030 |  | PF.093 | PF.093 | 0% |  |  | 2026-01-16 |  | 2025-10-05 | 86
[5 empty] | 9000030 | 094 | 320001TUR | Stephen Yee | LEVEL 29 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 29 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-04-27 | [5 empty] | Kerri Pandolfi | 94 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 094-320001TUR | PRE-FAB - LEVEL 29 - LEVEL 29 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1390 | LEVEL 29 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.094 | 9000030 |  | PF.094 | PF.094 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[5 empty] | 9000030 | 095 | 320001TUR | Stephen Yee | LEVEL 30 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 30 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-05-04 | [5 empty] | Kerri Pandolfi | 95 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 095-320001TUR | PRE-FAB - LEVEL 30 - LEVEL 30 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1430 | LEVEL 30 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.095 | 9000030 |  | PF.095 | PF.095 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[5 empty] | 9000030 | 096 | 320001TUR | Stephen Yee | LEVEL 31 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 31 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-05-11 | [5 empty] | Kerri Pandolfi | 96 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 096-320001TUR | PRE-FAB - LEVEL 31 - LEVEL 31 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1469 | LEVEL 31 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.096 | 9000030 |  | PF.096 | PF.096 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[5 empty] | 9000030 | 097 | 320001TUR | Stephen Yee | LEVEL 32 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 32 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-05-18 | [5 empty] | Kerri Pandolfi | 97 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 097-320001TUR | PRE-FAB - LEVEL 32 - LEVEL 32 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1511 | LEVEL 32 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.097 | 9000030 |  | PF.097 | PF.097 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[5 empty] | 9000030 | 098 | 320001TUR | Stephen Yee | LEVEL 33 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 33 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-27 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-03 | 2026-02-04 | 2026-02-06 |  | 2026-02-06 | DATES MISALIGNED | 2026-05-26 | [5 empty] | Kerri Pandolfi | 98 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 098-320001TUR | PRE-FAB - LEVEL 33 - LEVEL 33 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1548 | LEVEL 33 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.098 | 9000030 |  | PF.098 | PF.098 | 0% |  |  | 2026-01-20 |  | 2025-10-05 | 88
[5 empty] | 9000030 | 099 | 320001TUR | Stephen Yee | LEVEL 34 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 34 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 10 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-20 | [7 empty] | 1.822 | 0.11388 | 1 | 2 | 2026-02-27 | 2026-03-01 | 2026-03-03 |  | 2026-03-10 | DATES MISALIGNED | 2026-06-02 | [5 empty] | Kerri Pandolfi | 99 | 26 |  | 0 | 0 | 0.1822 | 1.822 | 1.15 | 11.5 | 0.1822 | 0.9678 | 0 | -0.1822 | 26 | 099-320001TUR | PRE-FAB - LEVEL 34 - LEVEL 34 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | 1580 | LEVEL 34 - TIER 2 PIPE BENDS (3/4" -1 1/4" PIPE) T/D | PF.099 | 9000030 |  | PF.099 | PF.099 | 0% |  |  | 2026-02-13 |  | 2025-10-05 | 106
[5 empty] | 9000040 | 393 | 320001TUR | Stephen Yee | LEVEL 39 | VFD ASSEMBLY (1) | ROOFTOP DISCONNECTS | 25 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-13 | [7 empty] | 75 | 4.6875 | 5 | 2 | 2026-05-20 | 2026-05-27 | 2026-05-29 |  | 2026-05-29 | [7 empty] | Kerri Pandolfi | 393 | 26 |  | 0 | 0 | 3 | 75 | 4.1 | 102.5 | 3 | 1.1 | 0 | -3 | 26 | 393-320001TUR | PRE-FAB - LEVEL 39 - ROOFTOP DISCONNECTS | 1976 | INSTALL - LEVEL 40 DISCONNECTS | PF.393 | 9000040 |  | PF.393 | PF.393 | 0% |  |  | 2026-05-06 |  | 2025-10-05 | 164
[5 empty] | 9000062 | 394 | 320001TUR | Stephen Yee | LEVEL 1 | PIPE NIPPLES | 5" and 4" RIGID NIPPLES | 24 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-23 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 21.6 | 2.7 | 3 | 1 | 2025-06-30 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-35-52.jpeg |  | 8 | Kerri Pandolfi | 394 | 25 |  | 0.66667 | 16 | 0.9 | 21.6 | 1 | 24 | 0.9 | 0.1 | 0.66667 | -0.23333 | 25 | 394-320001TUR | PRE-FAB - LEVEL 1 - 5" and 4" RIGID NIPPLES | #NO MATCH | #NO MATCH | PF.394 | 9000062 |  | PF.394 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-16 |  | 2025-10-05 | -70
[5 empty] | 9000056 | 395 | 320001TUR | Stephen Yee | LEVEL 13 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-13 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-06-20 | 2025-06-21 | 2025-06-23 |  | 2025-06-23 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-06-23 07-25-29.jpeg |  |  | Kerri Pandolfi | 395 | 25 |  | 0.17647 | 3 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.17647 | -0.17353 | 25 | 395-320001TUR | PRE-FAB - LEVEL 13 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.395 | 9000056 |  | PF.395 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-06 |  | 2025-10-05 | -76
[5 empty] | 9000056 | 396 | 320001TUR | Stephen Yee | LEVEL 14 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-13 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-06-20 | 2025-06-23 | 2025-06-25 |  | 2025-06-25 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-06-25 13-32-13.jpeg |  | 9 | Kerri Pandolfi | 396 | 25 |  | 0.58824 | 10 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 396-320001TUR | PRE-FAB - LEVEL 14 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.396 | 9000056 |  | PF.396 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-06 |  | 2025-10-05 | -76
[5 empty] | 9000056 | 397 | 320001TUR | Stephen Yee | LEVEL 15 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-36-22.jpeg |  | 14 | Kerri Pandolfi | 397 | 25 |  | 0.11765 | 2 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.11765 | -0.23235 | 25 | 397-320001TUR | PRE-FAB - LEVEL 15 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.397 | 9000056 |  | PF.397 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-18 |  | 2025-10-05 | -68
[5 empty] | 9000056 | 398 | 320001TUR | Stephen Yee | LEVEL 16 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-36-40.jpeg |  | 14 | Kerri Pandolfi | 398 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 398-320001TUR | PRE-FAB - LEVEL 16 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.398 | 9000056 |  | PF.398 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-18 |  | 2025-10-05 | -68
[5 empty] | 9000056 | 399 | 320001TUR | Stephen Yee | LEVEL 17 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-36-58.jpeg |  | 8 | Kerri Pandolfi | 399 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 399-320001TUR | PRE-FAB - LEVEL 17 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.399 | 9000056 |  | PF.399 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-18 |  | 2025-10-05 | -68
[5 empty] | 9000056 | 400 | 320001TUR | Stephen Yee | LEVEL 18 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-02 10-37-25.jpeg |  | 8 | Kerri Pandolfi | 400 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 400-320001TUR | PRE-FAB - LEVEL 18 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.400 | 9000056 |  | PF.400 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-18 |  | 2025-10-05 | -68
[5 empty] | 9000056 | 401 | 320001TUR | Stephen Yee | LEVEL 19 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-07 07-32-09.jpeg |  | 8 | Kerri Pandolfi | 401 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 401-320001TUR | PRE-FAB - LEVEL 19 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.401 | 9000056 |  | PF.401 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-06-18 |  | 2025-10-05 | -68
[5 empty] | 9000056 | 402 | 320001TUR | Stephen Yee | LEVEL 20 | (1) CONDUIT SLEEVE (NO THREAD) | Deck Sleeves | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-06-25 | 2025-06-16 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-02 | 2025-07-03 | 2025-07-05 |  | 2025-07-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-07 07-32-28.jpeg |  | 8 | Kerri Pandolfi | 402 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 402-320001TUR | PRE-FAB - LEVEL 20 - Deck Sleeves | #NO MATCH | #NO MATCH | PF.402 | 9000056 |  | PF.402 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-06-18 |  | 2025-10-05 | -68
[5 empty] | 9000220 | 403 | 320001TUR | Stephen Yee | MULTI LEVEL | TEMPS (SMALL) | temp power quad outlets | 31 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-03 | 2025-07-11 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 31 | 3.875 | 4 | 1 | 2025-07-10 | 2025-07-16 | 2025-07-18 |  | 2025-07-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-16 10-59-22.jpeg |  | 5 | Kerri Pandolfi | 403 | 25 |  | 1.129 | 35 | 1 | 31 | 2 | 62 | 1 | 1 | 1 | 0 | 25 | 403-320001TUR | PRE-FAB - MULTI LEVEL - temp power quad outlets | #NO MATCH | #NO MATCH | PF.403 | 9000220 |  | PF.403 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-26 |  | 2025-10-05 | -62
[5 empty] | 9000220 | 404 | 320001TUR | Stephen Yee | MULTI LEVEL | TEMPS (SMALL) | temp power quad outlets | 31 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-16 | 2025-07-11 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 31 | 3.875 | 4 | 1 | 2025-07-23 | 2025-07-29 | 2025-07-31 |  | 2025-08-05 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-25 10-26-49.jpeg |  | 6 | Kerri Pandolfi | 404 | 25 |  | 0.35484 | 11 | 1 | 31 | 2 | 62 | 1 | 1 | 0.35484 | -0.64516 | 25 | 404-320001TUR | PRE-FAB - MULTI LEVEL - temp power quad outlets | #NO MATCH | #NO MATCH | PF.404 | 9000220 |  | PF.404 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-09 |  | 2025-10-05 | -53
[5 empty] | 9000056 | 405 | 320001TUR | Stephen Yee | LEVEL 21 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-21-52.jpeg |  | 8 | Kerri Pandolfi | 405 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 405-320001TUR | PRE-FAB - LEVEL 21 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.405 | 9000056 |  | PF.405 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[5 empty] | 9000056 | 406 | 320001TUR | Stephen Yee | LEVEL 22 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-22-14.jpeg |  | 8 | Kerri Pandolfi | 406 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 406-320001TUR | PRE-FAB - LEVEL 22 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.406 | 9000056 |  | PF.406 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[5 empty] | 9000056 | 407 | 320001TUR | Stephen Yee | LEVEL 23 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-22-39.jpeg |  | 8 | Kerri Pandolfi | 407 | 25 |  | 0 | 0 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0 | -0.35 | 25 | 407-320001TUR | PRE-FAB - LEVEL 23 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.407 | 9000056 |  | PF.407 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[5 empty] | 9000056 | 408 | 320001TUR | Stephen Yee | LEVEL 24 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-23-07.jpeg |  | 8 | Kerri Pandolfi | 408 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 408-320001TUR | PRE-FAB - LEVEL 24 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.408 | 9000056 |  | PF.408 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[5 empty] | 9000056 | 409 | 320001TUR | Stephen Yee | LEVEL 25 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-22 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-07-29 | 2025-07-30 | 2025-08-01 |  | 2025-08-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-28 13-23-39.jpeg |  | 8 | Kerri Pandolfi | 409 | 25 |  | 0.70588 | 12 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 409-320001TUR | PRE-FAB - LEVEL 25 - DECK SLEEVES | #NO MATCH | #NO MATCH | PF.409 | 9000056 |  | PF.409 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-15 |  | 2025-10-05 | -49 | TRUE
[5 empty] | 9000056 | 410 | 320001TUR | Stephen Yee | LEVEL 26 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-46-21.jpeg |  | 9 | Kerri Pandolfi | 410 | 25 |  | 1.1176 | 19 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 410-320001TUR | PRE-FAB - LEVEL 26 - DECK SLEEVES | 183 |  | PF.410 | 9000056 |  | PF.410 | PF.410 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 411 | 320001TUR | Stephen Yee | LEVEL 27 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-46-45.jpeg |  | 9 | Kerri Pandolfi | 411 | 25 |  | 0.29412 | 5 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.29412 | -0.055882 | 25 | 411-320001TUR | PRE-FAB - LEVEL 27 - DECK SLEEVES | 184 |  | PF.411 | 9000056 |  | PF.411 | PF.411 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 412 | 320001TUR | Stephen Yee | LEVEL 28 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-47-16.jpeg |  | 9 | Kerri Pandolfi | 412 | 25 |  | 0.058824 | 1 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.058824 | -0.29118 | 25 | 412-320001TUR | PRE-FAB - LEVEL 28 - DECK SLEEVES | 185 |  | PF.412 | 9000056 |  | PF.412 | PF.412 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 413 | 320001TUR | Stephen Yee | LEVEL 29 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-45-47.jpeg |  | 9 | Kerri Pandolfi | 413 | 25 |  | 0.058824 | 1 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.058824 | -0.29118 | 25 | 413-320001TUR | PRE-FAB - LEVEL 29 - DECK SLEEVES | 186 |  | PF.413 | 9000056 |  | PF.413 | PF.413 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 414 | 320001TUR | Stephen Yee | LEVEL 30 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-09-19 |  | 2025-09-17 | TRUE |  | Image 2025-08-12 08-44-39.jpeg |  | 9 | Kerri Pandolfi | 414 | 25 |  | 0 | 0 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0 | -0.35 | 25 | 414-320001TUR | PRE-FAB - LEVEL 30 - DECK SLEEVES | 187 |  | PF.414 | 9000056 |  | PF.414 | PF.414 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 415 | 320001TUR | Stephen Yee | LEVEL 31 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-49-30.jpeg |  | 9 | Kerri Pandolfi | 415 | 25 |  | 0.35294 | 6 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 415-320001TUR | PRE-FAB - LEVEL 31 - DECK SLEEVES | 335 |  | PF.415 | 9000056 |  | PF.415 | PF.415 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 416 | 320001TUR | Stephen Yee | LEVEL 32 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-49-53.jpeg |  | 9 | Kerri Pandolfi | 416 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 416-320001TUR | PRE-FAB - LEVEL 32 - DECK SLEEVES | 336 |  | PF.416 | 9000056 |  | PF.416 | PF.416 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 417 | 320001TUR | Stephen Yee | LEVEL 33 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-50-21.jpeg |  | 9 | Kerri Pandolfi | 417 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 417-320001TUR | PRE-FAB - LEVEL 33 - DECK SLEEVES | 337 |  | PF.417 | 9000056 |  | PF.417 | PF.417 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 418 | 320001TUR | Stephen Yee | LEVEL 34 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-50-55.jpeg |  | 9 | Kerri Pandolfi | 418 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 418-320001TUR | PRE-FAB - LEVEL 34 - DECK SLEEVES | 338 |  | PF.418 | 9000056 |  | PF.418 | PF.418 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 419 | 320001TUR | Stephen Yee | LEVEL 35 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-29 | 2025-07-03 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-08-05 | 2025-08-06 | 2025-08-08 |  | 2025-10-31 |  | 2025-10-29 | TRUE |  | Image 2025-08-12 08-51-17.jpeg |  | 9 | Kerri Pandolfi | 419 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 419-320001TUR | PRE-FAB - LEVEL 35 - DECK SLEEVES | 339 |  | PF.419 | 9000056 |  | PF.419 | PF.419 | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000056 | 420 | 320001TUR | Stephen Yee | LEVEL 36 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-07-07 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 |  | 2025-11-24 |  |  | Image 2025-09-26 09-44-02.jpeg |  | 2 | Kerri Pandolfi | 420 | 25 |  | 0.51471 | 8.75 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 420-320001TUR | PRE-FAB - LEVEL 36 - DECK SLEEVES | 476 |  | PF.420 | 9000056 |  | PF.420 | PF.420 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000056 | 421 | 320001TUR | Stephen Yee | LEVEL 37 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-07-07 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 |  | 2025-11-24 |  |  | Image 2025-09-26 09-44-29.jpeg |  | 2 | Kerri Pandolfi | 421 | 25 |  | 0.47059 | 8 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 421-320001TUR | PRE-FAB - LEVEL 37 - DECK SLEEVES | 477 |  | PF.421 | 9000056 |  | PF.421 | PF.421 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000056 | 422 | 320001TUR | Stephen Yee | LEVEL 38 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-07-07 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 |  | 2025-11-24 |  |  | Image 2025-09-26 09-45-15.jpeg |  | 2 | Kerri Pandolfi | 422 | 25 |  | 0.44118 | 7.5 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 422-320001TUR | PRE-FAB - LEVEL 38 - DECK SLEEVES | 478 |  | PF.422 | 9000056 |  | PF.422 | PF.422 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000056 | 423 | 320001TUR | Stephen Yee | LEVEL 39 | (1) CONDUIT SLEEVE (NO THREAD) | DECK SLEEVES | 17 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-07-07 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.95 | 0.74375 | 1 | 1 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 |  | 2025-11-24 |  |  | Image 2025-09-26 09-45-42.jpeg |  | 2 | Kerri Pandolfi | 423 | 25 |  | 0.23529 | 4 | 0.35 | 5.95 |  | 0 | 0.35 | -0.35 | 0.23529 | -0.11471 | 25 | 423-320001TUR | PRE-FAB - LEVEL 39 - DECK SLEEVES | 479 |  | PF.423 | 9000056 |  | PF.423 | PF.423 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000056 | 424 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 30 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-03 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 10.5 | 1.3125 | 2 | 1 | 2025-07-10 | 2025-07-12 | 2025-07-14 |  | 2025-07-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-07-11 11-14-44.jpeg |  | 5 | Kerri Pandolfi | 424 | 25 |  | 0 | 0 | 0.35 | 10.5 |  | 0 | 0.35 | -0.35 | 0 | -0.35 | 25 | 424-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | #NO MATCH | #NO MATCH | PF.424 | 9000056 |  | PF.424 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-06-26 |  | 2025-10-05 | -62
[5 empty] | 9000056 | 425 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 30 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 10.5 | 1.3125 | 2 | 1 | 2025-08-08 | 2025-08-12 | 2025-08-14 |  | 2025-08-18 |  | 2025-08-15 | TRUE |  | Image 2025-08-13 12-43-01.jpeg |  | 8 | Kerri Pandolfi | 425 | 25 |  | 0.26667 | 8 | 0.35 | 10.5 |  | 0 | 0.35 | -0.35 | 0.26667 | -0.083333 | 25 | 425-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | 86 |  | PF.425 | 9000056 |  | PF.425 | PF.425 | 100% | TRUE |  | 2025-07-25 |  | 2025-10-05 | -41 | TRUE
[5 empty] | 9000056 | 426 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 30 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 10.5 | 1.3125 | 2 | 1 | 2025-08-08 | 2025-08-12 | 2025-08-14 |  | 2025-09-22 |  | 2025-09-19 | TRUE |  | Image 2025-08-13 13-17-41.jpeg |  | 8 | Kerri Pandolfi | 426 | 25 |  | 0.26667 | 8 | 0.35 | 10.5 |  | 0 | 0.35 | -0.35 | 0.26667 | -0.083333 | 25 | 426-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | 196 |  | PF.426 | 9000056 |  | PF.426 | PF.426 | 100% | TRUE |  | 2025-07-25 |  | 2025-10-05 | -41 | TRUE
[5 empty] | 9000056 | 427 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 28 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 9.8 | 1.225 | 2 | 1 | 2025-08-08 | 2025-08-12 | 2025-08-14 |  | 2025-10-27 |  | 2025-10-24 | TRUE |  | Image 2025-08-13 13-19-46.jpeg |  | 8 | Kerri Pandolfi | 427 | 25 |  | 0.57143 | 16 | 0.35 | 9.8 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 427-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | 307 |  | PF.427 | 9000056 |  | PF.427 | PF.427 | 100% | TRUE |  | 2025-07-25 |  | 2025-10-05 | -41 | TRUE
[5 empty] | 9000056 | 428 | 320001TUR | Stephen Yee | MULTI LEVEL | (1) CONDUIT SLEEVE (NO THREAD) | CORE SHEER WALL SLEEVES | 11 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-07-08 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3.85 | 0.48125 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-12-01 |  | 2025-12-02 | TRUE |  | Image 2025-08-13 13-33-53.jpeg |  | 8 | Kerri Pandolfi | 428 | 25 |  | 0.45455 | 5 | 0.35 | 3.85 |  | 0 | 0.35 | -0.35 | 0.35 | 0 | 25 | 428-320001TUR | PRE-FAB - MULTI LEVEL - CORE SHEER WALL SLEEVES | 511 |  | PF.428 | 9000056 |  | PF.428 | PF.428 | 100% | TRUE |  | 2025-07-28 |  | 2025-10-05 | -40 | TRUE
[5 empty] | 9000060 | 429 | 320001TUR | Stephen Yee | LEVEL 21 | PANEL ASSEMBLY (STRUT BUILD) | PANEL HPH21 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-01-16 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-01-23 | 2026-01-24 | 2026-01-26 |  | 2026-01-26 |  | 2026-01-29 | [5 empty] | Kerri Pandolfi | 429 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 429-320001TUR | PRE-FAB - LEVEL 21 - PANEL HPH21 | 867 | INSTALL - LEVEL 21 - DISTRIBUTION EQUIP | PF.429 | 9000060 |  | PF.429 | PF.429 | 0% |  |  | 2026-01-09 |  | 2025-10-05 | 81
[5 empty] | 9000060 | 430 | 320001TUR | Stephen Yee | LEVEL 24 | PANEL ASSEMBLY (STRUT BUILD) | PANEL EPH24,EPL24 | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-02-17 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2026-02-24 | 2026-02-25 | 2026-02-27 |  | 2026-02-27 |  | 2026-03-04 | [5 empty] | Kerri Pandolfi | 430 | 26 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 26 | 430-320001TUR | PRE-FAB - LEVEL 24 - PANEL EPH24,EPL24 | 1052 | LEVEL 24 - TIER 2 - PANEL ASSEMBLY (STRUT BUILD) | PF.430 | 9000060 |  | PF.430 | PF.430 | 0% |  |  | 2026-02-10 |  | 2025-10-05 | 103
[5 empty] | 9000060 | 431 | 320001TUR | Stephen Yee | LEVEL 25 | PANEL ASSEMBLY (STRUT BUILD) | PANEL HPH25 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-02-16 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-02-23 | 2026-02-24 | 2026-02-26 |  | 2026-02-26 |  | 2026-03-03 | [5 empty] | Kerri Pandolfi | 431 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 431-320001TUR | PRE-FAB - LEVEL 25 - PANEL HPH25 | 1047 | LEVEL 25 - TIER 2 - PANEL PL25 | PF.431 | 9000060 |  | PF.431 | PF.431 | 0% |  |  | 2026-02-09 |  | 2025-10-05 | 102
[5 empty] | 9000060 | 432 | 320001TUR | Stephen Yee | LEVEL 33 | PANEL ASSEMBLY (STRUT BUILD) | PANEL HPH33 | 1 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-01 | 2025-09-16 | [6 empty] | 0.5 | 0.0625 | 1 | 1 | 2026-05-08 | 2026-05-11 | 2026-05-13 |  | 2026-05-13 |  | 2026-05-18 | [5 empty] | Kerri Pandolfi | 432 | 26 |  | 0 | 0 | 0.5 | 0.5 | 0.7 | 0.7 | 0.5 | 0.2 | 0 | -0.5 | 26 | 432-320001TUR | PRE-FAB - LEVEL 33 - PANEL HPH33 | 1506 | INSTALL - LEVEL 33 - DISTRIBUTION EQUIP | PF.432 | 9000060 |  | PF.432 | PF.432 | 0% |  |  | 2026-04-24 |  | 2025-10-05 | 156
[5 empty] | 9000060 | 433 | 320001TUR | Stephen Yee | LEVEL 34 | PANEL ASSEMBLY (STRUT BUILD) | PANELS EPH34,EPL34 | 2 | Red | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-04-28 | 2025-09-16 | [6 empty] | 1 | 0.125 | 1 | 1 | 2026-05-05 | 2026-05-06 | 2026-05-08 |  | 2026-05-08 |  | 2026-05-13 | [5 empty] | Kerri Pandolfi | 433 | 26 |  | 0 | 0 | 0.5 | 1 | 0.7 | 1.4 | 0.5 | 0.2 | 0 | -0.5 | 26 | 433-320001TUR | PRE-FAB - LEVEL 34 - PANELS EPH34,EPL34 | 1468 | LEVEL 34 - TIER 2 - PANEL PL34 | PF.433 | 9000060 |  | PF.433 | PF.433 | 0% |  |  | 2026-04-21 |  | 2025-10-05 | 153
[5 empty] | 9000056 | 434 | 320001TUR | Stephen Yee | LEVEL 18 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC X 8" LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-01 | 2025-08-04 | 2025-08-06 |  | 2025-08-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-13-22.jpeg |  | 9 | Kerri Pandolfi | 434 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 434-320001TUR | PRE-FAB - LEVEL 18 - 6" PVC X 8" LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.434 | 9000056 |  | PF.434 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[5 empty] | 9000056 | 435 | 320001TUR | Stephen Yee | LEVEL 19 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC X 8" LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-01 | 2025-08-04 | 2025-08-06 |  | 2025-08-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-13-45.jpeg |  | 9 | Kerri Pandolfi | 435 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 435-320001TUR | PRE-FAB - LEVEL 19 - 6" PVC X 8" LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.435 | 9000056 |  | PF.435 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[5 empty] | 9000056 | 436 | 320001TUR | Stephen Yee | LEVEL 20 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC X 8" LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-01 | 2025-08-04 | 2025-08-06 |  | 2025-08-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-14-11.jpeg |  | 9 | Kerri Pandolfi | 436 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 436-320001TUR | PRE-FAB - LEVEL 20 - 6" PVC X 8" LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.436 | 9000056 |  | PF.436 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[5 empty] | 9000056 | 437 | 320001TUR | Stephen Yee | LEVEL 21 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-01 | 2025-08-04 | 2025-08-06 |  | 2025-08-06 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-14-32.jpeg |  | 9 | Kerri Pandolfi | 437 | 25 |  | 0.4375 | 3.5 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.4375 | -0.5625 | 25 | 437-320001TUR | PRE-FAB - LEVEL 21 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.437 | 9000056 |  | PF.437 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[5 empty] | 9000056 | 438 | 320001TUR | Stephen Yee | LEVEL 22 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-08 | 2025-08-09 | 2025-08-11 |  | 2025-08-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-18-00.jpeg |  | 9 | Kerri Pandolfi | 438 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 438-320001TUR | PRE-FAB - LEVEL 22 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.438 | 9000056 |  | PF.438 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-25 |  | 2025-10-05 | -41
[5 empty] | 9000056 | 439 | 320001TUR | Stephen Yee | LEVEL 23 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-08 | 2025-08-09 | 2025-08-11 |  | 2025-08-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-18-25.jpeg |  | 9 | Kerri Pandolfi | 439 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 439-320001TUR | PRE-FAB - LEVEL 23 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.439 | 9000056 |  | PF.439 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-25 |  | 2025-10-05 | -41
[5 empty] | 9000056 | 440 | 320001TUR | Stephen Yee | LEVEL 24 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-08 | 2025-08-09 | 2025-08-11 |  | 2025-08-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-18-45.jpeg |  | 9 | Kerri Pandolfi | 440 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 440-320001TUR | PRE-FAB - LEVEL 24 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.440 | 9000056 |  | PF.440 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-25 |  | 2025-10-05 | -41
[5 empty] | 9000056 | 441 | 320001TUR | Stephen Yee | LEVEL 25 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-01 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-08 | 2025-08-09 | 2025-08-11 |  | 2025-08-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-19-16.jpeg |  | 9 | Kerri Pandolfi | 441 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 441-320001TUR | PRE-FAB - LEVEL 25 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.441 | 9000056 |  | PF.441 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-25 |  | 2025-10-05 | -41
[5 empty] | 9000056 | 442 | 320001TUR | Stephen Yee | LEVEL 26 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-28-20.jpeg |  | 9 | Kerri Pandolfi | 442 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 442-320001TUR | PRE-FAB - LEVEL 26 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.442 | 9000056 |  | PF.442 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[5 empty] | 9000056 | 443 | 320001TUR | Stephen Yee | LEVEL 27 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-28-39.jpeg |  | 9 | Kerri Pandolfi | 443 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 443-320001TUR | PRE-FAB - LEVEL 27 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.443 | 9000056 |  | PF.443 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[5 empty] | 9000056 | 444 | 320001TUR | Stephen Yee | LEVEL 28 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-28-59.jpeg |  | 9 | Kerri Pandolfi | 444 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 444-320001TUR | PRE-FAB - LEVEL 28 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.444 | 9000056 |  | PF.444 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[5 empty] | 9000056 | 445 | 320001TUR | Stephen Yee | LEVEL 29 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-14 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-29-17.jpeg |  | 9 | Kerri Pandolfi | 445 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 445-320001TUR | PRE-FAB - LEVEL 29 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.445 | 9000056 |  | PF.445 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-28 |  | 2025-10-05 | -40
[5 empty] | 9000056 | 446 | 320001TUR | Stephen Yee | LEVEL 30 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-15 | 2025-08-17 | 2025-08-19 |  | 2025-08-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-32-39.jpeg |  | 9 | Kerri Pandolfi | 446 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 446-320001TUR | PRE-FAB - LEVEL 30 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.446 | 9000056 |  | PF.446 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-01 |  | 2025-10-05 | -36
[5 empty] | 9000056 | 447 | 320001TUR | Stephen Yee | LEVEL 31 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-15 | 2025-08-17 | 2025-08-19 |  | 2025-08-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-32-01.jpeg |  | 9 | Kerri Pandolfi | 447 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 447-320001TUR | PRE-FAB - LEVEL 31 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.447 | 9000056 |  | PF.447 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-01 |  | 2025-10-05 | -36
[5 empty] | 9000056 | 448 | 320001TUR | Stephen Yee | LEVEL 32 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-15 | 2025-08-17 | 2025-08-19 |  | 2025-08-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-31-35.jpeg |  | 9 | Kerri Pandolfi | 448 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 448-320001TUR | PRE-FAB - LEVEL 32 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.448 | 9000056 |  | PF.448 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-01 |  | 2025-10-05 | -36
[5 empty] | 9000056 | 449 | 320001TUR | Stephen Yee | LEVEL 33 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-15 | 2025-08-17 | 2025-08-19 |  | 2025-08-19 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-31-07.jpeg |  | 9 | Kerri Pandolfi | 449 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 449-320001TUR | PRE-FAB - LEVEL 33 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.449 | 9000056 |  | PF.449 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-01 |  | 2025-10-05 | -36
[5 empty] | 9000056 | 450 | 320001TUR | Stephen Yee | LEVEL 34 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-12 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-30-45.jpeg |  |  | Kerri Pandolfi | 450 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 450-320001TUR | PRE-FAB - LEVEL 34 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.450 | 9000056 |  | PF.450 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[5 empty] | 9000056 | 451 | 320001TUR | Stephen Yee | LEVEL 35 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-12 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-30-09.jpeg |  |  | Kerri Pandolfi | 451 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 451-320001TUR | PRE-FAB - LEVEL 35 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.451 | 9000056 |  | PF.451 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[5 empty] | 9000056 | 452 | 320001TUR | Stephen Yee | LEVEL 36 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-12 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-19 | 2025-08-20 | 2025-08-22 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 08-29-49.jpeg |  |  | Kerri Pandolfi | 452 | 25 |  | 0 | 0 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0 | -1 | 25 | 452-320001TUR | PRE-FAB - LEVEL 36 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.452 | 9000056 |  | PF.452 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-08-05 |  | 2025-10-05 | -34
[5 empty] | 9000056 | 453 | 320001TUR | Stephen Yee | LEVEL 37 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-01 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET |  |  | Image 2025-08-13 13-25-13.jpeg |  | 9 | Kerri Pandolfi | 453 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 453-320001TUR | PRE-FAB - LEVEL 37 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.453 | 9000056 |  | PF.453 | NOT ON PROJECT SCHEDULE | 99% | TRUE |  | 2025-07-28 |  | 2025-10-05 | -40 | TRUE
[5 empty] | 9000056 | 454 | 320001TUR | Stephen Yee | LEVEL 38 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-04 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-27 |  | NOT LINKED IN PROJECT SCHEDULE SHEET |  |  | Image 2025-08-13 13-25-57.jpeg |  | 9 | Kerri Pandolfi | 454 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 454-320001TUR | PRE-FAB - LEVEL 38 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.454 | 9000056 |  | PF.454 | NOT ON PROJECT SCHEDULE | 99% | TRUE |  | 2025-07-28 |  | 2025-10-05 | -40 | TRUE
[5 empty] | 9000056 | 455 | 320001TUR | Stephen Yee | LEVEL 39 | (1-4) CONDUIT SLEEVE ASSEMBLY (POWER) | 6" PVC x 8"LONG CONTROL POINTS | 8 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-04 | 2025-08-04 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 8 | 1 | 1 | 1 | 2025-08-11 | 2025-08-12 | 2025-08-14 |  | 2025-08-27 |  | NOT LINKED IN PROJECT SCHEDULE SHEET |  |  | Image 2025-08-13 13-27-15.jpeg |  | 9 | Kerri Pandolfi | 455 | 25 |  | 0.5 | 4 | 1 | 8 | 1.8 | 14.4 | 1 | 0.8 | 0.5 | -0.5 | 25 | 455-320001TUR | PRE-FAB - LEVEL 39 - 6" PVC x 8"LONG CONTROL POINTS | #NO MATCH | #NO MATCH | PF.455 | 9000056 |  | PF.455 | NOT ON PROJECT SCHEDULE | 99% | TRUE |  | 2025-07-28 |  | 2025-10-05 | -40 | TRUE
[5 empty] | 9000150 | 456 | 320001TUR | Stephen Yee | LEVEL 1 | IN-WALL ASSEMBLIES (AV) | shallow box, beam mockup | 1 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-07-25 | 2025-08-04 | james campbell | TRUE | true | TRUE | True | APPROVED | 0.27316 | 0.034145 | 1 | 1 | 2025-08-01 | 2025-08-02 | 2025-08-04 |  | 2025-08-04 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-05 07-22-27.jpeg |  |  | Kerri Pandolfi | 456 | 25 |  | 0 | 0 | 0.27316 | 0.27316 | 0.4 | 0.4 | 0.27316 | 0.12684 | 0 | -0.27316 | 25 | 456-320001TUR | PRE-FAB - LEVEL 1 - shallow box, beam mockup | #NO MATCH | #NO MATCH | PF.456 | 9000150 |  | PF.456 | NOT ON PROJECT SCHEDULE | 100% |  |  | 2025-07-18 |  | 2025-10-05 | -46
[5 empty] | 9000220 | 457 | 320001TUR | Stephen Yee | MULTI LEVEL | TEMPS (SMALL) | SPIDER BOXES / 15FT - FEMAILE WHIPS | 40 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo, Doug Durand | 2025-07-29 | 2025-08-13 | Arthur Mayo | TRUE | true | TRUE | True | APPROVED | 40 | 5 | 5 | 1 | 2025-08-05 | 2025-08-12 | 2025-08-14 |  | 2025-08-15 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-15 06-42-52.jpeg |  | 14 | Kerri Pandolfi | 457 | 25 |  | 0.4375 | 17.5 | 1 | 40 | 2 | 80 | 1 | 1 | 0.4375 | -0.5625 | 25 | 457-320001TUR | PRE-FAB - MULTI LEVEL - SPIDER BOXES / 15FT - FEMAILE WHIPS | #NO MATCH | #NO MATCH | PF.457 | 9000220 |  | PF.457 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-07-22 |  | 2025-10-05 | -44 | TRUE
[5 empty] | 9000220 | 458 | 320001TUR | Stephen Yee | SITE | TEMPS (LARGE) | TEMP PANELS | 2 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-08 | 2025-08-13 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 16 | 2 | 2 | 1 | 2025-08-15 | 2025-08-19 | 2025-08-21 |  | 2025-08-21 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-18 13-07-35.jpeg |  |  | Kerri Pandolfi | 458 | 25 |  | 17.75 | 35.5 | 8 | 16 |  | 0 | 8 | -8 | 8 | 0 | 25 | 458-320001TUR | PRE-FAB - SITE - TEMP PANELS | #NO MATCH | #NO MATCH | PF.458 | 9000220 |  | PF.458 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-08-01 |  | 2025-10-05 | -36
[5 empty] | 9000104 | 459 | 320001TUR | Stephen Yee | LEVEL 3 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 2 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-26 | 2025-08-15 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.0005814 | 1 | 430 | 2025-09-02 | 2025-09-03 | 2025-09-05 |  | 2025-09-05 |  | 2025-11-14 | TRUE |  | 2025-09-02 |  | 14 | Kerri Pandolfi | 459 | 25 |  | 2 | 4 | 1 | 2 | 1.8 | 3.6 | 1 | 0.8 | 1 | 0 | 25 | 459-320001TUR | PRE-FAB - LEVEL 3 - HILTI WALL SLEEVES | 426 | INSTALL - LEVEL 3 - HILTI WALL SLEEVES | PF.459 | 9000104 |  | PF.459 | PF.459 | 100% | TRUE |  | 2025-08-19 |  | 2025-10-05 | -24 | TRUE
[5 empty] | 9000104 | 460 | 320001TUR | Stephen Yee | LEVEL 4 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0016722 | 1 | 299 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-11-21 | TRUE |  | Image 2025-09-19 10-24-31.jpeg |  | 2 | Kerri Pandolfi | 460 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 460-320001TUR | PRE-FAB - LEVEL 4 - HILTI WALL SLEEVES | 470 | INSTALL - LEVEL 4 - HILTI WALL SLEEVES | PF.460 | 9000104 |  | PF.460 | PF.460 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[5 empty] | 9000104 | 461 | 320001TUR | Stephen Yee | LEVEL 5 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0016667 | 1 | 300 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-01 | TRUE |  | Image 2025-09-19 10-24-56.jpeg |  | 2 | Kerri Pandolfi | 461 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 461-320001TUR | PRE-FAB - LEVEL 5 - HILTI WALL SLEEVES | 509 | INSTALL - LEVEL 5 - HILTI WALL SLEEVES | PF.461 | 9000104 |  | PF.461 | PF.461 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[5 empty] | 9000104 | 462 | 320001TUR | Stephen Yee | LEVEL 6 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0016556 | 1 | 302 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-08 | TRUE |  | Image 2025-09-19 10-27-06.jpeg |  | 2 | Kerri Pandolfi | 462 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 462-320001TUR | PRE-FAB - LEVEL 6 - HILTI WALL SLEEVES | 549 | INSTALL - LEVEL 6 - HILTI WALL SLEEVES | PF.462 | 9000104 |  | PF.462 | PF.462 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[5 empty] | 9000104 | 463 | 320001TUR | Stephen Yee | LEVEL 7 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0011574 | 1 | 432 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-15 | TRUE |  | Image 2025-09-19 10-27-31.jpeg |  | 2 | Kerri Pandolfi | 463 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 463-320001TUR | PRE-FAB - LEVEL 7 - HILTI WALL SLEEVES | 583 | INSTALL - LEVEL 7 - HILTI WALL SLEEVES | PF.463 | 9000104 |  | PF.463 | PF.463 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[5 empty] | 9000104 | 464 | 320001TUR | Stephen Yee | LEVEL 8 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0017544 | 1 | 285 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-22 | TRUE |  | Image 2025-09-19 10-29-33.jpeg |  | 2 | Kerri Pandolfi | 464 | 25 |  | 0.0625 | 0.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.0625 | -0.9375 | 25 | 464-320001TUR | PRE-FAB - LEVEL 8 - HILTI WALL SLEEVES | 621 | INSTALL - LEVEL 8 - HILTI WALL SLEEVES | PF.464 | 9000104 |  | PF.464 | PF.464 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[5 empty] | 9000104 | 465 | 320001TUR | Stephen Yee | LEVEL 9 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-08 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.002381 | 1 | 210 | 2025-09-15 | 2025-09-16 | 2025-09-18 |  | 2025-09-25 |  | 2025-12-30 | TRUE |  | Image 2025-09-19 10-29-12.jpeg |  | 2 | Kerri Pandolfi | 465 | 25 |  | 1.1875 | 4.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 1 | 0 | 25 | 465-320001TUR | PRE-FAB - LEVEL 9 - HILTI WALL SLEEVES | 666 | INSTALL - LEVEL 9 - HILTI WALL SLEEVES | PF.465 | 9000104 |  | PF.465 | PF.465 | 100% | TRUE |  | 2025-09-01 |  | 2025-10-05 | -15 | TRUE
[5 empty] | 9000104 | 466 | 320001TUR | Stephen Yee | LEVEL 10 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0023585 | 1 | 212 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-01-07 | TRUE |  | Image 2025-09-19 10-28-51.jpeg |  | 2 | Kerri Pandolfi | 466 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 466-320001TUR | PRE-FAB - LEVEL 10 - HILTI WALL SLEEVES | 707 | INSTALL - LEVEL 10 - HILTI WALL SLEEVES | PF.466 | 9000104 |  | PF.466 | PF.466 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[5 empty] | 9000104 | 467 | 320001TUR | Stephen Yee | LEVEL 11 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0023364 | 1 | 214 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-01-14 | TRUE |  | Image 2025-09-19 10-28-23.jpeg |  | 2 | Kerri Pandolfi | 467 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 467-320001TUR | PRE-FAB - LEVEL 11 - HILTI WALL SLEEVES | 761 | INSTALL - LEVEL 11 - HILTI WALL SLEEVES | PF.467 | 9000104 |  | PF.467 | PF.467 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[5 empty] | 9000104 | 468 | 320001TUR | Stephen Yee | LEVEL 12 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0023256 | 1 | 215 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-01-22 | TRUE |  | Image 2025-09-19 10-34-11.jpeg |  | 2 | Kerri Pandolfi | 468 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 468-320001TUR | PRE-FAB - LEVEL 12 - HILTI WALL SLEEVES | 812 | INSTALL - LEVEL 12 - HILTI WALL SLEEVES | PF.468 | 9000104 |  | PF.468 | PF.468 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[5 empty] | 9000104 | 469 | 320001TUR | Stephen Yee | LEVEL 13 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0016502 | 1 | 303 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-01-29 | TRUE |  | Image 2025-09-19 10-33-47.jpeg |  | 2 | Kerri Pandolfi | 469 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 469-320001TUR | PRE-FAB - LEVEL 13 - HILTI WALL SLEEVES | 865 | INSTALL - LEVEL 13 - HILTI WALL SLEEVES | PF.469 | 9000104 |  | PF.469 | PF.469 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[5 empty] | 9000104 | 470 | 320001TUR | Stephen Yee | LEVEL 14 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.0022523 | 1 | 222 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-02 |  | 2026-02-05 | TRUE |  | Image 2025-09-19 10-33-22.jpeg |  | 2 | Kerri Pandolfi | 470 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 470-320001TUR | PRE-FAB - LEVEL 14 - HILTI WALL SLEEVES | 912 | INSTALL - LEVEL 14 - HILTI WALL SLEEVES | PF.470 | 9000104 |  | PF.470 | PF.470 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[5 empty] | 9000104 | 471 | 320001TUR | Stephen Yee | LEVEL 15 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-02-12 | TRUE |  | Image 2025-09-19 10-32-57.jpeg |  | 2 | Kerri Pandolfi | 471 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 471-320001TUR | PRE-FAB - LEVEL 15 - HILTI WALL SLEEVES | 954 | INSTALL - LEVEL 15 - HILTI WALL SLEEVES | PF.471 | 9000104 |  | PF.471 | PF.471 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 472 | 320001TUR | Stephen Yee | LEVEL 16 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-02-20 | TRUE |  | Image 2025-09-19 10-32-32.jpeg |  | 2 | Kerri Pandolfi | 472 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 472-320001TUR | PRE-FAB - LEVEL 16 - HILTI WALL SLEEVES | 999 | INSTALL - LEVEL 16 - HILTI WALL SLEEVES | PF.472 | 9000104 |  | PF.472 | PF.472 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 473 | 320001TUR | Stephen Yee | LEVEL 17 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-02-27 | TRUE |  | Image 2025-09-19 10-32-07.jpeg |  | 2 | Kerri Pandolfi | 473 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 473-320001TUR | PRE-FAB - LEVEL 17 - HILTI WALL SLEEVES | 1038 | INSTALL - LEVEL 17 - HILTI WALL SLEEVES | PF.473 | 9000104 |  | PF.473 | PF.473 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 474 | 320001TUR | Stephen Yee | LEVEL 18 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-03-06 | TRUE |  | Image 2025-09-19 10-31-19.jpeg |  | 2 | Kerri Pandolfi | 474 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 474-320001TUR | PRE-FAB - LEVEL 18 - HILTI WALL SLEEVES | 1084 | INSTALL - LEVEL 18 - HILTI WALL SLEEVES | PF.474 | 9000104 |  | PF.474 | PF.474 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 475 | 320001TUR | Stephen Yee | LEVEL 19 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-03-13 | TRUE |  | Image 2025-09-19 10-31-46.jpeg |  | 2 | Kerri Pandolfi | 475 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 475-320001TUR | PRE-FAB - LEVEL 19 - HILTI WALL SLEEVES | 1132 | INSTALL - LEVEL 19 - HILTI WALL SLEEVES | PF.475 | 9000104 |  | PF.475 | PF.475 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 476 | 320001TUR | Stephen Yee | LEVEL 20 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-13 | 2025-09-15 |  | 2025-10-22 |  | 2026-03-20 | TRUE |  | Image 2025-09-24 06-16-22.jpeg |  | 2 | Kerri Pandolfi | 476 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 476-320001TUR | PRE-FAB - LEVEL 20 - HILTI WALL SLEEVES | 1173 | INSTALL - LEVEL 20 - HILTI WALL SLEEVES | PF.476 | 9000104 |  | PF.476 | PF.476 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 477 | 320001TUR | Stephen Yee | LEVEL 21 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-03-27 | TRUE |  | Image 2025-09-24 06-15-57.jpeg |  | 2 | Kerri Pandolfi | 477 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 477-320001TUR | PRE-FAB - LEVEL 21 - HILTI WALL SLEEVES | 1219 | INSTALL - LEVEL 21 - HILTI WALL SLEEVES | PF.477 | 9000104 |  | PF.477 | PF.477 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 478 | 320001TUR | Stephen Yee | LEVEL 22 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-04-03 | TRUE |  | Image 2025-09-24 06-15-29.jpeg |  | 2 | Kerri Pandolfi | 478 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 478-320001TUR | PRE-FAB - LEVEL 22 - HILTI WALL SLEEVES | 1260 | INSTALL - LEVEL 22 - HILTI WALL SLEEVES | PF.478 | 9000104 |  | PF.478 | PF.478 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 479 | 320001TUR | Stephen Yee | LEVEL 23 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-04-10 | TRUE |  | Image 2025-09-24 06-15-09.jpeg |  | 2 | Kerri Pandolfi | 479 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 479-320001TUR | PRE-FAB - LEVEL 23 - HILTI WALL SLEEVES | 1300 | INSTALL - LEVEL 23 - HILTI WALL SLEEVES | PF.479 | 9000104 |  | PF.479 | PF.479 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 480 | 320001TUR | Stephen Yee | LEVEL 24 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-04-17 | TRUE |  | Image 2025-09-24 06-13-58.jpeg |  | 2 | Kerri Pandolfi | 480 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 480-320001TUR | PRE-FAB - LEVEL 24 - HILTI WALL SLEEVES | 1345 | INSTALL - LEVEL 24 - HILTI WALL SLEEVES | PF.480 | 9000104 |  | PF.480 | PF.480 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 481 | 320001TUR | Stephen Yee | LEVEL 25 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-04-27 | TRUE |  | Image 2025-09-24 06-13-33.jpeg |  | 2 | Kerri Pandolfi | 481 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 481-320001TUR | PRE-FAB - LEVEL 25 - HILTI WALL SLEEVES | 1382 | INSTALL - LEVEL 25 - HILTI WALL SLEEVES | PF.481 | 9000104 |  | PF.481 | PF.481 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 482 | 320001TUR | Stephen Yee | LEVEL 26 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-05-04 | TRUE |  | Image 2025-09-24 06-13-10.jpeg |  | 2 | Kerri Pandolfi | 482 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 482-320001TUR | PRE-FAB - LEVEL 26 - HILTI WALL SLEEVES | 1424 | INSTALL - LEVEL 26 - HILTI WALL SLEEVES | PF.482 | 9000104 |  | PF.482 | PF.482 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 483 | 320001TUR | Stephen Yee | LEVEL 27 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-05-11 | TRUE |  | Image 2025-09-24 06-12-50.jpeg |  | 2 | Kerri Pandolfi | 483 | 25 |  | 0.3125 | 1.25 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.3125 | -0.6875 | 25 | 483-320001TUR | PRE-FAB - LEVEL 27 - HILTI WALL SLEEVES | 1462 | INSTALL - LEVEL 27 - HILTI WALL SLEEVES | PF.483 | 9000104 |  | PF.483 | PF.483 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 484 | 320001TUR | Stephen Yee | LEVEL 28 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-14 | 2025-09-16 |  | 2025-10-16 |  | 2026-05-18 | TRUE |  | Image 2025-09-24 07-44-28.jpeg |  | 2 | Kerri Pandolfi | 484 | 25 |  | 0.25 | 1 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.25 | -0.75 | 25 | 484-320001TUR | PRE-FAB - LEVEL 28 - HILTI WALL SLEEVES | 1503 | INSTALL - LEVEL 28 - HILTI WALL SLEEVES | PF.484 | 9000104 |  | PF.484 | PF.484 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 485 | 320001TUR | Stephen Yee | LEVEL 29 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-05-26 | TRUE |  | Image 2025-09-24 07-44-55.jpeg |  | 2 | Kerri Pandolfi | 485 | 25 |  | 0.125 | 0.5 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.125 | -0.875 | 25 | 485-320001TUR | PRE-FAB - LEVEL 29 - HILTI WALL SLEEVES | 1545 | INSTALL - LEVEL 29 - HILTI WALL SLEEVES | PF.485 | 9000104 |  | PF.485 | PF.485 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 486 | 320001TUR | Stephen Yee | LEVEL 30 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-06-02 | TRUE |  | Image 2025-09-24 07-45-14.jpeg |  | 2 | Kerri Pandolfi | 486 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 486-320001TUR | PRE-FAB - LEVEL 30 - HILTI WALL SLEEVES | 1571 | INSTALL - LEVEL 30 - HILTI WALL SLEEVES | PF.486 | 9000104 |  | PF.486 | PF.486 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 487 | 320001TUR | Stephen Yee | LEVEL 31 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-06-09 | TRUE |  | Image 2025-09-24 07-47-01.jpeg |  | 2 | Kerri Pandolfi | 487 | 25 |  | 1.125 | 4.5 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 1 | 0 | 25 | 487-320001TUR | PRE-FAB - LEVEL 31 - HILTI WALL SLEEVES | 1608 | INSTALL - LEVEL 31 - HILTI WALL SLEEVES | PF.487 | 9000104 |  | PF.487 | PF.487 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 488 | 320001TUR | Stephen Yee | LEVEL 32 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-06-17 | TRUE |  | Image 2025-09-24 07-47-23.jpeg |  | 2 | Kerri Pandolfi | 488 | 25 |  | 0.1875 | 0.75 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.1875 | -0.8125 | 25 | 488-320001TUR | PRE-FAB - LEVEL 32 - HILTI WALL SLEEVES | 1650 | INSTALL - LEVEL 32 - HILTI WALL SLEEVES | PF.488 | 9000104 |  | PF.488 | PF.488 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 489 | 320001TUR | Stephen Yee | LEVEL 33 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-06-24 | TRUE |  | Image 2025-09-24 07-47-46.jpeg |  | 2 | Kerri Pandolfi | 489 | 25 |  | 0.125 | 0.5 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.125 | -0.875 | 25 | 489-320001TUR | PRE-FAB - LEVEL 33 - HILTI WALL SLEEVES | 1681 | INSTALL - LEVEL 33 - HILTI WALL SLEEVES | PF.489 | 9000104 |  | PF.489 | PF.489 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 490 | 320001TUR | Stephen Yee | LEVEL 34 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-07-01 | TRUE |  | Image 2025-09-24 07-46-36.jpeg |  | 2 | Kerri Pandolfi | 490 | 25 |  | 0.5 | 2 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.5 | -0.5 | 25 | 490-320001TUR | PRE-FAB - LEVEL 34 - HILTI WALL SLEEVES | 1709 | INSTALL - LEVEL 34 - HILTI WALL SLEEVES | PF.490 | 9000104 |  | PF.490 | PF.490 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 491 | 320001TUR | Stephen Yee | LEVEL 35 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-07-09 | TRUE |  | Image 2025-09-24 07-46-12.jpeg |  | 2 | Kerri Pandolfi | 491 | 25 |  | 0.5 | 2 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.5 | -0.5 | 25 | 491-320001TUR | PRE-FAB - LEVEL 35 - HILTI WALL SLEEVES | 1738 | INSTALL - LEVEL 35 - HILTI WALL SLEEVES | PF.491 | 9000104 |  | PF.491 | PF.491 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 492 | 320001TUR | Stephen Yee | LEVEL 36 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI WALL SLEEVES | 4 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-05 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4 | 0.5 | 1 | 1 | 2025-09-12 | 2025-09-15 | 2025-09-17 |  | 2025-10-17 |  | 2026-07-16 | TRUE |  | Image 2025-09-24 07-45-50.jpeg |  | 2 | Kerri Pandolfi | 492 | 25 |  | 0.5 | 2 | 1 | 4 | 1.8 | 7.2 | 1 | 0.8 | 0.5 | -0.5 | 25 | 492-320001TUR | PRE-FAB - LEVEL 36 - HILTI WALL SLEEVES | 1759 | INSTALL - LEVEL 36 - HILTI WALL SLEEVES | PF.492 | 9000104 |  | PF.492 | PF.492 | 100% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16 | TRUE
[5 empty] | 9000104 | 493 | 320001TUR | Stephen Yee | LEVEL 3 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | CONDUIT RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-26 | [7 empty] | 1 | 0.125 | 1 | 1 | 2025-09-02 | 2025-09-03 | 2025-09-05 |  | 2025-09-05 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 493 | 25 |  | 0 | 0 | 1 | 1 | 1.8 | 1.8 | 1 | 0.8 | 0 | -1 | 25 | 493-320001TUR | PRE-FAB - LEVEL 3 - CONDUIT RISER SLEEVES | #NO MATCH | #NO MATCH | PF.493 | 9000104 |  | PF.493 | DELETED | 100% |  |  | 2025-08-19 |  | 2025-10-05 | -24
[5 empty] | 9000104 | 494 | 320001TUR | Stephen Yee | LEVEL 4 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-02 | [7 empty] | 2 | 0.25 | 1 | 1 | 2025-09-09 | 2025-09-10 | 2025-09-12 |  | 2025-09-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 494 | 25 |  | 0 | 0 | 2 | 2 |  | 0 | 2 | -2 | 0 | -2 | 25 | 494-320001TUR | PRE-FAB - LEVEL 4 - HILTI RISER SLEEVES | #NO MATCH | #NO MATCH | PF.494 | 9000104 |  | PF.494 | DELETED | 100% |  |  | 2025-08-26 |  | 2025-10-05 | -19
[5 empty] | 9000104 | 495 | 320001TUR | Stephen Yee | LEVEL 5 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.25 | 1 | 1 | 2025-08-22 | 2025-08-23 | 2025-08-25 |  | 2025-08-25 |  | 2025-08-25 | TRUE |  | Image 2025-08-26 07-30-43.jpeg |  | 3 | Kerri Pandolfi | 495 | 25 |  | 2 | 2 | 2 | 2 |  | 0 | 2 | -2 | 2 | 0 | 25 | 495-320001TUR | PRE-FAB - LEVEL 5 - HILTI RISER SLEEVES | 112 |  | PF.495 | 9000104 |  | PF.495 | PF.495 | 100% | TRUE |  | 2025-08-08 |  | 2025-10-05 | -31 | TRUE
[5 empty] | 9000104 | 496 | 320001TUR | Stephen Yee | LEVEL 6 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 1 | 0.125 | 1 | 1 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-03 |  | 2025-08-27 | TRUE |  | Image 2025-09-03 09-24-58.jpeg |  | 3 | Kerri Pandolfi | 496 | 25 |  | 3 | 3 | 1 | 1 | 1.8 | 1.8 | 1 | 0.8 | 1 | 0 | 25 | 496-320001TUR | PRE-FAB - LEVEL 6 - HILTI RISER SLEEVES | 120 | PRE-FAB - LEVEL 5 - HILTI RISER SLEEVES | PF.496 | 9000104 |  | PF.496 | PF.496 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 497 | 320001TUR | Stephen Yee | LEVEL 7 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00047259 | 1 | 529 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-03 |  | 2025-08-27 | TRUE |  | Image 2025-09-03 09-25-33.jpeg |  | 3 | Kerri Pandolfi | 497 | 25 |  | 3 | 3 | 2 | 2 |  | 0 | 2 | -2 | 2 | 0 | 25 | 497-320001TUR | PRE-FAB - LEVEL 7 - HILTI RISER SLEEVES | 121 | PRE-FAB - LEVEL 5 - HILTI RISER SLEEVES | PF.497 | 9000104 |  | PF.497 | PF.497 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 498 | 320001TUR | Stephen Yee | LEVEL 8 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00032595 | 1 | 767 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-03 |  | 2025-08-29 | TRUE |  | Image 2025-09-03 09-26-21.jpeg |  | 3 | Kerri Pandolfi | 498 | 25 |  | 2 | 2 | 2 | 2 |  | 0 | 2 | -2 | 2 | 0 | 25 | 498-320001TUR | PRE-FAB - LEVEL 8 - HILTI RISER SLEEVES | 134 | PRE-FAB - LEVEL 7 - HILTI RISER SLEEVES | PF.498 | 9000104 |  | PF.498 | PF.498 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 499 | 320001TUR | Stephen Yee | LEVEL 9 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-25 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00065445 | 1 | 382 | 2025-09-01 | 2025-09-02 | 2025-09-04 |  | 2025-09-04 |  | 2025-09-04 | TRUE |  | Image 2025-09-03 09-26-54.jpeg |  | 3 | Kerri Pandolfi | 499 | 25 |  | 2 | 2 | 2 | 2 |  | 0 | 2 | -2 | 2 | 0 | 25 | 499-320001TUR | PRE-FAB - LEVEL 9 - HILTI RISER SLEEVES | 142 | PRE-FAB - LEVEL 8 - HILTI RISER SLEEVES | PF.499 | 9000104 |  | PF.499 | PF.499 | 100% | TRUE |  | 2025-08-18 |  | 2025-10-05 | -25 | TRUE
[5 empty] | 9000104 | 500 | 320001TUR | Stephen Yee | LEVEL 10 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00080906 | 1 | 309 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-08 |  | 2025-09-08 | TRUE |  | Image 2025-09-03 09-40-36.jpeg |  | 3 | Kerri Pandolfi | 500 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 500-320001TUR | PRE-FAB - LEVEL 10 - HILTI RISER SLEEVES | 154 | PRE-FAB - LEVEL 9 - HILTI RISER SLEEVES | PF.500 | 9000104 |  | PF.500 | PF.500 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 501 | 320001TUR | Stephen Yee | LEVEL 11 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00085616 | 1 | 292 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-10 |  | 2025-09-10 | TRUE |  | Image 2025-09-03 09-41-04.jpeg |  | 3 | Kerri Pandolfi | 501 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 501-320001TUR | PRE-FAB - LEVEL 11 - HILTI RISER SLEEVES | 165 | PRE-FAB - LEVEL 10 - HILTI RISER SLEEVES | PF.501 | 9000104 |  | PF.501 | PF.501 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 502 | 320001TUR | Stephen Yee | LEVEL 12 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00079618 | 1 | 314 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-15 |  | 2025-09-15 | TRUE |  | Image 2025-09-03 09-42-43.jpeg |  | 3 | Kerri Pandolfi | 502 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 502-320001TUR | PRE-FAB - LEVEL 12 - HILTI RISER SLEEVES | 174 | PRE-FAB - LEVEL 11 - HILTI RISER SLEEVES | PF.502 | 9000104 |  | PF.502 | PF.502 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 503 | 320001TUR | Stephen Yee | LEVEL 13 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00065274 | 1 | 383 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-17 |  | 2025-09-17 | TRUE |  | Image 2025-09-03 11-24-21.jpeg |  | 3 | Kerri Pandolfi | 503 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 503-320001TUR | PRE-FAB - LEVEL 13 - HILTI RISER SLEEVES | 188 | PRE-FAB - LEVEL 12 - HILTI RISER SLEEVES | PF.503 | 9000104 |  | PF.503 | PF.503 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 504 | 320001TUR | Stephen Yee | LEVEL 14 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.25 | 1 | 1 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-19 |  | 2025-09-19 | TRUE |  | Image 2025-09-03 11-25-07.jpeg |  | 3 | Kerri Pandolfi | 504 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 504-320001TUR | PRE-FAB - LEVEL 14 - HILTI RISER SLEEVES | 204 | PRE-FAB - LEVEL 13 - HILTI RISER SLEEVES | PF.504 | 9000104 |  | PF.504 | PF.504 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 505 | 320001TUR | Stephen Yee | LEVEL 15 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064935 | 1 | 385 | 2025-08-29 | 2025-09-01 | 2025-09-03 |  | 2025-09-23 |  | 2025-09-23 | TRUE |  | Image 2025-09-03 11-24-49.jpeg |  | 3 | Kerri Pandolfi | 505 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 505-320001TUR | PRE-FAB - LEVEL 15 - HILTI RISER SLEEVES | 211 | PRE-FAB - LEVEL 14 - HILTI RISER SLEEVES | PF.505 | 9000104 |  | PF.505 | PF.505 | 100% | TRUE |  | 2025-08-15 |  | 2025-10-05 | -26 | TRUE
[5 empty] | 9000104 | 506 | 320001TUR | Stephen Yee | LEVEL 16 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00080128 | 1 | 312 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-10-03 |  | 2025-09-26 | TRUE |  | Image 2025-09-24 12-46-20.jpeg |  | 2 | Kerri Pandolfi | 506 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 506-320001TUR | PRE-FAB - LEVEL 16 - HILTI RISER SLEEVES | 221 | PRE-FAB - LEVEL 15 - HILTI RISER SLEEVES | PF.506 | 9000104 |  | PF.506 | PF.506 | 100% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 507 | 320001TUR | Stephen Yee | LEVEL 17 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064767 | 1 | 386 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-07 |  | 2025-09-30 | TRUE |  | Image 2025-09-24 12-46-51.jpeg |  | 2 | Kerri Pandolfi | 507 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 507-320001TUR | PRE-FAB - LEVEL 17 - HILTI RISER SLEEVES | 231 | PRE-FAB - LEVEL 16 - HILTI RISER SLEEVES | PF.507 | 9000104 |  | PF.507 | PF.507 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[5 empty] | 9000104 | 508 | 320001TUR | Stephen Yee | LEVEL 18 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-22 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00078616 | 1 | 318 | 2025-09-29 | 2025-09-30 | 2025-10-02 |  | 2025-10-14 |  | 2025-10-02 | TRUE |  | Image 2025-09-24 12-47-12.jpeg |  | 2 | Kerri Pandolfi | 508 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 508-320001TUR | PRE-FAB - LEVEL 18 - HILTI RISER SLEEVES | 242 | PRE-FAB - LEVEL 17 - HILTI RISER SLEEVES | PF.508 | 9000104 |  | PF.508 | PF.508 | 100% | TRUE |  | 2025-09-15 |  | 2025-10-05 | -5 | TRUE
[5 empty] | 9000104 | 509 | 320001TUR | Stephen Yee | LEVEL 19 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-15 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00085324 | 1 | 293 | 2025-09-22 | 2025-09-23 | 2025-09-25 |  | 2025-10-07 |  | 2025-10-07 | TRUE |  | Image 2025-09-24 12-47-32.jpeg |  | 2 | Kerri Pandolfi | 509 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 509-320001TUR | PRE-FAB - LEVEL 19 - HILTI RISER SLEEVES | 251 | PRE-FAB - LEVEL 18 - HILTI RISER SLEEVES | PF.509 | 9000104 |  | PF.509 | PF.509 | 100% | TRUE |  | 2025-09-08 |  | 2025-10-05 | -10 | TRUE
[5 empty] | 9000104 | 510 | 320001TUR | Stephen Yee | LEVEL 20 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00085034 | 1 | 294 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-10-10 |  | 2025-10-09 | TRUE |  | Image 2025-09-24 12-48-03.jpeg |  | 2 | Kerri Pandolfi | 510 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 510-320001TUR | PRE-FAB - LEVEL 20 - HILTI RISER SLEEVES | 266 | PRE-FAB - LEVEL 19 - HILTI RISER SLEEVES | PF.510 | 9000104 |  | PF.510 | PF.510 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000104 | 511 | 320001TUR | Stephen Yee | LEVEL 21 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064599 | 1 | 387 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-10-14 |  | 2025-10-14 | TRUE |  | Image 2025-09-24 12-48-43.jpeg |  | 2 | Kerri Pandolfi | 511 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 511-320001TUR | PRE-FAB - LEVEL 21 - HILTI RISER SLEEVES | 275 | PRE-FAB - LEVEL 20 - HILTI RISER SLEEVES | PF.511 | 9000104 |  | PF.511 | PF.511 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000104 | 512 | 320001TUR | Stephen Yee | LEVEL 22 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064433 | 1 | 388 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-10-16 |  | 2025-10-16 | TRUE |  | Image 2025-09-24 12-49-16.jpeg |  | 2 | Kerri Pandolfi | 512 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 512-320001TUR | PRE-FAB - LEVEL 22 - HILTI RISER SLEEVES | 288 | PRE-FAB - LEVEL 21 - HILTI RISER SLEEVES | PF.512 | 9000104 |  | PF.512 | PF.512 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000104 | 513 | 320001TUR | Stephen Yee | LEVEL 23 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064267 | 1 | 389 | 2025-09-26 | 2025-09-28 | 2025-09-30 |  | 2025-10-21 |  | 2025-10-21 | TRUE |  | Image 2025-09-24 12-45-25.jpeg |  | 2 | Kerri Pandolfi | 513 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 513-320001TUR | PRE-FAB - LEVEL 23 - HILTI RISER SLEEVES | 299 | PRE-FAB - LEVEL 22 - HILTI RISER SLEEVES | PF.513 | 9000104 |  | PF.513 | PF.513 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000104 | 514 | 320001TUR | Stephen Yee | LEVEL 24 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-10-31 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00064103 | 1 | 390 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 | DATES MISALIGNED | 2025-10-23 |  |  | Image 2025-09-26 10-06-53.jpeg |  | 2 | Kerri Pandolfi | 514 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 514-320001TUR | PRE-FAB - LEVEL 24 - HILTI RISER SLEEVES | 309 | PRE-FAB - LEVEL 23 - HILTI RISER SLEEVES | PF.514 | 9000104 |  | PF.514 | PF.514 | 99% | TRUE |  | 2025-10-24 |  | 2025-10-05 | 26 | TRUE
[5 empty] | 9000104 | 515 | 320001TUR | Stephen Yee | LEVEL 25 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00077882 | 1 | 321 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-12 | DATES MISALIGNED | 2025-10-27 |  |  | Image 2025-09-26 09-53-03.jpeg |  | 2 | Kerri Pandolfi | 515 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 515-320001TUR | PRE-FAB - LEVEL 25 - HILTI RISER SLEEVES | 325 | PRE-FAB - LEVEL 24 - HILTI RISER SLEEVES | PF.515 | 9000104 |  | PF.515 | PF.515 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 516 | 320001TUR | Stephen Yee | LEVEL 26 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00084459 | 1 | 296 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-12 | DATES MISALIGNED | 2025-10-30 |  |  | Image 2025-09-26 09-54-08.jpeg |  | 2 | Kerri Pandolfi | 516 | 25 |  | 1.5 | 1.5 | 2 | 2 |  | 0 | 2 | -2 | 1.5 | -0.5 | 25 | 516-320001TUR | PRE-FAB - LEVEL 26 - HILTI RISER SLEEVES | 343 | PRE-FAB - LEVEL 25 - HILTI RISER SLEEVES | PF.516 | 9000104 |  | PF.516 | PF.516 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 517 | 320001TUR | Stephen Yee | LEVEL 27 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00084746 | 1 | 295 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-03 |  | 2025-11-03 |  |  | Image 2025-09-26 09-54-34.jpeg |  | 2 | Kerri Pandolfi | 517 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 517-320001TUR | PRE-FAB - LEVEL 27 - HILTI RISER SLEEVES | 369 | PRE-FAB - LEVEL 26 - HILTI RISER SLEEVES | PF.517 | 9000104 |  | PF.517 | PF.517 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 518 | 320001TUR | Stephen Yee | LEVEL 28 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00058275 | 1 | 429 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-05 |  | 2025-11-05 |  |  | Image 2025-09-26 09-55-07.jpeg |  | 2 | Kerri Pandolfi | 518 | 25 |  | 0.5 | 0.5 | 2 | 2 |  | 0 | 2 | -2 | 0.5 | -1.5 | 25 | 518-320001TUR | PRE-FAB - LEVEL 28 - HILTI RISER SLEEVES | 378 | PRE-FAB - LEVEL 27 - HILTI RISER SLEEVES | PF.518 | 9000104 |  | PF.518 | PF.518 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 519 | 320001TUR | Stephen Yee | LEVEL 29 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00083893 | 1 | 298 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-07 |  | 2025-11-12 |  |  | Image 2025-09-26 10-01-41.jpeg |  | 2 | Kerri Pandolfi | 519 | 25 |  | 1.5 | 1.5 | 2 | 2 |  | 0 | 2 | -2 | 1.5 | -0.5 | 25 | 519-320001TUR | PRE-FAB - LEVEL 29 - HILTI RISER SLEEVES | 402 | PRE-FAB - LEVEL 28 - HILTI RISER SLEEVES | PF.519 | 9000104 |  | PF.519 | PF.519 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 520 | 320001TUR | Stephen Yee | LEVEL 30 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00084175 | 1 | 297 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-13 |  | 2025-11-17 |  |  | Image 2025-09-26 10-03-56.jpeg |  | 2 | Kerri Pandolfi | 520 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 520-320001TUR | PRE-FAB - LEVEL 30 - HILTI RISER SLEEVES | 435 | PRE-FAB - LEVEL 29 - HILTI RISER SLEEVES | PF.520 | 9000104 |  | PF.520 | PF.520 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 521 | 320001TUR | Stephen Yee | LEVEL 31 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00058005 | 1 | 431 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-18 |  | 2025-11-21 |  |  | Image 2025-09-26 10-04-21.jpeg |  | 2 | Kerri Pandolfi | 521 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 521-320001TUR | PRE-FAB - LEVEL 31 - HILTI RISER SLEEVES | 472 | PRE-FAB - LEVEL 30 - HILTI RISER SLEEVES | PF.521 | 9000104 |  | PF.521 | PF.521 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 522 | 320001TUR | Stephen Yee | LEVEL 32 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00063776 | 1 | 392 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-11-24 | DATES MISALIGNED | 2025-12-04 |  |  | Image 2025-09-26 10-05-11.jpeg |  | 2 | Kerri Pandolfi | 522 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 522-320001TUR | PRE-FAB - LEVEL 32 - HILTI RISER SLEEVES | 521 | INSTALL - LEVEL 32 - HILTI RISER SLEEVES | PF.522 | 9000104 |  | PF.522 | PF.522 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 523 | 320001TUR | Stephen Yee | LEVEL 33 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00083056 | 1 | 301 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-12-05 | DATES MISALIGNED | 2025-12-16 |  |  | Image 2025-09-26 10-05-37.jpeg |  | 2 | Kerri Pandolfi | 523 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 523-320001TUR | PRE-FAB - LEVEL 33 - HILTI RISER SLEEVES | 588 | INSTALL - LEVEL 33 - HILTI RISER SLEEVES | PF.523 | 9000104 |  | PF.523 | PF.523 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 524 | 320001TUR | Stephen Yee | LEVEL 34 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.00057737 | 1 | 433 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-12-17 | DATES MISALIGNED | 2025-12-29 |  |  | Image 2025-09-26 10-07-16.jpeg |  | 2 | Kerri Pandolfi | 524 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 524-320001TUR | PRE-FAB - LEVEL 34 - HILTI RISER SLEEVES | 647 | INSTALL - LEVEL 34 - HILTI RISER SLEEVES | PF.524 | 9000104 |  | PF.524 | PF.524 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 525 | 320001TUR | Stephen Yee | LEVEL 35 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.0011962 | 1 | 209 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2025-12-30 |  | 2026-01-05 |  |  | Image 2025-09-26 10-07-40.jpeg |  | 2 | Kerri Pandolfi | 525 | 25 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 25 | 525-320001TUR | PRE-FAB - LEVEL 35 - HILTI RISER SLEEVES | 682 | INSTALL - LEVEL 35 - HILTI RISER SLEEVES | PF.525 | 9000104 |  | PF.525 | PF.525 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 526 | 320001TUR | Stephen Yee | LEVEL 36 | (8) CONDUIT SLEEVE ASSEMBLY (T/D) | HILTI RISER SLEEVES | 1 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-16 | 2025-08-19 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2 | 0.0011848 | 1 | 211 | 2025-09-23 | 2025-09-24 | 2025-09-26 |  | 2026-01-06 |  | 2026-01-09 |  |  | Image 2025-09-26 10-03-13.jpeg |  | 2 | Kerri Pandolfi | 526 | 26 |  | 1 | 1 | 2 | 2 |  | 0 | 2 | -2 | 1 | -1 | 26 | 526-320001TUR | PRE-FAB - LEVEL 36 - HILTI RISER SLEEVES | 719 | INSTALL - LEVEL 36 - HILTI RISER SLEEVES | PF.526 | 9000104 |  | PF.526 | PF.526 | 99% | TRUE |  | 2025-09-09 |  | 2025-10-05 | -9 | TRUE
[5 empty] | 9000104 | 527 | 320001TUR | Stephen Yee | LEVEL 37 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | CONDUIT RISER SLEEVES | 1 | Yellow | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-04 | 2025-08-19 | Stephen Yee | TRUE | true |  |  |  | 1 | 0.00058685 | 1 | 213 | 2026-05-11 | 2026-05-12 | 2026-05-14 | OVER DUE |  |  | 2026-01-15 | [5 empty] | Kerri Pandolfi | 527 |  |  | 0 | 0 | 1 | 1 | 1.8 | 1.8 | 1 | 0.8 | 0 | -1 |  | 527-320001TUR | PRE-FAB - LEVEL 37 - CONDUIT RISER SLEEVES | 766 | INSTALL - LEVEL 37 - CONDUIT RISER SLEEVES | PF.527 | 9000104 |  | PF.527 | PF.527 | 0% |  |  | 2026-04-27 |  | 2025-10-05 | 157
[5 empty] | 9000104 | 528 | 320001TUR | Stephen Yee | LEVEL 38 | (4) CONDUIT SLEEVE ASSEMBLY (T/D) | CONDUIT RISER SLEEVES | 1 | Yellow | 121 BROADWAY MXD TOWER | Paul Simcoe | 2026-05-18 | 2025-08-19 | Stephen Yee | TRUE | true |  |  |  | 1 | 0.00031807 | 1 | 393 | 2026-05-25 | 2026-05-26 | 2026-05-28 | OVER DUE |  |  | 2026-01-28 | [5 empty] | Kerri Pandolfi | 528 |  |  | 0 | 0 | 1 | 1 | 1.8 | 1.8 | 1 | 0.8 | 0 | -1 |  | 528-320001TUR | PRE-FAB - LEVEL 38 - CONDUIT RISER SLEEVES | 838 | INSTALL - LEVEL 38 - CONDUIT RISER SLEEVES | PF.528 | 9000104 |  | PF.528 | PF.528 | 0% |  |  | 2026-05-11 |  | 2025-10-05 | 167
[5 empty] | 9000220 | 529 | 320001TUR | Stephen Yee | MULTI LEVEL | TEMPS (SMALL) | SPIDER BOXES | 30 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-08-12 | 2025-08-21 | Arthur Mayo | TRUE | true | TRUE | True | APPROVED | 30 | 3.75 | 4 | 1 | 2025-08-19 | 2025-08-25 | 2025-08-27 |  | 2025-08-27 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-08-25 13-11-08.jpeg |  | 3 | Kerri Pandolfi | 529 | 25 |  | 0.16667 | 5 | 1 | 30 | 2 | 60 | 1 | 1 | 0.16667 | -0.83333 | 25 | 529-320001TUR | PRE-FAB - MULTI LEVEL - SPIDER BOXES | #NO MATCH | #NO MATCH | PF.529 | 9000220 |  | PF.529 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-08-05 |  | 2025-10-05 | -34 | TRUE
[5 empty] | 9000010 | 530 | 320001TUR | Stephen Yee | LEVEL 2 | LIGHT FIXTURE WIRED ASSEMBLY (1) LUMINARY WHIP | S50 - THREADED ROD CEILING MOUNT - VAULT | 20 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-09-19 | 2025-08-26 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 2.8 | 0.35 | 1 | 1 | 2025-09-26 | 2025-09-27 | 2025-09-29 |  | 2025-10-06 |  |  | TRUE |  | Image 2025-09-24 06-11-02.jpeg |  | 13 | Kerri Pandolfi | 530 | 25 |  | 0.575 | 11.5 | 0.14 | 2.8 | 0.15 | 3 | 0.14 | 0.01 | 0.14 | 0 | 25 | 530-320001TUR | PRE-FAB - LEVEL 2 - S50 - THREADED ROD CEILING MOUNT - VAULT | 1917 |  | PF.530 | 9000010 |  | PF.530 | PF.530 | 100% | TRUE |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000010 | 531 | 320001TUR | Stephen Yee | LEVEL 2 | LIGHT FIXTURE WIRED ASSEMBLY (1) LUMINARY WHIP | S50 - WALL MOUNT VAULT+L2.5 | 25 | Gray | 121 BROADWAY MXD TOWER | Paul Simcoe | 2025-08-27 | 2025-08-26 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 3.5 | 0.4375 | 1 | 1 | 2025-09-03 | 2025-09-04 | 2025-09-06 |  | 2025-09-08 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | Image 2025-09-08 09-58-27.jpeg |  | 2 | Kerri Pandolfi | 531 | 25 |  | 0.88 | 22 | 0.14 | 3.5 | 0.15 | 3.75 | 0.14 | 0.01 | 0.14 | 0 | 25 | 531-320001TUR | PRE-FAB - LEVEL 2 - S50 - WALL MOUNT VAULT+L2.5 | #NO MATCH | #NO MATCH | PF.531 | 9000010 |  | PF.531 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-08-20 |  | 2025-10-05 | -23 | TRUE
[5 empty] | 9000030 | 532 | 320001TUR | Stephen Yee | MULTI LEVEL | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | EUH HEATER PREWIRE | 29 | Gray | 121 BROADWAY MXD TOWER | Arthur Mayo | 2025-09-01 | [7 empty] | 5.2838 | 0.66048 | 1 | 1 | 2025-09-08 | 2025-09-09 | 2025-09-11 |  | 2025-09-11 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | X |  |  | Kerri Pandolfi | 532 | 25 |  | 0 | 0 | 0.1822 | 5.2838 | 1.15 | 33.35 | 0.1822 | 0.9678 | 0 | -0.1822 | 25 | 532-320001TUR | PRE-FAB - MULTI LEVEL - EUH HEATER PREWIRE | #NO MATCH | #NO MATCH | PF.532 | 9000030 |  | PF.532 | DELETED | 100% |  |  | 2025-08-25 |  | 2025-10-05 | -20
[5 empty] | 9000034 | 533 | 320001TUR | Stephen Yee | LEVEL 1 | SPECIAL CONTROL ASSEMBLY (BRANCH) | UNIT HEATERS (INSTALL MOUNTING HARDWARE) | 12 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-03 | [7 empty] | 48 | 6 | 6 | 1 | 2025-10-10 | 2025-10-18 | 2025-10-20 |  | 2025-10-20 | [7 empty] | Kerri Pandolfi | 533 | 25 |  | 0 | 0 | 4 | 48 | 4.25 | 51 | 4 | 0.25 | 0 | -4 | 25 | 533-320001TUR | PRE-FAB - LEVEL 1 - UNIT HEATERS (INSTALL MOUNTING HARDWARE) | 1915 |  | PF.533 | 9000034 |  | PF.533 | PF.533 | 0% |  |  | 2025-09-26 |  | 2025-10-05 | 6
[5 empty] | 9000030 | 534 | 320001TUR | Stephen Yee | LEVEL 13 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 483 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-10 | [7 empty] | 43.6101 | 2.7256 | 3 | 2 | 2025-12-17 | 2025-12-21 | 2025-12-23 |  | 2025-12-29 | DATES MISALIGNED | 2026-01-06 | [6 empty] | 534 | 25 |  | 0 | 0 | 0.09029 | 43.6101 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 534-320001TUR | PRE-FAB - LEVEL 13 - UNITS INWALL | 671 | LEVEL 13 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.534 | 9000030 |  | PF.534 | PF.534 | 0% |  |  | 2025-12-03 |  | 2025-10-05 | 54
[5 empty] | 9000030 | 535 | 320001TUR | Stephen Yee | LEVEL 22 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-11 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-02-18 | 2026-02-23 | 2026-02-25 |  | 2026-03-02 |  | 2026-03-06 | [6 empty] | 535 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 535-320001TUR | PRE-FAB - LEVEL 22 - UNITS INWALL | 1045 | LEVEL 22 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.535 | 9000030 |  | PF.535 | PF.535 | 0% |  |  | 2026-02-04 |  | 2025-10-05 | 99
[5 empty] | 9000030 | 536 | 320001TUR | Stephen Yee | LEVEL 23 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-18 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-02-25 | 2026-03-02 | 2026-03-04 |  | 2026-03-09 |  | 2026-03-13 | [6 empty] | 536 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 536-320001TUR | PRE-FAB - LEVEL 23 - UNITS INWALL | 1090 | LEVEL 23 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.536 | 9000030 |  | PF.536 | PF.536 | 0% |  |  | 2026-02-11 |  | 2025-10-05 | 104
[5 empty] | 9000030 | 537 | 320001TUR | Stephen Yee | LEVEL 24 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-25 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-03-04 | 2026-03-09 | 2026-03-11 |  | 2026-03-16 |  | 2026-03-20 | [6 empty] | 537 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 537-320001TUR | PRE-FAB - LEVEL 24 - UNITS INWALL | 1137 | LEVEL 24 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.537 | 9000030 |  | PF.537 | PF.537 | 0% |  |  | 2026-02-18 |  | 2025-10-05 | 109
[5 empty] | 9000030 | 538 | 320001TUR | Stephen Yee | LEVEL 25 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-04 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-03-11 | 2026-03-16 | 2026-03-18 |  | 2026-03-23 |  | 2026-03-27 | [6 empty] | 538 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 538-320001TUR | PRE-FAB - LEVEL 25 - UNITS INWALL | 1178 | LEVEL 25 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.538 | 9000030 |  | PF.538 | PF.538 | 0% |  |  | 2026-02-25 |  | 2025-10-05 | 114
[5 empty] | 9000030 | 539 | 320001TUR | Stephen Yee | LEVEL 26 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-11 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-03-18 | 2026-03-21 | 2026-03-23 |  | 2026-03-30 | DATES MISALIGNED | 2026-04-06 | [6 empty] | 539 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 539-320001TUR | PRE-FAB - LEVEL 26 - UNITS INWALL | 1230 | LEVEL 26 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.539 | 9000030 |  | PF.539 | PF.539 | 0% |  |  | 2026-03-04 |  | 2025-10-05 | 119
[5 empty] | 9000030 | 540 | 320001TUR | Stephen Yee | LEVEL 27 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-18 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-03-25 | 2026-03-30 | 2026-04-01 |  | 2026-04-06 |  | 2026-04-10 | [6 empty] | 540 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 540-320001TUR | PRE-FAB - LEVEL 27 - UNITS INWALL | 1264 | LEVEL 27 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.540 | 9000030 |  | PF.540 | PF.540 | 0% |  |  | 2026-03-11 |  | 2025-10-05 | 124
[5 empty] | 9000030 | 541 | 320001TUR | Stephen Yee | LEVEL 31 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-16 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-23 | 2026-04-28 | 2026-04-30 |  | 2026-05-05 |  | 2026-05-11 | [6 empty] | 541 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 541-320001TUR | PRE-FAB - LEVEL 31 - UNITS INWALL | 1429 | LEVEL 31 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.541 | 9000030 |  | PF.541 | PF.541 | 0% |  |  | 2026-04-09 |  | 2025-10-05 | 145
[5 empty] | 9000030 | 542 | 320001TUR | Stephen Yee | LEVEL 28 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-25 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-01 | 2026-04-06 | 2026-04-08 |  | 2026-04-13 |  | 2026-04-17 | [6 empty] | 542 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 542-320001TUR | PRE-FAB - LEVEL 28 - UNITS INWALL | 1304 | LEVEL 28 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.542 | 9000030 |  | PF.542 | PF.542 | 0% |  |  | 2026-03-18 |  | 2025-10-05 | 129
[5 empty] | 9000030 | 543 | 320001TUR | Stephen Yee | LEVEL 32 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-23 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-30 | 2026-05-05 | 2026-05-07 |  | 2026-05-12 |  | 2026-05-18 | [6 empty] | 543 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 543-320001TUR | PRE-FAB - LEVEL 32 - UNITS INWALL | 1467 | LEVEL 32 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.543 | 9000030 |  | PF.543 | PF.543 | 0% |  |  | 2026-04-16 |  | 2025-10-05 | 150
[5 empty] | 9000030 | 544 | 320001TUR | Stephen Yee | LEVEL 29 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-01 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-08 | 2026-04-13 | 2026-04-15 |  | 2026-04-21 |  | 2026-04-27 | [6 empty] | 544 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 544-320001TUR | PRE-FAB - LEVEL 29 - UNITS INWALL | 1348 | LEVEL 29 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.544 | 9000030 |  | PF.544 | PF.544 | 0% |  |  | 2026-03-25 |  | 2025-10-05 | 134
[5 empty] | 9000030 | 545 | 320001TUR | Stephen Yee | LEVEL 33 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-30 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-05-07 | 2026-05-12 | 2026-05-14 |  | 2026-05-19 | DATES MISALIGNED | 2026-05-26 | [6 empty] | 545 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 545-320001TUR | PRE-FAB - LEVEL 33 - UNITS INWALL | 1510 | LEVEL 33 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.545 | 9000030 |  | PF.545 | PF.545 | 0% |  |  | 2026-04-23 |  | 2025-10-05 | 155
[5 empty] | 9000030 | 546 | 320001TUR | Stephen Yee | LEVEL 34 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 386 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-07 | [7 empty] | 34.8519 | 2.1782 | 3 | 2 | 2026-05-14 | 2026-05-19 | 2026-05-21 |  | 2026-05-27 |  | 2026-06-02 | [6 empty] | 546 | 26 |  | 0 | 0 | 0.09029 | 34.8519 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 546-320001TUR | PRE-FAB - LEVEL 34 - UNITS INWALL | 1554 | LEVEL 34 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.546 | 9000030 |  | PF.546 | PF.546 | 0% |  |  | 2026-04-30 |  | 2025-10-05 | 160
[5 empty] | 9000030 | 547 | 320001TUR | Stephen Yee | LEVEL 30 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-09 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-04-16 | 2026-04-21 | 2026-04-23 |  | 2026-04-28 |  | 2026-05-04 | [6 empty] | 547 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 547-320001TUR | PRE-FAB - LEVEL 30 - UNITS INWALL | 1389 | LEVEL 30 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.547 | 9000030 |  | PF.547 | PF.547 | 0% |  |  | 2026-04-02 |  | 2025-10-05 | 140
[5 empty] | 9000030 | 548 | 320001TUR | Stephen Yee | LEVEL 35 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 386 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-15 | [7 empty] | 34.8519 | 2.1782 | 3 | 2 | 2026-05-22 | 2026-05-27 | 2026-05-29 |  | 2026-06-03 |  | 2026-06-09 | [6 empty] | 548 | 26 |  | 0 | 0 | 0.09029 | 34.8519 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 548-320001TUR | PRE-FAB - LEVEL 35 - UNITS INWALL | 1586 | LEVEL 35 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.548 | 9000030 |  | PF.548 | PF.548 | 0% |  |  | 2026-05-08 |  | 2025-10-05 | 166
[5 empty] | 9000030 | 549 | 320001TUR | Stephen Yee | LEVEL 36 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-22 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-05-29 | 2026-06-03 | 2026-06-05 |  | 2026-06-10 |  | 2026-06-16 | [6 empty] | 549 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 549-320001TUR | PRE-FAB - LEVEL 36 - UNITS INWALL | 1617 | LEVEL 36 - TIER 3 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.549 | 9000030 |  | PF.549 | PF.549 | 0% |  |  | 2026-05-15 |  | 2025-10-05 | 171
[5 empty] | 9000030 | 550 | 320001TUR | Stephen Yee | LEVEL 3 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-01 | 2025-09-30 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 42.0751 | 2.6297 | 3 | 2 | 2025-10-08 | 2025-10-13 | 2025-10-15 |  | 2025-10-27 |  | 2025-10-24 |  |  |  |  | 2 |  | 550 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 550-320001TUR | PRE-FAB - LEVEL 3 - UNITS INWALL | 302 | LEVEL 3 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.550 | 9000030 |  | PF.550 | PF.550 | 0% |  |  | 2025-09-24 |  | 2025-10-05 | 4 | TRUE
[5 empty] | 9000030 | 551 | 320001TUR | Stephen Yee | LEVEL 4 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-08 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-10-15 | 2025-10-20 | 2025-10-22 |  | 2025-11-03 |  | 2025-10-31 | [6 empty] | 551 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 551-320001TUR | PRE-FAB - LEVEL 4 - UNITS INWALL | 331 | LEVEL 4 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.551 | 9000030 |  | PF.551 | PF.551 | 0% |  |  | 2025-10-01 |  | 2025-10-05 | 9
[5 empty] | 9000030 | 552 | 320001TUR | Stephen Yee | LEVEL 5 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-22 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-10-29 | 2025-11-02 | 2025-11-04 |  | 2025-11-07 |  | 2025-11-07 | [6 empty] | 552 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 552-320001TUR | PRE-FAB - LEVEL 5 - UNITS INWALL | 372 | LEVEL 5 - PODIUM IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.552 | 9000030 |  | PF.552 | PF.552 | 0% |  |  | 2025-10-15 |  | 2025-10-05 | 19
[5 empty] | 9000030 | 553 | 320001TUR | Stephen Yee | LEVEL 6 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-29 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-11-05 | 2025-11-10 | 2025-11-12 |  | 2025-11-12 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | [6 empty] | 553 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 553-320001TUR | PRE-FAB - LEVEL 6 - UNITS INWALL | #NO MATCH | #NO MATCH | PF.553 | 9000030 |  | PF.553 | NOT ON PROJECT SCHEDULE | 0% |  |  | 2025-10-22 |  | 2025-10-05 | 24
[5 empty] | 9000030 | 554 | 320001TUR | Stephen Yee | LEVEL 7 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-29 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-11-05 | 2025-11-10 | 2025-11-12 |  | 2025-11-17 |  | 2025-11-21 | [6 empty] | 554 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 554-320001TUR | PRE-FAB - LEVEL 7 - UNITS INWALL | 440 | LEVEL 7 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.554 | 9000030 |  | PF.554 | PF.554 | 0% |  |  | 2025-10-22 |  | 2025-10-05 | 24
[5 empty] | 9000030 | 555 | 320001TUR | Stephen Yee | LEVEL 8 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 466 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-05 | [7 empty] | 42.0751 | 2.6297 | 3 | 2 | 2025-11-12 | 2025-11-17 | 2025-11-19 |  | 2025-11-24 | DATES MISALIGNED | 2025-12-01 | [6 empty] | 555 | 25 |  | 0 | 0 | 0.09029 | 42.0751 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 555-320001TUR | PRE-FAB - LEVEL 8 - UNITS INWALL | 481 | LEVEL 8 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.555 | 9000030 |  | PF.555 | PF.555 | 0% |  |  | 2025-10-29 |  | 2025-10-05 | 29
[5 empty] | 9000030 | 556 | 320001TUR | Stephen Yee | LEVEL 9 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 491 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-12 | [7 empty] | 44.3324 | 2.7708 | 3 | 2 | 2025-11-19 | 2025-11-23 | 2025-11-25 |  | 2025-12-01 | DATES MISALIGNED | 2025-12-08 | [6 empty] | 556 | 25 |  | 0 | 0 | 0.09029 | 44.3324 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 556-320001TUR | PRE-FAB - LEVEL 9 - UNITS INWALL | 514 | LEVEL 9 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.556 | 9000030 |  | PF.556 | PF.556 | 0% |  |  | 2025-11-05 |  | 2025-10-05 | 34
[5 empty] | 9000030 | 557 | 320001TUR | Stephen Yee | LEVEL 10 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 491 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-19 | [7 empty] | 44.3324 | 2.7708 | 3 | 2 | 2025-11-26 | 2025-12-01 | 2025-12-03 |  | 2025-12-08 |  | 2025-12-12 | [6 empty] | 557 | 25 |  | 0 | 0 | 0.09029 | 44.3324 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 557-320001TUR | PRE-FAB - LEVEL 10 - UNITS INWALL | 553 | LEVEL 10 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.557 | 9000030 |  | PF.557 | PF.557 | 0% |  |  | 2025-11-12 |  | 2025-10-05 | 39
[5 empty] | 9000030 | 558 | 320001TUR | Stephen Yee | LEVEL 11 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 491 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-26 | [7 empty] | 44.3324 | 2.7708 | 3 | 2 | 2025-12-03 | 2025-12-08 | 2025-12-10 |  | 2025-12-15 |  | 2025-12-19 | [6 empty] | 558 | 25 |  | 0 | 0 | 0.09029 | 44.3324 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 558-320001TUR | PRE-FAB - LEVEL 11 - UNITS INWALL | 586 | LEVEL 11 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.558 | 9000030 |  | PF.558 | PF.558 | 0% |  |  | 2025-11-19 |  | 2025-10-05 | 44
[5 empty] | 9000030 | 559 | 320001TUR | Stephen Yee | LEVEL 12 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 491 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-03 | [7 empty] | 44.3324 | 2.7708 | 3 | 2 | 2025-12-10 | 2025-12-15 | 2025-12-17 |  | 2025-12-22 | DATES MISALIGNED | 2025-12-29 | [6 empty] | 559 | 25 |  | 0 | 0 | 0.09029 | 44.3324 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 25 | 559-320001TUR | PRE-FAB - LEVEL 12 - UNITS INWALL | 627 | LEVEL 12 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.559 | 9000030 |  | PF.559 | PF.559 | 0% |  |  | 2025-11-26 |  | 2025-10-05 | 49
[5 empty] | 9000030 | 560 | 320001TUR | Stephen Yee | LEVEL 14 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 483 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-17 | [7 empty] | 43.6101 | 2.7256 | 3 | 2 | 2025-12-24 | 2025-12-28 | 2025-12-30 |  | 2026-01-05 | DATES MISALIGNED | 2026-01-12 | [6 empty] | 560 | 26 |  | 0 | 0 | 0.09029 | 43.6101 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 560-320001TUR | PRE-FAB - LEVEL 14 - UNITS INWALL | 708 | LEVEL 14 - TIER 1 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.560 | 9000030 |  | PF.560 | PF.560 | 0% |  |  | 2025-12-10 |  | 2025-10-05 | 59
[5 empty] | 9000030 | 561 | 320001TUR | Stephen Yee | LEVEL 15 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-24 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2025-12-31 | 2026-01-05 | 2026-01-07 |  | 2026-01-12 |  | 2026-01-16 | [6 empty] | 561 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 561-320001TUR | PRE-FAB - LEVEL 15 - UNITS INWALL | 731 | LEVEL 15 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.561 | 9000030 |  | PF.561 | PF.561 | 0% |  |  | 2025-12-17 |  | 2025-10-05 | 64
[5 empty] | 9000030 | 562 | 320001TUR | Stephen Yee | LEVEL 16 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-31 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-01-07 | 2026-01-12 | 2026-01-14 |  | 2026-01-20 |  | 2026-01-26 | [6 empty] | 562 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 562-320001TUR | PRE-FAB - LEVEL 16 - UNITS INWALL | 784 | LEVEL 16 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.562 | 9000030 |  | PF.562 | PF.562 | 0% |  |  | 2025-12-24 |  | 2025-10-05 | 69
[5 empty] | 9000030 | 563 | 320001TUR | Stephen Yee | LEVEL 17 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-07 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-01-14 | 2026-01-19 | 2026-01-21 |  | 2026-01-26 | DATES MISALIGNED | 2026-02-02 | [6 empty] | 563 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 563-320001TUR | PRE-FAB - LEVEL 17 - UNITS INWALL | 834 | LEVEL 17 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.563 | 9000030 |  | PF.563 | PF.563 | 0% |  |  | 2025-12-31 |  | 2025-10-05 | 74
[5 empty] | 9000030 | 564 | 320001TUR | Stephen Yee | LEVEL 18 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-14 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-01-21 | 2026-01-26 | 2026-01-28 |  | 2026-02-02 |  | 2026-02-06 | [6 empty] | 564 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 564-320001TUR | PRE-FAB - LEVEL 18 - UNITS INWALL | 884 | LEVEL 18 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.564 | 9000030 |  | PF.564 | PF.564 | 0% |  |  | 2026-01-07 |  | 2025-10-05 | 79
[5 empty] | 9000030 | 565 | 320001TUR | Stephen Yee | LEVEL 19 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-21 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-01-28 | 2026-02-02 | 2026-02-04 |  | 2026-02-09 |  | 2026-02-13 | [6 empty] | 565 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 565-320001TUR | PRE-FAB - LEVEL 19 - UNITS INWALL | 924 | LEVEL 19 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.565 | 9000030 |  | PF.565 | PF.565 | 0% |  |  | 2026-01-14 |  | 2025-10-05 | 84
[5 empty] | 9000030 | 566 | 320001TUR | Stephen Yee | LEVEL 20 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 500 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-28 | [7 empty] | 45.145 | 2.8216 | 3 | 2 | 2026-02-04 | 2026-02-09 | 2026-02-11 |  | 2026-02-17 |  | 2026-02-23 | [6 empty] | 566 | 26 |  | 0 | 0 | 0.09029 | 45.145 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 566-320001TUR | PRE-FAB - LEVEL 20 - UNITS INWALL | 962 | LEVEL 20 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.566 | 9000030 |  | PF.566 | PF.566 | 0% |  |  | 2026-01-21 |  | 2025-10-05 | 89
[5 empty] | 9000030 | 567 | 320001TUR | Stephen Yee | LEVEL 21 | IN-WALL ASSEMBLIES (ROMEX) | UNITS INWALL | 503 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-04 | [7 empty] | 45.4159 | 2.8385 | 3 | 2 | 2026-02-11 | 2026-02-16 | 2026-02-18 |  | 2026-02-23 | DATES MISALIGNED | 2026-03-02 | [6 empty] | 567 | 26 |  | 0 | 0 | 0.09029 | 45.4159 |  | 0 | 0.09029 | -0.09029 | 0 | -0.09029 | 26 | 567-320001TUR | PRE-FAB - LEVEL 21 - UNITS INWALL | 1007 | LEVEL 21 - TIER 2 IN-WALL ASSEMBLIES (MIXED SYSTEMS) | PF.567 | 9000030 |  | PF.567 | PF.567 | 0% |  |  | 2026-01-28 |  | 2025-10-05 | 94
[5 empty] | 9000010 | 568 | 320001TUR | Chris Gauvin, Stephen Yee | LEVEL 1 | LIGHT FIXTURE WIRED ASSEMBLY (2) LUMINARY WHIPS | (LOADING DOCK) S50 FIXTURE STRUT ASSEMBLIES | 19 | Green | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-19 | 2025-09-10 | Chris Gauvin | TRUE | true | TRUE | True | APPROVED | 5.32 | 0.665 | 1 | 1 | 2025-09-26 | 2025-09-29 | 2025-10-01 |  | 2025-10-27 |  |  |  |  | Image 2025-09-29 13-53-41.jpeg |  | 13 | Kerri Pandolfi | 568 | 25 |  | 1.3158 | 25 | 0.28 | 5.32 | 0.29 | 5.51 | 0.28 | 0.01 | 0.28 | 0 | 25 | 568-320001TUR | PRE-FAB - LEVEL 1 - (LOADING DOCK) S50 FIXTURE STRUT ASSEMBLIES | 1916 |  | PF.568 | 9000010 |  | PF.568 | PF.568 | 99% |  |  | 2025-09-12 |  | 2025-10-05 | -6 | TRUE
[5 empty] | 9000030 | 569 | 320001TUR | Stephen Yee | LEVEL 3 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 3 - MOCK UP UNIT (S-2) INWALL | 24 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-09 | 2025-09-17 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 4.3728 | 0.5466 | 1 | 1 | 2025-09-16 | 2025-09-17 | 2025-09-19 |  | 2025-09-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | 2025-10-01 |  | 2 | Kerri Pandolfi | 569 | 25 |  | 0.25 | 6 | 0.1822 | 4.3728 | 1.15 | 27.6 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 569-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - MOCK UP UNIT (S-2) INWALL | #NO MATCH | #NO MATCH | PF.569 | 9000030 |  | PF.569 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-09-02 |  | 2025-10-05 | -14 | TRUE
[5 empty] | 9000030 | 570 | 320001TUR | Stephen Yee | LEVEL 3 | IN-WALL ASSEMBLIES (MIXED SYSTEMS) | LEVEL 3 - MOCK UP UNIT (A-1) INWALL | 31 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-09 | 2025-09-17 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 5.6482 | 0.70603 | 1 | 1 | 2025-09-16 | 2025-09-17 | 2025-09-19 |  | 2025-09-22 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE |  | 2025-10-01 |  | 2 | Kerri Pandolfi | 570 | 25 |  | 0.30645 | 9.5 | 0.1822 | 5.6482 | 1.15 | 35.65 | 0.1822 | 0.9678 | 0.1822 | 0 | 25 | 570-320001TUR | PRE-FAB - LEVEL 3 - LEVEL 3 - MOCK UP UNIT (A-1) INWALL | #NO MATCH | #NO MATCH | PF.570 | 9000030 |  | PF.570 | NOT ON PROJECT SCHEDULE | 100% | TRUE |  | 2025-09-02 |  | 2025-10-05 | -14 | TRUE
[5 empty] | 9000220 | 571 | 320001TUR | Stephen Yee | LEVEL 3 | TEMPS (SMALL) | CORE HOLE (PLYWOOD) PLUG | 60 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-05 | 2025-09-18 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 60 | 7.5 | 8 | 1 | 2025-09-12 | 2025-09-24 | 2025-09-26 |  | 2025-09-26 |  |  |  |  | 2025-09-29 |  |  | Kerri Pandolfi | 571 | 25 |  | 0 | 0 | 1 | 60 | 2 | 120 | 1 | 1 | 0 | -1 | 25 | 571-320001TUR | PRE-FAB - LEVEL 3 - CORE HOLE (PLYWOOD) PLUG | 1918 |  | PF.571 | 9000220 |  | PF.571 | PF.571 | 99% | TRUE |  | 2025-08-29 |  | 2025-10-05 | -16
[5 empty] | 9000140 | 572 | 320001TUR | Stephen Yee | LEVEL 3 | SITE LIGHTING ASSEMBLY | L3 - UNITS TEMP LIGHTING (STRINGERS) | 13 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-03 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 7.8 | 0.975 | 1 | 1 | 2025-10-10 | 2025-10-13 | 2025-10-15 |  | 2025-10-27 | [6 empty] | 2 | Kerri Pandolfi | 572 | 25 |  | 0 | 0 | 0.6 | 7.8 | 1.104 | 14.352 | 0.6 | 0.504 | 0 | -0.6 | 25 | 572-320001TUR | PRE-FAB - LEVEL 3 - L3 - UNITS TEMP LIGHTING (STRINGERS) | 1919 |  | PF.572 | 9000140 |  | PF.572 | PF.572 | 0% |  |  | 2025-09-26 |  | 2025-10-05 | 6 | TRUE
[5 empty] | 9000140 | 573 | 320001TUR | Stephen Yee | LEVEL 4 | SITE LIGHTING ASSEMBLY | L4 - UNITS TEMP LIGHTING (STRINGERS) | 13 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-10 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 7.8 | 0.975 | 1 | 1 | 2025-10-17 | 2025-10-20 | 2025-10-22 |  | 2025-10-27 | [7 empty] | Kerri Pandolfi | 573 | 25 |  | 0 | 0 | 0.6 | 7.8 | 1.104 | 14.352 | 0.6 | 0.504 | 0 | -0.6 | 25 | 573-320001TUR | PRE-FAB - LEVEL 4 - L4 - UNITS TEMP LIGHTING (STRINGERS) | 1920 |  | PF.573 | 9000140 |  | PF.573 | PF.573 | 0% |  |  | 2025-10-03 |  | 2025-10-05 | 11
[5 empty] | 9000140 | 574 | 320001TUR | Stephen Yee | LEVEL 5 | SITE LIGHTING ASSEMBLY | L5 - UNITS TEMP LIGHTING (STRINGERS) | 13 | Yellow | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-24 | 2025-09-22 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 7.8 | 0.975 | 1 | 1 | 2025-10-31 | 2025-11-02 | 2025-11-04 |  | 2025-11-07 | [7 empty] | Kerri Pandolfi | 574 | 25 |  | 0 | 0 | 0.6 | 7.8 | 1.104 | 14.352 | 0.6 | 0.504 | 0 | -0.6 | 25 | 574-320001TUR | PRE-FAB - LEVEL 5 - L5 - UNITS TEMP LIGHTING (STRINGERS) | 1921 |  | PF.574 | 9000140 |  | PF.574 | PF.574 | 0% |  |  | 2025-10-17 |  | 2025-10-05 | 21
[5 empty] | 9000140 | 575 | 320001TUR | Stephen Yee | LEVEL 7 | SITE LIGHTING ASSEMBLY | L7 - UNITS TEMP LIGHTING (STRINGERS) | 12 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-10-31 | [7 empty] | 7.2 | 0.9 | 1 | 1 | 2025-11-07 | 2025-11-10 | 2025-11-12 |  | 2025-11-17 | [7 empty] | Kerri Pandolfi | 575 | 25 |  | 0 | 0 | 0.6 | 7.2 | 1.104 | 13.248 | 0.6 | 0.504 | 0 | -0.6 | 25 | 575-320001TUR | PRE-FAB - LEVEL 7 - L7 - UNITS TEMP LIGHTING (STRINGERS) | 1922 |  | PF.575 | 9000140 |  | PF.575 | PF.575 | 0% |  |  | 2025-10-24 |  | 2025-10-05 | 26
[5 empty] | 9000140 | 576 | 320001TUR | Stephen Yee | LEVEL 8 | SITE LIGHTING ASSEMBLY | L8 - UNITS TEMP LIGHTING (STRINGERS) | 12 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-07 | [7 empty] | 7.2 | 0.9 | 1 | 1 | 2025-11-14 | 2025-11-17 | 2025-11-19 |  | 2025-11-24 | [7 empty] | Kerri Pandolfi | 576 | 25 |  | 0 | 0 | 0.6 | 7.2 | 1.104 | 13.248 | 0.6 | 0.504 | 0 | -0.6 | 25 | 576-320001TUR | PRE-FAB - LEVEL 8 - L8 - UNITS TEMP LIGHTING (STRINGERS) | 1923 |  | PF.576 | 9000140 |  | PF.576 | PF.576 | 0% |  |  | 2025-10-31 |  | 2025-10-05 | 31
[5 empty] | 9000140 | 577 | 320001TUR | Stephen Yee | LEVEL 9 | SITE LIGHTING ASSEMBLY | L9 - UNITS TEMP LIGHTING (STRINGERS) | 12 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-14 | [7 empty] | 7.2 | 0.9 | 1 | 1 | 2025-11-21 | 2025-11-23 | 2025-11-25 |  | 2025-12-01 | [7 empty] | Kerri Pandolfi | 577 | 25 |  | 0 | 0 | 0.6 | 7.2 | 1.104 | 13.248 | 0.6 | 0.504 | 0 | -0.6 | 25 | 577-320001TUR | PRE-FAB - LEVEL 9 - L9 - UNITS TEMP LIGHTING (STRINGERS) | 1924 |  | PF.577 | 9000140 |  | PF.577 | PF.577 | 0% |  |  | 2025-11-07 |  | 2025-10-05 | 36
[5 empty] | 9000140 | 578 | 320001TUR | Stephen Yee | LEVEL 10 | SITE LIGHTING ASSEMBLY | L10 - UNITS TEMP LIGHTING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-20 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-11-27 | 2025-12-01 | 2025-12-03 |  | 2025-12-08 | [7 empty] | Kerri Pandolfi | 578 | 25 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 25 | 578-320001TUR | PRE-FAB - LEVEL 10 - L10 - UNITS TEMP LIGHTING (STRINGERS) | 1925 |  | PF.578 | 9000140 |  | PF.578 | PF.578 | 0% |  |  | 2025-11-13 |  | 2025-10-05 | 40
[5 empty] | 9000140 | 579 | 320001TUR | Stephen Yee | LEVEL 11 | SITE LIGHTING ASSEMBLY | L11 - UNITS TEMP LIGHTING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-11-27 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-12-04 | 2025-12-08 | 2025-12-10 |  | 2025-12-15 | [7 empty] | Kerri Pandolfi | 579 | 25 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 25 | 579-320001TUR | PRE-FAB - LEVEL 11 - L11 - UNITS TEMP LIGHTING (STRINGERS) | 1926 |  | PF.579 | 9000140 |  | PF.579 | PF.579 | 0% |  |  | 2025-11-20 |  | 2025-10-05 | 45
[5 empty] | 9000140 | 580 | 320001TUR | Stephen Yee | LEVEL 12 | SITE LIGHTING ASSEMBLY | L12 - UNITS TEMP LIGHTING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-04 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-12-11 | 2025-12-15 | 2025-12-17 |  | 2025-12-22 | [7 empty] | Kerri Pandolfi | 580 | 25 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 25 | 580-320001TUR | PRE-FAB - LEVEL 12 - L12 - UNITS TEMP LIGHTING (STRINGERS) | 1928 |  | PF.580 | 9000140 |  | PF.580 | PF.580 | 0% |  |  | 2025-11-27 |  | 2025-10-05 | 50
[5 empty] | 9000140 | 581 | 320001TUR | Stephen Yee | LEVEL 13 | SITE LIGHTING ASSEMBLY | L13 - UNITS TEMP LIGHTING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-11 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-12-18 | 2025-12-21 | 2025-12-23 |  | 2025-12-29 | [7 empty] | Kerri Pandolfi | 581 | 25 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 25 | 581-320001TUR | PRE-FAB - LEVEL 13 - L13 - UNITS TEMP LIGHTING (STRINGERS) | 1929 |  | PF.581 | 9000140 |  | PF.581 | PF.581 | 0% |  |  | 2025-12-04 |  | 2025-10-05 | 55
[5 empty] | 9000140 | 582 | 320001TUR | Stephen Yee | LEVEL 14 | SITE LIGHTING ASSEMBLY | L14 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-18 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2025-12-25 | 2025-12-28 | 2025-12-30 |  | 2026-01-05 | [7 empty] | Kerri Pandolfi | 582 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 582-320001TUR | PRE-FAB - LEVEL 14 - L14 - UNITS TEMP LIGHTHING (STRINGERS) | 1930 |  | PF.582 | 9000140 |  | PF.582 | PF.582 | 0% |  |  | 2025-12-11 |  | 2025-10-05 | 60
[5 empty] | 9000140 | 583 | 320001TUR | Stephen Yee | LEVEL 15 | SITE LIGHTING ASSEMBLY | L15 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-12-25 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-01 | 2026-01-05 | 2026-01-07 |  | 2026-01-12 | [7 empty] | Kerri Pandolfi | 583 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 583-320001TUR | PRE-FAB - LEVEL 15 - L15 - UNITS TEMP LIGHTHING (STRINGERS) | 1931 |  | PF.583 | 9000140 |  | PF.583 | PF.583 | 0% |  |  | 2025-12-18 |  | 2025-10-05 | 65
[5 empty] | 9000140 | 584 | 320001TUR | Stephen Yee | LEVEL 16 | SITE LIGHTING ASSEMBLY | L16 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-01 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-08 | 2026-01-12 | 2026-01-14 |  | 2026-01-20 | [7 empty] | Kerri Pandolfi | 584 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 584-320001TUR | PRE-FAB - LEVEL 16 - L16 - UNITS TEMP LIGHTHING (STRINGERS) | 1932 |  | PF.584 | 9000140 |  | PF.584 | PF.584 | 0% |  |  | 2025-12-25 |  | 2025-10-05 | 70
[5 empty] | 9000140 | 585 | 320001TUR | Stephen Yee | LEVEL 17 | SITE LIGHTING ASSEMBLY | L17 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-08 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-15 | 2026-01-19 | 2026-01-21 |  | 2026-01-26 | [7 empty] | Kerri Pandolfi | 585 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 585-320001TUR | PRE-FAB - LEVEL 17 - L17 - UNITS TEMP LIGHTHING (STRINGERS) | 1933 |  | PF.585 | 9000140 |  | PF.585 | PF.585 | 0% |  |  | 2026-01-01 |  | 2025-10-05 | 75
[5 empty] | 9000140 | 586 | 320001TUR | Stephen Yee | LEVEL 18 | SITE LIGHTING ASSEMBLY | L18 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-15 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-22 | 2026-01-26 | 2026-01-28 |  | 2026-02-02 | [7 empty] | Kerri Pandolfi | 586 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 586-320001TUR | PRE-FAB - LEVEL 18 - L18 - UNITS TEMP LIGHTHING (STRINGERS) | 1935 |  | PF.586 | 9000140 |  | PF.586 | PF.586 | 0% |  |  | 2026-01-08 |  | 2025-10-05 | 80
[5 empty] | 9000140 | 587 | 320001TUR | Stephen Yee | LEVEL 19 | SITE LIGHTING ASSEMBLY | L19 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-22 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-01-29 | 2026-02-02 | 2026-02-04 |  | 2026-02-09 | [7 empty] | Kerri Pandolfi | 587 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 587-320001TUR | PRE-FAB - LEVEL 19 - L19 - UNITS TEMP LIGHTHING (STRINGERS) | 1936 |  | PF.587 | 9000140 |  | PF.587 | PF.587 | 0% |  |  | 2026-01-15 |  | 2025-10-05 | 85
[5 empty] | 9000140 | 588 | 320001TUR | Stephen Yee | LEVEL 20 | SITE LIGHTING ASSEMBLY | L20 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-01-29 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-02-05 | 2026-02-09 | 2026-02-11 |  | 2026-02-17 | [7 empty] | Kerri Pandolfi | 588 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 588-320001TUR | PRE-FAB - LEVEL 20 - L20 - UNITS TEMP LIGHTHING (STRINGERS) | 1937 |  | PF.588 | 9000140 |  | PF.588 | PF.588 | 0% |  |  | 2026-01-22 |  | 2025-10-05 | 90
[5 empty] | 9000140 | 589 | 320001TUR | Stephen Yee | LEVEL 21 | SITE LIGHTING ASSEMBLY | L21 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-05 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-02-12 | 2026-02-16 | 2026-02-18 |  | 2026-02-23 | [7 empty] | Kerri Pandolfi | 589 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 589-320001TUR | PRE-FAB - LEVEL 21 - L21 - UNITS TEMP LIGHTHING (STRINGERS) | 1938 |  | PF.589 | 9000140 |  | PF.589 | PF.589 | 0% |  |  | 2026-01-29 |  | 2025-10-05 | 95
[5 empty] | 9000140 | 590 | 320001TUR | Stephen Yee | LEVEL 22 | SITE LIGHTING ASSEMBLY | L22 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-12 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-02-19 | 2026-02-23 | 2026-02-25 |  | 2026-03-02 | [7 empty] | Kerri Pandolfi | 590 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 590-320001TUR | PRE-FAB - LEVEL 22 - L22 - UNITS TEMP LIGHTHING (STRINGERS) | 1939 |  | PF.590 | 9000140 |  | PF.590 | PF.590 | 0% |  |  | 2026-02-05 |  | 2025-10-05 | 100
[5 empty] | 9000140 | 591 | 320001TUR | Stephen Yee | LEVEL 23 | SITE LIGHTING ASSEMBLY | L23 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-19 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-02-26 | 2026-03-02 | 2026-03-04 |  | 2026-03-09 | [7 empty] | Kerri Pandolfi | 591 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 591-320001TUR | PRE-FAB - LEVEL 23 - L23 - UNITS TEMP LIGHTHING (STRINGERS) | 1940 |  | PF.591 | 9000140 |  | PF.591 | PF.591 | 0% |  |  | 2026-02-12 |  | 2025-10-05 | 105
[5 empty] | 9000140 | 592 | 320001TUR | Stephen Yee | LEVEL 24 | SITE LIGHTING ASSEMBLY | L24 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-02-26 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-03-05 | 2026-03-09 | 2026-03-11 |  | 2026-03-16 | [7 empty] | Kerri Pandolfi | 592 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 592-320001TUR | PRE-FAB - LEVEL 24 - L24 - UNITS TEMP LIGHTHING (STRINGERS) | 1942 |  | PF.592 | 9000140 |  | PF.592 | PF.592 | 0% |  |  | 2026-02-19 |  | 2025-10-05 | 110
[5 empty] | 9000140 | 593 | 320001TUR | Stephen Yee | LEVEL 25 | SITE LIGHTING ASSEMBLY | L25 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-05 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-03-12 | 2026-03-16 | 2026-03-18 |  | 2026-03-23 | [7 empty] | Kerri Pandolfi | 593 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 593-320001TUR | PRE-FAB - LEVEL 25 - L25 - UNITS TEMP LIGHTHING (STRINGERS) | 1943 |  | PF.593 | 9000140 |  | PF.593 | PF.593 | 0% |  |  | 2026-02-26 |  | 2025-10-05 | 115
[5 empty] | 9000140 | 594 | 320001TUR | Stephen Yee | LEVEL 26 | SITE LIGHTING ASSEMBLY | L26 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-13 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-03-20 | 2026-03-24 | 2026-03-26 |  | 2026-03-30 | [7 empty] | Kerri Pandolfi | 594 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 594-320001TUR | PRE-FAB - LEVEL 26 - L26 - UNITS TEMP LIGHTHING (STRINGERS) | 1945 |  | PF.594 | 9000140 |  | PF.594 | PF.594 | 0% |  |  | 2026-03-06 |  | 2025-10-05 | 121
[5 empty] | 9000140 | 595 | 320001TUR | Stephen Yee | LEVEL 27 | SITE LIGHTING ASSEMBLY | L27 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-19 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-03-26 | 2026-03-30 | 2026-04-01 |  | 2026-04-06 | [7 empty] | Kerri Pandolfi | 595 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 595-320001TUR | PRE-FAB - LEVEL 27 - L27 - UNITS TEMP LIGHTHING (STRINGERS) | 1947 |  | PF.595 | 9000140 |  | PF.595 | PF.595 | 0% |  |  | 2026-03-12 |  | 2025-10-05 | 125
[5 empty] | 9000140 | 596 | 320001TUR | Stephen Yee | LEVEL 28 | SITE LIGHTING ASSEMBLY | L28 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-03-26 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-04-02 | 2026-04-06 | 2026-04-08 |  | 2026-04-13 | [7 empty] | Kerri Pandolfi | 596 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 596-320001TUR | PRE-FAB - LEVEL 28 - L28 - UNITS TEMP LIGHTHING (STRINGERS) | 1949 |  | PF.596 | 9000140 |  | PF.596 | PF.596 | 0% |  |  | 2026-03-19 |  | 2025-10-05 | 130
[5 empty] | 9000140 | 597 | 320001TUR | Stephen Yee | LEVEL 29 | SITE LIGHTING ASSEMBLY | L29 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-02 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-04-09 | 2026-04-13 | 2026-04-15 |  | 2026-04-21 | [7 empty] | Kerri Pandolfi | 597 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 597-320001TUR | PRE-FAB - LEVEL 29 - L29 - UNITS TEMP LIGHTHING (STRINGERS) | 1951 |  | PF.597 | 9000140 |  | PF.597 | PF.597 | 0% |  |  | 2026-03-26 |  | 2025-10-05 | 135
[5 empty] | 9000140 | 598 | 320001TUR | Stephen Yee | LEVEL 30 | SITE LIGHTING ASSEMBLY | L30 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-10 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-04-17 | 2026-04-21 | 2026-04-23 |  | 2026-04-28 | [7 empty] | Kerri Pandolfi | 598 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 598-320001TUR | PRE-FAB - LEVEL 30 - L30 - UNITS TEMP LIGHTHING (STRINGERS) | 1954 |  | PF.598 | 9000140 |  | PF.598 | PF.598 | 0% |  |  | 2026-04-03 |  | 2025-10-05 | 141
[5 empty] | 9000140 | 599 | 320001TUR | Stephen Yee | LEVEL 31 | SITE LIGHTING ASSEMBLY | L31 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-17 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-04-24 | 2026-04-28 | 2026-04-30 |  | 2026-05-05 | [7 empty] | Kerri Pandolfi | 599 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 599-320001TUR | PRE-FAB - LEVEL 31 - L31 - UNITS TEMP LIGHTHING (STRINGERS) | 1956 |  | PF.599 | 9000140 |  | PF.599 | PF.599 | 0% |  |  | 2026-04-10 |  | 2025-10-05 | 146
[5 empty] | 9000140 | 600 | 320001TUR | Stephen Yee | LEVEL 32 | SITE LIGHTING ASSEMBLY | L32 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-04-24 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-05-01 | 2026-05-05 | 2026-05-07 |  | 2026-05-12 | [7 empty] | Kerri Pandolfi | 600 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 600-320001TUR | PRE-FAB - LEVEL 32 - L32 - UNITS TEMP LIGHTHING (STRINGERS) | 1958 |  | PF.600 | 9000140 |  | PF.600 | PF.600 | 0% |  |  | 2026-04-17 |  | 2025-10-05 | 151
[5 empty] | 9000140 | 601 | 320001TUR | Stephen Yee | LEVEL 33 | SITE LIGHTING ASSEMBLY | L33 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-01 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-05-08 | 2026-05-12 | 2026-05-14 |  | 2026-05-19 | [7 empty] | Kerri Pandolfi | 601 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 601-320001TUR | PRE-FAB - LEVEL 33 - L33 - UNITS TEMP LIGHTHING (STRINGERS) | 1960 |  | PF.601 | 9000140 |  | PF.601 | PF.601 | 0% |  |  | 2026-04-24 |  | 2025-10-05 | 156
[5 empty] | 9000140 | 602 | 320001TUR | Stephen Yee | LEVEL 34 | SITE LIGHTING ASSEMBLY | L34 - UNITS TEMP LIGHTHING (STRINGERS) | 14 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-08 | [7 empty] | 8.4 | 1.05 | 2 | 1 | 2026-05-15 | 2026-05-19 | 2026-05-21 |  | 2026-05-27 | [7 empty] | Kerri Pandolfi | 602 | 26 |  | 0 | 0 | 0.6 | 8.4 | 1.104 | 15.456 | 0.6 | 0.504 | 0 | -0.6 | 26 | 602-320001TUR | PRE-FAB - LEVEL 34 - L34 - UNITS TEMP LIGHTHING (STRINGERS) | 1962 |  | PF.602 | 9000140 |  | PF.602 | PF.602 | 0% |  |  | 2026-05-01 |  | 2025-10-05 | 161
[5 empty] | 9000140 | 603 | 320001TUR | Stephen Yee | LEVEL 35 | SITE LIGHTING ASSEMBLY | L35 - UNITS TEMP LIGHTHING (STRINGERS) | 7 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-19 | [7 empty] | 4.2 | 0.525 | 1 | 1 | 2026-05-26 | 2026-05-27 | 2026-05-29 |  | 2026-06-03 | [7 empty] | Kerri Pandolfi | 603 | 26 |  | 0 | 0 | 0.6 | 4.2 | 1.104 | 7.728 | 0.6 | 0.504 | 0 | -0.6 | 26 | 603-320001TUR | PRE-FAB - LEVEL 35 - L35 - UNITS TEMP LIGHTHING (STRINGERS) | 1964 |  | PF.603 | 9000140 |  | PF.603 | PF.603 | 0% |  |  | 2026-05-12 |  | 2025-10-05 | 168
[5 empty] | 9000140 | 604 | 320001TUR | Stephen Yee | LEVEL 36 | SITE LIGHTING ASSEMBLY | L36 - UNITS TEMP LIGHTHING (STRINGERS) | 7 | Red | 121 BROADWAY MXD TOWER | Eriberto Velez | 2026-05-26 | [7 empty] | 4.2 | 0.525 | 1 | 1 | 2026-06-02 | 2026-06-03 | 2026-06-05 |  | 2026-06-10 | [7 empty] | Kerri Pandolfi | 604 | 26 |  | 0 | 0 | 0.6 | 4.2 | 1.104 | 7.728 | 0.6 | 0.504 | 0 | -0.6 | 26 | 604-320001TUR | PRE-FAB - LEVEL 36 - L36 - UNITS TEMP LIGHTHING (STRINGERS) | 1966 |  | PF.604 | 9000140 |  | PF.604 | PF.604 | 0% |  |  | 2026-05-19 |  | 2025-10-05 | 173
[5 empty] | 9000010 | 605 | 320001TUR | Stephen Yee | LEVEL 11 | IN-WALL SWITCH ASSEMBLIES (LIGHTING) | BOH DEVICES (L11-L36) | 234 | Gray | 121 BROADWAY MXD TOWER | Eriberto Velez | 2025-09-18 | 2025-09-23 | Stephen Yee | TRUE | true | TRUE | True | APPROVED | 17.55 | 1.0969 | 2 | 2 | 2025-09-25 | 2025-09-29 | 2025-10-01 |  | 2025-10-13 |  |  |  |  | Image 2025-09-29 13-53-08.jpeg |  | 14 | Kerri Pandolfi | 605 | 25 |  | 0.13248 | 31 | 0.075 | 17.55 | 0.62 | 145.08 | 0.075 | 0.545 | 0.075 | 0 | 25 | 605-320001TUR | PRE-FAB - LEVEL 11 - BOH DEVICES (L11-L36) | 1927 |  | PF.605 | 9000010 |  | PF.605 | PF.605 | 99% | TRUE |  | 2025-09-11 |  | 2025-10-05 | -7 | TRUE
[5 empty] | 9000221 | X | 320001TUR | John McCullough, Pat Cameron | LEVEL B1 | TEMP POWER DRAGO | 3000AMP DRAGO #206 | 1 | Gray | 121 BROADWAY MXD TOWER | Doug Durand, Eriberto Velez | 2023-10-30 | 2023-10-13 | Pat Cameron | TRUE | true | TRUE | True | APPROVED | 240 | 30 | 30 | 1 | 2023-11-06 | 2023-12-16 | 2023-12-18 |  | 2023-12-18 |  | NOT LINKED IN PROJECT SCHEDULE SHEET | TRUE | MATTHEW C MAJESKI | Image 2023-12-07 13-45-13.jpeg | N/A | 6 | Kerri Pandolfi | #INVALID VALUE | 23 |  | #INVALID VALUE | #INVALID VALUE | 240 | 240 |  | 0 | 240 | -240 | #INVALID VALUE | #INVALID VALUE | 23 | X-320001TUR | PRE-FAB - LEVEL B1 - 3000AMP DRAGO #206 | #NO MATCH | #NO MATCH | PF.X | 9000221 |  | PF.X | NOT ON PROJECT SCHEDULE | 100% |  |  | 2023-10-23 |  | 2025-10-05 | -500

## Comments
Row 9 | NO PIPE ON L4 | Eddie Velez | 10/03/25 2:47 PM
Row 10 | NO PIPE ON L5 | Eddie Velez | 10/03/25 2:47 PM
Row 11 | @jcampbell@sullymac.com Jimbo, what date should I push this out to? | Eddie Velez | 09/25/25 5:54 AM
Row 85 | NO PREFAB OUTSIDE LAUNDRY/BATHROOM | Eddie Velez | 08/28/25 6:37 AM
Row 86 | JBs ARE DUE IN ON 9/4/25 | Eddie Velez | 09/04/25 6:13 AM
Row 88 | NO JB ON L3 | Eddie Velez | 10/03/25 2:49 PM
Row 89 | NO JB ON L4 | Eddie Velez | 10/03/25 2:49 PM
Row 90 | NO JB ON L5 | Eddie Velez | 10/03/25 2:50 PM
Row 91 | Due to open ceilings and inaccessible ceiling areas, L6 is Direct-to-Device Homeruns | Eddie Velez | 09/18/25 5:57 AM
Row 125 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:26 PM
Row 126 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:27 PM
| THIS CHANGED FROM ALL OF L2 TO JUST VAULT HANGERS ON 9/5/25 | Eddie Velez | 09/05/25 11:53 AM
Row 127 | @warehouse180@sullymac.com @jcampbell@sullymac.com @syee@sullymac.com Tony/Jim, Please schedule this Fab to be picked with Fab 348 and have them both delivered to site for Monday 8/4. Thank you, | Paul Simcoe | 07/31/25 10:19 AM
Row 132 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:26 PM
Row 133 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:27 PM
Row 134 | COORDINATION TIMELINE TOO TIGHT | Paul Simcoe | 08/01/25 1:19 PM
Row 139 | TOO LATE FOR PREFAB BASED ON SULLYMAC START DATE | Paul Simcoe | 06/30/25 2:26 PM
Row 190 | CHANGED FROM A "WIRED" ASSEMBLY TO A STRUT ONLY BUILD (ADDED TO FAB#288) | Eddie Velez | 10/02/25 12:01 PM
Row 190 | NO PREFAB NEEDED | Arthur Mayo | 07/25/25 6:20 AM
Row 192 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:22 AM
Row 207 | NO PREFAB NEEDED | Arthur Mayo | 07/25/25 6:15 AM
Row 208 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:17 AM
Row 209 | NO PREFAB NEEDED | Arthur Mayo | 07/25/25 6:18 AM
Row 212 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:21 AM
Row 214 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:23 AM
Row 216 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:24 AM
Row 217 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:25 AM
Row 218 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:26 AM
Row 220 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:27 AM
Row 221 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:27 AM
Row 223 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:28 AM
Row 224 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:29 AM
Row 225 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:30 AM
Row 226 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:30 AM
Row 227 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:31 AM
Row 228 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:32 AM
Row 229 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:33 AM
Row 230 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:34 AM
Row 231 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:35 AM
Row 232 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:35 AM
Row 234 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:37 AM
Row 235 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:38 AM
Row 236 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:38 AM
Row 237 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:39 AM
Row 238 | PREFAB NOT NEEDED | Arthur Mayo | 07/25/25 6:39 AM
Row 243 | RFI OUT ON CHIEF PACS TEL DATA SIZE REQUIREMENTS | Eddie Velez | 09/04/25 6:14 AM
Row 251 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 252 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 275 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 276 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 277 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 278 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 279 | (30) SPIDER BOXES ON SITE TO COVER UP TO L25 | Eddie Velez | 07/17/25 1:23 PM
Row 358 | RFI OUT ON DEVICES FOR THIS AREA | Eddie Velez | 09/04/25 6:12 AM
Row 361 | ROUGHED IN THE FIELD | Eddie Velez | 10/03/25 12:00 PM
Row 457 | @amayo@sullymac.com @evelez@sullymac.com ARTY, CAN YOU PLEASE GET WITH MATT TO CONFIRM THE MATERIALS FOR THIS BUILD. | Douglas Durand | 08/12/25 7:03 AM
Row 459 | @jcampbell@sullymac.com @syee@sullymac.com Jim, Can we squeeze in this fab today with the riser sleeves? Steve wants this onsite as a reference for the rest of the building. | Paul Simcoe | 09/02/25 8:04 AM
| ON IT | james campbell | 09/02/25 8:57 AM
Row 493 | INSTALLED ONSITE | Paul Simcoe | 08/19/25 11:32 AM
Row 494 | INSTALLED ONSITE FOR MOCKUP | Paul Simcoe | 08/19/25 11:32 AM
Row 496 | @psimcoe@sullymac.com ill need a little more info on this | Warehouse Quality Control | 08/28/25 8:25 AM
Row 533 | STEVE HAS RFI OUT ON NEED FOR FUSED DISCOS | Eddie Velez | 09/04/25 6:15 AM
Row 571 | @evelez@sullymac.com you sent this to Purner...Right? | james campbell | 09/23/25 1:33 PM
| @jcampbell@sullymac.com No, but his handler did | Eddie Velez | 09/23/25 1:48 PM
| 😂 | james campbell | 09/23/25 1:57 PM
Row 572 | MATERIALS BOUGHT BY PAUL COBERT PRIOR TO TRANSITION | Eddie Velez | 09/22/25 9:41 AM
Row 606 | @ddurand@sullymac.com @evelez@sullymac.com I believe this is shipped? Just need to check the box | Shawn Leahy | 08/30/24 1:35 PM